## Instructions
Single Feature Forecaster or Throughput Forecaster
Want to learn how this works and how to use it? Read my "In-progress" book on Medium - Forecasting using Data
https://medium.com/forecasting-using-data
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
| 1.6 | 2017-06-09 | Added risk impact scores and increased risks to 10 entries
| 2 | 2018-01-17 | Refactored to support Excel 2007+ in all formulas
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). That's the odds of a coin-toss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for converting story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
About me….
I develop and teach how to use data in software development and operations teams for coaching or forecasting.
- Forecasting using Data workshop. Teach how to use these spreadsheets with practical hands-on examples based on your (and my) specific examples. Often run internally, sometimes publically.
- Data Driven Coaching workshop. Teach how to develop data driven approaches to improvement based on balancing multiple competing metrics. Often run internally, sometimes publically.
- Custom Dashboards or giving advice on your current dashboards. Take the next step in customizing our spreadsheets or deploying more advanced versions in Tableau or Power BI.
- Quantitative consulting or advice - give me a chance to answer something you need to know. I'll work with your teams in designing a prediction system or delivering a compelling visual demonstrting the issues.
Interested in chatting? Email me at troy.magennis@focusedobjective.com
Interested in stalking? Follow me on twitter @t_magennis
(best way to hear about new and improved spreadsheets like this)

## Forecast
Forecast Completion Date | [7 empty] | Results
Duration in
1. Start Date |  |  | 2017-07-01 |  |  |  |  | Likelihood | 1 week's | Date
[8 empty] | 100% | 39 | 2018-03-31
2. How many stories are remaining to be completed? | [7 empty] | 95% | 34 | 2018-02-24
(enter the range estimate of stories. Tip: start wide and narrow as certainty increases) | [7 empty] | 90% | 32 | 2018-02-10
| Low guess |  | 49 |  | Highest guess |  | 54 | 85% | 31 | 2018-02-03
[8 empty] | 80% | 30 | 2018-01-27
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [7 empty] | 75% | 29 | 2018-01-20
(often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here) | [7 empty] | 70% | 28 | 2018-01-13
| Low guess |  | 1 |  | Highest guess |  | 3 | 65% | 26 | 2017-12-30
[8 empty] | 60% | 25 | 2017-12-23
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [7 empty] | 55% | 24 | 2017-12-16
[8 empty] | 50% | 23 | 2017-12-09
Throughput/velocity data or estimate is for |  |  |  | 1 week | 7 | days |  | 45% | 22 | 2017-12-02
(choose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above) | [7 empty] | 40% | 21 | 2017-11-25
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Estimate | 35% | 20 | 2017-11-18
[8 empty] | 30% | 19 | 2017-11-11
[8 empty] | 25% | 18 | 2017-11-04
| Low guess |  | 3 |  | Highest guess |  | 6 | 20% | 16 | 2017-10-21
[8 empty] | 15% | 15 | 2017-10-14
[8 empty] | 10% | 14 | 2017-10-07
[8 empty] | 5% | 13 | 2017-09-30
[8 empty] | 0% | 11 | 2017-09-16
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | 1 weeks |  | Result: Total Pre-split Stories in 6 1 weeks
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 11.1667
[5 empty] | 85% | 12.8333 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 21.6667
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.
Exercise - Enter your dates and estimates into inputs 1, 2, 3 and 4 to forecast
Note on I16: Author: This is the measure of how two random groups of your sample data would align when forecasting. Anything below 25% is good, but lower is better. It grows if there is too little data, and ALSO if the process changes over time and you use too much data.

## Risks
Likelihood | Impact Low | Impact High | Description | Combined Impact (higher is worse) | Est. impact in 1 week's | Impact Rank (fix lowest first)
Calculations -
Likelihood | Impact Low | Impact High | Description | average story count | 103
30% | 10 | 15 | Server performance issues | duration at 85th P | 31
15% | 5 | 10 | Layout issues when text localized | count per period | 3.3226
20% | 5 | 15 | Layout in Safari issues
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For example, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.
Risk impact analysis
It can be hard to determine what risks are most impactful when they have different likelihoods and impacts. The risks are ranked here from most impactful (Rank = 1) to least impactful.
This is a simple ranking. It helps quickly see what is the most important to decrease likelihood or impact.

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2017-09-16 | 5
[14 empty] | 2017-09-23 | 9
[14 empty] | 2017-09-30 | 23
[14 empty] | 2017-10-07 | 24
[14 empty] | 2017-10-14 | 24
[14 empty] | 2017-10-21 | 22
[14 empty] | 2017-10-28 | 18
[14 empty] | 2017-11-04 | 19
[14 empty] | 2017-11-11 | 23
[14 empty] | 2017-11-18 | 18
[14 empty] | 2017-11-25 | 22
[14 empty] | 2017-12-02 | 26
[14 empty] | 2017-12-09 | 27
[14 empty] | 2017-12-16 | 20
[14 empty] | 2017-12-23 | 26
[14 empty] | 2017-12-30 | 25
[14 empty] | 2018-01-06 | 15
[14 empty] | 2018-01-13 | 25
[14 empty] | 2018-01-20 | 22
[14 empty] | 2018-01-27 | 26
[14 empty] | 2018-02-03 | 18
[14 empty] | 2018-02-10 | 17
[14 empty] | 2018-02-17 | 16
[14 empty] | 2018-02-24 | 12
[14 empty] | 2018-03-03 | 9
[14 empty] | 2018-03-10 | 5
[14 empty] | 2018-03-17 | 4
[14 empty] | 2018-03-24 | 0
[14 empty] | 2018-03-31 | 1
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 1 weeks | 8 1 weeks | 12 1 weeks | 16 1 weeks | 20 1 weeks | 24 1 weeks | 28 1 weeks | 32 1 weeks | 36 1 weeks | 40 1 weeks | 44 1 weeks | 48 1 weeks | 52 1 weeks
95% | 6.6667 | 15.6667 | 24.9917 | 34.5 | 44.1667 | 54.8333 | 64.3167 | 74.6667 | 85.3333 | 94.825 | 104.6583 | 114.8167 | 124.9833
85% | 8 | 17.6417 | 27.6667 | 37.6667 | 48.1667 | 59 | 69.5 | 79.8333 | 90.6417 | 100.6667 | 110.975 | 120.8333 | 131.5
5% | 15.175 | 28.1667 | 41.175 | 54.0083 | 66.3417 | 78.3333 | 89.6833 | 101.1833 | 114.3333 | 126 | 137.675 | 149.8417 | 160.5083
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Throughput Samples
Enter Samples Below | Group | Unique Rank
3 | 1 | 3
5 | 1 | 5
2 | 2 | 2
1 | 1 | 1
5 | 2 | 6
3 | 2 | 4
Stability Between Two Random Groups of the Samples
|  |  | Group | All | 1 | 2 | Diff
|  |  | count | 6 | 3 | 3 | 0
|  |  | min | 1 | 1 | 2
|  |  | max | 5 | 5 | 5
|  |  | avg | 3.1667 | 3 | 3.3333 | -0.33333
|  |  | median | 3 | 3 | 3 | 0
|  |  | avg error |  |  |  | 0.33333 | I also tried average of the mean and median error….but think average will do.
|  |  | error/range |  |  |  | 8.333% | Aim to keep this below 25%. By adding more sample data. You will see where to stop.
Transportable data formats
|  |  | Total Count |  | 6 |  |  |  |  | CSV | 3,5,2,1,5,3
|  |  | Data |  | 1 | 2 | 2 | 3 | 5 | SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="6" average="3.16666666666667" median="3">3,5,2,1,5,3</sip>
|  |  | Estimate |  | 4 | 4 | 5 | 5 | 6 | Distribution | <distribution name="dist" shape="fromSamples">3,5,2,1,5,3</distribution>
|  |  | Samples Or Data |  | 6 | 6 | 5 | 4 | 4
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
How many amples?
You could make this spreadsheet use more historical data, but its not statistically necessary. My advice: use the most recent 15 samples if you have them to avoid using "old" data that was cptured when the team was performing differently than it is now. You should use the most recent data where the error percentage is less than 10%

## Remaining Stories Actuals
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2017-07-01 | 27
2017-07-08 | 25
2017-07-15 | 20
2017-07-22 | 19
2017-07-29
2017-08-05
2017-08-12
2017-08-19
2017-08-26
2017-09-02
2017-09-09
2017-09-16
2017-09-23
2017-09-30
2017-10-07
2017-10-14
2017-10-21
2017-10-28
2017-11-04
2017-11-11
2017-11-18
2017-11-25
2017-12-02
2017-12-09
2017-12-16
2017-12-23
2017-12-30
2018-01-06
2018-01-13
2018-01-20
2018-01-27
2018-02-03
2018-02-10
2018-02-17
2018-02-24
2018-03-03
2018-03-10
2018-03-17
2018-03-24
2018-03-31
2018-04-07
2018-04-14
2018-04-21
2018-04-28
2018-05-05
2018-05-12
2018-05-19
2018-05-26
2018-06-02
2018-06-09
2018-06-16
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Settings
Duration name | days
1 week | 7
2 weeks | 14
3 weeks | 21
4 weeks | 28
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.

## Monte Carlo (hidden)
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
 | time axis 2017-07-01 to 2018-06-30
1 | 13 | 2017-09-30 | 51 | 48 | 45 | 39 | 36 | 32 | 29 | 23 | 20 | 17 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 16 | 2017-10-21 | 68 | 65 | 61 | 58 | 53 | 49 | 46 | 42 | 37 | 33 | 29 | 25 | 19 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 31 | 2018-02-03 | 133 | 129 | 126 | 121 | 116 | 111 | 105 | 102 | 97 | 91 | 87 | 82 | 78 | 74 | 69 | 66 | 62 | 57 | 53 | 47 | 44 | 40 | 34 | 30 | 24 | 19 | 15 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 19 | 2017-11-11 | 79 | 74 | 68 | 64 | 59 | 55 | 52 | 48 | 43 | 40 | 37 | 31 | 26 | 21 | 16 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 25 | 2017-12-23 | 109 | 104 | 101 | 98 | 95 | 89 | 86 | 82 | 77 | 71 | 68 | 65 | 59 | 55 | 51 | 45 | 41 | 35 | 29 | 25 | 22 | 18 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 26 | 2017-12-30 | 115 | 112 | 107 | 102 | 99 | 93 | 90 | 85 | 79 | 73 | 67 | 63 | 58 | 54 | 48 | 44 | 41 | 37 | 34 | 28 | 24 | 21 | 16 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 36 | 2018-03-10 | 158 | 155 | 150 | 146 | 141 | 137 | 133 | 129 | 123 | 118 | 112 | 108 | 105 | 100 | 96 | 91 | 88 | 83 | 78 | 74 | 70 | 65 | 62 | 58 | 54 | 50 | 46 | 41 | 37 | 31 | 26 | 22 | 18 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 32 | 2018-02-10 | 143 | 138 | 132 | 129 | 126 | 122 | 117 | 114 | 109 | 106 | 102 | 96 | 93 | 89 | 83 | 77 | 72 | 67 | 63 | 58 | 52 | 48 | 44 | 41 | 37 | 33 | 28 | 23 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 32 | 2018-02-10 | 150 | 146 | 141 | 136 | 130 | 124 | 118 | 113 | 109 | 105 | 102 | 98 | 92 | 88 | 82 | 78 | 73 | 67 | 62 | 57 | 51 | 47 | 43 | 39 | 36 | 30 | 24 | 21 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 14 | 2017-10-07 | 61 | 55 | 51 | 47 | 44 | 38 | 33 | 28 | 25 | 21 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 18 | 2017-11-04 | 81 | 76 | 71 | 65 | 59 | 54 | 48 | 42 | 39 | 36 | 30 | 24 | 21 | 17 | 14 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 15 | 2017-10-14 | 64 | 60 | 54 | 48 | 45 | 39 | 36 | 31 | 27 | 22 | 19 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 18 | 2017-11-04 | 78 | 73 | 70 | 64 | 58 | 54 | 48 | 45 | 39 | 35 | 30 | 25 | 20 | 16 | 13 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 28 | 2018-01-13 | 116 | 112 | 107 | 103 | 100 | 96 | 92 | 89 | 86 | 80 | 77 | 72 | 68 | 65 | 60 | 57 | 54 | 50 | 46 | 41 | 35 | 31 | 28 | 24 | 18 | 15 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 21 | 2017-11-25 | 90 | 87 | 82 | 78 | 74 | 71 | 68 | 63 | 59 | 53 | 50 | 47 | 43 | 38 | 34 | 30 | 24 | 20 | 15 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 30 | 2018-01-27 | 136 | 131 | 127 | 124 | 119 | 114 | 108 | 104 | 101 | 95 | 90 | 84 | 80 | 76 | 72 | 67 | 62 | 58 | 55 | 50 | 44 | 41 | 38 | 32 | 29 | 23 | 17 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 27 | 2018-01-06 | 119 | 113 | 107 | 104 | 99 | 96 | 90 | 86 | 83 | 78 | 73 | 69 | 63 | 59 | 56 | 53 | 47 | 42 | 37 | 31 | 27 | 24 | 19 | 16 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 23 | 2017-12-09 | 94 | 90 | 87 | 83 | 80 | 77 | 74 | 69 | 65 | 62 | 56 | 53 | 50 | 44 | 41 | 35 | 31 | 25 | 22 | 18 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 34 | 2018-02-24 | 149 | 146 | 143 | 138 | 134 | 131 | 128 | 123 | 119 | 113 | 108 | 105 | 102 | 99 | 95 | 89 | 84 | 78 | 73 | 70 | 66 | 62 | 57 | 51 | 45 | 39 | 33 | 30 | 27 | 24 | 21 | 18 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 16 | 2017-10-21 | 66 | 63 | 57 | 51 | 45 | 42 | 37 | 33 | 30 | 24 | 21 | 16 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 29 | 2018-01-20 | 132 | 128 | 124 | 121 | 118 | 115 | 109 | 104 | 98 | 93 | 87 | 81 | 77 | 74 | 69 | 63 | 57 | 54 | 49 | 43 | 37 | 31 | 28 | 25 | 21 | 18 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 14 | 2017-10-07 | 59 | 54 | 48 | 44 | 40 | 37 | 34 | 30 | 26 | 20 | 16 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 26 | 2017-12-30 | 120 | 116 | 110 | 106 | 101 | 97 | 91 | 87 | 82 | 79 | 73 | 67 | 62 | 57 | 53 | 50 | 44 | 39 | 33 | 27 | 23 | 19 | 15 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 19 | 2017-11-11 | 85 | 81 | 76 | 73 | 70 | 65 | 62 | 57 | 53 | 49 | 46 | 43 | 37 | 31 | 25 | 20 | 15 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 14 | 2017-10-07 | 64 | 60 | 54 | 49 | 44 | 41 | 36 | 33 | 27 | 22 | 17 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 13 | 2017-09-30 | 58 | 52 | 48 | 43 | 39 | 33 | 30 | 26 | 20 | 16 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 19 | 2017-11-11 | 68 | 64 | 61 | 57 | 53 | 50 | 46 | 43 | 40 | 34 | 31 | 28 | 24 | 21 | 18 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 33 | 2018-02-17 | 150 | 146 | 142 | 137 | 134 | 129 | 126 | 123 | 119 | 115 | 111 | 105 | 99 | 96 | 91 | 85 | 80 | 75 | 71 | 65 | 59 | 53 | 50 | 47 | 43 | 40 | 34 | 28 | 23 | 19 | 15 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 16 | 2017-10-21 | 73 | 70 | 67 | 63 | 59 | 53 | 47 | 41 | 37 | 31 | 26 | 22 | 16 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 30 | 2018-01-27 | 137 | 132 | 129 | 126 | 120 | 114 | 110 | 104 | 99 | 95 | 90 | 87 | 81 | 78 | 73 | 69 | 66 | 60 | 56 | 52 | 47 | 41 | 37 | 33 | 27 | 21 | 15 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 33 | 2018-02-17 | 140 | 136 | 131 | 126 | 123 | 118 | 112 | 108 | 102 | 99 | 96 | 90 | 85 | 81 | 75 | 71 | 67 | 62 | 57 | 51 | 48 | 45 | 40 | 35 | 31 | 27 | 24 | 19 | 16 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 24 | 2017-12-16 | 104 | 101 | 98 | 92 | 88 | 82 | 76 | 73 | 67 | 62 | 56 | 52 | 47 | 43 | 40 | 36 | 32 | 27 | 22 | 18 | 15 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 12 | 2017-09-23 | 59 | 53 | 47 | 42 | 37 | 31 | 26 | 20 | 15 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 23 | 2017-12-09 | 102 | 99 | 93 | 88 | 82 | 78 | 72 | 68 | 65 | 60 | 56 | 53 | 47 | 42 | 38 | 32 | 27 | 24 | 20 | 17 | 13 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 22 | 2017-12-02 | 99 | 94 | 90 | 85 | 80 | 77 | 72 | 68 | 64 | 60 | 55 | 50 | 44 | 39 | 36 | 30 | 26 | 22 | 19 | 14 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 26 | 2017-12-30 | 120 | 117 | 111 | 105 | 100 | 97 | 94 | 89 | 84 | 78 | 72 | 68 | 62 | 59 | 54 | 49 | 44 | 40 | 37 | 34 | 28 | 22 | 16 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 23 | 2017-12-09 | 105 | 102 | 97 | 94 | 88 | 84 | 79 | 73 | 69 | 63 | 60 | 55 | 49 | 46 | 41 | 35 | 31 | 25 | 21 | 16 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 28 | 2018-01-13 | 122 | 119 | 113 | 107 | 103 | 98 | 92 | 86 | 83 | 79 | 74 | 70 | 64 | 60 | 54 | 50 | 47 | 41 | 35 | 32 | 28 | 23 | 20 | 15 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 19 | 2017-11-11 | 89 | 85 | 81 | 78 | 73 | 67 | 64 | 59 | 53 | 48 | 45 | 40 | 34 | 30 | 26 | 21 | 16 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 16 | 2017-10-21 | 71 | 68 | 65 | 59 | 54 | 49 | 43 | 40 | 36 | 30 | 26 | 22 | 17 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 14 | 2017-10-07 | 62 | 58 | 55 | 50 | 44 | 39 | 33 | 29 | 25 | 20 | 16 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 31 | 2018-02-03 | 143 | 138 | 134 | 131 | 125 | 119 | 114 | 111 | 107 | 104 | 98 | 93 | 88 | 82 | 77 | 71 | 66 | 62 | 58 | 54 | 51 | 48 | 43 | 37 | 33 | 27 | 24 | 18 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 12 | 2017-09-23 | 54 | 50 | 46 | 42 | 36 | 30 | 24 | 20 | 17 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 39 | 2018-03-31 | 158 | 154 | 150 | 146 | 143 | 139 | 136 | 130 | 125 | 122 | 116 | 113 | 109 | 106 | 103 | 97 | 92 | 88 | 83 | 79 | 75 | 72 | 69 | 66 | 62 | 56 | 53 | 50 | 44 | 41 | 36 | 30 | 27 | 23 | 20 | 15 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 14 | 2017-10-07 | 64 | 61 | 55 | 50 | 47 | 41 | 35 | 30 | 24 | 21 | 18 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 28 | 2018-01-13 | 117 | 114 | 108 | 103 | 97 | 93 | 90 | 87 | 83 | 79 | 76 | 73 | 69 | 64 | 61 | 56 | 52 | 49 | 45 | 40 | 37 | 31 | 25 | 21 | 16 | 13 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 22 | 2017-12-02 | 100 | 97 | 92 | 87 | 81 | 77 | 72 | 68 | 62 | 57 | 53 | 48 | 45 | 41 | 38 | 32 | 28 | 22 | 18 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 28 | 2018-01-13 | 119 | 115 | 112 | 108 | 103 | 100 | 96 | 93 | 87 | 81 | 75 | 69 | 63 | 58 | 53 | 49 | 46 | 43 | 38 | 33 | 28 | 24 | 20 | 16 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 28 | 2018-01-13 | 125 | 120 | 116 | 111 | 107 | 102 | 97 | 94 | 91 | 86 | 82 | 76 | 73 | 69 | 65 | 59 | 53 | 48 | 42 | 36 | 31 | 27 | 22 | 16 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 23 | 2017-12-09 | 100 | 97 | 91 | 88 | 83 | 78 | 75 | 72 | 67 | 62 | 59 | 55 | 49 | 45 | 42 | 38 | 34 | 30 | 24 | 18 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 26 | 2017-12-30 | 123 | 119 | 115 | 111 | 105 | 102 | 96 | 92 | 86 | 80 | 74 | 70 | 65 | 61 | 55 | 49 | 44 | 40 | 35 | 29 | 26 | 23 | 19 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 15 | 2017-10-14 | 62 | 58 | 52 | 49 | 44 | 38 | 34 | 30 | 27 | 24 | 21 | 17 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 32 | 2018-02-10 | 146 | 142 | 136 | 130 | 124 | 121 | 115 | 112 | 106 | 101 | 97 | 92 | 86 | 83 | 80 | 76 | 73 | 69 | 64 | 61 | 58 | 53 | 48 | 42 | 37 | 31 | 27 | 24 | 18 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 23 | 2017-12-09 | 88 | 84 | 81 | 77 | 73 | 67 | 64 | 58 | 54 | 50 | 47 | 44 | 41 | 38 | 35 | 32 | 28 | 23 | 17 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 22 | 2017-12-02 | 105 | 99 | 96 | 92 | 88 | 82 | 77 | 73 | 69 | 64 | 58 | 52 | 46 | 41 | 37 | 31 | 27 | 24 | 18 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 27 | 2018-01-06 | 113 | 108 | 105 | 100 | 97 | 94 | 88 | 85 | 82 | 79 | 76 | 70 | 66 | 61 | 55 | 52 | 46 | 43 | 39 | 36 | 30 | 26 | 23 | 19 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 29 | 2018-01-20 | 141 | 138 | 132 | 127 | 122 | 118 | 115 | 109 | 103 | 97 | 91 | 86 | 82 | 76 | 71 | 66 | 62 | 57 | 52 | 47 | 41 | 37 | 31 | 27 | 24 | 18 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 26 | 2017-12-30 | 118 | 114 | 109 | 104 | 98 | 95 | 89 | 83 | 78 | 75 | 72 | 68 | 65 | 60 | 55 | 51 | 48 | 43 | 39 | 36 | 31 | 25 | 21 | 16 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 27 | 2018-01-06 | 122 | 116 | 111 | 107 | 101 | 98 | 92 | 89 | 85 | 82 | 76 | 73 | 69 | 66 | 61 | 55 | 50 | 47 | 42 | 38 | 33 | 27 | 21 | 16 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 36 | 2018-03-10 | 143 | 140 | 134 | 129 | 123 | 119 | 115 | 109 | 106 | 103 | 98 | 95 | 91 | 87 | 81 | 78 | 75 | 72 | 69 | 65 | 62 | 58 | 52 | 49 | 46 | 41 | 36 | 32 | 28 | 25 | 20 | 16 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 28 | 2018-01-13 | 129 | 123 | 117 | 111 | 107 | 101 | 97 | 93 | 89 | 86 | 83 | 77 | 71 | 67 | 64 | 58 | 52 | 46 | 40 | 35 | 30 | 27 | 22 | 18 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 13 | 2017-09-30 | 50 | 46 | 43 | 39 | 35 | 31 | 28 | 24 | 18 | 15 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 28 | 2018-01-13 | 122 | 118 | 114 | 111 | 108 | 104 | 101 | 96 | 91 | 88 | 84 | 78 | 75 | 72 | 68 | 62 | 57 | 51 | 48 | 44 | 39 | 36 | 32 | 26 | 21 | 16 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 28 | 2018-01-13 | 128 | 123 | 117 | 111 | 105 | 100 | 94 | 90 | 86 | 80 | 77 | 72 | 69 | 64 | 58 | 53 | 48 | 44 | 41 | 35 | 31 | 26 | 22 | 18 | 14 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 15 | 2017-10-14 | 63 | 59 | 53 | 50 | 47 | 44 | 40 | 36 | 33 | 29 | 24 | 19 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 30 | 2018-01-27 | 130 | 125 | 121 | 116 | 112 | 109 | 105 | 102 | 99 | 94 | 91 | 85 | 80 | 74 | 71 | 65 | 62 | 58 | 55 | 49 | 43 | 39 | 34 | 31 | 27 | 24 | 19 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 35 | 2018-03-03 | 155 | 149 | 145 | 141 | 135 | 130 | 125 | 119 | 114 | 108 | 103 | 100 | 96 | 92 | 89 | 86 | 83 | 78 | 75 | 72 | 69 | 66 | 62 | 59 | 53 | 48 | 42 | 36 | 30 | 26 | 22 | 17 | 14 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 33 | 2018-02-17 | 143 | 137 | 133 | 130 | 126 | 123 | 118 | 115 | 112 | 109 | 103 | 98 | 92 | 86 | 82 | 77 | 73 | 70 | 66 | 60 | 56 | 52 | 46 | 42 | 39 | 33 | 27 | 21 | 17 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 16 | 2017-10-21 | 65 | 62 | 59 | 53 | 49 | 46 | 41 | 38 | 32 | 29 | 26 | 20 | 14 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 12 | 2017-09-23 | 51 | 46 | 40 | 36 | 30 | 27 | 23 | 19 | 14 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 14 | 2017-10-07 | 60 | 56 | 50 | 46 | 40 | 36 | 33 | 29 | 23 | 20 | 15 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 29 | 2018-01-20 | 131 | 128 | 125 | 119 | 116 | 110 | 104 | 100 | 96 | 93 | 88 | 83 | 78 | 73 | 70 | 67 | 63 | 59 | 54 | 48 | 44 | 39 | 36 | 31 | 25 | 20 | 15 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 30 | 2018-01-27 | 133 | 130 | 125 | 119 | 115 | 109 | 105 | 102 | 98 | 93 | 90 | 87 | 82 | 79 | 76 | 71 | 67 | 61 | 55 | 49 | 44 | 38 | 32 | 29 | 25 | 19 | 15 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 37 | 2018-03-17 | 162 | 156 | 150 | 145 | 141 | 135 | 132 | 128 | 122 | 119 | 115 | 112 | 108 | 105 | 102 | 96 | 93 | 87 | 82 | 78 | 73 | 68 | 64 | 60 | 56 | 52 | 49 | 46 | 40 | 37 | 33 | 29 | 23 | 18 | 14 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 26 | 2017-12-30 | 116 | 112 | 109 | 105 | 100 | 96 | 90 | 86 | 83 | 77 | 72 | 66 | 62 | 57 | 53 | 49 | 43 | 39 | 35 | 29 | 24 | 18 | 15 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 21 | 2017-11-25 | 97 | 92 | 87 | 84 | 79 | 76 | 70 | 66 | 60 | 56 | 50 | 46 | 42 | 37 | 32 | 27 | 24 | 19 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 29 | 2018-01-20 | 127 | 121 | 117 | 111 | 107 | 102 | 98 | 93 | 89 | 84 | 79 | 74 | 69 | 64 | 61 | 57 | 54 | 51 | 45 | 41 | 37 | 32 | 26 | 23 | 18 | 15 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 24 | 2017-12-16 | 100 | 96 | 92 | 87 | 84 | 79 | 73 | 70 | 64 | 59 | 54 | 51 | 46 | 43 | 39 | 36 | 33 | 30 | 24 | 20 | 14 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 24 | 2017-12-16 | 104 | 100 | 94 | 90 | 85 | 80 | 77 | 72 | 68 | 65 | 61 | 58 | 54 | 50 | 45 | 40 | 34 | 31 | 27 | 24 | 18 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 24 | 2017-12-16 | 103 | 97 | 91 | 88 | 84 | 78 | 74 | 71 | 68 | 62 | 59 | 55 | 52 | 48 | 45 | 41 | 36 | 32 | 29 | 25 | 19 | 16 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 20 | 2017-11-18 | 85 | 79 | 76 | 70 | 67 | 64 | 58 | 55 | 49 | 46 | 42 | 39 | 35 | 29 | 23 | 19 | 16 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 27 | 2018-01-06 | 123 | 118 | 114 | 108 | 104 | 98 | 93 | 89 | 84 | 78 | 74 | 68 | 64 | 60 | 55 | 51 | 48 | 43 | 39 | 36 | 33 | 27 | 21 | 18 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 18 | 2017-11-04 | 74 | 71 | 66 | 60 | 57 | 54 | 50 | 46 | 40 | 34 | 30 | 25 | 22 | 18 | 15 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 16 | 2017-10-21 | 65 | 62 | 57 | 54 | 48 | 43 | 38 | 33 | 28 | 23 | 20 | 17 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 15 | 2017-10-14 | 62 | 57 | 52 | 47 | 44 | 39 | 34 | 28 | 24 | 20 | 16 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 27 | 2018-01-06 | 120 | 114 | 108 | 104 | 99 | 95 | 92 | 86 | 83 | 79 | 75 | 69 | 66 | 62 | 58 | 53 | 50 | 45 | 42 | 36 | 30 | 27 | 21 | 15 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 24 | 2017-12-16 | 112 | 106 | 103 | 99 | 96 | 91 | 85 | 80 | 74 | 69 | 65 | 59 | 55 | 50 | 47 | 42 | 37 | 34 | 28 | 22 | 16 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 17 | 2017-10-28 | 75 | 72 | 69 | 63 | 59 | 54 | 49 | 44 | 39 | 33 | 28 | 23 | 20 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 25 | 2017-12-23 | 109 | 105 | 101 | 98 | 95 | 90 | 85 | 80 | 76 | 70 | 64 | 60 | 54 | 51 | 46 | 41 | 38 | 32 | 28 | 25 | 21 | 17 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 29 | 2018-01-20 | 120 | 116 | 112 | 106 | 103 | 98 | 95 | 91 | 87 | 83 | 79 | 73 | 70 | 67 | 64 | 60 | 57 | 53 | 48 | 44 | 40 | 35 | 31 | 25 | 21 | 15 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 30 | 2018-01-27 | 132 | 128 | 123 | 117 | 111 | 108 | 103 | 97 | 93 | 89 | 83 | 79 | 73 | 70 | 65 | 60 | 57 | 52 | 47 | 44 | 39 | 36 | 32 | 28 | 23 | 17 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 21 | 2017-11-25 | 98 | 92 | 87 | 84 | 81 | 77 | 71 | 68 | 62 | 56 | 52 | 46 | 40 | 34 | 29 | 24 | 21 | 16 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 27 | 2018-01-06 | 126 | 123 | 119 | 114 | 109 | 103 | 100 | 95 | 89 | 86 | 83 | 79 | 73 | 68 | 65 | 61 | 55 | 51 | 45 | 39 | 34 | 28 | 23 | 18 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 35 | 2018-03-03 | 156 | 153 | 148 | 142 | 137 | 132 | 129 | 126 | 123 | 117 | 112 | 108 | 104 | 101 | 98 | 92 | 86 | 82 | 76 | 73 | 68 | 62 | 59 | 55 | 51 | 47 | 41 | 36 | 33 | 28 | 23 | 17 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 30 | 2018-01-27 | 144 | 140 | 134 | 129 | 125 | 121 | 115 | 109 | 103 | 97 | 91 | 87 | 84 | 80 | 74 | 69 | 64 | 61 | 57 | 53 | 48 | 42 | 39 | 35 | 30 | 24 | 20 | 16 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 22 | 2017-12-02 | 94 | 90 | 87 | 81 | 78 | 73 | 68 | 65 | 60 | 55 | 51 | 48 | 45 | 40 | 37 | 31 | 25 | 22 | 18 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 28 | 2018-01-13 | 133 | 127 | 122 | 116 | 113 | 109 | 103 | 97 | 93 | 87 | 82 | 77 | 73 | 68 | 63 | 59 | 55 | 49 | 45 | 42 | 37 | 33 | 28 | 25 | 21 | 15 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 27 | 2018-01-06 | 117 | 112 | 108 | 104 | 100 | 94 | 91 | 87 | 84 | 79 | 75 | 70 | 66 | 62 | 59 | 55 | 51 | 45 | 40 | 36 | 33 | 28 | 22 | 17 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 19 | 2017-11-11 | 85 | 80 | 76 | 72 | 67 | 61 | 58 | 53 | 50 | 46 | 43 | 39 | 33 | 27 | 21 | 15 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 34 | 2018-02-24 | 152 | 149 | 146 | 143 | 137 | 132 | 128 | 124 | 121 | 117 | 114 | 108 | 104 | 100 | 94 | 88 | 82 | 76 | 70 | 67 | 61 | 56 | 52 | 46 | 43 | 37 | 31 | 27 | 23 | 17 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 31 | 2018-02-03 | 140 | 134 | 131 | 126 | 122 | 119 | 115 | 111 | 105 | 101 | 98 | 93 | 88 | 85 | 79 | 73 | 67 | 64 | 60 | 54 | 51 | 48 | 43 | 40 | 34 | 30 | 25 | 19 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 19 | 2017-11-11 | 76 | 71 | 66 | 63 | 58 | 55 | 51 | 47 | 41 | 38 | 35 | 32 | 26 | 23 | 19 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 20 | 2017-11-18 | 92 | 86 | 80 | 75 | 70 | 64 | 59 | 56 | 52 | 48 | 44 | 39 | 33 | 27 | 21 | 18 | 15 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 23 | 2017-12-09 | 104 | 101 | 96 | 90 | 86 | 83 | 78 | 72 | 68 | 64 | 58 | 53 | 47 | 42 | 36 | 30 | 25 | 21 | 16 | 13 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 22 | 2017-12-02 | 93 | 89 | 83 | 78 | 73 | 67 | 64 | 61 | 56 | 53 | 50 | 44 | 40 | 36 | 31 | 26 | 23 | 19 | 14 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 26 | 2017-12-30 | 109 | 103 | 100 | 94 | 90 | 84 | 80 | 76 | 72 | 67 | 62 | 57 | 53 | 49 | 44 | 41 | 38 | 34 | 28 | 24 | 19 | 13 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 29 | 2018-01-20 | 125 | 119 | 114 | 108 | 103 | 100 | 95 | 92 | 87 | 84 | 79 | 75 | 72 | 69 | 64 | 61 | 55 | 49 | 43 | 37 | 32 | 29 | 25 | 22 | 19 | 15 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 28 | 2018-01-13 | 122 | 117 | 111 | 106 | 103 | 99 | 95 | 90 | 84 | 80 | 77 | 74 | 71 | 68 | 62 | 57 | 52 | 46 | 40 | 35 | 29 | 26 | 22 | 17 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 33 | 2018-02-17 | 146 | 142 | 137 | 134 | 129 | 124 | 118 | 112 | 109 | 103 | 100 | 94 | 90 | 86 | 80 | 77 | 74 | 70 | 64 | 58 | 53 | 49 | 46 | 40 | 34 | 31 | 26 | 21 | 18 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 23 | 2017-12-09 | 101 | 97 | 94 | 88 | 84 | 81 | 76 | 70 | 66 | 60 | 55 | 51 | 45 | 41 | 38 | 33 | 27 | 23 | 20 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 12 | 2017-09-23 | 56 | 50 | 46 | 40 | 34 | 29 | 26 | 23 | 17 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 20 | 2017-11-18 | 96 | 90 | 85 | 79 | 74 | 69 | 64 | 58 | 54 | 49 | 45 | 42 | 36 | 31 | 25 | 20 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 19 | 2017-11-11 | 71 | 67 | 63 | 59 | 54 | 50 | 46 | 43 | 39 | 33 | 30 | 26 | 22 | 18 | 14 | 11 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 30 | 2018-01-27 | 131 | 128 | 122 | 118 | 115 | 110 | 107 | 103 | 98 | 94 | 89 | 83 | 79 | 75 | 69 | 65 | 60 | 56 | 52 | 46 | 43 | 40 | 34 | 29 | 26 | 22 | 16 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 32 | 2018-02-10 | 139 | 134 | 131 | 127 | 121 | 116 | 112 | 107 | 103 | 99 | 96 | 92 | 87 | 83 | 79 | 75 | 72 | 69 | 65 | 62 | 59 | 53 | 48 | 45 | 42 | 36 | 30 | 26 | 21 | 15 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 21 | 2017-11-25 | 98 | 92 | 88 | 83 | 77 | 72 | 66 | 60 | 57 | 52 | 48 | 44 | 41 | 35 | 30 | 26 | 21 | 16 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 22 | 2017-12-02 | 101 | 98 | 93 | 88 | 82 | 77 | 71 | 66 | 60 | 54 | 49 | 44 | 40 | 35 | 32 | 28 | 24 | 18 | 13 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 19 | 2017-11-11 | 84 | 78 | 73 | 67 | 63 | 58 | 54 | 48 | 45 | 42 | 36 | 32 | 26 | 23 | 19 | 14 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 33 | 2018-02-17 | 147 | 141 | 138 | 135 | 131 | 125 | 119 | 114 | 111 | 107 | 103 | 99 | 95 | 89 | 84 | 78 | 72 | 68 | 62 | 57 | 54 | 51 | 47 | 41 | 37 | 34 | 28 | 24 | 21 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 36 | 2018-03-10 | 159 | 155 | 151 | 147 | 143 | 140 | 135 | 130 | 127 | 121 | 118 | 112 | 108 | 102 | 98 | 92 | 86 | 83 | 77 | 73 | 69 | 64 | 61 | 55 | 52 | 46 | 42 | 37 | 31 | 27 | 22 | 19 | 14 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 16 | 2017-10-21 | 67 | 64 | 60 | 57 | 53 | 50 | 45 | 42 | 38 | 34 | 28 | 22 | 17 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 13 | 2017-09-30 | 59 | 56 | 53 | 47 | 43 | 38 | 32 | 27 | 22 | 17 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 31 | 2018-02-03 | 130 | 126 | 120 | 117 | 111 | 107 | 101 | 98 | 95 | 91 | 87 | 84 | 78 | 75 | 70 | 66 | 62 | 58 | 52 | 48 | 45 | 39 | 35 | 31 | 28 | 24 | 19 | 15 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 29 | 2018-01-20 | 124 | 120 | 115 | 112 | 109 | 103 | 100 | 97 | 92 | 86 | 81 | 77 | 71 | 68 | 64 | 59 | 56 | 52 | 46 | 42 | 38 | 32 | 29 | 26 | 22 | 17 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 20 | 2017-11-18 | 94 | 89 | 86 | 80 | 76 | 71 | 65 | 59 | 53 | 47 | 41 | 37 | 32 | 28 | 25 | 20 | 14 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 32 | 2018-02-10 | 144 | 138 | 133 | 128 | 124 | 119 | 115 | 112 | 106 | 103 | 100 | 94 | 89 | 83 | 80 | 74 | 71 | 67 | 63 | 58 | 52 | 49 | 44 | 41 | 36 | 30 | 24 | 21 | 17 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 16 | 2017-10-21 | 73 | 70 | 66 | 61 | 56 | 52 | 46 | 41 | 38 | 32 | 26 | 20 | 16 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 27 | 2018-01-06 | 120 | 114 | 109 | 103 | 99 | 96 | 90 | 87 | 82 | 77 | 71 | 68 | 62 | 59 | 55 | 52 | 46 | 40 | 34 | 30 | 26 | 23 | 20 | 16 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 30 | 2018-01-27 | 143 | 139 | 133 | 128 | 122 | 118 | 112 | 107 | 101 | 98 | 94 | 90 | 85 | 80 | 74 | 69 | 66 | 60 | 54 | 49 | 43 | 39 | 34 | 31 | 27 | 22 | 19 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 14 | 2017-10-07 | 57 | 54 | 50 | 47 | 41 | 36 | 33 | 29 | 25 | 22 | 19 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 34 | 2018-02-24 | 158 | 155 | 151 | 148 | 143 | 138 | 132 | 126 | 123 | 119 | 114 | 111 | 106 | 102 | 96 | 90 | 84 | 81 | 78 | 72 | 68 | 63 | 59 | 55 | 50 | 45 | 41 | 38 | 32 | 27 | 23 | 17 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 14 | 2017-10-07 | 56 | 52 | 48 | 43 | 40 | 37 | 31 | 28 | 25 | 22 | 18 | 15 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 17 | 2017-10-28 | 76 | 72 | 68 | 64 | 60 | 56 | 51 | 47 | 42 | 39 | 33 | 30 | 25 | 19 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 15 | 2017-10-14 | 57 | 52 | 47 | 44 | 40 | 36 | 33 | 30 | 26 | 20 | 17 | 14 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 27 | 2018-01-06 | 128 | 124 | 119 | 114 | 109 | 103 | 99 | 93 | 87 | 81 | 75 | 70 | 64 | 59 | 56 | 52 | 46 | 41 | 37 | 31 | 27 | 24 | 21 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 26 | 2017-12-30 | 112 | 109 | 106 | 101 | 98 | 94 | 89 | 83 | 78 | 74 | 69 | 66 | 60 | 56 | 50 | 47 | 43 | 38 | 34 | 29 | 25 | 19 | 14 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 20 | 2017-11-18 | 89 | 86 | 81 | 78 | 72 | 69 | 66 | 61 | 56 | 50 | 46 | 41 | 35 | 31 | 25 | 20 | 16 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 13 | 2017-09-30 | 54 | 49 | 46 | 40 | 37 | 32 | 29 | 24 | 18 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 20 | 2017-11-18 | 85 | 82 | 77 | 72 | 66 | 60 | 57 | 53 | 48 | 45 | 42 | 38 | 32 | 29 | 24 | 18 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 28 | 2018-01-13 | 132 | 127 | 123 | 118 | 113 | 110 | 104 | 101 | 95 | 90 | 86 | 81 | 77 | 72 | 67 | 64 | 58 | 52 | 46 | 40 | 35 | 31 | 25 | 22 | 17 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 13 | 2017-09-30 | 57 | 51 | 48 | 44 | 41 | 36 | 31 | 28 | 22 | 16 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 14 | 2017-10-07 | 56 | 53 | 49 | 45 | 40 | 37 | 32 | 27 | 24 | 21 | 18 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 13 | 2017-09-30 | 61 | 56 | 51 | 45 | 39 | 35 | 32 | 27 | 21 | 16 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 14 | 2017-10-07 | 64 | 61 | 55 | 49 | 45 | 42 | 37 | 32 | 29 | 24 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 23 | 2017-12-09 | 97 | 93 | 89 | 84 | 80 | 77 | 73 | 68 | 63 | 59 | 55 | 50 | 46 | 43 | 37 | 33 | 29 | 25 | 19 | 16 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 26 | 2017-12-30 | 117 | 111 | 108 | 104 | 100 | 95 | 90 | 87 | 81 | 76 | 72 | 69 | 64 | 58 | 55 | 52 | 48 | 42 | 39 | 34 | 31 | 25 | 20 | 15 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 34 | 2018-02-24 | 151 | 145 | 142 | 137 | 133 | 129 | 126 | 120 | 116 | 110 | 106 | 103 | 97 | 91 | 87 | 82 | 77 | 71 | 66 | 61 | 55 | 49 | 45 | 42 | 36 | 32 | 28 | 24 | 20 | 16 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 14 | 2017-10-07 | 58 | 54 | 50 | 44 | 41 | 35 | 30 | 26 | 21 | 18 | 14 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 31 | 2018-02-03 | 148 | 142 | 137 | 132 | 126 | 121 | 115 | 109 | 105 | 99 | 93 | 88 | 82 | 77 | 73 | 67 | 61 | 58 | 55 | 52 | 48 | 43 | 37 | 32 | 27 | 24 | 18 | 14 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 14 | 2017-10-07 | 61 | 55 | 52 | 46 | 41 | 37 | 31 | 28 | 23 | 18 | 15 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 32 | 2018-02-10 | 152 | 147 | 141 | 136 | 132 | 128 | 122 | 118 | 112 | 106 | 103 | 99 | 93 | 88 | 83 | 78 | 72 | 66 | 63 | 59 | 55 | 49 | 43 | 37 | 34 | 31 | 25 | 22 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 26 | 2017-12-30 | 119 | 116 | 112 | 109 | 104 | 100 | 97 | 91 | 85 | 79 | 74 | 71 | 65 | 59 | 55 | 49 | 43 | 37 | 34 | 30 | 24 | 19 | 16 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 21 | 2017-11-25 | 88 | 83 | 80 | 77 | 72 | 69 | 63 | 60 | 57 | 54 | 51 | 45 | 40 | 35 | 31 | 27 | 23 | 20 | 17 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 34 | 2018-02-24 | 147 | 142 | 139 | 135 | 132 | 126 | 122 | 119 | 116 | 112 | 109 | 103 | 99 | 95 | 89 | 85 | 79 | 75 | 69 | 64 | 60 | 56 | 51 | 47 | 42 | 37 | 32 | 29 | 24 | 20 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 18 | 2017-11-04 | 84 | 78 | 75 | 72 | 66 | 61 | 55 | 49 | 45 | 40 | 35 | 30 | 24 | 18 | 14 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 32 | 2018-02-10 | 138 | 134 | 131 | 125 | 119 | 115 | 109 | 106 | 103 | 97 | 91 | 87 | 83 | 78 | 73 | 70 | 67 | 64 | 61 | 58 | 54 | 50 | 47 | 42 | 39 | 33 | 29 | 25 | 19 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 30 | 2018-01-27 | 123 | 119 | 116 | 113 | 108 | 105 | 100 | 97 | 91 | 85 | 79 | 74 | 70 | 67 | 62 | 59 | 55 | 51 | 46 | 43 | 40 | 35 | 29 | 24 | 20 | 17 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 25 | 2017-12-23 | 103 | 98 | 92 | 87 | 84 | 81 | 77 | 72 | 69 | 66 | 62 | 59 | 55 | 52 | 46 | 41 | 37 | 33 | 29 | 24 | 21 | 15 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 18 | 2017-11-04 | 90 | 84 | 78 | 72 | 69 | 65 | 60 | 54 | 48 | 44 | 38 | 33 | 27 | 21 | 15 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 37 | 2018-03-17 | 156 | 151 | 147 | 143 | 138 | 135 | 132 | 128 | 123 | 119 | 116 | 110 | 107 | 104 | 101 | 97 | 91 | 85 | 79 | 75 | 72 | 69 | 64 | 61 | 56 | 50 | 47 | 41 | 36 | 33 | 30 | 25 | 19 | 14 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 23 | 2017-12-09 | 93 | 89 | 84 | 81 | 77 | 73 | 69 | 63 | 60 | 57 | 53 | 47 | 44 | 41 | 38 | 34 | 30 | 25 | 22 | 16 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 30 | 2018-01-27 | 135 | 131 | 126 | 120 | 115 | 111 | 108 | 102 | 98 | 93 | 87 | 82 | 76 | 72 | 68 | 64 | 58 | 54 | 50 | 47 | 44 | 38 | 34 | 29 | 26 | 20 | 16 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 17 | 2017-10-28 | 68 | 63 | 60 | 57 | 52 | 49 | 44 | 41 | 37 | 34 | 31 | 25 | 21 | 15 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 25 | 2017-12-23 | 111 | 107 | 102 | 98 | 92 | 88 | 85 | 81 | 77 | 72 | 69 | 66 | 62 | 57 | 52 | 46 | 41 | 38 | 33 | 29 | 24 | 18 | 13 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 29 | 2018-01-20 | 126 | 122 | 117 | 113 | 107 | 104 | 100 | 94 | 89 | 84 | 79 | 75 | 71 | 67 | 64 | 58 | 52 | 46 | 43 | 38 | 35 | 29 | 26 | 23 | 18 | 14 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 16 | 2017-10-21 | 80 | 77 | 72 | 67 | 62 | 58 | 54 | 48 | 44 | 38 | 32 | 27 | 21 | 15 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 18 | 2017-11-04 | 81 | 77 | 71 | 65 | 61 | 57 | 54 | 50 | 46 | 42 | 36 | 30 | 26 | 20 | 17 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 14 | 2017-10-07 | 62 | 56 | 50 | 47 | 41 | 37 | 31 | 28 | 22 | 16 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 17 | 2017-10-28 | 72 | 69 | 65 | 60 | 56 | 51 | 48 | 43 | 40 | 36 | 31 | 28 | 22 | 17 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 16 | 2017-10-21 | 75 | 70 | 67 | 64 | 59 | 56 | 51 | 46 | 41 | 36 | 31 | 27 | 21 | 15 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 21 | 2017-11-25 | 80 | 76 | 72 | 69 | 66 | 63 | 60 | 57 | 51 | 48 | 45 | 40 | 36 | 30 | 24 | 21 | 17 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 15 | 2017-10-14 | 69 | 66 | 63 | 57 | 52 | 49 | 45 | 40 | 34 | 28 | 24 | 19 | 16 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 13 | 2017-09-30 | 52 | 47 | 44 | 41 | 38 | 32 | 27 | 24 | 20 | 15 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 29 | 2018-01-20 | 138 | 135 | 131 | 125 | 121 | 118 | 114 | 110 | 105 | 102 | 96 | 92 | 86 | 83 | 78 | 73 | 68 | 63 | 57 | 51 | 48 | 42 | 39 | 33 | 27 | 21 | 15 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 17 | 2017-10-28 | 71 | 67 | 62 | 59 | 56 | 52 | 48 | 44 | 40 | 36 | 30 | 26 | 20 | 16 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 23 | 2017-12-09 | 98 | 93 | 90 | 85 | 81 | 76 | 72 | 69 | 65 | 62 | 56 | 53 | 49 | 44 | 41 | 38 | 33 | 27 | 23 | 18 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 14 | 2017-10-07 | 58 | 54 | 49 | 46 | 41 | 36 | 31 | 27 | 24 | 20 | 14 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 22 | 2017-12-02 | 107 | 101 | 97 | 92 | 86 | 83 | 80 | 76 | 70 | 64 | 61 | 56 | 51 | 46 | 40 | 34 | 28 | 22 | 17 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 16 | 2017-10-21 | 68 | 62 | 58 | 55 | 49 | 43 | 38 | 34 | 29 | 24 | 21 | 17 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 13 | 2017-09-30 | 52 | 48 | 44 | 40 | 34 | 30 | 27 | 21 | 15 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 12 | 2017-09-23 | 58 | 53 | 48 | 43 | 37 | 31 | 27 | 23 | 18 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 15 | 2017-10-14 | 62 | 59 | 53 | 48 | 43 | 38 | 33 | 30 | 27 | 22 | 17 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 18 | 2017-11-04 | 86 | 80 | 75 | 70 | 65 | 59 | 55 | 52 | 46 | 42 | 37 | 32 | 26 | 21 | 15 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 36 | 2018-03-10 | 159 | 155 | 149 | 146 | 143 | 137 | 134 | 130 | 125 | 121 | 117 | 111 | 107 | 102 | 97 | 91 | 86 | 82 | 77 | 74 | 71 | 66 | 62 | 58 | 54 | 48 | 44 | 41 | 37 | 31 | 25 | 20 | 16 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 30 | 2018-01-27 | 137 | 131 | 127 | 124 | 120 | 117 | 112 | 106 | 101 | 95 | 92 | 89 | 85 | 82 | 79 | 74 | 69 | 64 | 58 | 52 | 46 | 40 | 35 | 29 | 26 | 23 | 19 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 29 | 2018-01-20 | 129 | 126 | 121 | 116 | 113 | 109 | 103 | 97 | 94 | 88 | 82 | 79 | 75 | 72 | 68 | 62 | 59 | 56 | 50 | 44 | 38 | 32 | 27 | 22 | 19 | 16 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 34 | 2018-02-24 | 148 | 144 | 139 | 133 | 128 | 125 | 122 | 119 | 113 | 108 | 103 | 99 | 93 | 87 | 83 | 77 | 74 | 71 | 67 | 64 | 60 | 57 | 53 | 47 | 44 | 38 | 34 | 29 | 24 | 21 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 25 | 2017-12-23 | 110 | 104 | 100 | 95 | 91 | 86 | 82 | 77 | 73 | 67 | 64 | 60 | 56 | 53 | 50 | 46 | 41 | 37 | 31 | 25 | 20 | 16 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 33 | 2018-02-17 | 152 | 149 | 146 | 143 | 140 | 136 | 131 | 128 | 123 | 117 | 112 | 106 | 103 | 97 | 93 | 87 | 84 | 78 | 73 | 67 | 61 | 57 | 52 | 47 | 42 | 37 | 32 | 26 | 21 | 16 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 28 | 2018-01-13 | 127 | 123 | 118 | 112 | 106 | 100 | 95 | 89 | 83 | 80 | 75 | 70 | 67 | 63 | 60 | 55 | 51 | 45 | 39 | 34 | 31 | 25 | 22 | 16 | 11 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 26 | 2017-12-30 | 117 | 113 | 108 | 103 | 98 | 93 | 89 | 83 | 80 | 75 | 69 | 63 | 58 | 55 | 52 | 47 | 41 | 36 | 33 | 28 | 24 | 19 | 13 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 35 | 2018-03-03 | 156 | 151 | 146 | 143 | 140 | 135 | 132 | 127 | 124 | 121 | 115 | 110 | 104 | 101 | 96 | 90 | 84 | 79 | 75 | 72 | 67 | 62 | 57 | 53 | 49 | 43 | 38 | 32 | 27 | 23 | 19 | 13 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 25 | 2017-12-23 | 112 | 106 | 101 | 97 | 91 | 87 | 82 | 77 | 72 | 69 | 63 | 59 | 54 | 50 | 45 | 41 | 36 | 33 | 28 | 22 | 18 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 19 | 2017-11-11 | 84 | 79 | 74 | 70 | 66 | 62 | 56 | 50 | 47 | 43 | 40 | 34 | 31 | 25 | 20 | 16 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 17 | 2017-10-28 | 74 | 68 | 62 | 58 | 54 | 49 | 44 | 39 | 36 | 33 | 27 | 23 | 19 | 16 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 19 | 2017-11-11 | 97 | 91 | 85 | 79 | 74 | 68 | 63 | 58 | 54 | 48 | 42 | 36 | 31 | 27 | 23 | 17 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 26 | 2017-12-30 | 125 | 120 | 115 | 109 | 104 | 100 | 96 | 92 | 86 | 80 | 74 | 69 | 65 | 62 | 58 | 55 | 52 | 46 | 40 | 34 | 28 | 23 | 17 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 26 | 2017-12-30 | 116 | 113 | 109 | 105 | 102 | 97 | 94 | 88 | 82 | 77 | 71 | 65 | 62 | 56 | 53 | 49 | 43 | 39 | 35 | 32 | 29 | 26 | 21 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 21 | 2017-11-25 | 93 | 87 | 82 | 76 | 73 | 68 | 65 | 60 | 56 | 53 | 50 | 47 | 43 | 38 | 33 | 27 | 21 | 17 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 22 | 2017-12-02 | 106 | 100 | 95 | 90 | 87 | 82 | 76 | 73 | 69 | 65 | 60 | 54 | 49 | 44 | 38 | 32 | 29 | 24 | 19 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 22 | 2017-12-02 | 101 | 96 | 92 | 86 | 81 | 75 | 72 | 67 | 61 | 56 | 53 | 49 | 46 | 42 | 38 | 32 | 28 | 23 | 18 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 25 | 2017-12-23 | 119 | 113 | 109 | 103 | 100 | 95 | 92 | 88 | 83 | 77 | 73 | 68 | 64 | 59 | 55 | 51 | 46 | 41 | 35 | 32 | 26 | 22 | 16 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 21 | 2017-11-25 | 98 | 94 | 91 | 87 | 81 | 76 | 70 | 66 | 60 | 55 | 49 | 43 | 40 | 36 | 31 | 25 | 21 | 17 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 21 | 2017-11-25 | 91 | 88 | 84 | 79 | 73 | 68 | 62 | 59 | 55 | 51 | 48 | 43 | 40 | 34 | 31 | 28 | 22 | 18 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 27 | 2018-01-06 | 120 | 115 | 112 | 106 | 103 | 99 | 94 | 88 | 82 | 78 | 75 | 70 | 67 | 61 | 55 | 49 | 46 | 41 | 38 | 35 | 30 | 24 | 21 | 17 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 19 | 2017-11-11 | 88 | 82 | 78 | 72 | 68 | 65 | 61 | 55 | 52 | 47 | 44 | 38 | 34 | 30 | 24 | 18 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 18 | 2017-11-04 | 86 | 81 | 76 | 71 | 66 | 61 | 58 | 53 | 49 | 43 | 37 | 31 | 28 | 24 | 21 | 15 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 14 | 2017-10-07 | 58 | 55 | 49 | 46 | 42 | 36 | 32 | 29 | 25 | 21 | 16 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 20 | 2017-11-18 | 87 | 84 | 78 | 74 | 69 | 66 | 60 | 56 | 50 | 47 | 43 | 37 | 32 | 28 | 24 | 20 | 14 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 22 | 2017-12-02 | 103 | 97 | 91 | 87 | 84 | 78 | 72 | 66 | 62 | 57 | 51 | 46 | 41 | 36 | 32 | 28 | 23 | 20 | 14 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 30 | 2018-01-27 | 129 | 123 | 120 | 115 | 109 | 106 | 103 | 99 | 95 | 89 | 84 | 79 | 73 | 70 | 67 | 61 | 58 | 53 | 50 | 45 | 40 | 36 | 32 | 26 | 23 | 19 | 13 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 13 | 2017-09-30 | 61 | 56 | 52 | 46 | 40 | 37 | 33 | 29 | 23 | 18 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 22 | 2017-12-02 | 103 | 98 | 92 | 88 | 84 | 81 | 78 | 73 | 68 | 65 | 59 | 54 | 48 | 42 | 38 | 33 | 28 | 22 | 16 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 27 | 2018-01-06 | 125 | 119 | 113 | 108 | 102 | 99 | 96 | 91 | 87 | 84 | 79 | 73 | 68 | 65 | 61 | 56 | 52 | 48 | 42 | 36 | 31 | 27 | 21 | 17 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 30 | 2018-01-27 | 137 | 133 | 130 | 125 | 119 | 113 | 109 | 103 | 100 | 95 | 90 | 86 | 83 | 77 | 74 | 68 | 63 | 57 | 51 | 45 | 39 | 36 | 33 | 29 | 23 | 19 | 14 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 19 | 2017-11-11 | 87 | 82 | 76 | 72 | 67 | 64 | 60 | 56 | 50 | 44 | 39 | 34 | 29 | 23 | 17 | 14 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 25 | 2017-12-23 | 112 | 106 | 101 | 97 | 93 | 89 | 85 | 82 | 76 | 70 | 67 | 61 | 56 | 50 | 46 | 40 | 35 | 29 | 26 | 23 | 20 | 17 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 25 | 2017-12-23 | 117 | 113 | 109 | 106 | 102 | 99 | 95 | 89 | 85 | 79 | 74 | 68 | 64 | 59 | 53 | 48 | 44 | 39 | 35 | 30 | 24 | 18 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 22 | 2017-12-02 | 97 | 91 | 85 | 82 | 79 | 75 | 70 | 67 | 62 | 57 | 54 | 48 | 42 | 39 | 35 | 30 | 25 | 21 | 15 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 22 | 2017-12-02 | 94 | 90 | 84 | 79 | 73 | 67 | 64 | 60 | 57 | 52 | 49 | 45 | 39 | 36 | 32 | 28 | 23 | 19 | 16 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 15 | 2017-10-14 | 62 | 58 | 55 | 49 | 46 | 40 | 35 | 30 | 26 | 23 | 17 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 16 | 2017-10-21 | 78 | 72 | 66 | 63 | 59 | 53 | 47 | 43 | 38 | 32 | 28 | 24 | 19 | 14 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 30 | 2018-01-27 | 130 | 126 | 121 | 118 | 115 | 109 | 105 | 99 | 93 | 87 | 83 | 80 | 76 | 70 | 64 | 60 | 57 | 53 | 49 | 46 | 41 | 36 | 32 | 29 | 26 | 23 | 19 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 28 | 2018-01-13 | 131 | 125 | 119 | 114 | 111 | 107 | 101 | 95 | 89 | 86 | 81 | 75 | 70 | 66 | 63 | 60 | 54 | 50 | 45 | 39 | 35 | 32 | 29 | 23 | 18 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 24 | 2017-12-16 | 109 | 104 | 99 | 96 | 92 | 88 | 82 | 79 | 73 | 67 | 63 | 59 | 55 | 51 | 47 | 42 | 38 | 32 | 29 | 24 | 18 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 23 | 2017-12-09 | 106 | 101 | 95 | 90 | 84 | 81 | 76 | 70 | 66 | 63 | 60 | 55 | 52 | 49 | 43 | 37 | 33 | 29 | 23 | 17 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 23 | 2017-12-09 | 95 | 92 | 89 | 83 | 80 | 75 | 71 | 67 | 61 | 56 | 52 | 48 | 44 | 41 | 35 | 32 | 28 | 25 | 21 | 18 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 20 | 2017-11-18 | 87 | 82 | 79 | 73 | 70 | 64 | 60 | 57 | 52 | 48 | 44 | 38 | 33 | 29 | 25 | 20 | 17 | 13 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 25 | 2017-12-23 | 113 | 109 | 104 | 99 | 96 | 93 | 87 | 83 | 79 | 74 | 68 | 62 | 57 | 54 | 48 | 42 | 39 | 34 | 29 | 26 | 21 | 18 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 24 | 2017-12-16 | 113 | 108 | 104 | 98 | 93 | 89 | 86 | 83 | 79 | 75 | 71 | 65 | 61 | 55 | 50 | 44 | 40 | 34 | 29 | 23 | 17 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 31 | 2018-02-03 | 140 | 135 | 132 | 127 | 124 | 121 | 115 | 112 | 108 | 104 | 101 | 98 | 92 | 89 | 84 | 80 | 75 | 69 | 64 | 58 | 54 | 48 | 42 | 37 | 31 | 25 | 21 | 16 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 28 | 2018-01-13 | 127 | 121 | 118 | 112 | 108 | 102 | 96 | 93 | 88 | 85 | 82 | 78 | 75 | 71 | 67 | 64 | 58 | 52 | 46 | 40 | 34 | 29 | 25 | 22 | 18 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 21 | 2017-11-25 | 90 | 87 | 82 | 77 | 73 | 67 | 64 | 61 | 55 | 52 | 49 | 45 | 39 | 35 | 31 | 28 | 24 | 18 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 26 | 2017-12-30 | 119 | 113 | 109 | 105 | 101 | 96 | 90 | 87 | 82 | 77 | 74 | 71 | 65 | 62 | 58 | 53 | 48 | 43 | 37 | 31 | 28 | 22 | 16 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 26 | 2017-12-30 | 110 | 105 | 101 | 95 | 92 | 89 | 83 | 79 | 74 | 71 | 66 | 60 | 56 | 50 | 46 | 42 | 36 | 30 | 27 | 22 | 18 | 15 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 21 | 2017-11-25 | 98 | 93 | 90 | 86 | 82 | 76 | 71 | 65 | 60 | 57 | 52 | 46 | 41 | 36 | 30 | 26 | 21 | 17 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 19 | 2017-11-11 | 77 | 74 | 69 | 66 | 61 | 58 | 55 | 52 | 47 | 43 | 37 | 31 | 28 | 22 | 19 | 15 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 20 | 2017-11-18 | 84 | 81 | 75 | 71 | 66 | 63 | 59 | 56 | 52 | 48 | 42 | 39 | 36 | 30 | 27 | 23 | 18 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 21 | 2017-11-25 | 90 | 86 | 83 | 79 | 74 | 71 | 65 | 61 | 57 | 54 | 50 | 45 | 39 | 34 | 28 | 24 | 19 | 15 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 21 | 2017-11-25 | 93 | 89 | 84 | 78 | 75 | 71 | 66 | 61 | 55 | 51 | 47 | 43 | 38 | 33 | 30 | 25 | 20 | 15 | 11 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 13 | 2017-09-30 | 59 | 53 | 49 | 46 | 42 | 37 | 34 | 29 | 23 | 19 | 16 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 18 | 2017-11-04 | 82 | 76 | 72 | 68 | 62 | 58 | 53 | 48 | 43 | 40 | 34 | 31 | 27 | 21 | 15 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 22 | 2017-12-02 | 96 | 91 | 86 | 83 | 78 | 73 | 67 | 61 | 56 | 53 | 47 | 44 | 38 | 35 | 32 | 28 | 22 | 19 | 15 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 17 | 2017-10-28 | 74 | 69 | 66 | 62 | 57 | 53 | 47 | 41 | 35 | 29 | 25 | 22 | 16 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 24 | 2017-12-16 | 103 | 99 | 93 | 88 | 83 | 77 | 74 | 71 | 66 | 63 | 59 | 54 | 49 | 43 | 37 | 34 | 31 | 26 | 23 | 19 | 15 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 20 | 2017-11-18 | 87 | 82 | 79 | 75 | 69 | 66 | 61 | 56 | 51 | 46 | 43 | 38 | 33 | 29 | 24 | 21 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 33 | 2018-02-17 | 138 | 134 | 129 | 125 | 119 | 113 | 108 | 104 | 101 | 97 | 91 | 88 | 85 | 80 | 76 | 70 | 66 | 62 | 56 | 53 | 50 | 47 | 44 | 41 | 38 | 35 | 32 | 26 | 20 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 14 | 2017-10-07 | 59 | 54 | 49 | 43 | 39 | 36 | 32 | 29 | 23 | 18 | 15 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 37 | 2018-03-17 | 153 | 149 | 146 | 140 | 134 | 130 | 125 | 119 | 115 | 110 | 106 | 101 | 96 | 92 | 89 | 85 | 80 | 77 | 74 | 69 | 65 | 59 | 56 | 50 | 47 | 43 | 38 | 35 | 30 | 27 | 24 | 20 | 15 | 11 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 23 | 2017-12-09 | 97 | 93 | 89 | 84 | 79 | 75 | 69 | 66 | 63 | 58 | 55 | 52 | 48 | 43 | 39 | 33 | 27 | 24 | 19 | 15 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 31 | 2018-02-03 | 137 | 133 | 127 | 124 | 120 | 114 | 111 | 106 | 103 | 99 | 93 | 87 | 83 | 77 | 71 | 68 | 65 | 61 | 57 | 51 | 48 | 43 | 39 | 33 | 27 | 24 | 21 | 15 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 15 | 2017-10-14 | 68 | 63 | 59 | 56 | 51 | 48 | 43 | 37 | 31 | 27 | 22 | 19 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 29 | 2018-01-20 | 124 | 119 | 113 | 108 | 105 | 99 | 95 | 92 | 88 | 84 | 79 | 75 | 72 | 68 | 62 | 58 | 54 | 51 | 48 | 45 | 40 | 35 | 30 | 26 | 23 | 18 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 18 | 2017-11-04 | 91 | 87 | 81 | 76 | 73 | 67 | 61 | 55 | 49 | 45 | 39 | 33 | 27 | 22 | 16 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 25 | 2017-12-23 | 103 | 99 | 96 | 92 | 86 | 80 | 75 | 72 | 69 | 65 | 62 | 58 | 52 | 49 | 46 | 43 | 37 | 34 | 28 | 22 | 18 | 14 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 25 | 2017-12-23 | 106 | 101 | 98 | 92 | 89 | 86 | 82 | 79 | 74 | 68 | 64 | 59 | 55 | 52 | 49 | 44 | 41 | 35 | 30 | 25 | 19 | 14 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 29 | 2018-01-20 | 117 | 114 | 111 | 107 | 103 | 97 | 93 | 89 | 85 | 80 | 74 | 70 | 67 | 64 | 60 | 54 | 51 | 48 | 44 | 40 | 35 | 31 | 28 | 23 | 20 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 22 | 2017-12-02 | 101 | 95 | 90 | 85 | 82 | 76 | 70 | 67 | 62 | 59 | 54 | 50 | 45 | 40 | 36 | 30 | 25 | 22 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 22 | 2017-12-02 | 98 | 93 | 90 | 85 | 80 | 76 | 70 | 64 | 58 | 52 | 47 | 44 | 40 | 37 | 32 | 28 | 25 | 22 | 17 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 25 | 2017-12-23 | 106 | 102 | 99 | 94 | 89 | 86 | 83 | 78 | 74 | 70 | 66 | 61 | 58 | 53 | 49 | 45 | 39 | 34 | 29 | 24 | 21 | 17 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 25 | 2017-12-23 | 111 | 107 | 104 | 98 | 95 | 91 | 85 | 82 | 76 | 70 | 66 | 60 | 54 | 51 | 47 | 41 | 37 | 31 | 26 | 23 | 20 | 15 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 18 | 2017-11-04 | 73 | 68 | 65 | 61 | 56 | 50 | 46 | 42 | 39 | 35 | 32 | 29 | 26 | 20 | 17 | 13 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 27 | 2018-01-06 | 124 | 121 | 115 | 111 | 105 | 102 | 98 | 93 | 89 | 84 | 78 | 74 | 69 | 65 | 59 | 55 | 49 | 45 | 39 | 34 | 31 | 25 | 20 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 13 | 2017-09-30 | 52 | 49 | 45 | 39 | 35 | 32 | 26 | 23 | 17 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 21 | 2017-11-25 | 85 | 82 | 78 | 75 | 72 | 66 | 62 | 57 | 53 | 48 | 44 | 38 | 35 | 30 | 26 | 22 | 19 | 13 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 13 | 2017-09-30 | 62 | 59 | 53 | 49 | 43 | 37 | 31 | 28 | 22 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 30 | 2018-01-27 | 133 | 130 | 126 | 123 | 117 | 113 | 109 | 104 | 101 | 97 | 93 | 89 | 84 | 79 | 73 | 68 | 62 | 56 | 53 | 47 | 42 | 36 | 32 | 29 | 26 | 21 | 18 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 35 | 2018-03-03 | 150 | 147 | 142 | 139 | 134 | 131 | 127 | 123 | 118 | 115 | 110 | 104 | 99 | 96 | 92 | 88 | 82 | 79 | 75 | 72 | 68 | 62 | 59 | 54 | 49 | 44 | 41 | 35 | 29 | 24 | 21 | 17 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 28 | 2018-01-13 | 128 | 122 | 118 | 112 | 109 | 104 | 100 | 95 | 90 | 85 | 80 | 75 | 69 | 63 | 58 | 53 | 49 | 44 | 38 | 35 | 32 | 27 | 23 | 20 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 14 | 2017-10-07 | 68 | 62 | 57 | 53 | 47 | 41 | 36 | 30 | 26 | 21 | 16 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 33 | 2018-02-17 | 146 | 140 | 136 | 132 | 127 | 124 | 119 | 114 | 110 | 104 | 98 | 94 | 89 | 86 | 83 | 80 | 75 | 70 | 66 | 63 | 60 | 56 | 52 | 49 | 46 | 40 | 34 | 28 | 25 | 19 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 32 | 2018-02-10 | 137 | 133 | 129 | 125 | 120 | 117 | 114 | 110 | 105 | 102 | 96 | 93 | 88 | 82 | 78 | 73 | 68 | 65 | 62 | 57 | 51 | 47 | 43 | 37 | 32 | 28 | 24 | 21 | 17 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 30 | 2018-01-27 | 136 | 130 | 126 | 122 | 119 | 113 | 108 | 105 | 101 | 98 | 95 | 92 | 87 | 84 | 78 | 72 | 68 | 63 | 57 | 54 | 48 | 43 | 39 | 36 | 30 | 24 | 21 | 16 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 21 | 2017-11-25 | 100 | 95 | 90 | 85 | 82 | 79 | 76 | 72 | 66 | 61 | 56 | 51 | 47 | 41 | 35 | 30 | 25 | 19 | 15 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 21 | 2017-11-25 | 104 | 98 | 92 | 86 | 82 | 77 | 74 | 69 | 64 | 59 | 53 | 49 | 44 | 38 | 32 | 28 | 23 | 18 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 18 | 2017-11-04 | 72 | 68 | 64 | 59 | 54 | 51 | 48 | 45 | 42 | 38 | 32 | 26 | 22 | 17 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 26 | 2017-12-30 | 130 | 125 | 119 | 113 | 107 | 101 | 95 | 90 | 87 | 84 | 78 | 72 | 69 | 64 | 59 | 55 | 49 | 45 | 40 | 34 | 31 | 26 | 20 | 16 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 21 | 2017-11-25 | 92 | 86 | 83 | 79 | 76 | 70 | 65 | 61 | 57 | 51 | 48 | 42 | 39 | 35 | 32 | 26 | 21 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 24 | 2017-12-16 | 112 | 108 | 103 | 100 | 95 | 91 | 85 | 82 | 76 | 70 | 64 | 58 | 53 | 49 | 46 | 42 | 39 | 34 | 28 | 24 | 18 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 14 | 2017-10-07 | 55 | 52 | 48 | 42 | 36 | 33 | 28 | 25 | 22 | 17 | 14 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 31 | 2018-02-03 | 136 | 132 | 129 | 125 | 119 | 115 | 112 | 108 | 104 | 99 | 93 | 87 | 84 | 79 | 74 | 68 | 64 | 59 | 56 | 51 | 47 | 44 | 39 | 35 | 32 | 27 | 22 | 19 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 18 | 2017-11-04 | 78 | 73 | 69 | 64 | 59 | 56 | 50 | 46 | 43 | 37 | 33 | 29 | 23 | 19 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 29 | 2018-01-20 | 130 | 125 | 122 | 116 | 112 | 108 | 104 | 99 | 94 | 91 | 88 | 83 | 79 | 73 | 67 | 63 | 57 | 54 | 49 | 43 | 39 | 34 | 31 | 27 | 23 | 17 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 24 | 2017-12-16 | 100 | 96 | 91 | 88 | 84 | 80 | 75 | 71 | 68 | 64 | 60 | 54 | 50 | 47 | 44 | 39 | 35 | 30 | 24 | 19 | 13 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 27 | 2018-01-06 | 121 | 116 | 110 | 104 | 98 | 94 | 89 | 85 | 79 | 75 | 69 | 65 | 61 | 58 | 53 | 50 | 47 | 44 | 39 | 36 | 32 | 28 | 25 | 21 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 22 | 2017-12-02 | 98 | 92 | 86 | 81 | 78 | 72 | 69 | 63 | 59 | 56 | 52 | 48 | 43 | 37 | 31 | 27 | 23 | 19 | 13 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 29 | 2018-01-20 | 132 | 127 | 122 | 116 | 110 | 107 | 103 | 100 | 97 | 94 | 90 | 87 | 81 | 76 | 70 | 64 | 59 | 55 | 52 | 46 | 42 | 37 | 31 | 28 | 22 | 16 | 13 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 25 | 2017-12-23 | 106 | 101 | 97 | 93 | 88 | 84 | 80 | 74 | 69 | 66 | 62 | 56 | 53 | 50 | 46 | 43 | 40 | 37 | 33 | 27 | 23 | 17 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 31 | 2018-02-03 | 132 | 126 | 123 | 117 | 111 | 108 | 103 | 99 | 93 | 90 | 84 | 81 | 78 | 74 | 70 | 65 | 59 | 54 | 48 | 44 | 39 | 34 | 30 | 27 | 24 | 19 | 15 | 11 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 34 | 2018-02-24 | 155 | 150 | 147 | 143 | 139 | 133 | 127 | 122 | 117 | 111 | 105 | 102 | 98 | 92 | 89 | 86 | 83 | 77 | 74 | 71 | 66 | 61 | 56 | 50 | 45 | 40 | 35 | 32 | 27 | 24 | 19 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 25 | 2017-12-23 | 113 | 108 | 103 | 97 | 94 | 91 | 87 | 83 | 80 | 74 | 71 | 65 | 59 | 54 | 49 | 43 | 40 | 34 | 29 | 25 | 21 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 30 | 2018-01-27 | 134 | 131 | 127 | 124 | 120 | 114 | 111 | 106 | 101 | 96 | 93 | 89 | 85 | 79 | 74 | 68 | 65 | 61 | 55 | 49 | 45 | 41 | 35 | 32 | 27 | 23 | 19 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 33 | 2018-02-17 | 144 | 141 | 138 | 132 | 126 | 123 | 117 | 113 | 110 | 106 | 101 | 98 | 95 | 92 | 87 | 81 | 76 | 73 | 68 | 63 | 60 | 55 | 51 | 46 | 40 | 34 | 31 | 26 | 23 | 17 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 23 | 2017-12-09 | 101 | 97 | 94 | 90 | 86 | 82 | 77 | 71 | 66 | 60 | 54 | 50 | 45 | 42 | 39 | 33 | 27 | 22 | 16 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 31 | 2018-02-03 | 137 | 133 | 130 | 127 | 124 | 120 | 116 | 113 | 107 | 101 | 96 | 91 | 85 | 82 | 79 | 73 | 67 | 62 | 56 | 52 | 49 | 46 | 40 | 35 | 29 | 23 | 17 | 14 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 11 | 2017-09-16 | 50 | 44 | 41 | 36 | 33 | 30 | 24 | 21 | 15 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 33 | 2018-02-17 | 149 | 143 | 137 | 132 | 129 | 124 | 121 | 115 | 111 | 108 | 102 | 98 | 92 | 87 | 83 | 78 | 75 | 71 | 66 | 63 | 60 | 55 | 50 | 47 | 43 | 39 | 33 | 27 | 23 | 18 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 25 | 2017-12-23 | 111 | 108 | 102 | 99 | 94 | 89 | 84 | 81 | 76 | 71 | 65 | 60 | 54 | 50 | 47 | 41 | 38 | 35 | 32 | 29 | 24 | 20 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 33 | 2018-02-17 | 151 | 146 | 140 | 136 | 130 | 124 | 121 | 118 | 115 | 109 | 106 | 101 | 96 | 91 | 86 | 82 | 77 | 71 | 65 | 62 | 58 | 55 | 51 | 48 | 43 | 38 | 34 | 28 | 22 | 16 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 13 | 2017-09-30 | 51 | 47 | 44 | 40 | 36 | 33 | 29 | 26 | 20 | 17 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 32 | 2018-02-10 | 148 | 145 | 139 | 133 | 130 | 124 | 118 | 113 | 107 | 104 | 98 | 92 | 89 | 84 | 78 | 72 | 68 | 63 | 60 | 55 | 49 | 45 | 42 | 36 | 30 | 27 | 23 | 19 | 16 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 30 | 2018-01-27 | 124 | 118 | 115 | 109 | 104 | 98 | 94 | 89 | 85 | 82 | 79 | 76 | 73 | 70 | 66 | 63 | 57 | 51 | 48 | 45 | 41 | 37 | 34 | 30 | 25 | 21 | 17 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 14 | 2017-10-07 | 68 | 63 | 58 | 55 | 49 | 45 | 41 | 35 | 32 | 27 | 22 | 16 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 13 | 2017-09-30 | 59 | 55 | 50 | 45 | 41 | 37 | 31 | 25 | 21 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 36 | 2018-03-10 | 146 | 142 | 139 | 136 | 131 | 128 | 124 | 120 | 116 | 113 | 109 | 106 | 100 | 96 | 90 | 85 | 81 | 76 | 70 | 65 | 61 | 55 | 51 | 47 | 43 | 39 | 34 | 31 | 28 | 24 | 20 | 16 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 13 | 2017-09-30 | 55 | 49 | 46 | 42 | 39 | 33 | 29 | 25 | 22 | 19 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 14 | 2017-10-07 | 65 | 60 | 55 | 49 | 43 | 38 | 35 | 30 | 26 | 20 | 15 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 22 | 2017-12-02 | 101 | 96 | 90 | 87 | 83 | 80 | 77 | 72 | 67 | 64 | 58 | 54 | 49 | 43 | 37 | 34 | 29 | 23 | 19 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 29 | 2018-01-20 | 128 | 123 | 118 | 112 | 107 | 101 | 97 | 94 | 90 | 87 | 81 | 76 | 72 | 69 | 65 | 62 | 59 | 54 | 49 | 44 | 40 | 34 | 29 | 26 | 20 | 16 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 32 | 2018-02-10 | 136 | 132 | 128 | 125 | 121 | 116 | 113 | 107 | 103 | 98 | 94 | 89 | 86 | 82 | 76 | 72 | 68 | 63 | 59 | 54 | 51 | 46 | 40 | 36 | 32 | 28 | 25 | 22 | 18 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 20 | 2017-11-18 | 86 | 83 | 77 | 72 | 67 | 63 | 59 | 53 | 47 | 44 | 40 | 36 | 30 | 27 | 22 | 19 | 14 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 21 | 2017-11-25 | 83 | 79 | 75 | 70 | 67 | 61 | 57 | 52 | 47 | 44 | 39 | 35 | 31 | 28 | 25 | 19 | 16 | 13 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 19 | 2017-11-11 | 88 | 85 | 80 | 76 | 72 | 68 | 63 | 58 | 55 | 49 | 44 | 40 | 35 | 31 | 25 | 19 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 17 | 2017-10-28 | 70 | 65 | 59 | 56 | 51 | 48 | 45 | 41 | 37 | 31 | 27 | 23 | 19 | 16 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 31 | 2018-02-03 | 136 | 132 | 126 | 122 | 116 | 110 | 104 | 101 | 95 | 89 | 84 | 80 | 75 | 70 | 64 | 61 | 56 | 50 | 45 | 42 | 39 | 36 | 33 | 30 | 26 | 21 | 16 | 11 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 32 | 2018-02-10 | 136 | 130 | 125 | 122 | 117 | 113 | 109 | 105 | 100 | 96 | 93 | 90 | 87 | 84 | 81 | 76 | 72 | 69 | 66 | 60 | 57 | 52 | 48 | 43 | 38 | 33 | 27 | 22 | 17 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 17 | 2017-10-28 | 75 | 70 | 65 | 61 | 58 | 53 | 47 | 41 | 37 | 31 | 28 | 24 | 18 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 26 | 2017-12-30 | 110 | 107 | 102 | 99 | 96 | 90 | 87 | 82 | 76 | 71 | 66 | 60 | 57 | 54 | 49 | 44 | 40 | 37 | 34 | 28 | 24 | 18 | 14 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 33 | 2018-02-17 | 136 | 131 | 128 | 124 | 118 | 114 | 110 | 104 | 101 | 96 | 92 | 89 | 84 | 80 | 76 | 73 | 68 | 63 | 60 | 55 | 52 | 46 | 43 | 39 | 35 | 30 | 27 | 24 | 19 | 16 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 29 | 2018-01-20 | 134 | 130 | 125 | 122 | 116 | 113 | 107 | 101 | 98 | 94 | 91 | 86 | 82 | 78 | 73 | 68 | 65 | 62 | 57 | 52 | 46 | 41 | 36 | 31 | 27 | 21 | 15 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 25 | 2017-12-23 | 108 | 104 | 98 | 95 | 92 | 89 | 86 | 81 | 76 | 70 | 64 | 60 | 57 | 54 | 49 | 46 | 40 | 34 | 31 | 25 | 22 | 17 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 28 | 2018-01-13 | 131 | 127 | 123 | 119 | 115 | 109 | 106 | 103 | 97 | 94 | 88 | 84 | 79 | 75 | 69 | 63 | 57 | 53 | 47 | 43 | 38 | 34 | 30 | 24 | 18 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 26 | 2017-12-30 | 102 | 98 | 92 | 86 | 83 | 79 | 76 | 70 | 66 | 63 | 60 | 56 | 51 | 47 | 41 | 38 | 33 | 30 | 27 | 24 | 19 | 16 | 13 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 15 | 2017-10-14 | 64 | 61 | 55 | 52 | 48 | 45 | 40 | 36 | 30 | 25 | 22 | 19 | 14 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 22 | 2017-12-02 | 105 | 99 | 95 | 92 | 89 | 84 | 78 | 72 | 69 | 64 | 58 | 52 | 46 | 40 | 35 | 31 | 26 | 22 | 19 | 14 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 13 | 2017-09-30 | 51 | 48 | 44 | 41 | 36 | 30 | 27 | 24 | 20 | 17 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 20 | 2017-11-18 | 84 | 79 | 75 | 72 | 68 | 62 | 59 | 56 | 51 | 47 | 43 | 40 | 37 | 33 | 27 | 23 | 18 | 13 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 32 | 2018-02-10 | 145 | 139 | 136 | 130 | 125 | 121 | 116 | 112 | 106 | 102 | 99 | 95 | 91 | 87 | 84 | 78 | 74 | 70 | 65 | 62 | 56 | 52 | 47 | 43 | 37 | 32 | 27 | 21 | 17 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 16 | 2017-10-21 | 63 | 59 | 54 | 48 | 43 | 40 | 36 | 30 | 27 | 22 | 19 | 16 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 13 | 2017-09-30 | 61 | 56 | 50 | 44 | 41 | 37 | 31 | 28 | 22 | 16 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 33 | 2018-02-17 | 154 | 149 | 145 | 140 | 136 | 133 | 130 | 124 | 120 | 115 | 109 | 104 | 99 | 94 | 88 | 84 | 81 | 75 | 69 | 63 | 59 | 55 | 49 | 45 | 39 | 35 | 30 | 26 | 21 | 17 | 13 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 18 | 2017-11-04 | 73 | 67 | 62 | 57 | 54 | 49 | 44 | 41 | 38 | 33 | 29 | 26 | 23 | 19 | 16 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 23 | 2017-12-09 | 104 | 98 | 92 | 86 | 81 | 76 | 73 | 68 | 65 | 61 | 58 | 53 | 49 | 44 | 40 | 35 | 29 | 26 | 21 | 16 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 21 | 2017-11-25 | 94 | 90 | 85 | 81 | 76 | 71 | 65 | 59 | 54 | 48 | 45 | 41 | 38 | 34 | 29 | 25 | 21 | 15 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 14 | 2017-10-07 | 64 | 60 | 54 | 50 | 44 | 38 | 33 | 29 | 25 | 22 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 34 | 2018-02-24 | 146 | 142 | 137 | 132 | 129 | 124 | 120 | 116 | 112 | 109 | 103 | 99 | 95 | 91 | 88 | 83 | 78 | 73 | 68 | 62 | 56 | 51 | 47 | 42 | 36 | 32 | 29 | 25 | 21 | 18 | 15 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 33 | 2018-02-17 | 142 | 138 | 135 | 131 | 127 | 123 | 117 | 114 | 109 | 104 | 99 | 95 | 89 | 85 | 79 | 76 | 71 | 65 | 62 | 56 | 50 | 47 | 44 | 39 | 36 | 31 | 27 | 22 | 18 | 15 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 27 | 2018-01-06 | 117 | 112 | 107 | 104 | 98 | 93 | 90 | 86 | 81 | 75 | 72 | 66 | 61 | 56 | 51 | 48 | 43 | 39 | 35 | 31 | 28 | 24 | 21 | 18 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 30 | 2018-01-27 | 131 | 125 | 119 | 116 | 111 | 105 | 100 | 96 | 92 | 89 | 84 | 81 | 77 | 74 | 69 | 66 | 60 | 54 | 50 | 44 | 41 | 38 | 34 | 28 | 25 | 22 | 18 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 29 | 2018-01-20 | 129 | 123 | 119 | 113 | 110 | 106 | 101 | 98 | 93 | 90 | 84 | 81 | 76 | 73 | 69 | 65 | 60 | 57 | 51 | 46 | 41 | 37 | 34 | 30 | 24 | 20 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 30 | 2018-01-27 | 131 | 127 | 121 | 118 | 115 | 110 | 104 | 99 | 94 | 91 | 88 | 83 | 77 | 72 | 66 | 60 | 57 | 52 | 48 | 44 | 39 | 34 | 31 | 26 | 22 | 16 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 11 | 2017-09-16 | 50 | 45 | 40 | 36 | 30 | 26 | 23 | 17 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 24 | 2017-12-16 | 99 | 95 | 89 | 84 | 81 | 77 | 73 | 69 | 64 | 58 | 55 | 52 | 47 | 41 | 38 | 35 | 29 | 26 | 20 | 17 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 35 | 2018-03-03 | 142 | 139 | 133 | 128 | 125 | 119 | 116 | 111 | 107 | 102 | 98 | 95 | 92 | 87 | 84 | 80 | 77 | 71 | 68 | 64 | 58 | 55 | 51 | 47 | 44 | 39 | 35 | 32 | 28 | 23 | 18 | 15 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 33 | 2018-02-17 | 143 | 140 | 135 | 131 | 128 | 125 | 120 | 114 | 110 | 107 | 101 | 98 | 93 | 89 | 86 | 82 | 78 | 73 | 70 | 66 | 62 | 57 | 53 | 50 | 44 | 39 | 33 | 27 | 24 | 21 | 15 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 15 | 2017-10-14 | 68 | 64 | 58 | 52 | 49 | 46 | 41 | 37 | 31 | 28 | 22 | 18 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 24 | 2017-12-16 | 107 | 103 | 97 | 92 | 87 | 81 | 78 | 75 | 71 | 67 | 62 | 59 | 55 | 49 | 43 | 38 | 32 | 29 | 24 | 20 | 14 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 22 | 2017-12-02 | 99 | 93 | 89 | 86 | 80 | 76 | 70 | 64 | 61 | 56 | 52 | 49 | 46 | 41 | 36 | 32 | 26 | 22 | 16 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 15 | 2017-10-14 | 62 | 59 | 54 | 49 | 44 | 41 | 37 | 34 | 31 | 28 | 23 | 20 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 23 | 2017-12-09 | 94 | 91 | 85 | 82 | 79 | 76 | 71 | 66 | 60 | 57 | 53 | 49 | 45 | 41 | 38 | 33 | 30 | 25 | 22 | 19 | 15 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 19 | 2017-11-11 | 91 | 87 | 82 | 79 | 76 | 71 | 66 | 60 | 54 | 50 | 44 | 38 | 35 | 29 | 23 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 24 | 2017-12-16 | 99 | 96 | 93 | 90 | 86 | 83 | 77 | 72 | 69 | 65 | 60 | 55 | 52 | 46 | 41 | 37 | 34 | 31 | 28 | 25 | 20 | 15 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 24 | 2017-12-16 | 100 | 96 | 92 | 88 | 85 | 82 | 79 | 75 | 70 | 64 | 60 | 56 | 50 | 45 | 40 | 36 | 32 | 29 | 23 | 20 | 16 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 26 | 2017-12-30 | 117 | 113 | 109 | 104 | 98 | 94 | 88 | 84 | 79 | 74 | 71 | 66 | 61 | 56 | 53 | 48 | 43 | 39 | 35 | 31 | 27 | 24 | 19 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 30 | 2018-01-27 | 145 | 139 | 135 | 129 | 125 | 119 | 115 | 112 | 107 | 101 | 97 | 93 | 90 | 86 | 82 | 78 | 74 | 69 | 66 | 60 | 56 | 51 | 46 | 40 | 34 | 29 | 23 | 17 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 18 | 2017-11-04 | 85 | 82 | 76 | 70 | 67 | 61 | 56 | 52 | 48 | 44 | 38 | 32 | 26 | 22 | 16 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 18 | 2017-11-04 | 82 | 79 | 74 | 70 | 65 | 59 | 55 | 49 | 44 | 41 | 35 | 31 | 25 | 21 | 17 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 30 | 2018-01-27 | 139 | 135 | 131 | 128 | 122 | 117 | 113 | 107 | 103 | 97 | 94 | 88 | 82 | 78 | 73 | 68 | 63 | 58 | 52 | 47 | 42 | 39 | 34 | 29 | 25 | 19 | 13 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 15 | 2017-10-14 | 61 | 55 | 52 | 46 | 40 | 35 | 29 | 25 | 22 | 19 | 15 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 15 | 2017-10-14 | 61 | 57 | 53 | 47 | 42 | 38 | 35 | 32 | 29 | 23 | 19 | 15 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 20 | 2017-11-18 | 82 | 76 | 72 | 67 | 63 | 60 | 57 | 52 | 47 | 42 | 38 | 35 | 29 | 26 | 22 | 19 | 15 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 19 | 2017-11-11 | 91 | 86 | 80 | 76 | 70 | 67 | 61 | 56 | 50 | 44 | 38 | 33 | 30 | 27 | 22 | 19 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 24 | 2017-12-16 | 99 | 94 | 90 | 84 | 81 | 76 | 73 | 69 | 65 | 61 | 58 | 52 | 48 | 44 | 41 | 38 | 34 | 31 | 27 | 22 | 17 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 28 | 2018-01-13 | 115 | 111 | 106 | 103 | 100 | 94 | 89 | 85 | 80 | 77 | 72 | 69 | 64 | 61 | 57 | 54 | 51 | 48 | 42 | 36 | 32 | 29 | 23 | 18 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 14 | 2017-10-07 | 57 | 51 | 47 | 43 | 38 | 33 | 29 | 26 | 22 | 18 | 13 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 12 | 2017-09-23 | 52 | 46 | 42 | 38 | 34 | 29 | 26 | 22 | 16 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 15 | 2017-10-14 | 64 | 58 | 53 | 50 | 46 | 43 | 37 | 31 | 28 | 24 | 19 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 20 | 2017-11-18 | 82 | 77 | 74 | 71 | 67 | 61 | 58 | 54 | 49 | 45 | 41 | 35 | 31 | 27 | 24 | 20 | 15 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 32 | 2018-02-10 | 151 | 146 | 140 | 137 | 131 | 126 | 123 | 120 | 115 | 111 | 106 | 102 | 96 | 91 | 87 | 81 | 78 | 72 | 66 | 60 | 55 | 49 | 43 | 39 | 34 | 29 | 26 | 20 | 15 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 14 | 2017-10-07 | 63 | 60 | 54 | 48 | 45 | 39 | 34 | 28 | 24 | 19 | 16 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 34 | 2018-02-24 | 147 | 144 | 138 | 135 | 131 | 126 | 123 | 117 | 113 | 110 | 107 | 101 | 97 | 91 | 86 | 82 | 79 | 76 | 72 | 66 | 62 | 57 | 53 | 50 | 45 | 42 | 37 | 31 | 28 | 23 | 20 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 24 | 2017-12-16 | 120 | 114 | 109 | 103 | 98 | 95 | 89 | 85 | 80 | 77 | 72 | 66 | 60 | 55 | 49 | 44 | 41 | 35 | 30 | 27 | 22 | 17 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 12 | 2017-09-23 | 54 | 50 | 46 | 42 | 36 | 33 | 30 | 24 | 18 | 13 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 25 | 2017-12-23 | 118 | 114 | 108 | 102 | 96 | 92 | 88 | 84 | 81 | 77 | 71 | 65 | 59 | 53 | 49 | 43 | 37 | 34 | 31 | 25 | 21 | 16 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 19 | 2017-11-11 | 78 | 72 | 66 | 63 | 59 | 56 | 53 | 49 | 43 | 39 | 35 | 32 | 28 | 24 | 20 | 16 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 31 | 2018-02-03 | 137 | 133 | 129 | 123 | 118 | 114 | 110 | 107 | 101 | 95 | 92 | 86 | 81 | 78 | 72 | 68 | 65 | 59 | 54 | 49 | 44 | 38 | 35 | 32 | 29 | 24 | 20 | 15 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 15 | 2017-10-14 | 74 | 68 | 62 | 56 | 50 | 45 | 40 | 37 | 31 | 27 | 22 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 23 | 2017-12-09 | 99 | 95 | 89 | 85 | 79 | 75 | 70 | 67 | 62 | 58 | 52 | 49 | 46 | 40 | 36 | 31 | 27 | 23 | 20 | 17 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 32 | 2018-02-10 | 140 | 137 | 131 | 127 | 123 | 117 | 112 | 106 | 100 | 96 | 93 | 89 | 85 | 80 | 77 | 71 | 67 | 64 | 59 | 53 | 50 | 47 | 44 | 38 | 35 | 32 | 27 | 22 | 19 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 21 | 2017-11-25 | 90 | 85 | 82 | 76 | 70 | 66 | 63 | 58 | 55 | 49 | 44 | 38 | 33 | 29 | 24 | 20 | 16 | 11 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 16 | 2017-10-21 | 72 | 66 | 63 | 59 | 53 | 49 | 46 | 43 | 40 | 34 | 29 | 24 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 25 | 2017-12-23 | 113 | 107 | 102 | 96 | 93 | 87 | 81 | 76 | 71 | 66 | 63 | 57 | 54 | 51 | 45 | 42 | 36 | 33 | 29 | 24 | 21 | 18 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 15 | 2017-10-14 | 67 | 61 | 55 | 50 | 46 | 43 | 37 | 31 | 26 | 23 | 19 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 31 | 2018-02-03 | 136 | 132 | 127 | 121 | 117 | 113 | 107 | 101 | 95 | 92 | 86 | 83 | 80 | 76 | 73 | 69 | 64 | 61 | 57 | 53 | 47 | 43 | 40 | 34 | 30 | 26 | 21 | 16 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 23 | 2017-12-09 | 107 | 104 | 98 | 93 | 88 | 84 | 80 | 77 | 71 | 68 | 65 | 62 | 56 | 50 | 44 | 41 | 36 | 30 | 24 | 18 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 28 | 2018-01-13 | 123 | 119 | 116 | 111 | 107 | 103 | 100 | 95 | 89 | 83 | 78 | 74 | 69 | 66 | 63 | 57 | 54 | 48 | 43 | 39 | 33 | 28 | 22 | 18 | 15 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 16 | 2017-10-21 | 80 | 77 | 71 | 67 | 63 | 57 | 53 | 48 | 43 | 37 | 31 | 27 | 21 | 17 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 29 | 2018-01-20 | 131 | 128 | 123 | 119 | 116 | 111 | 107 | 104 | 100 | 97 | 92 | 86 | 81 | 77 | 71 | 65 | 62 | 59 | 53 | 47 | 42 | 36 | 30 | 27 | 24 | 19 | 15 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 11 | 2017-09-16 | 51 | 48 | 42 | 36 | 30 | 26 | 21 | 16 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 24 | 2017-12-16 | 110 | 105 | 99 | 93 | 87 | 82 | 79 | 73 | 69 | 65 | 62 | 56 | 50 | 46 | 43 | 39 | 36 | 31 | 25 | 20 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 21 | 2017-11-25 | 96 | 92 | 89 | 83 | 79 | 76 | 71 | 66 | 62 | 56 | 51 | 45 | 41 | 35 | 31 | 25 | 20 | 17 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 13 | 2017-09-30 | 59 | 55 | 52 | 49 | 43 | 37 | 32 | 29 | 24 | 20 | 16 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 17 | 2017-10-28 | 83 | 79 | 73 | 68 | 63 | 58 | 52 | 47 | 44 | 38 | 32 | 26 | 21 | 17 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 28 | 2018-01-13 | 134 | 131 | 126 | 120 | 114 | 110 | 104 | 99 | 95 | 90 | 84 | 81 | 75 | 69 | 65 | 60 | 55 | 50 | 45 | 39 | 34 | 28 | 24 | 20 | 16 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 15 | 2017-10-14 | 64 | 60 | 54 | 51 | 48 | 43 | 37 | 32 | 27 | 21 | 18 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 14 | 2017-10-07 | 59 | 55 | 52 | 49 | 43 | 38 | 34 | 30 | 24 | 19 | 15 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 31 | 2018-02-03 | 129 | 125 | 122 | 117 | 114 | 110 | 105 | 102 | 98 | 92 | 87 | 84 | 80 | 77 | 72 | 68 | 62 | 59 | 56 | 51 | 46 | 43 | 38 | 35 | 32 | 27 | 23 | 20 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 13 | 2017-09-30 | 56 | 52 | 47 | 42 | 39 | 35 | 29 | 25 | 19 | 15 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 29 | 2018-01-20 | 135 | 131 | 126 | 122 | 117 | 111 | 105 | 99 | 96 | 93 | 88 | 84 | 78 | 72 | 69 | 63 | 58 | 52 | 47 | 44 | 40 | 35 | 32 | 26 | 23 | 19 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 12 | 2017-09-23 | 54 | 48 | 43 | 40 | 34 | 30 | 25 | 21 | 16 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 25 | 2017-12-23 | 110 | 106 | 102 | 98 | 93 | 87 | 83 | 79 | 75 | 70 | 66 | 62 | 58 | 55 | 50 | 47 | 42 | 39 | 36 | 32 | 26 | 21 | 17 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 23 | 2017-12-09 | 92 | 88 | 84 | 79 | 76 | 73 | 70 | 64 | 58 | 55 | 50 | 47 | 44 | 41 | 37 | 33 | 29 | 23 | 18 | 15 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 26 | 2017-12-30 | 120 | 114 | 109 | 105 | 102 | 97 | 93 | 90 | 87 | 81 | 75 | 70 | 66 | 62 | 57 | 51 | 45 | 42 | 37 | 33 | 28 | 24 | 20 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 34 | 2018-02-24 | 152 | 147 | 141 | 137 | 134 | 131 | 127 | 121 | 117 | 112 | 106 | 102 | 97 | 94 | 91 | 88 | 85 | 79 | 74 | 69 | 63 | 58 | 54 | 50 | 46 | 43 | 38 | 35 | 29 | 24 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 25 | 2017-12-23 | 117 | 111 | 107 | 101 | 98 | 94 | 89 | 85 | 79 | 73 | 68 | 63 | 58 | 52 | 46 | 42 | 39 | 34 | 30 | 27 | 23 | 18 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 32 | 2018-02-10 | 136 | 131 | 128 | 125 | 120 | 114 | 109 | 103 | 100 | 94 | 88 | 85 | 82 | 78 | 72 | 67 | 64 | 60 | 55 | 50 | 46 | 43 | 37 | 34 | 30 | 24 | 19 | 16 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 19 | 2017-11-11 | 80 | 74 | 68 | 65 | 62 | 59 | 55 | 51 | 47 | 44 | 39 | 35 | 30 | 27 | 22 | 17 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 17 | 2017-10-28 | 80 | 76 | 70 | 67 | 61 | 58 | 52 | 46 | 40 | 37 | 32 | 26 | 20 | 14 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 31 | 2018-02-03 | 140 | 135 | 130 | 127 | 121 | 117 | 112 | 109 | 103 | 97 | 93 | 89 | 86 | 83 | 78 | 72 | 66 | 60 | 57 | 51 | 47 | 41 | 35 | 31 | 27 | 24 | 21 | 15 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 18 | 2017-11-04 | 84 | 81 | 75 | 69 | 65 | 59 | 53 | 47 | 43 | 38 | 32 | 29 | 25 | 21 | 17 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 16 | 2017-10-21 | 76 | 72 | 67 | 62 | 56 | 52 | 47 | 41 | 35 | 31 | 28 | 24 | 18 | 14 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 26 | 2017-12-30 | 113 | 110 | 107 | 101 | 96 | 91 | 88 | 82 | 78 | 75 | 72 | 67 | 63 | 57 | 54 | 48 | 44 | 38 | 34 | 29 | 24 | 21 | 16 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 31 | 2018-02-03 | 139 | 134 | 131 | 127 | 121 | 118 | 113 | 108 | 104 | 101 | 96 | 93 | 88 | 85 | 79 | 73 | 67 | 62 | 59 | 54 | 51 | 46 | 43 | 38 | 34 | 28 | 25 | 19 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 12 | 2017-09-23 | 59 | 54 | 49 | 45 | 40 | 35 | 29 | 24 | 18 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 18 | 2017-11-04 | 74 | 69 | 65 | 60 | 56 | 53 | 49 | 44 | 39 | 36 | 31 | 28 | 23 | 19 | 14 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 29 | 2018-01-20 | 126 | 122 | 118 | 115 | 111 | 107 | 104 | 101 | 96 | 93 | 89 | 85 | 81 | 75 | 72 | 67 | 62 | 56 | 50 | 45 | 41 | 37 | 31 | 26 | 20 | 15 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 17 | 2017-10-28 | 75 | 69 | 65 | 62 | 59 | 55 | 50 | 44 | 41 | 37 | 33 | 28 | 22 | 18 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 22 | 2017-12-02 | 101 | 97 | 91 | 85 | 82 | 76 | 70 | 65 | 60 | 56 | 50 | 46 | 43 | 37 | 34 | 29 | 26 | 22 | 17 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 19 | 2017-11-11 | 91 | 88 | 84 | 79 | 74 | 68 | 65 | 62 | 56 | 51 | 48 | 42 | 36 | 30 | 24 | 21 | 15 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 17 | 2017-10-28 | 68 | 65 | 61 | 58 | 54 | 50 | 47 | 42 | 39 | 36 | 30 | 27 | 23 | 18 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 16 | 2017-10-21 | 69 | 66 | 60 | 55 | 51 | 48 | 45 | 40 | 35 | 32 | 28 | 22 | 16 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 30 | 2018-01-27 | 133 | 128 | 122 | 116 | 112 | 109 | 105 | 100 | 96 | 92 | 88 | 84 | 79 | 76 | 72 | 68 | 63 | 60 | 54 | 50 | 47 | 42 | 39 | 36 | 30 | 24 | 19 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 22 | 2017-12-02 | 102 | 96 | 93 | 89 | 85 | 82 | 78 | 74 | 68 | 63 | 57 | 53 | 47 | 41 | 35 | 32 | 27 | 23 | 19 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 29 | 2018-01-20 | 130 | 125 | 122 | 118 | 115 | 112 | 108 | 102 | 99 | 96 | 90 | 84 | 78 | 74 | 70 | 66 | 60 | 54 | 50 | 45 | 41 | 36 | 33 | 30 | 24 | 20 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 34 | 2018-02-24 | 155 | 149 | 146 | 140 | 134 | 131 | 125 | 121 | 117 | 114 | 110 | 104 | 99 | 96 | 92 | 86 | 81 | 75 | 71 | 65 | 59 | 55 | 52 | 46 | 42 | 39 | 35 | 30 | 26 | 21 | 18 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 20 | 2017-11-18 | 94 | 91 | 87 | 82 | 76 | 70 | 67 | 63 | 57 | 52 | 46 | 42 | 36 | 30 | 26 | 21 | 17 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 31 | 2018-02-03 | 139 | 136 | 130 | 127 | 122 | 117 | 111 | 108 | 104 | 100 | 94 | 89 | 85 | 81 | 75 | 70 | 65 | 62 | 59 | 53 | 48 | 44 | 40 | 34 | 28 | 23 | 19 | 14 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 22 | 2017-12-02 | 93 | 89 | 83 | 79 | 74 | 71 | 66 | 63 | 59 | 54 | 50 | 47 | 43 | 40 | 36 | 31 | 26 | 20 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 22 | 2017-12-02 | 100 | 97 | 91 | 87 | 83 | 80 | 74 | 71 | 65 | 61 | 55 | 49 | 43 | 38 | 32 | 29 | 24 | 19 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 20 | 2017-11-18 | 88 | 83 | 79 | 73 | 68 | 65 | 60 | 56 | 52 | 48 | 44 | 41 | 35 | 31 | 25 | 21 | 18 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 30 | 2018-01-27 | 140 | 135 | 130 | 124 | 120 | 115 | 109 | 103 | 98 | 93 | 90 | 85 | 81 | 78 | 73 | 70 | 64 | 59 | 53 | 49 | 45 | 40 | 36 | 31 | 27 | 21 | 16 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 23 | 2017-12-09 | 92 | 89 | 83 | 77 | 74 | 71 | 68 | 63 | 60 | 57 | 54 | 50 | 46 | 42 | 37 | 34 | 31 | 26 | 22 | 19 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 13 | 2017-09-30 | 54 | 51 | 47 | 43 | 37 | 33 | 27 | 23 | 20 | 16 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 30 | 2018-01-27 | 142 | 137 | 131 | 125 | 119 | 115 | 110 | 107 | 104 | 99 | 94 | 88 | 82 | 76 | 73 | 67 | 63 | 59 | 55 | 51 | 47 | 41 | 37 | 32 | 27 | 22 | 19 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 15 | 2017-10-14 | 60 | 55 | 52 | 48 | 43 | 39 | 36 | 32 | 26 | 22 | 19 | 16 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 17 | 2017-10-28 | 72 | 66 | 63 | 59 | 54 | 51 | 46 | 41 | 37 | 33 | 30 | 24 | 21 | 15 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 20 | 2017-11-18 | 87 | 84 | 78 | 73 | 70 | 64 | 59 | 54 | 51 | 47 | 43 | 38 | 33 | 30 | 26 | 20 | 16 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 23 | 2017-12-09 | 110 | 106 | 100 | 97 | 91 | 85 | 79 | 75 | 72 | 66 | 62 | 57 | 54 | 50 | 45 | 41 | 35 | 29 | 24 | 19 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 17 | 2017-10-28 | 71 | 66 | 60 | 57 | 54 | 49 | 43 | 39 | 36 | 32 | 27 | 23 | 19 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 13 | 2017-09-30 | 52 | 49 | 45 | 41 | 38 | 34 | 28 | 24 | 20 | 17 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 31 | 2018-02-03 | 135 | 131 | 126 | 123 | 118 | 114 | 109 | 106 | 102 | 98 | 95 | 91 | 85 | 79 | 75 | 71 | 67 | 61 | 57 | 52 | 47 | 43 | 37 | 34 | 30 | 24 | 19 | 16 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 25 | 2017-12-23 | 113 | 110 | 104 | 99 | 95 | 90 | 86 | 80 | 74 | 68 | 62 | 56 | 51 | 47 | 44 | 40 | 36 | 32 | 26 | 22 | 19 | 15 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 28 | 2018-01-13 | 125 | 122 | 118 | 115 | 111 | 106 | 101 | 97 | 94 | 88 | 82 | 76 | 72 | 67 | 61 | 57 | 52 | 48 | 45 | 41 | 35 | 31 | 25 | 21 | 18 | 15 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 28 | 2018-01-13 | 117 | 111 | 106 | 101 | 96 | 91 | 87 | 83 | 80 | 77 | 73 | 70 | 67 | 63 | 58 | 52 | 47 | 41 | 35 | 31 | 26 | 22 | 18 | 15 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 26 | 2017-12-30 | 114 | 110 | 104 | 99 | 93 | 88 | 84 | 80 | 74 | 69 | 66 | 63 | 59 | 55 | 49 | 46 | 43 | 40 | 35 | 30 | 25 | 20 | 16 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 16 | 2017-10-21 | 66 | 60 | 56 | 52 | 47 | 44 | 41 | 38 | 32 | 28 | 23 | 17 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 28 | 2018-01-13 | 122 | 117 | 112 | 108 | 102 | 99 | 96 | 91 | 88 | 85 | 81 | 78 | 74 | 68 | 62 | 59 | 56 | 52 | 46 | 41 | 37 | 33 | 27 | 21 | 17 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 22 | 2017-12-02 | 102 | 97 | 91 | 85 | 82 | 79 | 76 | 73 | 67 | 64 | 58 | 55 | 50 | 44 | 38 | 35 | 29 | 24 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 11 | 2017-09-16 | 56 | 50 | 45 | 39 | 34 | 28 | 23 | 20 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 35 | 2018-03-03 | 160 | 154 | 148 | 143 | 137 | 133 | 130 | 127 | 121 | 116 | 111 | 107 | 101 | 97 | 91 | 86 | 81 | 76 | 71 | 68 | 64 | 59 | 56 | 53 | 49 | 45 | 41 | 35 | 32 | 28 | 25 | 20 | 16 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 15 | 2017-10-14 | 68 | 63 | 58 | 52 | 48 | 45 | 40 | 34 | 28 | 22 | 19 | 16 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 25 | 2017-12-23 | 113 | 108 | 102 | 96 | 91 | 87 | 84 | 80 | 76 | 72 | 69 | 64 | 58 | 52 | 48 | 44 | 39 | 33 | 27 | 23 | 19 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 16 | 2017-10-21 | 65 | 62 | 57 | 53 | 49 | 45 | 41 | 37 | 31 | 27 | 23 | 19 | 14 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 16 | 2017-10-21 | 63 | 59 | 54 | 51 | 47 | 42 | 37 | 34 | 31 | 28 | 23 | 19 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 29 | 2018-01-20 | 117 | 113 | 110 | 105 | 102 | 98 | 94 | 91 | 88 | 84 | 81 | 75 | 71 | 66 | 60 | 56 | 53 | 49 | 46 | 42 | 37 | 33 | 28 | 25 | 19 | 16 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 17 | 2017-10-28 | 77 | 72 | 67 | 63 | 60 | 54 | 49 | 46 | 43 | 37 | 31 | 28 | 24 | 18 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 16 | 2017-10-21 | 76 | 72 | 68 | 63 | 59 | 54 | 49 | 45 | 40 | 34 | 28 | 23 | 17 | 12 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 17 | 2017-10-28 | 79 | 73 | 69 | 63 | 58 | 52 | 46 | 42 | 38 | 33 | 29 | 26 | 20 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 28 | 2018-01-13 | 125 | 121 | 116 | 113 | 108 | 104 | 100 | 97 | 94 | 88 | 83 | 77 | 74 | 69 | 63 | 60 | 54 | 49 | 45 | 40 | 35 | 31 | 27 | 21 | 15 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 19 | 2017-11-11 | 82 | 79 | 74 | 70 | 67 | 62 | 56 | 50 | 47 | 43 | 39 | 33 | 30 | 27 | 23 | 18 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 13 | 2017-09-30 | 63 | 57 | 51 | 45 | 42 | 38 | 33 | 29 | 26 | 20 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 21 | 2017-11-25 | 90 | 87 | 82 | 79 | 73 | 70 | 65 | 60 | 55 | 51 | 48 | 45 | 40 | 37 | 31 | 26 | 20 | 17 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 24 | 2017-12-16 | 105 | 102 | 97 | 91 | 88 | 85 | 82 | 78 | 72 | 69 | 66 | 61 | 56 | 53 | 48 | 43 | 39 | 33 | 29 | 23 | 17 | 13 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 26 | 2017-12-30 | 115 | 110 | 107 | 103 | 97 | 91 | 87 | 83 | 79 | 76 | 72 | 69 | 65 | 60 | 55 | 50 | 46 | 40 | 36 | 32 | 26 | 20 | 16 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 37 | 2018-03-17 | 156 | 153 | 149 | 143 | 139 | 135 | 131 | 128 | 125 | 120 | 115 | 110 | 105 | 101 | 98 | 95 | 91 | 87 | 82 | 79 | 75 | 69 | 64 | 61 | 58 | 53 | 48 | 42 | 36 | 31 | 28 | 25 | 22 | 17 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 25 | 2017-12-23 | 103 | 98 | 95 | 89 | 83 | 79 | 76 | 73 | 68 | 63 | 58 | 55 | 50 | 46 | 42 | 38 | 34 | 28 | 25 | 22 | 19 | 16 | 12 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 32 | 2018-02-10 | 135 | 132 | 126 | 122 | 116 | 111 | 105 | 100 | 95 | 91 | 87 | 83 | 80 | 77 | 74 | 68 | 64 | 61 | 58 | 55 | 52 | 49 | 46 | 42 | 37 | 31 | 27 | 22 | 18 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 17 | 2017-10-28 | 78 | 72 | 69 | 65 | 62 | 56 | 52 | 47 | 44 | 40 | 34 | 30 | 26 | 22 | 16 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 15 | 2017-10-14 | 66 | 60 | 54 | 49 | 46 | 42 | 36 | 32 | 27 | 24 | 21 | 17 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 18 | 2017-11-04 | 81 | 75 | 70 | 66 | 60 | 54 | 50 | 44 | 39 | 35 | 30 | 24 | 21 | 17 | 14 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 27 | 2018-01-06 | 122 | 117 | 112 | 109 | 106 | 101 | 96 | 92 | 88 | 84 | 81 | 77 | 73 | 68 | 63 | 57 | 53 | 47 | 44 | 39 | 33 | 29 | 23 | 17 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 23 | 2017-12-09 | 100 | 97 | 93 | 89 | 84 | 80 | 76 | 71 | 65 | 62 | 57 | 54 | 49 | 46 | 40 | 36 | 32 | 27 | 22 | 19 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 26 | 2017-12-30 | 117 | 111 | 106 | 103 | 97 | 92 | 89 | 83 | 78 | 73 | 69 | 65 | 60 | 56 | 52 | 46 | 41 | 38 | 33 | 28 | 25 | 19 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 11 | 2017-09-16 | 53 | 48 | 44 | 39 | 33 | 27 | 22 | 16 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 23 | 2017-12-09 | 104 | 101 | 97 | 94 | 89 | 83 | 79 | 73 | 68 | 63 | 59 | 54 | 50 | 44 | 38 | 35 | 32 | 26 | 21 | 18 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 19 | 2017-11-11 | 82 | 77 | 71 | 68 | 63 | 57 | 53 | 50 | 45 | 42 | 37 | 34 | 28 | 24 | 19 | 14 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 15 | 2017-10-14 | 69 | 66 | 60 | 56 | 50 | 47 | 42 | 36 | 31 | 28 | 25 | 19 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 16 | 2017-10-21 | 67 | 62 | 56 | 52 | 46 | 42 | 39 | 36 | 31 | 25 | 22 | 18 | 14 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 34 | 2018-02-24 | 142 | 136 | 130 | 127 | 124 | 118 | 115 | 112 | 107 | 104 | 98 | 95 | 92 | 87 | 84 | 78 | 74 | 68 | 65 | 62 | 59 | 53 | 49 | 45 | 40 | 36 | 30 | 27 | 24 | 20 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 22 | 2017-12-02 | 83 | 80 | 76 | 73 | 70 | 67 | 64 | 59 | 56 | 53 | 49 | 45 | 42 | 37 | 32 | 29 | 26 | 22 | 17 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 23 | 2017-12-09 | 94 | 90 | 86 | 80 | 77 | 72 | 69 | 63 | 58 | 52 | 49 | 46 | 41 | 37 | 31 | 26 | 23 | 18 | 15 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 25 | 2017-12-23 | 118 | 114 | 108 | 104 | 99 | 95 | 89 | 83 | 80 | 75 | 69 | 66 | 61 | 56 | 51 | 46 | 40 | 36 | 30 | 25 | 19 | 16 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 20 | 2017-11-18 | 100 | 97 | 94 | 89 | 84 | 80 | 75 | 70 | 64 | 59 | 53 | 47 | 43 | 37 | 31 | 27 | 21 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 24 | 2017-12-16 | 99 | 94 | 89 | 86 | 83 | 77 | 73 | 70 | 65 | 61 | 56 | 53 | 47 | 42 | 39 | 33 | 29 | 25 | 22 | 19 | 16 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 19 | 2017-11-11 | 80 | 75 | 69 | 66 | 62 | 59 | 55 | 52 | 47 | 44 | 40 | 34 | 28 | 23 | 20 | 17 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 23 | 2017-12-09 | 103 | 97 | 94 | 90 | 86 | 81 | 77 | 73 | 70 | 65 | 62 | 56 | 50 | 47 | 42 | 37 | 31 | 28 | 25 | 19 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 35 | 2018-03-03 | 156 | 153 | 150 | 145 | 139 | 136 | 131 | 128 | 123 | 117 | 112 | 108 | 105 | 99 | 94 | 88 | 85 | 82 | 76 | 71 | 68 | 63 | 60 | 56 | 52 | 48 | 45 | 40 | 35 | 31 | 26 | 22 | 16 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 32 | 2018-02-10 | 148 | 142 | 139 | 134 | 128 | 123 | 118 | 112 | 108 | 102 | 98 | 94 | 91 | 87 | 82 | 79 | 74 | 68 | 62 | 59 | 54 | 48 | 44 | 40 | 36 | 31 | 28 | 23 | 19 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 33 | 2018-02-17 | 153 | 148 | 145 | 142 | 136 | 130 | 124 | 121 | 117 | 111 | 105 | 101 | 96 | 91 | 86 | 82 | 76 | 72 | 68 | 62 | 58 | 52 | 49 | 45 | 41 | 35 | 32 | 26 | 22 | 16 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 35 | 2018-03-03 | 159 | 155 | 152 | 149 | 145 | 140 | 135 | 132 | 129 | 125 | 121 | 116 | 110 | 105 | 101 | 97 | 91 | 85 | 81 | 76 | 71 | 67 | 63 | 58 | 52 | 46 | 41 | 35 | 30 | 27 | 21 | 17 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 15 | 2017-10-14 | 56 | 53 | 50 | 47 | 41 | 36 | 33 | 29 | 24 | 21 | 17 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 23 | 2017-12-09 | 99 | 95 | 92 | 87 | 83 | 79 | 73 | 70 | 66 | 60 | 56 | 53 | 50 | 44 | 39 | 34 | 29 | 24 | 19 | 14 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 30 | 2018-01-27 | 133 | 130 | 125 | 119 | 113 | 108 | 102 | 97 | 93 | 89 | 83 | 77 | 74 | 69 | 64 | 58 | 55 | 51 | 47 | 44 | 40 | 37 | 32 | 29 | 24 | 19 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 19 | 2017-11-11 | 81 | 75 | 72 | 69 | 63 | 58 | 53 | 48 | 43 | 39 | 33 | 30 | 26 | 22 | 18 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 26 | 2017-12-30 | 131 | 125 | 120 | 115 | 109 | 103 | 97 | 92 | 86 | 83 | 80 | 75 | 69 | 63 | 58 | 54 | 49 | 43 | 37 | 33 | 27 | 21 | 18 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 23 | 2017-12-09 | 97 | 92 | 87 | 82 | 78 | 75 | 72 | 67 | 64 | 59 | 56 | 53 | 48 | 43 | 40 | 36 | 30 | 26 | 22 | 16 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 28 | 2018-01-13 | 127 | 123 | 117 | 114 | 111 | 108 | 102 | 98 | 94 | 88 | 85 | 79 | 73 | 68 | 64 | 61 | 55 | 49 | 43 | 37 | 33 | 30 | 27 | 24 | 18 | 13 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 15 | 2017-10-14 | 68 | 62 | 56 | 52 | 46 | 41 | 35 | 30 | 27 | 24 | 21 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 35 | 2018-03-03 | 153 | 150 | 146 | 143 | 138 | 132 | 126 | 122 | 118 | 115 | 112 | 108 | 104 | 101 | 95 | 91 | 85 | 80 | 74 | 71 | 67 | 61 | 58 | 54 | 50 | 47 | 43 | 40 | 35 | 29 | 24 | 18 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 28 | 2018-01-13 | 118 | 114 | 111 | 105 | 102 | 97 | 94 | 91 | 86 | 82 | 79 | 73 | 69 | 66 | 63 | 58 | 55 | 51 | 46 | 42 | 37 | 31 | 28 | 24 | 19 | 13 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 24 | 2017-12-16 | 99 | 94 | 91 | 86 | 83 | 79 | 74 | 70 | 66 | 62 | 59 | 53 | 48 | 43 | 39 | 36 | 33 | 28 | 25 | 19 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:BD2,1,[Weeks to Zero]+1),"")

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 13.5 | 11 | 22.5 | 36.5 | 46.8333 | 57.1667 | 68.1667 | 79.1667 | 86.3333 | 98.3333 | 107.8333 | 117.3333 | 131.3333 | 144.3333 | 3 | 2 | 3 | 3 | 1.5 | 1 | 4 | 5 | 2 | 2 | 4 | 6 | 6 | 1.3333 | 1.6667 | 1.3333 | 3 | 1.6667 | 1.6667 | 4 | 1 | 5 | 1 | 4 | 1.5 | 2 | 1.5 | 6 | 2 | 1.3333 | 1.3333 | 2.5 | 1.6667 | 1.3333 | 5 | 4 | 3 | 2 | 2 | 2.5 | 1 | 5 | 2 | 1.5 | 6 | 1 | 4 | 3 | 3 | 3 | 4 | 3
2 | 18.1667 | 13.6667 | 23.1667 | 35.1667 | 46.3333 | 56.8333 | 65.5 | 78.5 | 89.3333 | 103.5 | 112.5 | 123.3333 | 134.6667 | 148.6667 | 2 | 6 | 4 | 1.6667 | 3 | 1.5 | 1 | 4 | 5 | 2 | 2 | 3 | 1 | 2.5 | 6 | 1.6667 | 2 | 3 | 2.5 | 3 | 3 | 1.5 | 2.5 | 1.6667 | 2 | 2 | 3 | 6 | 4 | 1.5 | 1.3333 | 4 | 1.6667 | 1.5 | 6 | 5 | 2.5 | 1 | 3 | 2.5 | 1.5 | 1.6667 | 6 | 1.6667 | 3 | 1.6667 | 5 | 1.6667 | 1.5 | 2.5 | 6 | 4
3 | 17.6667 | 11.6667 | 26.6667 | 41.6667 | 53.6667 | 70.6667 | 82.3333 | 94 | 117 | 131.3333 | 140.6667 | 149.5 | 157.1667 | 170.6667 | 3 | 6 | 1 | 1.6667 | 3 | 3 | 6 | 3 | 2 | 3 | 4 | 6 | 4 | 3 | 3 | 2 | 5 | 5 | 5 | 2 | 3 | 6 | 1.3333 | 1.3333 | 6 | 3 | 1.3333 | 1.3333 | 6 | 6 | 6 | 5 | 2 | 1.3333 | 5 | 6 | 2 | 1.6667 | 4 | 1.6667 | 1.5 | 1.6667 | 1.6667 | 4 | 1.5 | 1.6667 | 2 | 2.5 | 2 | 5 | 4 | 2.5
4 | 23.5 | 13.5 | 29 | 36.5 | 46.1667 | 56.6667 | 67.5 | 74.1667 | 84.1667 | 99.1667 | 112.6667 | 123 | 139 | 149.5 | 5 | 1.5 | 3 | 4 | 6 | 4 | 4 | 1.5 | 1.6667 | 1.3333 | 3 | 1.5 | 5 | 1.6667 | 1.3333 | 1.6667 | 6 | 2 | 1 | 1.5 | 1.3333 | 2.5 | 2 | 5 | 2 | 1.6667 | 1 | 2 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 6 | 2 | 5 | 5 | 1.5 | 3 | 4 | 2 | 1.3333 | 2 | 3 | 5 | 6 | 2.5 | 1 | 5 | 2
5 | 20.1667 | 12.1667 | 23.1667 | 28.8333 | 41.8333 | 55.8333 | 69.8333 | 80.6667 | 89 | 101 | 111.5 | 123 | 132.3333 | 138.8333 | 1.6667 | 2.5 | 6 | 2 | 6 | 2 | 1.5 | 1.5 | 1.3333 | 1 | 2 | 1.3333 | 4 | 1 | 6 | 2 | 4 | 5 | 2 | 3 | 6 | 4 | 2 | 2 | 2.5 | 4 | 3 | 1.3333 | 1.3333 | 2 | 2 | 3 | 4 | 4 | 1 | 3 | 3 | 3 | 2 | 2.5 | 6 | 1.6667 | 2.5 | 1.3333 | 5 | 2 | 1 | 1.3333 | 1.5 | 1.5 | 1.5 | 2
6 | 16.3333 | 8.3333 | 20.6667 | 34.3333 | 45.5 | 54 | 66 | 79 | 87 | 105.5 | 112.8333 | 122.8333 | 135.8333 | 148.8333 | 4 | 1 | 2 | 1.3333 | 5 | 3 | 3 | 1.3333 | 4 | 4 | 1.6667 | 4 | 2 | 6 | 1.5 | 1.6667 | 1.5 | 1.5 | 3 | 2.5 | 6 | 1 | 3 | 2 | 2 | 3 | 6 | 2 | 3 | 2 | 2 | 1 | 2.5 | 6 | 5 | 5 | 2 | 2.5 | 1.3333 | 1.5 | 2.5 | 2 | 2.5 | 3 | 6 | 4 | 2 | 1 | 1 | 3 | 3 | 6
7 | 16 | 9 | 22.5 | 35 | 54.5 | 62.5 | 78.5 | 84.5 | 99.5 | 109 | 119.6667 | 127.3333 | 138.8333 | 145.3333 | 1.3333 | 5 | 1 | 1.6667 | 5 | 2 | 1.5 | 5 | 1 | 1.5 | 6 | 4 | 6 | 2.5 | 6 | 5 | 1 | 2 | 2 | 3 | 2 | 5 | 3 | 6 | 2 | 1.3333 | 1.6667 | 1 | 1 | 6 | 5 | 3 | 1.5 | 3 | 2.5 | 2.5 | 1.3333 | 1.3333 | 6 | 2 | 2 | 3 | 1.6667 | 1 | 2 | 6 | 2 | 1.5 | 1 | 1.5 | 1 | 3
8 | 16.1667 | 9.1667 | 19.5 | 27 | 37.6667 | 45.8333 | 61.8333 | 74.8333 | 83.6667 | 97.1667 | 105.1667 | 119.5 | 126.5 | 139.5 | 2.5 | 1.6667 | 3 | 2 | 6 | 1 | 2 | 1.3333 | 2 | 1 | 3 | 1.5 | 4 | 3 | 1.6667 | 2 | 3 | 1.6667 | 2 | 1.5 | 2 | 6 | 2 | 6 | 2 | 4 | 2 | 5 | 3 | 3 | 1.3333 | 1.5 | 5 | 2.5 | 3 | 3 | 4 | 2 | 1 | 1 | 5 | 1.3333 | 3 | 5 | 1 | 2 | 3 | 1 | 5 | 3 | 3 | 2
9 | 17.1667 | 11.1667 | 20.1667 | 38.5 | 52.5 | 69 | 85.3333 | 95.5 | 103.8333 | 114.3333 | 120.1667 | 132.1667 | 147.3333 | 159.3333 | 2 | 1.6667 | 5 | 2.5 | 1 | 5 | 2 | 1 | 6 | 1.3333 | 6 | 5 | 2 | 6 | 4 | 2 | 2.5 | 6 | 3 | 5 | 3 | 6 | 6 | 1.3333 | 1.5 | 4 | 1.6667 | 3 | 2 | 3 | 1.6667 | 1.6667 | 1.5 | 2 | 3 | 4 | 1 | 1 | 2.5 | 1.3333 | 3 | 1.6667 | 1.3333 | 6 | 2.5 | 5 | 6 | 1.6667 | 2.5 | 5 | 3 | 1.5
10 | 19.5 | 15.5 | 25.1667 | 36.1667 | 45.6667 | 54.8333 | 65.8333 | 82.3333 | 93.8333 | 105.3333 | 119.8333 | 128.8333 | 139.8333 | 152.8333 | 6 | 2 | 6 | 1.5 | 2 | 2 | 1.6667 | 4 | 1 | 5 | 2 | 3 | 4 | 1.5 | 2 | 2 | 2 | 1.6667 | 3 | 2.5 | 1 | 3 | 5 | 2 | 4 | 1.5 | 5 | 6 | 3 | 5 | 2 | 1.5 | 2 | 3 | 4 | 2.5 | 6 | 1 | 1.5 | 6 | 3 | 1.5 | 3 | 1.5 | 1.5 | 4 | 2.5 | 3 | 6 | 2.5 | 2.5 | 2
11 | 15.5 | 11.5 | 18.1667 | 27.1667 | 39 | 48.3333 | 61.3333 | 69.8333 | 76.5 | 82.8333 | 96.3333 | 104.6667 | 115.6667 | 129.6667 | 1.5 | 1.5 | 2.5 | 6 | 1.5 | 2.5 | 1.3333 | 1.3333 | 1 | 4 | 1 | 3 | 5 | 4 | 1.3333 | 1.5 | 5 | 2 | 1.3333 | 1 | 2 | 2 | 5 | 4 | 2 | 1.5 | 3 | 2 | 2 | 1.3333 | 1.3333 | 2 | 2.5 | 1.3333 | 1 | 1.5 | 6 | 2 | 4 | 1.5 | 1 | 5 | 1.3333 | 1 | 5 | 3 | 1.3333 | 1.6667 | 6 | 4 | 1.5 | 2.5
12 | 14.1667 | 8.1667 | 17.6667 | 26.1667 | 42.1667 | 49.1667 | 60.3333 | 68.3333 | 79.3333 | 90.6667 | 102 | 114.5 | 127.1667 | 139 | 1.5 | 3 | 2 | 1.6667 | 4 | 2 | 2.5 | 1 | 1 | 3 | 1.5 | 3 | 6 | 4 | 4 | 2 | 2 | 3 | 1 | 1 | 1.6667 | 1.5 | 5 | 3 | 2 | 1 | 3 | 2 | 2.5 | 4 | 3 | 1.5 | 1.6667 | 2 | 1.6667 | 6 | 1.3333 | 3 | 1 | 6 | 5 | 1.5 | 4 | 2 | 1.6667 | 3 | 5 | 3 | 6 | 1.3333 | 2 | 2.5
13 | 18.1667 | 8.1667 | 21.6667 | 31.6667 | 48.6667 | 59 | 67.6667 | 82.6667 | 89.8333 | 103.5 | 115.6667 | 123.3333 | 133.3333 | 143.3333 | 4 | 1.3333 | 1.3333 | 1.5 | 4 | 6 | 1.5 | 2 | 4 | 2.5 | 1.5 | 2 | 6 | 4 | 1 | 6 | 3 | 2 | 4 | 1.3333 | 1.6667 | 4 | 2 | 1 | 4 | 3 | 5 | 3 | 3 | 1 | 1.5 | 1.6667 | 5 | 3 | 4 | 1.6667 | 5 | 2.5 | 3 | 1.6667 | 1 | 2 | 3 | 1.6667 | 2 | 4 | 2 | 2 | 1.3333 | 1.3333 | 1.3333 | 6
14 | 16.8333 | 7.8333 | 22.8333 | 32 | 43 | 52.6667 | 63.3333 | 73.6667 | 93.6667 | 108.6667 | 118.1667 | 128.1667 | 138.1667 | 143.5 | 3 | 1.5 | 1.6667 | 1.6667 | 4 | 5 | 2 | 4 | 1.5 | 1.6667 | 2 | 4 | 5 | 3 | 1.6667 | 1.3333 | 3 | 1.3333 | 1.3333 | 4 | 2 | 4 | 1.6667 | 3 | 1.3333 | 3 | 4 | 2 | 6 | 6 | 3 | 5 | 6 | 6 | 1.5 | 1.5 | 3 | 1.5 | 3 | 2 | 2.5 | 1.5 | 4 | 2 | 2 | 2.5 | 3 | 2.5 | 1.3333 | 1.3333 | 1.3333 | 1.3333
15 | 12.5 | 9.5 | 20 | 29.6667 | 42.3333 | 57.8333 | 72.8333 | 82.3333 | 95.6667 | 111.3333 | 124.6667 | 132.6667 | 147.3333 | 156.5 | 1 | 1 | 5 | 2.5 | 1.3333 | 1.6667 | 1.5 | 6 | 4 | 3 | 1.3333 | 1.3333 | 6 | 4 | 1 | 1.6667 | 4 | 2.5 | 4 | 5 | 6 | 4 | 2 | 3 | 2 | 3 | 3 | 1.5 | 5 | 1.3333 | 5 | 2 | 5 | 3 | 6 | 1.6667 | 4 | 3 | 1.3333 | 5 | 2.5 | 2 | 2.5 | 1 | 4 | 6 | 1.6667 | 3 | 1.3333 | 1.5 | 1.3333 | 5
16 | 10.1667 | 6.1667 | 16.1667 | 28.8333 | 39 | 54.5 | 61 | 70.1667 | 81 | 91 | 104.5 | 113.1667 | 119.1667 | 130.1667 | 1 | 1.5 | 1.6667 | 2 | 2 | 2 | 4 | 2 | 3 | 5 | 3 | 1.6667 | 1.5 | 1.6667 | 3 | 4 | 6 | 6 | 2.5 | 1 | 1.3333 | 2.5 | 1 | 1.6667 | 2.5 | 1.6667 | 3 | 2 | 1.3333 | 6 | 2.5 | 1 | 3 | 1.3333 | 1.6667 | 4 | 4 | 2.5 | 6 | 1 | 4 | 1.5 | 1.5 | 1.6667 | 1.5 | 1.5 | 1 | 2 | 1 | 4 | 1 | 5
17 | 10.3333 | 6.3333 | 15.6667 | 27.6667 | 38.5 | 49 | 59.6667 | 72.5 | 86.5 | 96.5 | 111.5 | 128 | 138.3333 | 150.3333 | 1 | 2 | 1.6667 | 1.6667 | 3 | 1 | 1.3333 | 4 | 3 | 2 | 3 | 4 | 5 | 2.5 | 1.3333 | 2 | 1.5 | 2 | 3 | 4 | 4 | 1.6667 | 2 | 3 | 2.5 | 6 | 1.3333 | 3 | 2 | 5 | 4 | 3 | 2 | 3 | 2 | 3 | 5 | 4 | 3 | 3 | 6 | 6 | 3 | 1.5 | 3 | 3 | 1.3333 | 3 | 1 | 5 | 5 | 1
18 | 19 | 9 | 21.5 | 34 | 40.8333 | 54.3333 | 64.3333 | 74.1667 | 80.8333 | 89.5 | 97.6667 | 106.3333 | 114.8333 | 125.5 | 3 | 3 | 1 | 2 | 5 | 5 | 1.5 | 1 | 3 | 6 | 2 | 1.5 | 2.5 | 1.3333 | 1.3333 | 1.6667 | 4 | 2.5 | 5 | 2 | 2 | 1 | 1 | 6 | 1.3333 | 5 | 1.5 | 2 | 3 | 1.3333 | 1 | 1.3333 | 2 | 4 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 2.5 | 3 | 1.5 | 4 | 1.5 | 1.6667 | 2.5 | 1.3333 | 3 | 1.6667 | 1.3333 | 6 | 2 | 1.3333
19 | 14.8333 | 7.5 | 22.8333 | 31.8333 | 39.8333 | 47.5 | 54.1667 | 66.1667 | 72.8333 | 82.8333 | 90.6667 | 99 | 111 | 117.5 | 1.6667 | 3 | 1.3333 | 1.5 | 1.3333 | 6 | 5 | 3 | 3 | 2 | 2 | 2 | 1.5 | 2.5 | 2.5 | 1.5 | 1 | 2 | 1.6667 | 3 | 1.3333 | 2 | 1.3333 | 2 | 4 | 2 | 1 | 5 | 1 | 1 | 3 | 1.6667 | 1 | 5 | 3 | 1 | 1.3333 | 2.5 | 2.5 | 1.5 | 2 | 1.3333 | 1 | 4 | 1.5 | 1.5 | 3 | 6 | 2 | 1 | 1.5 | 2
20 | 16.1667 | 12.1667 | 20.1667 | 28.6667 | 34.6667 | 43 | 48.8333 | 58 | 65 | 73 | 88.5 | 98 | 110 | 121 | 6 | 1.6667 | 3 | 1.5 | 2 | 2 | 2.5 | 1.5 | 2 | 1.5 | 3 | 2 | 1 | 2 | 1.3333 | 1.6667 | 2 | 2 | 3 | 1.3333 | 1.5 | 1.5 | 1.5 | 1.3333 | 1 | 2.5 | 1.6667 | 4 | 2.5 | 2 | 1 | 1.5 | 1 | 2 | 2 | 3 | 6 | 5 | 2 | 2.5 | 1.5 | 1 | 5 | 2 | 4 | 3 | 1 | 4 | 3 | 1 | 3 | 4
21 | 17 | 11 | 21.5 | 33 | 41.8333 | 56.6667 | 67.1667 | 77 | 89.1667 | 95.5 | 110.1667 | 120.1667 | 134.1667 | 141 | 2.5 | 2.5 | 1 | 5 | 1 | 5 | 2.5 | 2 | 6 | 2 | 2 | 1.5 | 1.6667 | 2.5 | 1.6667 | 3 | 1.5 | 1.3333 | 6 | 6 | 5 | 1.5 | 3 | 1 | 1.3333 | 2 | 2.5 | 4 | 5 | 1.5 | 1.6667 | 4 | 2 | 2 | 1 | 1.3333 | 6 | 3 | 1.6667 | 4 | 2 | 3 | 4 | 1 | 3 | 2 | 6 | 3 | 1.6667 | 2.5 | 1 | 1.6667
22 | 15 | 10 | 20 | 29.3333 | 41.3333 | 52.3333 | 65.1667 | 75.5 | 88 | 94.8333 | 108.1667 | 122.1667 | 134.5 | 141.1667 | 1.5 | 1.5 | 3 | 4 | 2 | 3 | 2 | 3 | 2.5 | 2.5 | 1.3333 | 3 | 2.5 | 1.5 | 2 | 6 | 3 | 5 | 1 | 2 | 1.3333 | 3 | 2.5 | 6 | 4 | 1.3333 | 3 | 2 | 4 | 2 | 5 | 1.5 | 1.3333 | 1.5 | 1.5 | 2.5 | 5 | 1.3333 | 1 | 6 | 1 | 6 | 5 | 2 | 4 | 4 | 1.3333 | 3 | 2 | 2 | 1 | 1.6667
23 | 14.3333 | 12 | 17.3333 | 24.5 | 31.8333 | 48.1667 | 56.6667 | 76.6667 | 89.1667 | 96.1667 | 107.5 | 122 | 143 | 155 | 4 | 1 | 6 | 1 | 1.3333 | 1 | 1.6667 | 1.3333 | 1.5 | 1.6667 | 1 | 3 | 2.5 | 2.5 | 1.3333 | 1 | 6 | 1.3333 | 3 | 6 | 2 | 2 | 2.5 | 2 | 6 | 6 | 3 | 5 | 2.5 | 1 | 3 | 6 | 2.5 | 1 | 2 | 1.5 | 1.6667 | 1.6667 | 5 | 3 | 6 | 3 | 3 | 2.5 | 6 | 5 | 6 | 4 | 3 | 1 | 6 | 2
24 | 16.3333 | 14 | 22.3333 | 32.8333 | 44.3333 | 52 | 59.8333 | 71.1667 | 78.5 | 85.5 | 96.3333 | 108.3333 | 119.8333 | 128.3333 | 5 | 3 | 3 | 3 | 1 | 1.3333 | 2 | 4 | 3 | 3 | 2 | 2.5 | 3 | 3 | 4 | 1.5 | 2.5 | 1.3333 | 1.3333 | 2.5 | 1.3333 | 1 | 1.5 | 4 | 5 | 3 | 1.6667 | 1.6667 | 2 | 1.3333 | 2.5 | 1.5 | 2 | 1.6667 | 2 | 1.3333 | 1.6667 | 1.5 | 1.6667 | 6 | 6 | 1 | 3 | 2 | 2.5 | 3 | 2 | 4 | 4 | 1.6667 | 1.5 | 1.3333
25 | 16.8333 | 12.3333 | 25.8333 | 37.8333 | 46.8333 | 59.8333 | 71.5 | 84 | 92.3333 | 110.3333 | 126 | 136.6667 | 149.6667 | 159.1667 | 1.3333 | 1 | 5 | 5 | 1.5 | 3 | 5 | 4 | 4 | 2.5 | 2.5 | 3 | 1.6667 | 2 | 1.3333 | 4 | 3 | 5 | 2 | 3 | 3 | 3 | 4 | 1.6667 | 6 | 3 | 1.5 | 2 | 1.6667 | 4 | 1 | 1.6667 | 5 | 5 | 2 | 6 | 1.6667 | 5 | 6 | 3 | 6 | 1.6667 | 1.3333 | 1.6667 | 3 | 2 | 2 | 6 | 1.5 | 1.5 | 1.5 | 5
26 | 13.3333 | 9.8333 | 16.1667 | 26.5 | 34.5 | 45.3333 | 59.6667 | 68.5 | 82.5 | 94 | 106 | 114 | 122.8333 | 133.8333 | 1.5 | 2 | 1.3333 | 5 | 2 | 1.5 | 1.5 | 1.3333 | 4 | 3 | 1.6667 | 1.6667 | 1.5 | 2.5 | 2.5 | 1.5 | 6 | 2.5 | 1 | 1.3333 | 4 | 3 | 1.3333 | 6 | 1.5 | 1.3333 | 3 | 3 | 6 | 3 | 2 | 3 | 2 | 2 | 1.5 | 6 | 2 | 3 | 3 | 4 | 1 | 3 | 3 | 1 | 1 | 2.5 | 1.3333 | 4 | 1 | 2 | 3 | 5
27 | 15 | 10 | 23 | 33 | 42.6667 | 53.1667 | 69.6667 | 80.6667 | 91.1667 | 105.1667 | 116 | 130.1667 | 141.6667 | 152.6667 | 5 | 1.3333 | 1.6667 | 2 | 3 | 2 | 6 | 2 | 3 | 3 | 1 | 3 | 3 | 3 | 1.6667 | 2 | 3 | 2.5 | 1 | 4 | 3 | 6 | 5 | 2.5 | 3 | 4 | 2 | 2 | 6 | 1.3333 | 1.6667 | 1.5 | 3 | 3 | 4 | 4 | 6 | 1.5 | 1.3333 | 2 | 1.6667 | 5 | 1.5 | 6 | 1 | 5 | 3 | 2.5 | 6 | 1.6667 | 1.6667 | 1.6667
28 | 18.8333 | 11.3333 | 23.3333 | 41.3333 | 50 | 61 | 70.6667 | 86.6667 | 97.6667 | 107.1667 | 114.1667 | 122.5 | 131.8333 | 139.6667 | 2 | 5 | 3 | 1.3333 | 5 | 2.5 | 3 | 1.5 | 5 | 5 | 3 | 5 | 3 | 1.6667 | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 1.3333 | 1.3333 | 4 | 3 | 5 | 5 | 3 | 6 | 1.3333 | 1.6667 | 2 | 1 | 1 | 5 | 2.5 | 1 | 2 | 1.5 | 2.5 | 1.5 | 2.5 | 3 | 1.3333 | 1 | 3 | 1.3333 | 4 | 1.5 | 2 | 3 | 1.3333
29 | 14.8333 | 11.5 | 17.3333 | 25.8333 | 38.8333 | 45.8333 | 54.8333 | 63.8333 | 78.5 | 88.3333 | 94.8333 | 106.3333 | 116.6667 | 126.1667 | 3 | 5 | 1 | 2.5 | 1.6667 | 1.6667 | 1 | 1.5 | 1.5 | 1 | 3 | 3 | 5 | 1 | 6 | 1 | 2 | 2 | 1.5 | 1.5 | 2 | 2 | 2 | 3 | 3 | 3 | 1.6667 | 1.3333 | 5 | 1.6667 | 3 | 5 | 2 | 4 | 1.3333 | 2.5 | 2 | 2 | 1 | 1.5 | 3 | 2 | 1.5 | 5 | 1.3333 | 3 | 3 | 3 | 2 | 2 | 3 | 2.5
30 | 18.3333 | 14 | 23 | 36.6667 | 45.5 | 54.8333 | 63.1667 | 70.6667 | 79.6667 | 91 | 97 | 108 | 117 | 124.5 | 5 | 2 | 2 | 5 | 3 | 1.3333 | 1.6667 | 3 | 3 | 6 | 1.6667 | 3 | 2.5 | 2 | 1.3333 | 3 | 6 | 1 | 1.3333 | 1 | 1.6667 | 3 | 1.6667 | 2 | 1.5 | 1.6667 | 1.3333 | 3 | 1.5 | 2.5 | 4 | 1 | 5 | 2 | 1.3333 | 3 | 1.3333 | 1.3333 | 1.3333 | 2 | 2 | 3 | 4 | 2 | 1 | 3 | 2 | 3 | 1.5 | 3 | 2 | 1
31 | 21 | 13 | 24 | 31.5 | 44.1667 | 54.3333 | 73.3333 | 86.3333 | 94.8333 | 107.3333 | 117.6667 | 131.1667 | 140.3333 | 150.5 | 1 | 6 | 2 | 4 | 2 | 6 | 1.6667 | 1.3333 | 1.5 | 1 | 3 | 2 | 4 | 1.6667 | 5 | 2 | 1.6667 | 3 | 2.5 | 3 | 3 | 6 | 6 | 4 | 6 | 2.5 | 2 | 2.5 | 2.5 | 1.3333 | 1.6667 | 3 | 3 | 3 | 1.5 | 5 | 1.3333 | 4 | 2 | 3 | 6 | 3 | 2 | 2.5 | 2 | 2.5 | 1.6667 | 3 | 5 | 1.5 | 2 | 1.6667
32 | 18.1667 | 12.5 | 22.8333 | 35.1667 | 45.3333 | 53.6667 | 63.6667 | 73.6667 | 89.6667 | 100 | 115.3333 | 124.6667 | 135.6667 | 144.6667 | 2 | 5 | 3 | 2.5 | 4 | 1.6667 | 3 | 1.6667 | 2 | 6 | 3 | 1.3333 | 5 | 1.6667 | 1 | 2.5 | 2.5 | 3 | 1.3333 | 1.5 | 5 | 1.3333 | 2 | 1.6667 | 1 | 6 | 2 | 1 | 3 | 5 | 4 | 4 | 1 | 6 | 2 | 1.3333 | 1.3333 | 4 | 4 | 6 | 3 | 3 | 1.3333 | 2 | 3 | 5 | 1 | 2 | 1.5 | 5 | 1.5 | 1
33 | 12.1667 | 8.1667 | 15.6667 | 27 | 34.1667 | 41.3333 | 52.1667 | 68.6667 | 80.1667 | 92.5 | 100.5 | 110.6667 | 115.5 | 129.1667 | 1.5 | 1.3333 | 4 | 1.3333 | 2 | 2 | 2.5 | 1 | 1.3333 | 2 | 5 | 3 | 1.5 | 2 | 1.6667 | 2 | 1.5 | 1 | 1.6667 | 3 | 1.3333 | 4 | 3 | 2.5 | 2.5 | 5 | 6 | 3 | 2.5 | 2 | 6 | 1 | 6 | 3 | 2 | 1.3333 | 3 | 2 | 1.5 | 1.5 | 4 | 1.5 | 1.6667 | 3 | 1.3333 | 1.5 | 1 | 1 | 5 | 1.6667 | 4 | 3
34 | 17.8333 | 9.8333 | 21.3333 | 27.6667 | 36.6667 | 49.6667 | 64.6667 | 74.1667 | 91.1667 | 101 | 117.5 | 129.5 | 137.3333 | 148.3333 | 2.5 | 1 | 5 | 1.3333 | 4 | 4 | 1 | 2.5 | 1.5 | 1.6667 | 1.5 | 1.6667 | 1.5 | 5 | 1 | 1.5 | 3 | 5 | 4 | 1 | 2 | 5 | 5 | 3 | 2 | 1.5 | 3 | 3 | 2 | 6 | 5 | 4 | 4 | 1.6667 | 2.5 | 1.6667 | 2.5 | 6 | 5 | 3 | 5 | 3 | 1 | 3 | 2 | 1.3333 | 2 | 2.5 | 2.5 | 3 | 4 | 1.5
35 | 13.8333 | 9.6667 | 18.5 | 26.1667 | 34.8333 | 47.3333 | 53.8333 | 62.3333 | 80 | 88.6667 | 97.1667 | 105.6667 | 118.3333 | 125 | 2 | 5 | 1.3333 | 1.3333 | 2.5 | 1.6667 | 3 | 1.6667 | 1.5 | 2 | 1.6667 | 2.5 | 2 | 2 | 3 | 1.6667 | 3 | 6 | 1.5 | 2 | 1 | 1.5 | 2 | 2 | 2 | 2 | 2.5 | 2 | 5 | 6 | 1.6667 | 5 | 2.5 | 3 | 1.6667 | 1.5 | 3 | 2.5 | 1.6667 | 1.3333 | 2 | 1.5 | 2 | 3 | 1.6667 | 4 | 2 | 5 | 1.6667 | 1.6667 | 2 | 1.3333
36 | 19.3333 | 9.3333 | 25 | 34.5 | 47.1667 | 62.1667 | 70.5 | 80.5 | 94.8333 | 109.8333 | 116.6667 | 134.1667 | 140.8333 | 154.1667 | 1.3333 | 3 | 2 | 3 | 5 | 5 | 1.6667 | 4 | 4 | 1.5 | 3 | 1 | 5 | 2 | 1.6667 | 4 | 2 | 1 | 6 | 6 | 1 | 2 | 4 | 1.3333 | 1.3333 | 1.6667 | 5 | 2 | 5 | 2 | 1.3333 | 6 | 4 | 1 | 6 | 4 | 1.5 | 2 | 2 | 1.3333 | 1.5 | 4 | 6 | 6 | 1.3333 | 2 | 2 | 1.3333 | 3 | 5 | 4 | 1.3333
37 | 19 | 11 | 23.5 | 36.5 | 46.5 | 58.5 | 67.1667 | 77.5 | 85.1667 | 91.5 | 101.6667 | 113 | 121 | 130.3333 | 5 | 2.5 | 2 | 1.5 | 2 | 6 | 3 | 1.5 | 5 | 2 | 1 | 5 | 3 | 2 | 1 | 4 | 6 | 2.5 | 1.5 | 2 | 1.6667 | 2 | 2 | 3 | 5 | 3 | 1 | 1.3333 | 2 | 3 | 1.3333 | 1.3333 | 2 | 1.3333 | 1.6667 | 1.3333 | 1.6667 | 3 | 3 | 2.5 | 2.5 | 1.3333 | 2.5 | 5 | 3 | 1.5 | 2.5 | 1 | 1 | 2 | 5 | 1.3333
38 | 18.3333 | 14 | 26 | 37.5 | 53.5 | 66 | 78.6667 | 89.6667 | 97.8333 | 113 | 128 | 137.1667 | 154.6667 | 165 | 2.5 | 2.5 | 6 | 3 | 3 | 1.3333 | 6 | 1.6667 | 5 | 2 | 2.5 | 2 | 1.5 | 2.5 | 6 | 6 | 2 | 2.5 | 5 | 3 | 2 | 1.6667 | 6 | 3 | 3 | 2 | 4 | 2 | 2.5 | 1 | 1.6667 | 3 | 1.6667 | 5 | 6 | 2.5 | 5 | 2 | 2 | 6 | 1.5 | 3 | 1.6667 | 3 | 5 | 2.5 | 4 | 6 | 2 | 5 | 2 | 1.3333
39 | 19 | 12.5 | 23.1667 | 33.5 | 44 | 54.3333 | 61.3333 | 68.8333 | 80.6667 | 93.1667 | 99.6667 | 108.1667 | 121.5 | 132.1667 | 2 | 6 | 2.5 | 2 | 2.5 | 4 | 1.6667 | 2.5 | 1.5 | 5 | 2.5 | 1.3333 | 2.5 | 1.3333 | 5 | 1.6667 | 1 | 3 | 5 | 1.3333 | 2 | 2 | 1 | 2 | 1.5 | 3 | 1.3333 | 1.6667 | 2 | 2.5 | 1.3333 | 6 | 1.5 | 1 | 6 | 4 | 1.3333 | 1.5 | 2 | 1.6667 | 1.5 | 2 | 2 | 3 | 1.3333 | 3 | 3 | 6 | 2 | 3 | 4 | 1.6667
40 | 15.6667 | 11.6667 | 23.6667 | 30 | 44 | 48.8333 | 58.8333 | 70.8333 | 78.1667 | 89.5 | 98.5 | 107.1667 | 120.6667 | 133 | 4 | 1.6667 | 3 | 3 | 1 | 3 | 4 | 4 | 2 | 1.3333 | 2 | 1 | 2.5 | 2.5 | 6 | 3 | 1 | 1 | 1.3333 | 1.5 | 4 | 3 | 1.3333 | 1.6667 | 1 | 1 | 6 | 4 | 2 | 2 | 1.3333 | 2 | 1.3333 | 5 | 2 | 3 | 2.5 | 1.5 | 1 | 4 | 1 | 3 | 3 | 1.6667 | 5 | 5 | 2 | 1.5 | 3 | 2 | 6 | 1.3333
41 | 15 | 10.6667 | 18.3333 | 27.3333 | 36.8333 | 46.1667 | 59.8333 | 73.8333 | 82.5 | 94 | 100.3333 | 110.8333 | 117.5 | 125.8333 | 6 | 1.6667 | 1.6667 | 1.3333 | 1.3333 | 3 | 2 | 1.3333 | 1 | 2 | 3 | 3 | 2 | 1.5 | 1 | 5 | 5 | 1.3333 | 1.6667 | 1.3333 | 6 | 4 | 1.6667 | 2 | 2 | 6 | 3 | 3 | 2 | 1 | 1.6667 | 4 | 2.5 | 2 | 3 | 4 | 1.3333 | 2 | 2 | 1 | 3 | 1.5 | 3 | 3 | 1.6667 | 1 | 2 | 2 | 1.3333 | 1.5 | 4 | 1.5
42 | 18.8333 | 13.8333 | 22.1667 | 33.8333 | 48.1667 | 57.6667 | 69 | 81.6667 | 97.3333 | 115.3333 | 121.8333 | 131.3333 | 145.3333 | 158.3333 | 5 | 6 | 1.3333 | 1.5 | 4 | 1 | 2 | 1.3333 | 3 | 1.6667 | 4 | 3 | 5 | 1.3333 | 5 | 3 | 3 | 2 | 3 | 1.5 | 2 | 3 | 5 | 1.3333 | 5 | 3 | 1.6667 | 3 | 6 | 6 | 2 | 1.6667 | 6 | 4 | 2 | 6 | 2 | 2 | 1 | 1.5 | 1.3333 | 4 | 1.6667 | 2.5 | 1 | 6 | 2 | 5 | 4 | 2 | 4 | 3
43 | 19 | 11.6667 | 24 | 29.5 | 43.1667 | 53.6667 | 64.3333 | 76.1667 | 85.1667 | 93.8333 | 102 | 108.5 | 119.5 | 128.6667 | 6 | 2 | 1.6667 | 2 | 1.3333 | 6 | 3 | 2 | 1.5 | 1.6667 | 1.3333 | 1 | 6 | 3 | 1.6667 | 3 | 3 | 2.5 | 3 | 2 | 5 | 3 | 1 | 1.6667 | 1.3333 | 2.5 | 6 | 2 | 2 | 3 | 3 | 1 | 1.6667 | 4 | 1.3333 | 1.6667 | 2 | 3 | 1.6667 | 1.5 | 1.3333 | 1.3333 | 2.5 | 1.3333 | 2 | 3 | 2 | 4 | 1.5 | 3 | 3 | 1.6667
44 | 16 | 10 | 24 | 37.3333 | 43.6667 | 56 | 62.5 | 74.1667 | 83.3333 | 95.8333 | 105.8333 | 120 | 128.8333 | 135.6667 | 2 | 1.5 | 5 | 1.5 | 4 | 2 | 3 | 5 | 1.3333 | 3 | 5 | 4 | 2 | 1.3333 | 1.6667 | 1.3333 | 2 | 5 | 1.3333 | 4 | 1.6667 | 2.5 | 1.3333 | 1 | 2.5 | 1.5 | 6 | 1.6667 | 2.5 | 1 | 4 | 1.6667 | 3 | 5 | 1.5 | 3 | 2 | 2 | 5 | 1 | 5 | 1.5 | 1.6667 | 6 | 1.3333 | 2 | 4 | 1.5 | 2.5 | 1.3333 | 1 | 2
45 | 21.6667 | 14.6667 | 28.6667 | 41.6667 | 53.8333 | 64.1667 | 69.8333 | 81.3333 | 94 | 106 | 121.6667 | 134.6667 | 144.6667 | 154.5 | 6 | 1.6667 | 4 | 3 | 4 | 3 | 3 | 4 | 4 | 6 | 1.5 | 1.5 | 3 | 2.5 | 5 | 1.6667 | 1 | 2 | 6 | 1.3333 | 1.5 | 1.6667 | 1.5 | 1 | 2.5 | 2 | 3 | 4 | 2 | 4 | 1.6667 | 5 | 1.6667 | 3 | 6 | 1.3333 | 2 | 1.6667 | 6 | 6 | 2.5 | 2 | 2.5 | 6 | 2 | 2 | 2 | 4 | 1.5 | 5 | 2 | 1.3333
46 | 15.6667 | 13 | 23.1667 | 30.8333 | 44.3333 | 62.3333 | 73.3333 | 82.6667 | 92.8333 | 99.8333 | 110.3333 | 126 | 140 | 147.6667 | 4 | 2 | 3 | 4 | 1 | 1.6667 | 1.5 | 6 | 2 | 1 | 1.6667 | 3 | 2.5 | 3 | 3 | 5 | 4 | 3 | 6 | 5 | 2 | 2.5 | 1.5 | 5 | 1 | 1.6667 | 5 | 1.6667 | 1.6667 | 2.5 | 3 | 3 | 3 | 1 | 1 | 2 | 1 | 2 | 5 | 2.5 | 6 | 5 | 1.6667 | 3 | 5 | 6 | 2 | 1 | 1.6667 | 2 | 1.5 | 2.5
47 | 20 | 14 | 27.3333 | 31.6667 | 47 | 55.3333 | 71.3333 | 79.6667 | 94.6667 | 108.8333 | 121.8333 | 136.6667 | 153 | 161.1667 | 4 | 5 | 2 | 3 | 3 | 3 | 6 | 1.3333 | 1 | 1 | 1.3333 | 1 | 6 | 1.3333 | 3 | 5 | 1.6667 | 1.6667 | 2 | 3 | 2 | 5 | 4 | 5 | 1.5 | 1.5 | 4 | 1.3333 | 4 | 5 | 5 | 1 | 6 | 1.6667 | 1.5 | 5 | 3 | 5 | 1 | 4 | 6 | 2.5 | 5 | 1.3333 | 6 | 5 | 1.3333 | 4 | 2.5 | 3 | 1 | 1.6667
48 | 13.3333 | 7.3333 | 21.3333 | 38.3333 | 52.3333 | 63.6667 | 75.6667 | 88.1667 | 99.5 | 113 | 129 | 135.3333 | 150.6667 | 159.6667 | 1.3333 | 2 | 3 | 1 | 2 | 4 | 2 | 6 | 2 | 4 | 5 | 6 | 3 | 2.5 | 2.5 | 6 | 2 | 3 | 1.3333 | 5 | 3 | 6 | 1.3333 | 1.6667 | 2 | 2.5 | 6 | 2 | 2.5 | 1.5 | 1.3333 | 6 | 2 | 3 | 2.5 | 6 | 2.5 | 2.5 | 6 | 5 | 1.5 | 1.3333 | 2 | 1.5 | 3 | 6 | 5 | 1.3333 | 2 | 4 | 1.6667 | 1.3333
49 | 17.5 | 10.5 | 29.5 | 39.3333 | 53.3333 | 63.6667 | 74.6667 | 85.1667 | 99.1667 | 107.3333 | 118.5 | 134 | 142.6667 | 150 | 3 | 2 | 2.5 | 3 | 5 | 2 | 6 | 6 | 2 | 2.5 | 4 | 1.3333 | 5 | 1 | 3 | 5 | 1.3333 | 4 | 1 | 4 | 1 | 2 | 2 | 6 | 2 | 3 | 4 | 1.5 | 5 | 4 | 2 | 3 | 2.5 | 1.6667 | 2 | 2 | 3 | 1.5 | 5 | 1.6667 | 5 | 6 | 2 | 2.5 | 2 | 3 | 1.6667 | 2 | 1.3333 | 3 | 1 | 2
50 | 12.3333 | 9 | 15.8333 | 25.3333 | 43.6667 | 53.1667 | 62.6667 | 75.3333 | 83.1667 | 98.1667 | 112.6667 | 118.3333 | 126 | 134.5 | 5 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 2 | 2 | 1.5 | 2 | 4 | 1.5 | 2 | 6 | 6 | 1.3333 | 5 | 2 | 3 | 3 | 1.5 | 3 | 1.5 | 3 | 2 | 6 | 3 | 1.6667 | 2 | 1.3333 | 1 | 3 | 2.5 | 2 | 4 | 6 | 3 | 6 | 2.5 | 4 | 2 | 1 | 1.5 | 1.6667 | 1.5 | 2 | 1.3333 | 1.3333 | 3 | 2 | 2.5 | 3 | 1
51 | 9.8333 | 6.8333 | 16.8333 | 26 | 40.3333 | 54.8333 | 62.8333 | 69 | 79.6667 | 89.6667 | 103.6667 | 116.8333 | 126.8333 | 142.8333 | 3 | 1.5 | 1 | 1.3333 | 2 | 1 | 3 | 4 | 3 | 3 | 1.6667 | 1.5 | 4 | 1.3333 | 3 | 6 | 3 | 6 | 3 | 2.5 | 2.5 | 1.5 | 2.5 | 1.5 | 2 | 1.5 | 1.6667 | 1 | 3 | 3 | 1.6667 | 3 | 4 | 2 | 2 | 2 | 3 | 4 | 5 | 2 | 2.5 | 6 | 3 | 1.6667 | 2 | 3 | 3 | 2 | 4 | 3 | 4 | 5
52 | 18.5 | 13.5 | 22.5 | 33.1667 | 43.1667 | 55.3333 | 63.3333 | 79.3333 | 92.8333 | 100.3333 | 109.1667 | 119.6667 | 126.5 | 140.8333 | 2.5 | 2.5 | 6 | 2.5 | 3 | 2 | 2.5 | 1.5 | 1.6667 | 3 | 2 | 4 | 1.5 | 1.5 | 1 | 6 | 3 | 6 | 1.6667 | 1.5 | 3 | 1.5 | 1.5 | 2 | 6 | 2.5 | 5 | 2.5 | 2.5 | 6 | 3 | 2 | 2.5 | 2 | 1.6667 | 1.3333 | 1.3333 | 4 | 1.5 | 2 | 5 | 2 | 2 | 1.5 | 1 | 1.3333 | 2.5 | 2 | 6 | 1.3333 | 2 | 5
53 | 21.3333 | 10.3333 | 27.3333 | 37.3333 | 45.3333 | 54.3333 | 63.1667 | 73.6667 | 89.1667 | 101.6667 | 114.1667 | 128.6667 | 141 | 152.1667 | 5 | 1.3333 | 2 | 2 | 5 | 6 | 4 | 2 | 2 | 4 | 1 | 3 | 1.6667 | 3 | 1.3333 | 2 | 2 | 1.3333 | 1.6667 | 4 | 1.6667 | 1.5 | 1.6667 | 4 | 2 | 5 | 1.5 | 2 | 2.5 | 4 | 3 | 6 | 3 | 2 | 2.5 | 5 | 3 | 2 | 1.5 | 6 | 6 | 1 | 6 | 1.5 | 4 | 3 | 1.3333 | 4 | 1.6667 | 1.5 | 4 | 4
54 | 12.8333 | 9.1667 | 16.5 | 23.8333 | 38.8333 | 48.3333 | 62.8333 | 77.1667 | 86.6667 | 97.5 | 107 | 116.8333 | 126.1667 | 135.8333 | 3 | 2.5 | 2 | 1.6667 | 1.6667 | 2 | 2 | 1.6667 | 2.5 | 1.3333 | 2.5 | 1 | 2 | 3 | 6 | 4 | 1.5 | 4 | 2 | 2 | 6 | 1.5 | 2 | 5 | 4 | 3 | 6 | 1.3333 | 1.5 | 2 | 4 | 2 | 5 | 1.3333 | 1.5 | 3 | 3 | 2 | 3 | 1.5 | 1.3333 | 1 | 2.5 | 5 | 2 | 1 | 1.3333 | 5 | 1 | 4 | 1.6667 | 3
55 | 19.1667 | 11.1667 | 24.1667 | 31.1667 | 39.6667 | 53.1667 | 63.8333 | 74.3333 | 83.1667 | 98.1667 | 105.3333 | 117 | 128.6667 | 134.5 | 2.5 | 1 | 1.6667 | 6 | 5 | 3 | 2 | 3 | 2 | 1.5 | 1.5 | 2 | 2 | 1 | 3 | 2.5 | 3 | 2.5 | 6 | 2 | 1.3333 | 2 | 1.3333 | 6 | 2 | 2.5 | 4 | 2 | 1.3333 | 2 | 1.5 | 4 | 3 | 4 | 4 | 4 | 1 | 2 | 2.5 | 1.6667 | 2 | 1.6667 | 5 | 3 | 1.6667 | 2 | 2 | 6 | 1.3333 | 1.6667 | 1.5 | 1.3333
56 | 19.1667 | 13.1667 | 25.1667 | 35.6667 | 45 | 56.3333 | 63 | 74.3333 | 90.3333 | 96.6667 | 111.1667 | 118.6667 | 130.1667 | 143.6667 | 6 | 1.6667 | 4 | 1.5 | 3 | 3 | 2 | 4 | 4 | 3 | 2 | 1.5 | 1.3333 | 1 | 5 | 2 | 6 | 2 | 2 | 1.3333 | 1.6667 | 1.5 | 2.5 | 1 | 1.3333 | 1 | 4 | 5 | 3 | 6 | 6 | 1 | 1.3333 | 2 | 1.5 | 1.5 | 6 | 1 | 6 | 1.5 | 1 | 2 | 1.5 | 3 | 2 | 1.5 | 2 | 6 | 5 | 5 | 1.5 | 2
57 | 15 | 8.5 | 23.5 | 38.8333 | 47 | 57.5 | 68.5 | 75.3333 | 81.6667 | 95 | 104 | 114.5 | 125.5 | 136.1667 | 1.5 | 2 | 4 | 1 | 4 | 2.5 | 2.5 | 6 | 4 | 5 | 5 | 1.3333 | 3 | 1.3333 | 2.5 | 1.3333 | 1 | 6 | 1.5 | 2 | 2 | 2 | 3 | 4 | 1.6667 | 1.5 | 2 | 1.6667 | 3 | 1 | 1.3333 | 1 | 1.3333 | 6 | 2 | 4 | 3 | 3 | 2 | 1 | 6 | 1.5 | 1.3333 | 1.6667 | 3 | 5 | 1 | 2 | 5 | 3 | 1.6667 | 1
58 | 13.8333 | 8.1667 | 16.3333 | 22.8333 | 31.3333 | 42.6667 | 58.1667 | 67.8333 | 79.3333 | 92 | 106.5 | 116.8333 | 128.8333 | 141.8333 | 1.6667 | 2 | 2 | 2.5 | 1.6667 | 4 | 1 | 1.5 | 1.6667 | 1.3333 | 1.5 | 2 | 2 | 1 | 4 | 1.5 | 4 | 3 | 1.3333 | 3 | 2.5 | 5 | 2 | 6 | 4 | 1.6667 | 2 | 2 | 2.5 | 5 | 2.5 | 1.5 | 5 | 1.6667 | 3 | 3 | 2 | 6 | 4 | 2.5 | 3 | 2 | 4 | 1.3333 | 5 | 3 | 2.5 | 1.5 | 6 | 4 | 1.3333 | 1.6667
59 | 23 | 13 | 26 | 36.6667 | 44.3333 | 55.8333 | 71.8333 | 82.8333 | 96.5 | 107.5 | 117.5 | 125.5 | 135.3333 | 145.8333 | 3 | 3 | 2 | 5 | 4 | 6 | 1.5 | 1.5 | 3 | 3 | 1.6667 | 3 | 1.5 | 1.6667 | 3 | 1.5 | 2 | 6 | 2 | 1.5 | 2 | 2 | 6 | 6 | 1 | 1 | 4 | 5 | 3 | 5 | 1.6667 | 4 | 1.5 | 2 | 1.5 | 6 | 2 | 3 | 3 | 2 | 4 | 1.3333 | 1 | 1.6667 | 2 | 1.5 | 1.3333 | 5 | 6 | 2.5 | 1 | 1
60 | 18.6667 | 12 | 22.6667 | 37.6667 | 48.5 | 60.3333 | 72.3333 | 83.6667 | 91.1667 | 103.3333 | 113.1667 | 122.6667 | 132.5 | 141.5 | 5 | 1.3333 | 1.6667 | 4 | 5 | 1.6667 | 3 | 1 | 3 | 3 | 3 | 6 | 3 | 1.3333 | 4 | 2.5 | 6 | 1.3333 | 2 | 2.5 | 3 | 3 | 3 | 3 | 1.6667 | 1.6667 | 6 | 2 | 1.5 | 2 | 3 | 1 | 5 | 2.5 | 1.6667 | 3 | 6 | 1 | 1.3333 | 1.5 | 2.5 | 2.5 | 2.5 | 2 | 4 | 3 | 1.5 | 1.3333 | 1 | 2 | 3 | 3
61 | 15.1667 | 7.6667 | 21.1667 | 33.5 | 48.5 | 61.1667 | 71.6667 | 85 | 97.5 | 109.5 | 123.5 | 129 | 134.3333 | 142.3333 | 1.6667 | 1 | 2 | 3 | 1.5 | 6 | 2 | 4 | 1.3333 | 2 | 4 | 5 | 2 | 5 | 3 | 5 | 5 | 1.6667 | 2 | 4 | 1.6667 | 1.3333 | 2.5 | 5 | 3 | 1.3333 | 6 | 3 | 3 | 3 | 5 | 1.5 | 4 | 2 | 3 | 3 | 5 | 6 | 2 | 1 | 1.5 | 1.3333 | 1 | 1.6667 | 1 | 1.3333 | 1 | 2 | 3 | 1.6667 | 2 | 1.3333
62 | 14.1667 | 11.1667 | 18.6667 | 32.6667 | 40.6667 | 55.6667 | 70.6667 | 87.3333 | 103.3333 | 115.1667 | 125.3333 | 138.3333 | 148.8333 | 162.8333 | 1.6667 | 2 | 2.5 | 5 | 1 | 2 | 3 | 1.5 | 6 | 1 | 2 | 5 | 1 | 2 | 2 | 3 | 2.5 | 2.5 | 5 | 5 | 1.3333 | 6 | 6 | 1.6667 | 4 | 6 | 5 | 1.6667 | 4 | 5 | 2 | 5 | 3 | 1.5 | 1.3333 | 6 | 5 | 1.6667 | 1.5 | 2 | 1.5 | 5 | 4 | 2.5 | 5 | 1 | 2.5 | 2 | 2.5 | 5 | 1.5 | 5
63 | 10.1667 | 7.5 | 15.1667 | 23.1667 | 31.8333 | 42.1667 | 55.1667 | 64.6667 | 76.6667 | 82.6667 | 91.3333 | 100 | 109.6667 | 122.1667 | 1.5 | 3 | 1 | 2 | 1.3333 | 1.3333 | 3 | 2 | 2 | 3 | 1 | 2 | 3 | 1.3333 | 1.3333 | 3 | 4 | 1.3333 | 1 | 4 | 3 | 6 | 1 | 3 | 1 | 1 | 5 | 2.5 | 3 | 2 | 4 | 3 | 1 | 2 | 1.6667 | 1.3333 | 2 | 4 | 1 | 1.6667 | 2.5 | 2.5 | 1.6667 | 2 | 1.3333 | 5 | 1.6667 | 1.6667 | 2 | 6 | 3 | 1.5
64 | 12.3333 | 10 | 16.6667 | 27.1667 | 38.1667 | 50.1667 | 62.1667 | 81.1667 | 92.3333 | 113.3333 | 121.1667 | 139.1667 | 151 | 166 | 3 | 2 | 2 | 3 | 1 | 1.3333 | 1.3333 | 3 | 4 | 2 | 2 | 2.5 | 4 | 1 | 5 | 1 | 1 | 4 | 5 | 2 | 1 | 5 | 5 | 1 | 6 | 4 | 5 | 4 | 2.5 | 1 | 6 | 1.6667 | 5 | 6 | 6 | 4 | 1 | 2.5 | 1.3333 | 3 | 5 | 6 | 2 | 5 | 4 | 4 | 2.5 | 1.3333 | 3 | 5 | 4 | 3
65 | 14 | 10 | 22 | 31 | 39 | 46.8333 | 54.1667 | 60.6667 | 72.6667 | 81.5 | 94 | 100.3333 | 112.1667 | 123.8333 | 1.5 | 5 | 2 | 1.5 | 2 | 2 | 4 | 4 | 1 | 1 | 3 | 4 | 1.5 | 3 | 1.5 | 2 | 1.3333 | 2 | 2.5 | 2 | 2 | 1.3333 | 1.5 | 2.5 | 1.5 | 1.6667 | 2 | 1.3333 | 2 | 2 | 3 | 5 | 2.5 | 1.6667 | 1.6667 | 3 | 3 | 2 | 1.5 | 6 | 1.3333 | 1 | 1.5 | 2.5 | 3 | 1.3333 | 1.5 | 6 | 2 | 2 | 1.6667 | 6
66 | 13.6667 | 8 | 18.1667 | 28.5 | 38 | 50 | 63.5 | 75 | 84.6667 | 91.3333 | 105.3333 | 112.3333 | 123.6667 | 137.1667 | 2 | 2 | 1.5 | 2.5 | 1.6667 | 4 | 2 | 2.5 | 1.6667 | 1 | 6 | 1.6667 | 2 | 1 | 2.5 | 4 | 2 | 3 | 4 | 3 | 4 | 1.5 | 5 | 3 | 2 | 1.5 | 6 | 2 | 1.6667 | 5 | 1.6667 | 1.3333 | 1.6667 | 2 | 1 | 2 | 1 | 5 | 3 | 5 | 1 | 1.5 | 3 | 1.5 | 4 | 2 | 4 | 1.3333 | 6 | 4 | 1.5 | 2
67 | 23.6667 | 18 | 27.6667 | 39.6667 | 48.6667 | 62.8333 | 74.8333 | 88.3333 | 98.8333 | 109.6667 | 120.5 | 132.1667 | 148.8333 | 160.8333 | 2 | 6 | 5 | 5 | 1.6667 | 4 | 2 | 2 | 3 | 1.6667 | 1.3333 | 6 | 1 | 1 | 1 | 6 | 5 | 1.6667 | 1.5 | 6 | 2 | 6 | 3 | 1 | 1.5 | 5 | 2 | 5 | 3 | 2.5 | 2.5 | 2.5 | 2.5 | 4 | 3 | 1.3333 | 4 | 2.5 | 3 | 1.3333 | 5 | 1.6667 | 2.5 | 2.5 | 3 | 6 | 6 | 1.6667 | 1.6667 | 6 | 1.3333 | 3
68 | 14.3333 | 9.8333 | 21.6667 | 33.3333 | 41.3333 | 51.8333 | 65.8333 | 74.5 | 86.1667 | 95.1667 | 105.5 | 115.8333 | 127.8333 | 136.6667 | 1.3333 | 1.5 | 1 | 6 | 2.5 | 2 | 1.3333 | 6 | 3 | 6 | 1.6667 | 1 | 2.5 | 2 | 2.5 | 1 | 2.5 | 1.3333 | 1.6667 | 5 | 5 | 5 | 1.5 | 2.5 | 1 | 1.6667 | 2 | 4 | 2 | 3 | 5 | 1.6667 | 1.3333 | 3 | 3 | 1.6667 | 6 | 1.3333 | 2 | 1 | 3 | 2 | 4 | 1.3333 | 1.6667 | 1.3333 | 5 | 4 | 1.3333 | 1.5 | 5 | 1
69 | 17 | 11.5 | 27 | 38 | 48.5 | 59.3333 | 69.3333 | 83.6667 | 92.5 | 100.8333 | 111.6667 | 119.8333 | 127 | 143.3333 | 3 | 2.5 | 4 | 2 | 3 | 2.5 | 5 | 5 | 4 | 3 | 2 | 2 | 5 | 2.5 | 1.6667 | 1.3333 | 1.3333 | 5 | 2.5 | 2 | 5 | 1.6667 | 2 | 1.3333 | 5 | 4 | 1.3333 | 4 | 1.6667 | 1.5 | 1.6667 | 4 | 1 | 1.3333 | 3 | 3 | 6 | 1.3333 | 1.5 | 2 | 3 | 2 | 1.6667 | 1.5 | 1.3333 | 2 | 1.3333 | 2.5 | 6 | 1.3333 | 6 | 3
70 | 12.6667 | 9.6667 | 15.6667 | 26.8333 | 34.1667 | 44 | 54.5 | 70 | 76.3333 | 86.3333 | 100.8333 | 108.8333 | 116 | 125.1667 | 3 | 2 | 1.6667 | 3 | 2 | 1 | 2 | 1 | 5 | 3 | 1.6667 | 1.5 | 2 | 2 | 2 | 1.3333 | 2 | 4 | 1.3333 | 2.5 | 2 | 4 | 2.5 | 2 | 3 | 2.5 | 6 | 4 | 1.3333 | 1.3333 | 2 | 1.6667 | 4 | 3 | 2 | 1 | 3 | 5 | 5 | 1.5 | 1.3333 | 3 | 1.6667 | 2 | 3 | 1.5 | 1.6667 | 1 | 3 | 2 | 1.6667 | 2.5
71 | 13 | 7 | 17 | 27.1667 | 43.1667 | 56.1667 | 65.5 | 77.8333 | 88 | 96 | 102.5 | 112 | 120 | 126.1667 | 1 | 1 | 3 | 2 | 3 | 3 | 2 | 2 | 1.5 | 2 | 5 | 1.6667 | 2 | 4 | 5 | 5 | 4 | 5 | 3 | 1 | 3 | 4 | 1 | 1.3333 | 5 | 1.3333 | 3 | 3 | 1.3333 | 6 | 1.5 | 1.3333 | 1.6667 | 2 | 1.3333 | 3 | 1.6667 | 1.3333 | 1.5 | 2 | 2.5 | 1.5 | 2.5 | 3 | 1.5 | 1 | 4 | 1.5 | 1.6667 | 1 | 1 | 2.5
72 | 13 | 9.6667 | 19.5 | 32.5 | 40 | 51 | 62 | 70.5 | 84.5 | 90.3333 | 98.6667 | 111.6667 | 122.6667 | 136.6667 | 2 | 2 | 4 | 1.6667 | 2 | 1.3333 | 2.5 | 4 | 2 | 2 | 4 | 5 | 1 | 2.5 | 1.5 | 2.5 | 5 | 3 | 2 | 1 | 3 | 4 | 3 | 1 | 1.5 | 2 | 2 | 3 | 2 | 5 | 6 | 1 | 2 | 1.5 | 1 | 1.3333 | 1.3333 | 3 | 2 | 2 | 3 | 6 | 2 | 2 | 5 | 2.5 | 2.5 | 1 | 6 | 2.5 | 1.5 | 4
73 | 16.5 | 14 | 23.1667 | 35.8333 | 47.8333 | 58.1667 | 68.6667 | 80.6667 | 94 | 103.5 | 113.5 | 122.6667 | 127.6667 | 137.6667 | 3 | 2 | 4 | 5 | 1 | 1.5 | 1.6667 | 5 | 3 | 4 | 4 | 1.6667 | 5 | 5 | 1 | 1 | 2 | 1.6667 | 5 | 1.6667 | 4 | 4 | 1.5 | 1 | 4 | 2.5 | 3 | 2.5 | 5 | 1.3333 | 3 | 4 | 2 | 3 | 2 | 2.5 | 1 | 6 | 1 | 2 | 1.6667 | 3 | 1.5 | 3 | 1.3333 | 1.3333 | 1.3333 | 1 | 1 | 1.5 | 2.5 | 5
74 | 17 | 11.5 | 21.6667 | 28.1667 | 42.1667 | 55.1667 | 70.1667 | 84.1667 | 98.1667 | 110.8333 | 122.1667 | 130.3333 | 136.6667 | 150.1667 | 6 | 3 | 1 | 1.5 | 3 | 2.5 | 3 | 1.6667 | 1.3333 | 1.6667 | 2 | 1.5 | 5 | 2 | 5 | 2 | 3 | 4 | 3 | 3 | 3 | 3 | 4 | 5 | 4 | 2 | 3 | 5 | 2 | 3 | 6 | 3 | 1.6667 | 6 | 1 | 4 | 4 | 3 | 3 | 1.3333 | 1 | 1.5 | 1.6667 | 4 | 1 | 1.3333 | 1 | 3 | 5 | 5 | 1.5 | 2
75 | 14 | 8.5 | 20 | 31.5 | 42.1667 | 51.5 | 67 | 81.5 | 88.5 | 99.6667 | 107.8333 | 118.1667 | 129.8333 | 141.5 | 2.5 | 1 | 4 | 1 | 2.5 | 3 | 3 | 3 | 4 | 1.5 | 3 | 3 | 1 | 1.6667 | 2 | 6 | 3 | 1 | 1.3333 | 4 | 6 | 3 | 5 | 1.5 | 3 | 3 | 6 | 2.5 | 1.3333 | 1 | 1.6667 | 3 | 4 | 1.6667 | 2.5 | 3 | 1 | 3 | 2.5 | 1.6667 | 2 | 5 | 2 | 1.3333 | 2 | 2 | 1.6667 | 6 | 3 | 4 | 3 | 1.6667
76 | 19.3333 | 15.3333 | 23 | 37.5 | 48.5 | 58 | 68 | 82.3333 | 95.3333 | 102.8333 | 111.3333 | 122.6667 | 129.3333 | 144.3333 | 1.3333 | 4 | 6 | 4 | 1.5 | 2.5 | 2 | 1.6667 | 5 | 3 | 5 | 1.5 | 6 | 1 | 3 | 1 | 1 | 3 | 3 | 2.5 | 4 | 2.5 | 1 | 2.5 | 4 | 4 | 5 | 1.3333 | 6 | 3 | 1 | 3 | 2 | 2 | 1 | 2.5 | 1.6667 | 3 | 2.5 | 1.3333 | 3 | 5 | 2 | 1.3333 | 1.3333 | 2 | 1.3333 | 2 | 6 | 6 | 2 | 1
77 | 17 | 11.5 | 23.5 | 33.1667 | 44.6667 | 55.6667 | 64.6667 | 72.3333 | 81.3333 | 91.8333 | 108.3333 | 122.8333 | 137.8333 | 148.3333 | 2 | 5 | 1.5 | 3 | 2.5 | 3 | 4 | 2.5 | 1 | 1.6667 | 6 | 1 | 1 | 2.5 | 6 | 2 | 2 | 5 | 2 | 2 | 2.5 | 1.5 | 3 | 2 | 3 | 1.6667 | 1.5 | 1.5 | 2.5 | 2 | 2 | 2.5 | 3 | 3 | 1.5 | 3 | 2.5 | 6 | 4 | 4 | 6 | 1 | 2.5 | 5 | 5 | 2 | 6 | 2 | 6 | 1.5 | 1.6667 | 1.3333
78 | 17 | 12 | 19.6667 | 32.6667 | 45.1667 | 57.1667 | 69.1667 | 87.1667 | 100.1667 | 106.8333 | 120.3333 | 131.8333 | 138.6667 | 145 | 4 | 3 | 3 | 2 | 3 | 2 | 1.3333 | 1.3333 | 3 | 6 | 1 | 3 | 3 | 5 | 2.5 | 2 | 2 | 6 | 3 | 1 | 4 | 2 | 3 | 3 | 5 | 5 | 3 | 5 | 3 | 4 | 2 | 4 | 2.5 | 1.5 | 1.3333 | 1.3333 | 3 | 6 | 3 | 1.5 | 2.5 | 5 | 2 | 2 | 1.6667 | 1.5 | 2 | 1.6667 | 2 | 2 | 1 | 1.3333
79 | 12 | 7.5 | 18 | 28.3333 | 37 | 46 | 60 | 76 | 84 | 95 | 105 | 116.5 | 127.8333 | 139.5 | 3 | 1 | 1.5 | 2 | 3 | 1.5 | 5 | 1 | 5 | 1.3333 | 2 | 2 | 1.6667 | 1.6667 | 1.3333 | 4 | 2 | 3 | 2 | 2 | 3 | 5 | 4 | 2 | 3 | 3 | 6 | 4 | 1 | 3 | 3 | 1 | 1 | 2 | 6 | 2 | 1.5 | 4 | 3 | 1.5 | 2 | 3 | 2.5 | 4 | 3 | 3 | 1.3333 | 4 | 2 | 6 | 2 | 1.6667
80 | 12.1667 | 9 | 16 | 36 | 46 | 58.3333 | 72.3333 | 83 | 97.3333 | 107.6667 | 119.1667 | 130.1667 | 139.8333 | 147.6667 | 1 | 2.5 | 3 | 2.5 | 1.6667 | 1.5 | 2.5 | 1.3333 | 6 | 6 | 3 | 5 | 2 | 5 | 2 | 1 | 1.6667 | 6 | 1.6667 | 3 | 1 | 5 | 6 | 2 | 4 | 4 | 1.6667 | 1 | 6 | 1 | 6 | 1.3333 | 5 | 2 | 2 | 1.3333 | 3 | 2.5 | 5 | 1 | 1 | 1 | 6 | 3 | 3 | 3 | 1.6667 | 2 | 1.3333 | 2 | 3 | 1.5
81 | 18.3333 | 10.3333 | 21.8333 | 33.6667 | 47.1667 | 59.1667 | 73.1667 | 84.5 | 97.5 | 108.3333 | 114.3333 | 126.3333 | 134.3333 | 146 | 6 | 1.3333 | 1 | 2 | 3 | 5 | 2 | 1.5 | 5 | 1.3333 | 2.5 | 3 | 6 | 1.5 | 3 | 3 | 2 | 3 | 6 | 1 | 2 | 5 | 3 | 4 | 2 | 6 | 2 | 1.3333 | 5 | 6 | 1 | 1 | 5 | 3 | 1.5 | 1.3333 | 2 | 1.5 | 1 | 1.5 | 6 | 1.5 | 2 | 2.5 | 3 | 2 | 1.6667 | 1.3333 | 2 | 3 | 5 | 1.6667
82 | 21.1667 | 15.1667 | 30.1667 | 46.1667 | 53.1667 | 64.6667 | 75.6667 | 89.1667 | 96.3333 | 114.3333 | 128 | 136.3333 | 147.3333 | 158 | 2.5 | 1.6667 | 6 | 5 | 4 | 2 | 3 | 6 | 5 | 2.5 | 6 | 2.5 | 1 | 1 | 3 | 2 | 1.5 | 5 | 3 | 2 | 1 | 3 | 2 | 5 | 4 | 1.5 | 3 | 5 | 1.5 | 1 | 1.6667 | 3 | 6 | 5 | 3 | 4 | 2 | 1.6667 | 5 | 5 | 3 | 2 | 2 | 1.3333 | 2 | 4 | 2 | 3 | 1.6667 | 2.5 | 2.5 | 4
83 | 13.6667 | 10 | 17.8333 | 25.5 | 35.5 | 48.3333 | 57.3333 | 64.3333 | 74 | 87 | 98.3333 | 106.5 | 115 | 123.8333 | 2 | 1.3333 | 5 | 1.6667 | 1.6667 | 2 | 1.6667 | 2.5 | 3 | 1.6667 | 1.6667 | 1.3333 | 2 | 3 | 3 | 2 | 1.3333 | 4 | 2.5 | 5 | 2.5 | 2 | 2 | 2.5 | 2 | 2 | 2 | 1 | 3 | 3 | 2 | 1.6667 | 6 | 2 | 2 | 3 | 6 | 2 | 1.3333 | 2 | 1.6667 | 1 | 2.5 | 3 | 2 | 1.5 | 4 | 1 | 3 | 1.3333 | 3 | 1.5
84 | 14 | 10.8333 | 20.3333 | 30 | 42.3333 | 56.8333 | 69.3333 | 81.6667 | 94.1667 | 105.1667 | 114.8333 | 126.8333 | 135.1667 | 149.1667 | 5 | 1.3333 | 1.5 | 3 | 1.6667 | 1.5 | 5 | 1.3333 | 3 | 3 | 2 | 1.6667 | 3 | 5 | 1.3333 | 3 | 1.5 | 3 | 6 | 4 | 4 | 1.5 | 2 | 5 | 1.3333 | 2.5 | 2.5 | 6 | 3 | 6 | 1.5 | 2 | 5 | 1.5 | 3 | 1.5 | 2.5 | 2.5 | 3 | 1.6667 | 5 | 1 | 4 | 2 | 3 | 1.6667 | 2 | 1.6667 | 3 | 4 | 5 | 2
85 | 17.1667 | 9.5 | 24.1667 | 36.1667 | 50.6667 | 62.8333 | 78.3333 | 96.3333 | 105.3333 | 114.3333 | 123.5 | 135.8333 | 146.5 | 154.1667 | 2.5 | 2 | 2 | 3 | 6 | 1.6667 | 6 | 1 | 2 | 4 | 3 | 3 | 1.5 | 5 | 5 | 3 | 2 | 2.5 | 6 | 1.6667 | 5 | 1.5 | 3 | 6 | 5 | 6 | 6 | 1 | 3 | 2.5 | 1.5 | 2 | 3 | 1.6667 | 1.3333 | 3 | 1.6667 | 4 | 2.5 | 1 | 1.6667 | 6 | 3 | 1.6667 | 3 | 2 | 4 | 1.6667 | 2 | 3 | 1.6667 | 1
86 | 16.5 | 7.5 | 24 | 33.3333 | 45.8333 | 60.3333 | 71.3333 | 83.6667 | 95.6667 | 105.6667 | 114.3333 | 122.1667 | 135.6667 | 144 | 1 | 3 | 2.5 | 1 | 5 | 4 | 5 | 2.5 | 1.6667 | 3 | 1.6667 | 3 | 3 | 1.5 | 6 | 2 | 4 | 5 | 1.5 | 4 | 2 | 5 | 2 | 2 | 2 | 1.3333 | 5 | 4 | 2 | 2 | 3 | 5 | 1 | 2 | 4 | 3 | 2.5 | 1.5 | 1.6667 | 3 | 2 | 1.5 | 1.3333 | 3 | 4 | 1.5 | 6 | 2 | 1.6667 | 3 | 1.6667 | 2
87 | 20.3333 | 11.3333 | 24.8333 | 38.3333 | 51.1667 | 64.8333 | 75.8333 | 86.5 | 95.5 | 104.8333 | 118.3333 | 128.3333 | 141.8333 | 156.3333 | 4 | 3 | 3 | 1.3333 | 5 | 4 | 1.5 | 3 | 4 | 3 | 1.5 | 5 | 1.3333 | 5 | 2.5 | 4 | 4 | 3 | 5 | 1.6667 | 1.5 | 2 | 5 | 2.5 | 6 | 1.6667 | 1.3333 | 1.6667 | 2 | 4 | 2 | 1 | 3 | 1 | 1.3333 | 4 | 4 | 3 | 1.5 | 5 | 2 | 2.5 | 1.5 | 4 | 2.5 | 3 | 5 | 3 | 2.5 | 6 | 4 | 2
88 | 14 | 10 | 18 | 33 | 41.3333 | 48.8333 | 58.5 | 73.3333 | 82.8333 | 90 | 100.8333 | 114.1667 | 125.6667 | 134.5 | 2 | 3 | 3 | 2 | 3 | 1 | 3 | 1 | 6 | 3 | 2 | 4 | 1 | 1.3333 | 3 | 3 | 1.5 | 3 | 2 | 1 | 1 | 6 | 1 | 1.6667 | 6 | 6 | 1.3333 | 1.5 | 4 | 2.5 | 1.6667 | 1.3333 | 1.5 | 1.6667 | 3 | 1 | 6 | 1.5 | 2 | 1.3333 | 3 | 5 | 4 | 1.3333 | 1 | 3 | 6 | 1.5 | 1.6667 | 1.6667 | 1.5 | 4
89 | 14.8333 | 11.3333 | 19.3333 | 24.6667 | 33.5 | 43.3333 | 55.5 | 68 | 76.1667 | 87.5 | 96.1667 | 106.3333 | 120.8333 | 131.3333 | 1.6667 | 1.6667 | 6 | 2 | 2 | 1.5 | 3 | 1.5 | 1.3333 | 1.6667 | 1.3333 | 1 | 2 | 1.3333 | 2.5 | 3 | 5 | 2.5 | 1 | 1.3333 | 2 | 1.6667 | 2.5 | 6 | 1.5 | 3 | 5 | 3 | 3 | 1.6667 | 1 | 2.5 | 1 | 4 | 1.3333 | 5 | 2 | 1.6667 | 2.5 | 2.5 | 1 | 1.6667 | 6 | 1.5 | 2 | 6 | 2.5 | 4 | 5 | 1.5 | 3 | 1
90 | 19.5 | 12.5 | 26.5 | 44 | 56 | 68 | 77 | 91 | 103.1667 | 111.3333 | 118.8333 | 131.1667 | 141.5 | 150.3333 | 3 | 2.5 | 1 | 6 | 6 | 1 | 5 | 2 | 2.5 | 6 | 6 | 3 | 1.5 | 4 | 2.5 | 4 | 1 | 1 | 5 | 5 | 1.5 | 1 | 4 | 2.5 | 6 | 3 | 3 | 2 | 3 | 5 | 1.6667 | 2.5 | 2 | 1.5 | 1.6667 | 3 | 2.5 | 3 | 1 | 1 | 2 | 1.3333 | 6 | 3 | 4 | 2 | 3 | 1.3333 | 1.5 | 4 | 1.3333 | 2
91 | 21.1667 | 12.1667 | 28.8333 | 44.8333 | 59.8333 | 66.3333 | 77.1667 | 93.1667 | 102.6667 | 116.1667 | 127.8333 | 139.3333 | 153.6667 | 162.6667 | 3 | 1.6667 | 1.5 | 6 | 3 | 6 | 1.6667 | 6 | 4 | 6 | 3 | 3 | 3 | 4 | 2 | 6 | 2 | 1 | 2.5 | 1 | 5 | 1.3333 | 2.5 | 2 | 6 | 5 | 3 | 2 | 1.6667 | 1.3333 | 4 | 2.5 | 4 | 1.5 | 5 | 3 | 5 | 3 | 2 | 1.6667 | 1.6667 | 1.3333 | 2.5 | 6 | 1.3333 | 5 | 3 | 5 | 2 | 1 | 5 | 1
92 | 9 | 6 | 14 | 22 | 29.1667 | 37.8333 | 45.1667 | 51.3333 | 61.5 | 77.5 | 85.6667 | 93.6667 | 107.1667 | 113 | 1 | 1.6667 | 1.3333 | 2 | 1.3333 | 1.6667 | 3 | 2 | 1.5 | 1.5 | 1 | 4 | 1.3333 | 1.6667 | 2.5 | 1.6667 | 2 | 1.6667 | 2 | 3 | 3 | 1.6667 | 1.3333 | 1.3333 | 1.5 | 1.6667 | 2 | 1 | 2.5 | 3 | 1.6667 | 3 | 5 | 4 | 2 | 5 | 3 | 1.6667 | 1.5 | 2 | 2 | 2 | 1.5 | 2.5 | 3 | 1.5 | 5 | 4 | 1 | 1.3333 | 1 | 2.5
93 | 21.6667 | 15 | 25.8333 | 38.8333 | 50.1667 | 61.5 | 68 | 75.8333 | 90.6667 | 97 | 107.3333 | 118 | 128.5 | 140 | 2 | 6 | 2 | 5 | 5 | 1.6667 | 1.6667 | 2.5 | 3 | 2 | 3 | 5 | 5 | 2.5 | 2.5 | 1.3333 | 6 | 2.5 | 1.3333 | 1.5 | 1.5 | 2 | 1.3333 | 1.6667 | 2 | 2.5 | 2 | 1.3333 | 1.3333 | 5 | 2.5 | 6 | 1.3333 | 2 | 1 | 2 | 2 | 2 | 5 | 1.3333 | 2 | 1.3333 | 6 | 1.3333 | 2.5 | 3 | 3 | 2 | 2 | 2 | 5 | 2.5
94 | 17 | 13 | 20.5 | 33.5 | 43.5 | 57.8333 | 70 | 82.3333 | 91.8333 | 103.8333 | 115.8333 | 132.3333 | 142 | 160 | 2 | 4 | 4 | 3 | 1.5 | 2.5 | 2 | 1.5 | 5 | 1.6667 | 1.3333 | 5 | 1 | 5 | 1 | 3 | 1.3333 | 2 | 5 | 6 | 6 | 1.6667 | 1.5 | 3 | 1.6667 | 1.6667 | 6 | 3 | 4 | 1 | 2 | 2.5 | 2 | 3 | 1 | 6 | 6 | 1.5 | 3 | 1.5 | 6 | 5 | 3 | 2.5 | 4 | 3 | 1 | 1.6667 | 4 | 6 | 5 | 3
95 | 10 | 6.3333 | 18 | 31 | 41 | 55.5 | 67.1667 | 79.1667 | 94.1667 | 106.1667 | 119.1667 | 128.6667 | 138.8333 | 151.3333 | 1.5 | 1.5 | 1.3333 | 2 | 1.6667 | 2 | 6 | 2 | 5 | 2 | 2 | 4 | 3 | 1.5 | 1.5 | 4 | 5 | 2.5 | 2 | 5 | 3 | 2 | 1.6667 | 5 | 3 | 2.5 | 2.5 | 4 | 6 | 1 | 5 | 3 | 2.5 | 4 | 1.5 | 4 | 5 | 5 | 1 | 2 | 2 | 2.5 | 2 | 3 | 3 | 3 | 2.5 | 1.6667 | 5 | 2.5 | 3 | 2
96 | 8.1667 | 4.6667 | 14.1667 | 28.1667 | 34.5 | 49 | 69 | 88 | 94.6667 | 108.6667 | 117.1667 | 126.6667 | 136.1667 | 143.6667 | 1 | 1.6667 | 1 | 1 | 1.5 | 2 | 2 | 4 | 2 | 6 | 3 | 3 | 1.5 | 1.5 | 1.6667 | 1.6667 | 2.5 | 6 | 2 | 4 | 6 | 2 | 6 | 6 | 6 | 6 | 3 | 4 | 2 | 1.5 | 1.6667 | 1.5 | 6 | 3 | 3 | 2 | 3 | 2.5 | 1.3333 | 1.6667 | 4 | 1 | 1.5 | 3 | 2 | 1.5 | 3 | 3 | 2 | 1.6667 | 1.3333 | 2.5
97 | 18.5 | 10.8333 | 25.8333 | 34.1667 | 43.1667 | 54.8333 | 66.5 | 75.5 | 89 | 99 | 111.3333 | 123.8333 | 131.1667 | 146.6667 | 2.5 | 2 | 5 | 1.3333 | 6 | 1.6667 | 1.3333 | 6 | 2 | 3 | 1.3333 | 2 | 1 | 1 | 4 | 3 | 2 | 2 | 1.6667 | 6 | 3 | 1.6667 | 2 | 5 | 2 | 1.6667 | 4 | 1.3333 | 4 | 4 | 3 | 2.5 | 2 | 3 | 3 | 2 | 1.6667 | 4 | 5 | 1.6667 | 1.5 | 2 | 6 | 3 | 1.6667 | 2 | 1.6667 | 2 | 6 | 3 | 5 | 1.5
98 | 13.3333 | 8.3333 | 21.3333 | 31.8333 | 39.5 | 46.3333 | 57.3333 | 67 | 74.5 | 87.6667 | 94.6667 | 105.8333 | 118.3333 | 126.3333 | 3 | 2 | 2 | 1.3333 | 2 | 3 | 2 | 6 | 3 | 2 | 2.5 | 3 | 1.6667 | 1.5 | 2.5 | 2 | 2 | 2 | 1.3333 | 1.5 | 2 | 3 | 2 | 4 | 4 | 1.5 | 1.6667 | 2.5 | 2 | 1 | 2 | 2.5 | 5 | 1.6667 | 5 | 1.5 | 1 | 1.5 | 1.5 | 3 | 2.5 | 3 | 4 | 1.6667 | 2 | 3 | 2.5 | 5 | 3 | 2 | 1.5 | 1.5
99 | 13.1667 | 10.5 | 22.1667 | 35.1667 | 51.1667 | 58.8333 | 68.3333 | 75.8333 | 83 | 94.6667 | 106.1667 | 115.6667 | 124.1667 | 135.5 | 2 | 4 | 2.5 | 2 | 1.3333 | 1.3333 | 4 | 5 | 3 | 6 | 3 | 1 | 5 | 3 | 2 | 6 | 2 | 3 | 1.3333 | 1.3333 | 1 | 2.5 | 2 | 4 | 1 | 2 | 2.5 | 2 | 1.6667 | 2 | 2 | 1.5 | 4 | 1.6667 | 2 | 4 | 4 | 1.5 | 3 | 3 | 2 | 2 | 3 | 2.5 | 2 | 2.5 | 1.5 | 2.5 | 2 | 6 | 1.3333 | 2
100 | 17.8333 | 12.5 | 21.8333 | 35.8333 | 46 | 58 | 68.5 | 81.1667 | 92.1667 | 100.6667 | 116.3333 | 123.6667 | 138.8333 | 151 | 4 | 3 | 3 | 2.5 | 1.3333 | 4 | 2 | 2 | 2 | 1 | 6 | 5 | 2 | 1.6667 | 2.5 | 4 | 1 | 5 | 3 | 3 | 2 | 4 | 2.5 | 2 | 6 | 3 | 1.6667 | 2 | 2.5 | 1.5 | 4 | 3 | 2 | 1.5 | 4 | 1 | 6 | 2 | 1.6667 | 6 | 3 | 1.3333 | 1.6667 | 1.3333 | 1.6667 | 6 | 5 | 2.5 | 5 | 1.6667 | 3 | 2.5
101 | 19 | 7 | 29 | 40 | 51.1667 | 61.8333 | 75.8333 | 86.8333 | 97.3333 | 109.8333 | 119.8333 | 139.8333 | 150.8333 | 163.3333 | 1 | 2 | 1.5 | 2.5 | 6 | 6 | 6 | 4 | 3 | 4 | 2 | 2 | 2.5 | 5 | 2 | 1.6667 | 4 | 3 | 2 | 1.6667 | 2 | 3 | 3 | 6 | 2 | 3 | 1 | 5 | 3 | 5 | 1 | 1.5 | 2 | 5 | 2.5 | 3 | 4 | 1.3333 | 1.6667 | 3 | 5 | 6 | 4 | 5 | 4 | 2 | 2 | 3 | 5 | 2 | 2.5 | 3
102 | 14.3333 | 7 | 18.8333 | 28.5 | 38.8333 | 47.8333 | 62.8333 | 76.8333 | 85 | 94.6667 | 101.6667 | 111.5 | 120 | 132 | 1.3333 | 1 | 1.6667 | 3 | 1.3333 | 6 | 2.5 | 2 | 4 | 1.6667 | 2 | 2 | 2 | 3 | 1.3333 | 4 | 2 | 3 | 1.5 | 2.5 | 3 | 5 | 6 | 1 | 4 | 3 | 4 | 3 | 1.5 | 3 | 1.6667 | 2 | 1 | 5 | 2 | 1.6667 | 2 | 1 | 1 | 3 | 3 | 1.3333 | 1.5 | 4 | 2 | 2.5 | 1 | 3 | 5 | 2 | 3 | 2
103 | 14.8333 | 10.8333 | 19.8333 | 27.3333 | 34.1667 | 42.6667 | 49.8333 | 61.3333 | 72.5 | 86.5 | 94.3333 | 103.6667 | 112.8333 | 120.8333 | 1.5 | 1.3333 | 5 | 3 | 1.5 | 2.5 | 3 | 2 | 1.3333 | 1.5 | 3 | 1.6667 | 1.3333 | 1.3333 | 2.5 | 1.6667 | 1.6667 | 3 | 1.3333 | 2.5 | 1.3333 | 1.6667 | 1.6667 | 2.5 | 2 | 1.5 | 3 | 5 | 2 | 1.6667 | 5 | 2.5 | 2 | 6 | 4 | 2 | 3 | 1.5 | 2 | 1.3333 | 1.3333 | 5 | 2 | 1 | 3 | 3 | 1.6667 | 1.5 | 1.6667 | 2 | 3 | 1.3333
104 | 21.6667 | 15.6667 | 28.6667 | 37.6667 | 43.1667 | 59.1667 | 65.6667 | 75.1667 | 87.1667 | 97.1667 | 106.3333 | 120.3333 | 129.5 | 136.8333 | 1.6667 | 5 | 6 | 3 | 5 | 1 | 6 | 1 | 2.5 | 2.5 | 1 | 3 | 1.5 | 1.3333 | 1.3333 | 1.3333 | 5 | 1 | 4 | 6 | 1 | 1.3333 | 2.5 | 1.6667 | 2.5 | 1.3333 | 4 | 1.6667 | 2.5 | 5 | 2 | 2.5 | 3 | 2 | 3 | 2 | 1.6667 | 1.5 | 4 | 2 | 1.5 | 5 | 1.5 | 6 | 1.5 | 1.6667 | 5 | 1 | 2 | 1.3333 | 2 | 2
105 | 14.6667 | 8.6667 | 19.1667 | 32.3333 | 41.3333 | 48 | 59 | 75 | 86.5 | 93.5 | 106.6667 | 118.6667 | 131.1667 | 145.1667 | 3 | 2 | 1.6667 | 2 | 2 | 4 | 2 | 2.5 | 4 | 2.5 | 5 | 1.6667 | 3 | 1.5 | 2.5 | 2 | 2 | 1.6667 | 2 | 1 | 2.5 | 5 | 2 | 1.5 | 6 | 3 | 2 | 5 | 2 | 3 | 5 | 1.5 | 1.3333 | 1.6667 | 3 | 1 | 6 | 4 | 1.6667 | 1.5 | 3 | 6 | 2 | 1 | 5 | 2.5 | 3 | 2 | 6 | 4 | 1 | 3
106 | 19.5 | 13 | 24 | 36.6667 | 46.6667 | 62.1667 | 71 | 82.5 | 95 | 112 | 120.3333 | 131.8333 | 143.5 | 153.5 | 3 | 2 | 3 | 5 | 4 | 2.5 | 3 | 1.5 | 1 | 4 | 1.6667 | 6 | 4 | 2 | 2 | 2 | 2.5 | 2 | 5 | 6 | 4 | 1.3333 | 1 | 2.5 | 1.5 | 6 | 1 | 3 | 4 | 1 | 2.5 | 5 | 5 | 5 | 1 | 6 | 4 | 1.5 | 1.3333 | 1.5 | 4 | 2.5 | 3 | 2 | 1.6667 | 3 | 3 | 4 | 1.5 | 1.5 | 4 | 3
107 | 13.8333 | 7.8333 | 20.3333 | 29 | 34.6667 | 48.1667 | 59.6667 | 75.1667 | 83.8333 | 92.1667 | 107.1667 | 116.1667 | 126.6667 | 139.1667 | 2 | 3 | 1.3333 | 1.5 | 3 | 3 | 4 | 2.5 | 1.6667 | 2 | 1 | 4 | 1.3333 | 1.6667 | 1.3333 | 1.3333 | 4 | 2.5 | 5 | 2 | 1 | 4 | 1.5 | 5 | 4 | 1.5 | 6 | 4 | 1.3333 | 4 | 2 | 1.3333 | 1.3333 | 1.6667 | 4 | 1.3333 | 3 | 3 | 4 | 5 | 3 | 4 | 1 | 1 | 2 | 5 | 1 | 2.5 | 6 | 1 | 3 | 2.5
108 | 15.3333 | 12 | 18.8333 | 30.5 | 37.5 | 45.8333 | 55.3333 | 63.8333 | 71.5 | 84 | 99 | 106.6667 | 120.6667 | 131.1667 | 2 | 3 | 3 | 4 | 1.3333 | 2 | 2.5 | 1 | 3 | 4 | 1.6667 | 3 | 1.6667 | 1.3333 | 2 | 2 | 1.3333 | 3 | 2 | 2 | 2.5 | 3 | 3 | 1 | 1.6667 | 1.3333 | 2.5 | 3 | 1.6667 | 3 | 1.6667 | 1.3333 | 1.5 | 2 | 3 | 6 | 3 | 4 | 3 | 5 | 3 | 1.3333 | 2 | 1.3333 | 2 | 5 | 3 | 4 | 1.3333 | 1.5 | 1.6667 | 6
109 | 14.1667 | 10.6667 | 22.1667 | 35.8333 | 52.3333 | 60.5 | 66.8333 | 73.8333 | 85.6667 | 96.1667 | 107.1667 | 120 | 133 | 140.8333 | 1.5 | 1.6667 | 6 | 1.5 | 1.5 | 2 | 4 | 4 | 1.6667 | 3 | 6 | 3 | 6 | 1.5 | 6 | 3 | 1.6667 | 3 | 2.5 | 1 | 1.3333 | 2.5 | 1 | 1.5 | 1.3333 | 1.6667 | 2 | 2 | 1.3333 | 2.5 | 2 | 6 | 4 | 1 | 2.5 | 3 | 1.5 | 2.5 | 4 | 3 | 1.3333 | 2.5 | 5 | 4 | 1 | 3 | 6 | 3 | 1.3333 | 1.5 | 2 | 3
110 | 17.1667 | 13 | 21.8333 | 32.5 | 39.1667 | 54.6667 | 63 | 78 | 90.6667 | 96.8333 | 111.3333 | 120.3333 | 131.1667 | 137.6667 | 2 | 2 | 3 | 6 | 1.6667 | 2.5 | 1.6667 | 3 | 2.5 | 1.6667 | 4 | 2.5 | 2 | 1.6667 | 1 | 2 | 3 | 4 | 6 | 2.5 | 1.3333 | 3 | 2 | 2 | 6 | 3 | 2 | 4 | 6 | 1.3333 | 1.3333 | 4 | 1.3333 | 1.5 | 1.3333 | 2 | 5 | 3 | 5 | 1.5 | 1.3333 | 1.6667 | 4 | 2 | 6 | 1.6667 | 1.6667 | 1.5 | 3 | 1 | 1 | 1.5
111 | 17.1667 | 14.5 | 24.8333 | 37.8333 | 46.8333 | 56.3333 | 71.3333 | 80.3333 | 87.3333 | 101.3333 | 117.3333 | 131.6667 | 141.3333 | 152.8333 | 3 | 3 | 6 | 2.5 | 1.6667 | 1 | 1.6667 | 6 | 3 | 5 | 2 | 3 | 1.5 | 2.5 | 1 | 4 | 2 | 3 | 2 | 2.5 | 4 | 3 | 5 | 3 | 2 | 1 | 5 | 1 | 1.3333 | 2.5 | 1.5 | 1.6667 | 5 | 3 | 3 | 3 | 6 | 3 | 6 | 1 | 2 | 1.3333 | 6 | 5 | 3 | 1.6667 | 3 | 2 | 1 | 2 | 6 | 2.5
112 | 11.1667 | 7.1667 | 17.1667 | 22.6667 | 33.1667 | 44.6667 | 59.6667 | 66.5 | 83.5 | 94.8333 | 109.6667 | 128.6667 | 142.6667 | 155.6667 | 2 | 2 | 1.6667 | 1.5 | 1 | 3 | 2 | 4 | 1.3333 | 1.6667 | 1 | 1.5 | 3 | 1.5 | 5 | 1 | 3 | 5 | 2 | 1.5 | 3 | 5 | 5 | 2 | 2 | 1.3333 | 2 | 1.5 | 2.5 | 2.5 | 6 | 6 | 4 | 4 | 2 | 1.3333 | 1.3333 | 5 | 6 | 2.5 | 6 | 5 | 6 | 2 | 2 | 6 | 1 | 5 | 2 | 2 | 6 | 3
113 | 14.6667 | 10.1667 | 22.6667 | 34.6667 | 47 | 59.5 | 71.6667 | 83.6667 | 93.5 | 106 | 115.8333 | 122.1667 | 129.1667 | 137.8333 | 1.5 | 2 | 1.6667 | 5 | 2 | 2.5 | 2 | 6 | 5 | 1.5 | 2.5 | 3 | 3 | 1.3333 | 4 | 4 | 5 | 3 | 2 | 2.5 | 5 | 1.6667 | 3 | 2.5 | 2.5 | 5 | 1.5 | 3 | 2 | 1.3333 | 1.5 | 5 | 6 | 1 | 2.5 | 3 | 3 | 1.3333 | 3 | 2.5 | 1.6667 | 1.6667 | 1.6667 | 1.3333 | 1 | 2 | 1.5 | 2.5 | 2.5 | 2 | 1.6667 | 2.5
114 | 21 | 10 | 27.5 | 35.1667 | 49 | 61.5 | 70.1667 | 77.6667 | 92.5 | 107 | 117.5 | 130.3333 | 144.5 | 156 | 4 | 3 | 1.3333 | 1.6667 | 5 | 6 | 5 | 1.5 | 3 | 1.6667 | 2 | 1 | 1.3333 | 1.5 | 6 | 5 | 3 | 2 | 1.5 | 6 | 3 | 3 | 1 | 1.6667 | 1.5 | 3 | 1.3333 | 1.6667 | 6 | 1.5 | 6 | 1.3333 | 5 | 5 | 1.5 | 3 | 2 | 2 | 2.5 | 4 | 4 | 1.3333 | 2.5 | 5 | 6 | 2.5 | 4 | 1.6667 | 2 | 1.5 | 3 | 5
115 | 14.3333 | 6.3333 | 20.3333 | 33.8333 | 45.3333 | 55.5 | 69.8333 | 76.5 | 90.3333 | 104.8333 | 116.8333 | 131.3333 | 146 | 152.6667 | 1.3333 | 1.5 | 2.5 | 1 | 6 | 2 | 4 | 2 | 2.5 | 5 | 2 | 4 | 6 | 1.5 | 1 | 3 | 1.5 | 1.3333 | 1.3333 | 6 | 4 | 3 | 6 | 1.3333 | 1 | 1.6667 | 1 | 3 | 1.5 | 5 | 1.3333 | 6 | 3 | 5 | 2.5 | 4 | 4 | 2 | 3 | 3 | 3 | 4 | 5 | 2.5 | 1.6667 | 6 | 2 | 5 | 1 | 2 | 1.6667 | 2
116 | 15 | 10 | 23 | 31.8333 | 40.8333 | 55.3333 | 63.8333 | 71.8333 | 81.8333 | 97.8333 | 111.3333 | 119.8333 | 133.3333 | 142 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | 2 | 3 | 2.5 | 1.3333 | 2 | 2.5 | 2 | 2 | 2.5 | 3 | 4 | 5 | 2.5 | 2 | 2 | 1.5 | 3 | 3 | 1.3333 | 1.6667 | 2 | 3 | 2.5 | 2.5 | 2 | 6 | 2 | 3 | 5 | 6 | 2 | 3 | 2.5 | 3 | 2 | 2.5 | 1 | 3 | 2.5 | 2 | 6 | 2 | 1.6667 | 2 | 3
117 | 23 | 20 | 27 | 43 | 57 | 67.5 | 77.5 | 92.1667 | 98.6667 | 108.6667 | 117.5 | 128.8333 | 138.6667 | 150.1667 | 6 | 6 | 6 | 2 | 2 | 1 | 1 | 3 | 5 | 3 | 6 | 2 | 3 | 6 | 3 | 2 | 2.5 | 4 | 2 | 2 | 1.5 | 4 | 1.5 | 3 | 6 | 5 | 2 | 1.6667 | 1 | 1.6667 | 2.5 | 1.3333 | 1.3333 | 1.6667 | 3 | 4 | 2.5 | 1.3333 | 2 | 3 | 1.3333 | 2 | 5 | 3 | 1.5 | 2 | 1.3333 | 5 | 5 | 2 | 2 | 2.5
118 | 19.3333 | 17 | 22.8333 | 38.3333 | 51.3333 | 60.8333 | 73.8333 | 84.1667 | 90.3333 | 102.3333 | 112.3333 | 123.3333 | 139.6667 | 151.5 | 5 | 3 | 6 | 3 | 1 | 1.3333 | 2.5 | 1 | 2.5 | 6 | 2 | 5 | 5 | 2.5 | 3 | 2.5 | 2.5 | 3 | 2.5 | 1.5 | 4 | 3 | 3 | 3 | 1 | 5 | 3 | 1.3333 | 1.6667 | 2 | 1 | 1.5 | 1 | 2 | 3 | 6 | 2 | 5 | 2 | 1 | 4 | 5 | 1 | 1 | 1.3333 | 3 | 6 | 6 | 5 | 4 | 1.5 | 1.3333
119 | 13.1667 | 7.1667 | 16.8333 | 30 | 38.6667 | 50.6667 | 60.8333 | 78.5 | 87.5 | 94.5 | 108.5 | 120.5 | 128.8333 | 142.1667 | 1.5 | 1.6667 | 2 | 2 | 5 | 1 | 2 | 1.6667 | 2.5 | 3 | 1.6667 | 6 | 1.5 | 1.6667 | 3 | 2.5 | 2 | 3 | 1 | 6 | 1.6667 | 3 | 1.5 | 4 | 1.6667 | 5 | 5 | 6 | 1.5 | 3 | 2.5 | 2 | 1.5 | 1.5 | 2.5 | 1.5 | 5 | 2 | 3 | 4 | 4 | 3 | 2.5 | 2.5 | 1.3333 | 2.5 | 1.5 | 3 | 6 | 1.3333 | 3 | 3
120 | 15.8333 | 8.3333 | 21.8333 | 33.3333 | 40.8333 | 50.1667 | 60 | 70 | 88 | 97.3333 | 106.3333 | 115.6667 | 124.1667 | 133.5 | 2 | 1.3333 | 3 | 2 | 6 | 1.5 | 2 | 4 | 4 | 3 | 2 | 2.5 | 1 | 1.5 | 2 | 3 | 1.3333 | 1.5 | 5 | 1.5 | 1.3333 | 1.5 | 4 | 3 | 3 | 3 | 2 | 2 | 6 | 5 | 5 | 2 | 1.3333 | 1 | 4 | 3 | 1 | 1 | 5 | 2 | 1.3333 | 4 | 2 | 2 | 2 | 1 | 3 | 2.5 | 5 | 1 | 2 | 1.3333
121 | 19.3333 | 12.3333 | 22.8333 | 38.8333 | 51.3333 | 61.5 | 72 | 79.3333 | 91.3333 | 102.1667 | 112.3333 | 124.3333 | 133.1667 | 145.1667 | 4 | 2 | 5 | 1.3333 | 4 | 3 | 1 | 2.5 | 6 | 4 | 4 | 2 | 2.5 | 6 | 2.5 | 1.5 | 2.5 | 2 | 4 | 1.6667 | 1.5 | 2 | 4 | 3 | 1.6667 | 1.3333 | 1.3333 | 3 | 5 | 1.6667 | 4 | 1.3333 | 1.6667 | 1.6667 | 6 | 1.5 | 1.6667 | 2 | 5 | 1.5 | 3 | 1 | 5 | 3 | 2.5 | 1.3333 | 2.5 | 2.5 | 6 | 2.5 | 2.5 | 1
122 | 20.5 | 15 | 28.1667 | 42.1667 | 53.5 | 66.5 | 84.5 | 94.3333 | 108.8333 | 119 | 129.1667 | 137.3333 | 149.3333 | 155.5 | 2 | 1 | 6 | 6 | 3 | 2.5 | 1.6667 | 6 | 4 | 4 | 1 | 5 | 4 | 1.6667 | 1.6667 | 4 | 2 | 3 | 6 | 2 | 6 | 2 | 5 | 5 | 2.5 | 3 | 3 | 1.3333 | 6 | 2 | 2.5 | 4 | 5 | 1 | 1.6667 | 2.5 | 3 | 1.5 | 4 | 1.6667 | 2 | 2.5 | 2 | 1.6667 | 2 | 4 | 3 | 3 | 1.6667 | 1.3333 | 1.5 | 1.6667
123 | 13.3333 | 10.6667 | 18 | 38 | 55 | 68.1667 | 77.6667 | 90 | 100.3333 | 107.6667 | 116 | 128.1667 | 147.1667 | 157.3333 | 3 | 4 | 2 | 1.6667 | 1.6667 | 1 | 1.6667 | 3 | 6 | 6 | 5 | 3 | 2 | 5 | 5 | 5 | 2.5 | 3 | 1.6667 | 6 | 2 | 2 | 4 | 1.5 | 2 | 1.3333 | 6 | 3 | 1.6667 | 5 | 1.6667 | 2 | 2 | 3 | 1 | 1.3333 | 1.3333 | 1 | 4 | 2 | 1.6667 | 6 | 3 | 1.5 | 2 | 6 | 6 | 5 | 2 | 4 | 1.6667 | 2.5
124 | 14.8333 | 9.3333 | 20.8333 | 32.8333 | 50.5 | 60 | 77 | 85.6667 | 105.3333 | 116.3333 | 128.6667 | 148.6667 | 162.8333 | 173.5 | 1.3333 | 1.3333 | 5 | 1.6667 | 4 | 1.5 | 3 | 3 | 2 | 1.5 | 6 | 2.5 | 1.6667 | 6 | 5 | 5 | 1 | 3 | 3 | 2.5 | 3 | 5 | 6 | 3 | 2 | 4 | 1.3333 | 1.3333 | 6 | 1.6667 | 6 | 6 | 2.5 | 3 | 2.5 | 3 | 3 | 1.3333 | 5 | 3 | 3 | 5 | 6 | 6 | 1.6667 | 5 | 5 | 2.5 | 3 | 3 | 3 | 1.6667
125 | 17.8333 | 9.3333 | 25.8333 | 42.3333 | 53.1667 | 64 | 78 | 91 | 101.1667 | 109 | 118 | 125 | 139 | 149 | 1 | 1.3333 | 4 | 3 | 2.5 | 6 | 2 | 6 | 2 | 2.5 | 6 | 6 | 1.6667 | 6 | 1.5 | 1.6667 | 1.3333 | 1.5 | 6 | 2 | 6 | 2 | 3 | 3 | 6 | 1 | 1 | 5 | 1.6667 | 2 | 4 | 2.5 | 2 | 3 | 1.5 | 1.3333 | 1.5 | 2 | 3 | 2.5 | 1.3333 | 3 | 1.3333 | 1.3333 | 2.5 | 3 | 2.5 | 6 | 6 | 1.6667 | 1.3333 | 1
126 | 13.6667 | 9.8333 | 22.6667 | 31.6667 | 41.8333 | 53.5 | 66 | 80.5 | 90.5 | 104.5 | 117.3333 | 127 | 139.3333 | 153.6667 | 1.3333 | 4 | 2 | 2.5 | 1.3333 | 2.5 | 5 | 4 | 1.6667 | 1.3333 | 3 | 3 | 1.6667 | 1.5 | 5 | 2 | 6 | 1 | 3 | 1.6667 | 3 | 4 | 3 | 2.5 | 3 | 6 | 3 | 2.5 | 2.5 | 1.5 | 3 | 3 | 4 | 3 | 3 | 4 | 2.5 | 6 | 1.3333 | 3 | 1.6667 | 1.6667 | 5 | 1.3333 | 1.6667 | 3 | 6 | 1.6667 | 5 | 1.3333 | 2 | 6
127 | 19.6667 | 14 | 23.1667 | 35.8333 | 45.8333 | 58.1667 | 66.5 | 81.1667 | 89.6667 | 97.1667 | 109.6667 | 120.8333 | 129.5 | 140 | 3 | 2 | 3 | 6 | 1.6667 | 4 | 2 | 1.5 | 2 | 5 | 4 | 1.6667 | 2.5 | 5 | 1.5 | 1 | 1.3333 | 6 | 2.5 | 2.5 | 3 | 2 | 1.6667 | 1.6667 | 6 | 5 | 1.6667 | 2 | 2.5 | 1 | 2 | 3 | 2 | 1 | 3 | 1.5 | 2 | 6 | 3 | 1.5 | 6 | 1.3333 | 1.3333 | 2.5 | 3 | 2.5 | 1.6667 | 1.5 | 1.5 | 2 | 4 | 3
128 | 15.3333 | 12 | 20.3333 | 30.3333 | 45 | 58 | 70.5 | 78.3333 | 90.8333 | 97.5 | 105.8333 | 115.3333 | 122.8333 | 136.8333 | 3 | 1 | 6 | 2 | 2 | 1.3333 | 3 | 2 | 2 | 3 | 3 | 2 | 1.6667 | 6 | 3 | 4 | 3 | 5 | 2 | 3 | 2 | 1.5 | 3 | 6 | 1.5 | 2 | 3 | 1.3333 | 6 | 2.5 | 1.5 | 2.5 | 2 | 1.3333 | 1.3333 | 2 | 1.3333 | 5 | 1 | 1 | 1.5 | 2 | 1 | 5 | 1 | 1 | 3 | 2.5 | 6 | 2 | 3 | 3
129 | 17.8333 | 8.8333 | 23.8333 | 38.5 | 45 | 53.5 | 64 | 75.3333 | 85.8333 | 94.6667 | 105.6667 | 120.6667 | 134.3333 | 145.1667 | 1.3333 | 3 | 2 | 2.5 | 6 | 3 | 5 | 1 | 6 | 1.6667 | 6 | 1 | 1.5 | 2 | 2 | 1 | 2.5 | 1.5 | 3 | 1.5 | 2 | 1.5 | 1 | 6 | 3 | 1.6667 | 5 | 1.6667 | 1.5 | 3 | 2 | 4 | 3 | 3 | 1.5 | 1.3333 | 3 | 2.5 | 3 | 2.5 | 5 | 2.5 | 6 | 1.5 | 6 | 3 | 3 | 1.6667 | 3 | 2.5 | 1.3333 | 4
130 | 12.3333 | 8.8333 | 18.6667 | 31 | 41.8333 | 48.6667 | 64 | 77.5 | 87.6667 | 98.6667 | 108.1667 | 119.8333 | 128.5 | 137.3333 | 1 | 1.3333 | 2.5 | 4 | 1.5 | 2 | 1.3333 | 5 | 4 | 3 | 1.3333 | 4 | 6 | 1.5 | 2 | 1.3333 | 1 | 3 | 1.3333 | 1.5 | 5 | 1.3333 | 6 | 3 | 6 | 3 | 2.5 | 2 | 1.5 | 6 | 1.3333 | 1.3333 | 5 | 2 | 3 | 1 | 3 | 1 | 1.5 | 4 | 5 | 1.6667 | 2 | 3 | 1.6667 | 2.5 | 2.5 | 2 | 1.5 | 5 | 1.3333 | 1
131 | 12.5 | 6.5 | 15.6667 | 25.6667 | 36.6667 | 44.1667 | 51.6667 | 58.1667 | 67.1667 | 82.6667 | 92 | 102 | 115.3333 | 128.3333 | 2.5 | 1 | 2 | 1 | 3 | 3 | 1.5 | 1.6667 | 2 | 2.5 | 3 | 2.5 | 2.5 | 2 | 1.5 | 5 | 2 | 3 | 1 | 1.5 | 3 | 1.6667 | 1.5 | 1.3333 | 2 | 1 | 1 | 2.5 | 1.5 | 1.5 | 5 | 1 | 5 | 6 | 3 | 1.5 | 1.3333 | 2 | 5 | 1 | 4 | 2 | 3 | 1 | 5 | 2 | 1.3333 | 5 | 2.5 | 2 | 6 | 2.5
132 | 13.5 | 9 | 19 | 30.6667 | 42.5 | 56.5 | 67.5 | 80.5 | 89 | 97 | 104.1667 | 112.1667 | 125.1667 | 136.6667 | 2.5 | 2.5 | 3 | 1 | 3 | 1.5 | 3 | 2.5 | 3 | 4 | 3 | 1.6667 | 5 | 2.5 | 1.3333 | 3 | 6 | 3 | 2 | 3 | 1 | 3 | 2 | 5 | 5 | 1.5 | 1.5 | 5 | 1.6667 | 1.3333 | 1.5 | 4 | 3 | 2.5 | 1.5 | 1 | 2 | 1 | 2.5 | 1.6667 | 4 | 1.3333 | 1.6667 | 1 | 3 | 2 | 2 | 6 | 3 | 2.5 | 4 | 2
133 | 21.1667 | 12.6667 | 26.1667 | 40.8333 | 48.6667 | 60.6667 | 70.6667 | 79.3333 | 93.3333 | 102.1667 | 113.8333 | 123.5 | 137.5 | 152.3333 | 6 | 2 | 1.6667 | 3 | 6 | 2.5 | 3 | 2 | 1.6667 | 5 | 3 | 5 | 1.5 | 3 | 1.3333 | 2 | 2 | 1 | 3 | 6 | 3 | 1 | 5 | 1 | 3 | 1.3333 | 1.3333 | 3 | 1.5 | 2.5 | 4 | 6 | 2 | 2.5 | 3 | 1.3333 | 3 | 1.6667 | 2 | 5 | 1.6667 | 3 | 1 | 4 | 4 | 2.5 | 1.5 | 6 | 1.5 | 1.3333 | 6 | 6
134 | 16.5 | 11.5 | 21.8333 | 30.8333 | 39.1667 | 52.1667 | 62 | 71.5 | 81.1667 | 94 | 107 | 116 | 126 | 140 | 4 | 2 | 1.5 | 4 | 2 | 3 | 4 | 1.3333 | 2 | 2 | 3 | 2 | 2 | 1.3333 | 1 | 4 | 3 | 5 | 4 | 1 | 2 | 5 | 1.3333 | 1.5 | 2 | 2.5 | 3 | 2 | 1.3333 | 1.3333 | 3 | 4 | 3 | 6 | 1.3333 | 2.5 | 2 | 2 | 6 | 3 | 1 | 2 | 2 | 4 | 2 | 3 | 3 | 2 | 2.5 | 4 | 5 | 2.5
135 | 10.5 | 7.1667 | 17 | 26 | 42 | 49 | 63.3333 | 72.1667 | 81.1667 | 90.1667 | 102.1667 | 109.6667 | 120 | 131 | 1.6667 | 1.5 | 1 | 3 | 1.6667 | 1.6667 | 1.5 | 5 | 1.3333 | 1.6667 | 3 | 3 | 3 | 5 | 3 | 5 | 1 | 3 | 2 | 1 | 6 | 1 | 1.3333 | 6 | 2.5 | 3 | 2 | 1.3333 | 4 | 1.5 | 2 | 1.5 | 1 | 1.5 | 2.5 | 4 | 5 | 1.3333 | 4 | 1.6667 | 2.5 | 1 | 2 | 2 | 3 | 4 | 1.3333 | 2 | 2 | 2.5 | 4 | 2.5
136 | 12.6667 | 9.6667 | 19.1667 | 27.5 | 36.5 | 44.1667 | 50.8333 | 62.3333 | 77.8333 | 88.8333 | 96.6667 | 103 | 114.5 | 129 | 2 | 1.6667 | 2 | 4 | 1.3333 | 1.6667 | 5 | 1.5 | 1.3333 | 3 | 2 | 2 | 1.6667 | 3 | 1.3333 | 3 | 1 | 4 | 1.3333 | 1.3333 | 2 | 1 | 2 | 1.6667 | 3 | 3 | 3 | 2.5 | 6 | 2 | 1.5 | 6 | 3 | 2 | 1 | 5 | 3 | 1.5 | 2 | 1.3333 | 1 | 3 | 1.3333 | 1 | 4 | 1.5 | 4 | 2 | 2.5 | 5 | 2 | 5
137 | 20.1667 | 15.5 | 24.6667 | 36.6667 | 52.3333 | 62.8333 | 72.1667 | 78.8333 | 90.3333 | 102.3333 | 111.3333 | 119.8333 | 130 | 144.5 | 4 | 5 | 4 | 2.5 | 3 | 1.6667 | 2 | 2.5 | 1 | 2 | 3 | 6 | 1.6667 | 2 | 6 | 6 | 2.5 | 5 | 1 | 2 | 3 | 2 | 3 | 1.3333 | 1.6667 | 1 | 1.5 | 2.5 | 3 | 2 | 5 | 1.5 | 3 | 2 | 1 | 6 | 1.5 | 2 | 4 | 1.5 | 2 | 2.5 | 1 | 3 | 2.5 | 1.6667 | 2 | 4 | 5 | 2 | 5 | 2.5
138 | 11.8333 | 7.8333 | 17.8333 | 31.5 | 45.5 | 55.5 | 63.8333 | 80.8333 | 93.8333 | 108.1667 | 123.1667 | 136.6667 | 145.1667 | 154 | 1.3333 | 2 | 1.5 | 3 | 1 | 3 | 3 | 3 | 3 | 3 | 1.6667 | 6 | 2.5 | 5 | 2.5 | 4 | 5 | 2 | 2 | 1 | 1.3333 | 4 | 2 | 1 | 4 | 2 | 6 | 5 | 3 | 3 | 6 | 1 | 1.3333 | 3 | 5 | 5 | 6 | 2 | 5 | 2 | 1 | 5 | 2.5 | 5 | 3 | 1.3333 | 2.5 | 1.6667 | 2 | 2.5 | 1.3333 | 3
139 | 13 | 6.5 | 19 | 30.5 | 42.3333 | 52.8333 | 60.1667 | 73.6667 | 80.6667 | 93.5 | 113.5 | 127 | 135.1667 | 146.6667 | 1 | 2 | 1.5 | 2 | 5 | 1.5 | 2 | 4 | 3 | 6 | 1 | 1.5 | 1.3333 | 3 | 6 | 1.5 | 5 | 1 | 1.5 | 3 | 1 | 2 | 3 | 1.3333 | 5 | 4 | 1.5 | 3 | 1 | 3 | 1.3333 | 1.6667 | 4 | 5 | 1.3333 | 2.5 | 5 | 5 | 6 | 4 | 4 | 6 | 2 | 1.5 | 1.6667 | 3 | 1 | 2.5 | 2.5 | 3 | 3 | 3
140 | 11.6667 | 7.3333 | 19.6667 | 31.6667 | 39.1667 | 46 | 62 | 73 | 79 | 89 | 94.6667 | 102.8333 | 112.5 | 124.5 | 1.5 | 1.3333 | 3 | 1.5 | 1.3333 | 3 | 2 | 6 | 1 | 3 | 2 | 6 | 1.3333 | 1.6667 | 1.5 | 3 | 1.6667 | 2 | 1.6667 | 1.5 | 1 | 5 | 4 | 6 | 2 | 4 | 3 | 2 | 2 | 1.3333 | 1.6667 | 1 | 3 | 1 | 5 | 1 | 1.5 | 1 | 1.5 | 1.6667 | 2 | 1.6667 | 2.5 | 2 | 5 | 1 | 1.6667 | 2 | 1 | 6 | 2.5 | 2.5
141 | 15.8333 | 12.3333 | 19.6667 | 29 | 39.6667 | 50 | 63 | 73 | 84 | 91.8333 | 103.1667 | 112.1667 | 124.1667 | 130.6667 | 2.5 | 6 | 2.5 | 1.3333 | 2 | 1.5 | 2.5 | 1.3333 | 1.3333 | 2.5 | 3 | 2.5 | 2 | 1.6667 | 3 | 4 | 3 | 3 | 3 | 1.3333 | 4 | 3 | 5 | 1 | 3 | 2 | 2 | 3 | 2 | 6 | 1 | 2 | 2 | 2.5 | 2 | 1.3333 | 4 | 1.6667 | 1.6667 | 4 | 3 | 3 | 2 | 1 | 3 | 1 | 5 | 3 | 2.5 | 1 | 1 | 2
142 | 14.6667 | 9.6667 | 18.1667 | 26.3333 | 34 | 47.6667 | 56.5 | 64 | 69.1667 | 84.1667 | 95.5 | 115.5 | 125.6667 | 137.1667 | 1.6667 | 3 | 3 | 2 | 4 | 1 | 1.5 | 2 | 2 | 2 | 2.5 | 1.6667 | 2 | 2 | 2 | 1.6667 | 6 | 2 | 4 | 1.6667 | 1.5 | 2 | 4 | 1.3333 | 2 | 2.5 | 1 | 2 | 1.5 | 1 | 1.6667 | 1 | 4 | 1 | 6 | 4 | 3 | 1.3333 | 6 | 1 | 6 | 4 | 4 | 6 | 1.6667 | 5 | 2 | 1.5 | 1 | 5 | 2.5 | 3
143 | 15.3333 | 9.3333 | 26.3333 | 36.1667 | 49.6667 | 58.3333 | 70.5 | 77.5 | 84.5 | 94.8333 | 101 | 109.3333 | 123.8333 | 133.5 | 1.3333 | 4 | 2 | 2 | 3 | 3 | 5 | 6 | 1.5 | 5 | 1.6667 | 1.6667 | 2.5 | 2 | 4 | 5 | 3 | 2.5 | 1.6667 | 1.5 | 2.5 | 2 | 6 | 1.6667 | 1.6667 | 2 | 1.3333 | 2 | 3 | 1 | 1.5 | 1.5 | 2 | 4 | 3 | 1.3333 | 1.6667 | 1.3333 | 1.5 | 1.6667 | 2 | 1.3333 | 3 | 2 | 3 | 6 | 4 | 1.5 | 1.6667 | 2 | 2 | 4
144 | 16.1667 | 8.1667 | 25.1667 | 33.6667 | 43.6667 | 53 | 62.5 | 78.8333 | 87.3333 | 97.5 | 110 | 115.6667 | 122.8333 | 134.5 | 1.6667 | 3 | 1 | 2.5 | 2 | 6 | 5 | 4 | 4 | 1.5 | 2 | 1 | 2 | 4 | 2 | 2 | 2 | 3 | 3 | 1.3333 | 1 | 3 | 2.5 | 3 | 1.3333 | 5 | 4 | 6 | 4 | 1.5 | 1 | 2 | 1.5 | 5 | 2 | 1.6667 | 1.5 | 5 | 4 | 2 | 1.6667 | 2 | 1 | 1 | 2 | 1.6667 | 1 | 2.5 | 2 | 5 | 3 | 1.6667
145 | 18.5 | 11.5 | 24.5 | 39.5 | 52.8333 | 59.1667 | 66.6667 | 79.1667 | 89.6667 | 102.1667 | 113.5 | 125.5 | 133.3333 | 141.8333 | 4 | 2.5 | 2 | 3 | 5 | 2 | 4 | 2 | 1.6667 | 1.3333 | 6 | 6 | 4 | 1.3333 | 5 | 3 | 1.5 | 1.6667 | 1.5 | 1.6667 | 3 | 2 | 1.5 | 1 | 6 | 3 | 2 | 1.5 | 6 | 1.6667 | 1.3333 | 1.5 | 1.5 | 6 | 4 | 1 | 1.3333 | 1 | 4 | 5 | 3 | 2 | 2 | 5 | 2.5 | 2 | 1.3333 | 2 | 1 | 3 | 2 | 2.5
146 | 21.6667 | 10.6667 | 25.5 | 31.3333 | 36.5 | 45.8333 | 56 | 63.5 | 76.3333 | 89.5 | 100.3333 | 113.6667 | 121.5 | 134.5 | 1.3333 | 2 | 1.3333 | 6 | 6 | 5 | 1.3333 | 2.5 | 1.6667 | 1.5 | 1.6667 | 1 | 1.3333 | 1 | 1.5 | 1.3333 | 3 | 1.3333 | 1 | 4 | 1.6667 | 2.5 | 3 | 3 | 2 | 2.5 | 1.6667 | 1.3333 | 2.5 | 5 | 1.3333 | 4 | 2.5 | 1.6667 | 3 | 6 | 2 | 2.5 | 5 | 1.3333 | 1 | 5 | 1.3333 | 6 | 2 | 1.5 | 3 | 1.3333 | 4 | 3 | 4 | 2
147 | 13 | 9 | 19 | 33 | 52 | 67.5 | 78.5 | 95.5 | 105 | 118.6667 | 131.1667 | 141.6667 | 154.6667 | 165.1667 | 2 | 3 | 1 | 3 | 3 | 1 | 5 | 1 | 6 | 4 | 2 | 2 | 5 | 6 | 3 | 5 | 2.5 | 4 | 3 | 6 | 6 | 1 | 1.5 | 2.5 | 5 | 5 | 2 | 5 | 2.5 | 1.5 | 2.5 | 3 | 1.3333 | 5 | 1.3333 | 6 | 6 | 2 | 3 | 1.5 | 1.5 | 2 | 6 | 1 | 1 | 5 | 3 | 4 | 3 | 1.5 | 5 | 1
148 | 12.3333 | 7.6667 | 15.6667 | 23 | 36.5 | 46.1667 | 55.1667 | 68.3333 | 78.3333 | 93.5 | 98.8333 | 111.1667 | 122.3333 | 132.3333 | 1.6667 | 2 | 1 | 3 | 1.6667 | 3 | 1.3333 | 2 | 1.5 | 2.5 | 1.3333 | 2 | 2 | 6 | 1.5 | 4 | 4 | 2 | 2 | 1.6667 | 3 | 2 | 3 | 1 | 4 | 1.5 | 1.6667 | 6 | 2 | 3 | 2.5 | 2.5 | 6 | 5 | 1.6667 | 2.5 | 1.6667 | 1 | 1.3333 | 1.3333 | 5 | 4 | 1.6667 | 1.6667 | 2.5 | 5 | 1.6667 | 2 | 3 | 1 | 4 | 2
149 | 18 | 9 | 21.5 | 30.5 | 44.1667 | 53.3333 | 64.3333 | 76.3333 | 87.6667 | 99.6667 | 107.1667 | 119.6667 | 132.1667 | 148.6667 | 3 | 3 | 1.5 | 1.5 | 6 | 3 | 2.5 | 1 | 1.3333 | 2 | 1.6667 | 4 | 6 | 3 | 1.6667 | 3 | 1.6667 | 1.5 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 5 | 2 | 2 | 2 | 5 | 3 | 1.3333 | 3 | 5 | 2 | 2 | 4 | 1.5 | 1 | 1 | 2.5 | 2 | 5 | 3 | 6 | 3 | 2 | 1.5 | 3 | 2.5 | 5 | 6
150 | 16.8333 | 11.1667 | 27.8333 | 45.3333 | 60.8333 | 74.3333 | 83.6667 | 93.6667 | 103.5 | 114.8333 | 121 | 132.5 | 142.5 | 154.5 | 3 | 1.5 | 1.6667 | 5 | 4 | 1.6667 | 6 | 5 | 6 | 2.5 | 4 | 5 | 6 | 3 | 2.5 | 4 | 1.5 | 3 | 5 | 4 | 4 | 1.6667 | 1.6667 | 2 | 4 | 3 | 1.6667 | 1.3333 | 1.3333 | 2 | 2.5 | 4 | 1.3333 | 6 | 1 | 3 | 1 | 2 | 1.6667 | 1.5 | 1 | 2.5 | 3 | 5 | 1 | 5 | 2 | 2 | 2 | 5 | 3 | 2
151 | 16.6667 | 10.6667 | 22 | 37 | 50.5 | 58.8333 | 71.3333 | 82 | 94.5 | 106.5 | 122.5 | 133.1667 | 143.3333 | 152.3333 | 1.6667 | 3 | 3 | 3 | 2 | 4 | 1.3333 | 4 | 1.6667 | 1.3333 | 6 | 6 | 5 | 1.5 | 4 | 3 | 1 | 1.3333 | 5 | 1 | 2 | 1.5 | 3 | 6 | 5 | 2 | 2 | 1.6667 | 4 | 2.5 | 2 | 4 | 5 | 2 | 2.5 | 2.5 | 2 | 6 | 5 | 3 | 3 | 3 | 3 | 1.6667 | 2.5 | 1.6667 | 3 | 3 | 1.6667 | 1.3333 | 3 | 3
152 | 17.8333 | 15 | 22.5 | 29 | 35 | 43.5 | 63.5 | 74.8333 | 84.3333 | 94.3333 | 100.6667 | 110.8333 | 123.1667 | 134.3333 | 1.5 | 6 | 1.5 | 6 | 1.5 | 1.3333 | 3 | 1.6667 | 1.5 | 2 | 1.5 | 1.5 | 2 | 1.3333 | 1 | 1.6667 | 3 | 1 | 1.5 | 3 | 5 | 6 | 3 | 6 | 1.3333 | 1 | 3 | 6 | 2 | 3 | 3 | 1.5 | 3 | 2 | 2 | 3 | 2 | 1 | 2 | 1.3333 | 2 | 1.6667 | 1.5 | 5 | 1.3333 | 3 | 2 | 6 | 2 | 1.6667 | 1.5 | 6
153 | 14.6667 | 11.6667 | 17.6667 | 25.8333 | 37.3333 | 49.3333 | 64 | 76.5 | 84 | 100.3333 | 112.3333 | 132.3333 | 149.3333 | 163.3333 | 6 | 1.6667 | 1 | 3 | 2 | 1 | 1 | 2 | 1.6667 | 2 | 1.5 | 3 | 2.5 | 2 | 3 | 4 | 2 | 2 | 5 | 3 | 1.6667 | 2 | 6 | 5 | 2.5 | 1.5 | 6 | 2.5 | 3 | 1.5 | 1.5 | 1.5 | 6 | 6 | 1.3333 | 3 | 6 | 1.5 | 2.5 | 2 | 6 | 5 | 4 | 5 | 6 | 6 | 3 | 2 | 5 | 3 | 4 | 2
154 | 22.3333 | 20 | 34.3333 | 41.3333 | 55.8333 | 64.8333 | 75.3333 | 88.3333 | 96 | 112 | 127.1667 | 138.1667 | 147.1667 | 158.5 | 6 | 6 | 5 | 3 | 1 | 1.3333 | 6 | 6 | 1.5 | 2.5 | 1 | 2 | 6 | 3 | 3 | 2.5 | 5 | 1.3333 | 1 | 1.6667 | 2 | 2 | 1.5 | 5 | 1 | 4 | 3 | 5 | 1.6667 | 2.5 | 2 | 1.5 | 5 | 4 | 2 | 5 | 6 | 1.6667 | 2.5 | 5 | 2.5 | 1.5 | 2 | 5 | 2 | 3 | 3 | 1 | 2 | 1.3333 | 2 | 6
155 | 16 | 12 | 26 | 35 | 42.3333 | 53.3333 | 60.3333 | 73 | 84.8333 | 93.3333 | 104 | 116 | 129 | 135.6667 | 5 | 1 | 3 | 3 | 2 | 2 | 6 | 4 | 1 | 1.3333 | 1.6667 | 5 | 3 | 1 | 2 | 1.3333 | 4 | 4 | 1 | 2 | 1.5 | 2.5 | 1.5 | 1.5 | 2 | 4 | 1.6667 | 5 | 1.6667 | 2.5 | 6 | 1.6667 | 1.5 | 3 | 2.5 | 1.5 | 4 | 3 | 1.6667 | 2 | 1 | 6 | 3 | 2 | 3 | 3 | 3 | 4 | 1.3333 | 1.3333 | 2 | 2
156 | 11.1667 | 6.1667 | 14.6667 | 29.6667 | 40.1667 | 51.1667 | 65.6667 | 73.6667 | 86.1667 | 99.1667 | 107.6667 | 118.1667 | 127.5 | 139.5 | 2 | 1.3333 | 1.5 | 1.3333 | 1 | 4 | 1.5 | 2 | 2 | 4 | 4 | 5 | 2.5 | 2.5 | 2.5 | 3 | 2 | 2.5 | 2.5 | 4 | 5 | 3 | 2.5 | 4 | 2.5 | 2.5 | 1.6667 | 1.3333 | 6 | 2 | 2.5 | 2 | 2 | 2 | 6 | 3 | 3 | 2 | 2 | 1.5 | 1.6667 | 1.3333 | 5 | 2.5 | 1 | 4 | 3 | 1.3333 | 2 | 2.5 | 5 | 2.5
157 | 20.5 | 14.5 | 25.5 | 36 | 43 | 50.8333 | 60.8333 | 69 | 80.5 | 89.1667 | 96 | 105.5 | 120.5 | 127.5 | 2.5 | 5 | 2 | 5 | 2 | 4 | 2 | 3 | 2.5 | 3 | 3 | 2 | 2 | 3 | 1 | 1 | 1.3333 | 4 | 1 | 1.5 | 3 | 2 | 2 | 3 | 1.6667 | 3 | 2 | 1.5 | 4 | 1.5 | 3 | 3 | 4 | 2 | 1 | 1.6667 | 1.6667 | 2 | 1.5 | 1.6667 | 2 | 2.5 | 3 | 2 | 5 | 5 | 2 | 3 | 2 | 1 | 2 | 2
158 | 18.5 | 14.5 | 24 | 37 | 47 | 63 | 69.8333 | 81.8333 | 94.1667 | 110.6667 | 122.3333 | 132.1667 | 146.8333 | 157.5 | 2.5 | 5 | 4 | 3 | 1 | 3 | 1.5 | 4 | 5 | 3 | 2 | 3 | 4 | 3 | 1.3333 | 1.6667 | 5 | 6 | 3 | 2 | 2 | 1.6667 | 1.5 | 1.6667 | 2.5 | 6 | 1.5 | 2 | 2 | 6 | 1.3333 | 3 | 5 | 5 | 5 | 1.5 | 2 | 1.6667 | 5 | 3 | 1.5 | 6 | 1 | 1.3333 | 2 | 6 | 5 | 1.6667 | 1 | 5 | 1.6667 | 3
159 | 10.6667 | 7.8333 | 15.3333 | 30.3333 | 45.3333 | 53.6667 | 64.8333 | 76.8333 | 89.1667 | 109.1667 | 120.5 | 130.6667 | 146.6667 | 159.1667 | 1.6667 | 1.5 | 3 | 1.6667 | 1.5 | 1.3333 | 3 | 1.6667 | 5 | 2.5 | 1.5 | 6 | 2 | 2 | 5 | 6 | 2.5 | 1.6667 | 2.5 | 1.6667 | 1 | 1.6667 | 2.5 | 6 | 2 | 2 | 3 | 5 | 2 | 6 | 3 | 1.3333 | 6 | 6 | 6 | 2 | 1.3333 | 3 | 3 | 4 | 1.6667 | 6 | 1 | 1.5 | 4 | 5 | 2 | 5 | 1 | 2.5 | 6 | 3
160 | 20.5 | 12.5 | 26.5 | 43.5 | 52 | 58 | 71 | 78.5 | 87 | 94 | 106 | 112.8333 | 124.8333 | 135.1667 | 2 | 1.5 | 6 | 3 | 2 | 6 | 3 | 3 | 5 | 4 | 5 | 3 | 1 | 3 | 3 | 1.5 | 1 | 1 | 2 | 2 | 2.5 | 4 | 2.5 | 4 | 3 | 1.5 | 2 | 1 | 1.6667 | 3 | 1.3333 | 2.5 | 2 | 2 | 1 | 2 | 2 | 3 | 3 | 4 | 1.3333 | 2.5 | 1.6667 | 1.3333 | 5 | 2 | 1 | 4 | 1.3333 | 1 | 5 | 3
161 | 16 | 10.6667 | 24 | 32.1667 | 37.5 | 45 | 52.1667 | 63.6667 | 79.1667 | 89 | 107.5 | 123.5 | 137.8333 | 152.1667 | 1.6667 | 4 | 3 | 2 | 4 | 1.3333 | 6 | 2 | 1 | 1.6667 | 2.5 | 3 | 1 | 1 | 1.3333 | 2 | 1.3333 | 1.6667 | 2.5 | 2 | 1.6667 | 2 | 2 | 1.5 | 1.5 | 1.5 | 2.5 | 6 | 2.5 | 6 | 6 | 1 | 1.3333 | 4 | 1.5 | 3 | 2.5 | 6 | 5 | 5 | 6 | 1.5 | 6 | 2.5 | 2 | 1.3333 | 6 | 5 | 5 | 5 | 3 | 1.3333
162 | 20.1667 | 12.1667 | 23.1667 | 37.8333 | 47.8333 | 60.8333 | 78.3333 | 87.1667 | 102.1667 | 115.1667 | 131.6667 | 139.5 | 150 | 160.8333 | 6 | 2.5 | 1.6667 | 2 | 5 | 3 | 1.5 | 1.5 | 5 | 5 | 1.6667 | 3 | 3 | 2 | 2 | 3 | 1.6667 | 4 | 6 | 1.3333 | 4 | 2.5 | 5 | 6 | 1.3333 | 2 | 4 | 1.5 | 6 | 3 | 3 | 3 | 4 | 3 | 4 | 2 | 5 | 6 | 1.5 | 4 | 1.5 | 2 | 3 | 1.3333 | 2 | 1.5 | 2 | 5 | 1.5 | 2 | 6 | 1.3333
163 | 12.6667 | 10 | 17.6667 | 24.3333 | 37.8333 | 47.8333 | 65.3333 | 80.8333 | 94.8333 | 101 | 109.8333 | 117.3333 | 130.8333 | 145.8333 | 6 | 1 | 1 | 2 | 1.3333 | 1.3333 | 3 | 2 | 1 | 1 | 1.6667 | 3 | 3 | 5 | 4 | 1.5 | 4 | 2.5 | 2 | 1.5 | 1.5 | 6 | 4 | 6 | 1.5 | 5 | 6 | 3 | 6 | 3 | 2 | 3 | 1.3333 | 1.6667 | 1.5 | 1.6667 | 4 | 1.5 | 1.3333 | 2 | 1.5 | 2 | 2 | 2 | 4 | 5 | 2 | 2.5 | 6 | 3 | 3 | 3
164 | 16.1667 | 12 | 20.1667 | 31.5 | 43 | 54 | 65.1667 | 77.8333 | 90.3333 | 103 | 115.5 | 127 | 137.3333 | 143 | 3 | 1 | 3 | 5 | 2.5 | 1.6667 | 2 | 2 | 2.5 | 2.5 | 1.3333 | 5 | 2 | 6 | 1.5 | 2 | 1 | 2 | 2 | 6 | 2.5 | 1.6667 | 6 | 1 | 2 | 5 | 4 | 1.6667 | 2 | 6 | 3 | 1.5 | 5 | 1.6667 | 3 | 3 | 4 | 3 | 1.5 | 4 | 1.5 | 6 | 1 | 3 | 3 | 1.6667 | 1.6667 | 4 | 1 | 1 | 1.6667 | 2
165 | 20 | 11.5 | 25 | 34.6667 | 50.6667 | 59.8333 | 72.8333 | 82.8333 | 94.5 | 107 | 116 | 126 | 142.5 | 156.5 | 3 | 4 | 3 | 1.5 | 2.5 | 6 | 3 | 2 | 1.6667 | 4 | 1 | 3 | 4 | 3 | 3 | 6 | 3 | 1.6667 | 2 | 2.5 | 2 | 6 | 1 | 4 | 1 | 1 | 3 | 5 | 2 | 5 | 1.6667 | 3 | 5 | 2 | 1.5 | 4 | 2 | 1.3333 | 1.6667 | 4 | 5 | 2.5 | 1.5 | 1 | 6 | 2 | 2.5 | 6 | 1.5 | 5 | 5 | 2.5
166 | 15.3333 | 9.3333 | 23.3333 | 32.6667 | 45.1667 | 51.5 | 60.8333 | 71 | 78 | 87.8333 | 95.3333 | 105.8333 | 115.5 | 123.6667 | 3 | 1.3333 | 2 | 3 | 3 | 3 | 4 | 4 | 2 | 2 | 1.3333 | 4 | 2 | 2 | 2.5 | 6 | 2 | 1.3333 | 1.6667 | 1.3333 | 5 | 1.3333 | 1 | 2 | 1.5 | 4 | 3 | 1.6667 | 1.3333 | 2.5 | 1.6667 | 1.5 | 5 | 1.5 | 1.3333 | 2 | 1.5 | 2 | 2 | 2 | 4 | 1.5 | 3 | 2 | 3 | 2 | 3 | 1.6667 | 1.5 | 2 | 3 | 1.6667
167 | 18.8333 | 13.8333 | 24.8333 | 37.3333 | 49 | 62 | 73.8333 | 87.5 | 95.3333 | 105.5 | 121 | 133 | 143 | 153.5 | 2.5 | 4 | 6 | 1.3333 | 4 | 1 | 3 | 3 | 2.5 | 3 | 6 | 1 | 3 | 2 | 5 | 1.6667 | 2 | 3 | 2 | 6 | 3 | 1.5 | 1.3333 | 6 | 3 | 1.6667 | 3 | 6 | 1.5 | 2.5 | 2.5 | 1.3333 | 1.6667 | 3 | 3 | 2.5 | 5 | 6 | 2.5 | 2 | 1 | 6 | 3 | 2 | 1.6667 | 4 | 1.3333 | 3 | 5 | 1.3333 | 2.5 | 1.6667
168 | 19.6667 | 12 | 23.6667 | 36.6667 | 54.3333 | 60.1667 | 66.1667 | 77.1667 | 85.3333 | 94.1667 | 101.6667 | 112.1667 | 121.5 | 134.6667 | 6 | 1.5 | 3 | 1.5 | 6 | 1.6667 | 2.5 | 1.5 | 5 | 3 | 2 | 3 | 6 | 1.6667 | 6 | 4 | 1.6667 | 1.3333 | 1.5 | 1.3333 | 1 | 2 | 1.3333 | 1.6667 | 3 | 1.5 | 2.5 | 4 | 1.6667 | 1.5 | 2.5 | 2.5 | 1.6667 | 4 | 1.6667 | 1.5 | 2 | 1.5 | 3 | 1 | 2 | 1.5 | 4 | 3 | 3 | 2.5 | 2.5 | 1.3333 | 3 | 2.5 | 6 | 1.6667
169 | 15.1667 | 11 | 20.1667 | 35.1667 | 44.3333 | 52.3333 | 65.3333 | 73.3333 | 86.3333 | 99.8333 | 109.3333 | 116.6667 | 128.3333 | 140.3333 | 3 | 3 | 2 | 3 | 1.6667 | 2.5 | 1 | 4 | 3 | 1 | 6 | 5 | 1.3333 | 4 | 2.5 | 1.3333 | 1.5 | 3 | 2 | 1.5 | 2 | 6 | 1 | 4 | 2 | 3 | 1 | 2 | 2 | 4 | 3 | 4 | 3 | 2.5 | 2 | 6 | 1.5 | 2 | 4 | 2 | 2.5 | 1.5 | 1.6667 | 1.6667 | 3 | 3 | 1.6667 | 4 | 2.5 | 2.5 | 2 | 5
170 | 11.5 | 9 | 20 | 32.3333 | 39.3333 | 55.6667 | 62.8333 | 73.5 | 84.8333 | 98 | 111.3333 | 119.6667 | 129.6667 | 139.6667 | 2 | 4 | 1 | 2 | 1.5 | 1 | 6 | 2.5 | 2 | 5 | 4 | 1.3333 | 2 | 1.5 | 1.5 | 2 | 1.3333 | 4 | 5 | 6 | 2.5 | 2 | 1 | 1.6667 | 2 | 1.6667 | 6 | 1 | 1.3333 | 4 | 2 | 4 | 1.6667 | 3 | 2.5 | 6 | 4 | 6 | 2 | 1.3333 | 1.3333 | 2 | 2 | 3 | 3 | 4 | 1.3333 | 1.6667 | 2 | 4 | 3 | 1
171 | 20.3333 | 12.3333 | 24.5 | 37.1667 | 45.5 | 54.6667 | 60.3333 | 70.8333 | 85.3333 | 95 | 102 | 111.8333 | 121.5 | 131.8333 | 1.6667 | 3 | 1.6667 | 6 | 6 | 2 | 1.6667 | 2.5 | 1.6667 | 3 | 2 | 6 | 3 | 3 | 1 | 1.3333 | 3 | 1.6667 | 2.5 | 2 | 2 | 1.6667 | 1 | 1 | 2 | 2.5 | 1 | 5 | 1 | 5 | 2.5 | 6 | 1 | 2 | 5 | 1.6667 | 1 | 2 | 2.5 | 1.5 | 1.5 | 5 | 1.6667 | 1.6667 | 1 | 2 | 5 | 1.6667 | 4 | 2 | 1.3333 | 3
172 | 14.6667 | 10 | 21 | 31.8333 | 43.8333 | 54.1667 | 67.6667 | 80.3333 | 88.3333 | 98.8333 | 110.3333 | 118.3333 | 125.6667 | 135.6667 | 3 | 2 | 1 | 4 | 3 | 1.6667 | 1.3333 | 5 | 6 | 1.3333 | 2.5 | 1 | 1.5 | 1.5 | 4 | 5 | 4 | 1.3333 | 2 | 3 | 6 | 1.5 | 3 | 3 | 2 | 5 | 4 | 1.6667 | 2 | 1.5 | 1.5 | 3 | 2 | 4 | 2 | 2.5 | 4 | 2 | 4 | 1.5 | 2 | 1.3333 | 1.6667 | 3 | 3 | 1.5 | 1.3333 | 1.5 | 2 | 3 | 2 | 3
173 | 17.5 | 14.5 | 21.5 | 38.1667 | 46.1667 | 63.1667 | 76.1667 | 81.6667 | 93 | 107.5 | 115 | 121.6667 | 140.1667 | 150.8333 | 1.5 | 6 | 1 | 6 | 1.6667 | 1.3333 | 2 | 2 | 5 | 5 | 5 | 1.6667 | 1.3333 | 4 | 1.3333 | 1.3333 | 3 | 5 | 5 | 4 | 3 | 4 | 3 | 3 | 1 | 1.5 | 2 | 1 | 2 | 6 | 1.6667 | 1.6667 | 2 | 6 | 4 | 2.5 | 2.5 | 1.6667 | 1.3333 | 2 | 2 | 1.6667 | 1 | 2 | 1.5 | 5 | 6 | 6 | 1.3333 | 4 | 1.3333 | 4
174 | 16.1667 | 8.1667 | 20.1667 | 28.6667 | 36.5 | 47.6667 | 59.8333 | 73.1667 | 82.8333 | 93.3333 | 105 | 121.6667 | 131 | 145.3333 | 1.6667 | 3 | 1.5 | 2 | 5 | 3 | 2 | 2 | 3 | 1 | 3 | 1.5 | 3 | 1.3333 | 1 | 2.5 | 6 | 1.6667 | 1.5 | 2 | 6 | 3 | 1.6667 | 1.5 | 5 | 2 | 5 | 1.3333 | 5 | 1.6667 | 1.6667 | 1.3333 | 2 | 2 | 1.5 | 5 | 2 | 3 | 1.6667 | 5 | 1.6667 | 6 | 6 | 3 | 2 | 5 | 1 | 1.3333 | 4 | 5 | 1.3333 | 4
175 | 9.1667 | 5.6667 | 12.6667 | 19.8333 | 29.8333 | 40.3333 | 48.3333 | 56.6667 | 70.1667 | 84.1667 | 100.6667 | 110.1667 | 125.6667 | 140.3333 | 1.5 | 1.5 | 1.6667 | 1 | 2 | 1.5 | 1.5 | 2 | 1.6667 | 1.5 | 3 | 1 | 3 | 3 | 2 | 2 | 3 | 2 | 2.5 | 3 | 2.5 | 3 | 1.5 | 1 | 1.5 | 1.3333 | 2.5 | 3 | 5 | 1.5 | 4 | 3 | 2.5 | 6 | 2.5 | 3 | 5 | 5 | 5 | 1.5 | 2 | 1.5 | 4 | 2 | 5 | 1.5 | 3 | 6 | 4 | 6 | 1.6667 | 3
176 | 16 | 11.5 | 19.5 | 31.8333 | 45.1667 | 61.1667 | 70 | 82.1667 | 88.3333 | 95.8333 | 104.1667 | 117.1667 | 132.8333 | 148 | 2 | 4 | 2.5 | 3 | 3 | 1.5 | 1 | 2.5 | 1 | 6 | 1.3333 | 4 | 1.3333 | 3 | 6 | 3 | 3 | 2 | 6 | 5 | 1.3333 | 2.5 | 3 | 2 | 2.5 | 2 | 6 | 1.6667 | 1.6667 | 1.5 | 1 | 2 | 1 | 2.5 | 2 | 2 | 1.3333 | 3 | 2 | 2 | 5 | 1.6667 | 1.3333 | 5 | 3 | 6 | 5 | 1.6667 | 1.6667 | 6 | 1.5 | 6
177 | 18 | 12 | 22.6667 | 32.1667 | 39 | 51.5 | 66.5 | 83 | 92 | 106 | 113 | 119.3333 | 130 | 140.5 | 2 | 2 | 4 | 4 | 3 | 3 | 1.6667 | 3 | 1.5 | 2 | 4 | 2 | 1 | 2 | 1.3333 | 2.5 | 4 | 2 | 1.5 | 5 | 2.5 | 6 | 1.5 | 5 | 6 | 2.5 | 2 | 6 | 1.6667 | 3 | 3 | 1.3333 | 4 | 4 | 4 | 2 | 2.5 | 1.5 | 1.3333 | 1.6667 | 1.6667 | 1.6667 | 1 | 2 | 1.3333 | 4 | 4 | 1.3333 | 2 | 2 | 5 | 1.5
178 | 12.8333 | 10.1667 | 17.1667 | 26.1667 | 35.1667 | 44.3333 | 52 | 62.5 | 72.5 | 80.5 | 89.1667 | 96.8333 | 108.8333 | 123.5 | 2 | 1.6667 | 2.5 | 4 | 1.6667 | 1 | 3 | 1.3333 | 1.5 | 2.5 | 2 | 3 | 2 | 2 | 3 | 2 | 3 | 1.6667 | 2.5 | 2 | 1.6667 | 1.3333 | 3 | 1.6667 | 3 | 2 | 1.5 | 4 | 5 | 1.5 | 2 | 1.5 | 2 | 2 | 2 | 2 | 1.6667 | 2.5 | 3 | 1.5 | 1.3333 | 1.3333 | 2 | 3 | 3 | 5 | 1 | 3 | 6 | 3 | 4 | 1.6667
179 | 17.5 | 14 | 24.5 | 33.5 | 42 | 50.8333 | 61.3333 | 68.6667 | 74.8333 | 85.3333 | 96.1667 | 108.5 | 120 | 131 | 6 | 2.5 | 2.5 | 3 | 1.5 | 2 | 2 | 5 | 2 | 1 | 3 | 3 | 2.5 | 2 | 1 | 3 | 3 | 2.5 | 2 | 1.3333 | 2 | 4 | 3 | 1.5 | 1.6667 | 1 | 3 | 1.6667 | 2 | 1.5 | 1 | 1.6667 | 3 | 1 | 4 | 2.5 | 1 | 2.5 | 1.3333 | 6 | 1 | 1.3333 | 5 | 5 | 2 | 1.5 | 4 | 4 | 2 | 4 | 1 | 4
180 | 23.5 | 17 | 26 | 37.5 | 45.6667 | 59.1667 | 76.6667 | 87 | 93.3333 | 102 | 112.1667 | 122.6667 | 133.6667 | 145.1667 | 6 | 3 | 2 | 6 | 1.5 | 5 | 1.5 | 1 | 5 | 1.5 | 2 | 3 | 1.6667 | 1.5 | 3 | 2 | 5 | 1.5 | 5 | 2 | 5 | 5 | 1.5 | 6 | 4 | 1.3333 | 1 | 4 | 1.3333 | 2 | 2 | 1 | 3 | 1.3333 | 3 | 1.3333 | 2.5 | 2 | 1.6667 | 4 | 1 | 4 | 3 | 2.5 | 2 | 3 | 4 | 2 | 3 | 2.5 | 2 | 4
181 | 16.8333 | 11.8333 | 20.5 | 34.1667 | 42.3333 | 52.6667 | 59 | 71.5 | 82.6667 | 93.6667 | 104.5 | 110.5 | 120.5 | 129.5 | 2.5 | 3 | 5 | 1.3333 | 2 | 3 | 1.6667 | 2 | 1.6667 | 4 | 2 | 6 | 1.5 | 1.3333 | 1.3333 | 4 | 2 | 1.3333 | 6 | 1 | 1.3333 | 2 | 1 | 2 | 6 | 3 | 2 | 1.5 | 1.3333 | 6 | 1.3333 | 2.5 | 2 | 5 | 2 | 2 | 1.5 | 3 | 5 | 1.3333 | 1 | 2 | 1.5 | 1.5 | 3 | 3 | 1 | 3 | 2.5 | 3 | 1.5 | 2
182 | 17 | 13 | 20.3333 | 28.3333 | 35.5 | 46 | 62 | 76.1667 | 93.1667 | 101.8333 | 109.5 | 119.1667 | 132.1667 | 142.1667 | 4 | 2 | 2 | 5 | 3 | 1 | 2 | 1.3333 | 1 | 3 | 3 | 1 | 1.6667 | 1.6667 | 2.5 | 1.3333 | 1 | 2.5 | 5 | 2 | 6 | 3 | 5 | 2 | 6 | 1.6667 | 5 | 1.5 | 6 | 2.5 | 6 | 2.5 | 3 | 3 | 1.6667 | 1 | 1 | 2 | 1.6667 | 3 | 4 | 2 | 2 | 1.6667 | 1 | 6 | 4 | 2 | 2.5 | 2.5 | 1 | 4
183 | 17.5 | 10.5 | 21.8333 | 31.8333 | 46.3333 | 59.8333 | 68.5 | 78 | 84.6667 | 94.3333 | 103.5 | 120.8333 | 130.8333 | 139.5 | 1.5 | 4 | 3 | 2 | 3 | 4 | 3 | 1.3333 | 2.5 | 1 | 5 | 1.5 | 6 | 2 | 2.5 | 4 | 2.5 | 2 | 3 | 6 | 2.5 | 2 | 2.5 | 1.6667 | 4 | 2.5 | 2 | 1 | 1 | 3 | 1.3333 | 1.3333 | 1.6667 | 3 | 4 | 1 | 1.5 | 1.6667 | 3 | 3 | 1.3333 | 6 | 5 | 5 | 2 | 1 | 3 | 4 | 3 | 1 | 3 | 1.6667
184 | 20 | 13 | 23.3333 | 37 | 45.3333 | 59.8333 | 67.3333 | 78.6667 | 93.3333 | 106 | 117 | 130 | 141.3333 | 150.6667 | 1 | 4 | 3 | 5 | 4 | 3 | 1.3333 | 2 | 2 | 1.6667 | 5 | 5 | 1.6667 | 3 | 2 | 1.6667 | 3 | 2.5 | 6 | 3 | 1 | 1.5 | 3 | 2 | 1.3333 | 5 | 3 | 2 | 2 | 5 | 1.6667 | 6 | 1.6667 | 3 | 6 | 2 | 1 | 1 | 4 | 5 | 5 | 2.5 | 2.5 | 3 | 5 | 2 | 3 | 1.3333 | 5 | 2 | 1.3333 | 1
185 | 16.3333 | 10.6667 | 24.3333 | 37.3333 | 44.3333 | 54.3333 | 68 | 75.6667 | 86.1667 | 102.1667 | 110.1667 | 123.6667 | 135 | 145 | 3 | 1.6667 | 2 | 4 | 4 | 1.6667 | 4 | 4 | 1 | 5 | 1 | 6 | 2 | 1 | 2 | 2 | 5 | 1.6667 | 2 | 1.3333 | 5 | 1.6667 | 5 | 2 | 1.3333 | 1.3333 | 2 | 3 | 5 | 1.3333 | 2.5 | 1.6667 | 5 | 3 | 3 | 5 | 1 | 2 | 4 | 1 | 4 | 3 | 2.5 | 4 | 2 | 1.6667 | 6 | 1.6667 | 2 | 5 | 1 | 2
186 | 14.5 | 9.5 | 24.5 | 33.6667 | 40.6667 | 53.6667 | 65.1667 | 78 | 92.3333 | 103.8333 | 113.1667 | 121.3333 | 132.6667 | 140.6667 | 2.5 | 1 | 2 | 4 | 2.5 | 2.5 | 5 | 5 | 2.5 | 1.3333 | 4 | 1.3333 | 1.5 | 2 | 2.5 | 1 | 2.5 | 5 | 2.5 | 3 | 2.5 | 6 | 1 | 2 | 1.5 | 1.3333 | 5 | 5 | 1.3333 | 5 | 6 | 2 | 1 | 3 | 6 | 1.5 | 1 | 2 | 1.3333 | 5 | 1.3333 | 1.3333 | 2.5 | 3 | 1.3333 | 4 | 5 | 1 | 1 | 1.5 | 2.5 | 3
187 | 16.1667 | 12.6667 | 23.1667 | 33.1667 | 40.1667 | 50.1667 | 64.6667 | 80.6667 | 94 | 105 | 115.6667 | 126.3333 | 135.6667 | 146.3333 | 1.6667 | 6 | 2 | 3 | 1.5 | 2 | 3 | 4 | 4 | 2.5 | 2.5 | 1 | 1.3333 | 2 | 2 | 1.6667 | 1.6667 | 1.3333 | 5 | 2 | 5 | 2 | 6 | 1.5 | 5 | 4 | 1 | 6 | 5 | 5 | 1.6667 | 1.6667 | 2.5 | 3 | 3 | 2.5 | 2 | 5 | 2 | 1.6667 | 1.6667 | 3 | 2 | 4 | 2 | 2 | 1.3333 | 4 | 1 | 3 | 5 | 1.6667
188 | 10.3333 | 7 | 12.8333 | 24.8333 | 40.8333 | 48.6667 | 55.6667 | 64.5 | 74 | 85.6667 | 91.5 | 105.6667 | 118.3333 | 131.3333 | 1.6667 | 2 | 2 | 1.3333 | 2 | 1.3333 | 1.5 | 1 | 2.5 | 6 | 1 | 2.5 | 6 | 2 | 6 | 2 | 1.3333 | 1.5 | 2 | 3 | 1.5 | 1.5 | 2 | 2 | 2.5 | 3 | 1.3333 | 2 | 2.5 | 2 | 3 | 2 | 1.6667 | 6 | 1 | 3 | 1.5 | 1.5 | 1.3333 | 1.5 | 1.5 | 6 | 1.6667 | 5 | 2 | 6 | 3 | 1.6667 | 3 | 2 | 4 | 4
189 | 18.3333 | 12.3333 | 20.6667 | 33.8333 | 43.5 | 58 | 67.5 | 79.5 | 88 | 98 | 114 | 130 | 141.3333 | 152 | 3 | 1.3333 | 5 | 3 | 4 | 2 | 1.3333 | 1 | 4 | 6 | 1.6667 | 1.5 | 4 | 1 | 3 | 1.6667 | 6 | 2.5 | 3 | 3 | 2 | 2.5 | 2 | 3 | 6 | 2.5 | 2.5 | 1 | 2 | 2 | 2.5 | 2 | 1 | 1 | 5 | 3 | 5 | 3 | 3 | 5 | 1 | 6 | 6 | 3 | 3 | 1.6667 | 1.6667 | 5 | 1.5 | 1.6667 | 2.5 | 5
190 | 19 | 12.5 | 25 | 36 | 49 | 57 | 64 | 74.8333 | 88.8333 | 102.1667 | 111.6667 | 123 | 132.3333 | 141.8333 | 1 | 1.5 | 4 | 6 | 2.5 | 4 | 2 | 4 | 5 | 1.3333 | 3 | 1.6667 | 1 | 6 | 5 | 1 | 2 | 2.5 | 1.5 | 2 | 1 | 1.6667 | 3 | 1.3333 | 1.3333 | 5 | 2.5 | 2 | 5 | 5 | 2 | 2 | 3 | 3 | 6 | 1.3333 | 3 | 2 | 3 | 1.5 | 1 | 6 | 3 | 1.3333 | 1.3333 | 2.5 | 1.5 | 4 | 2 | 3 | 1.5 | 3
191 | 19.5 | 13 | 25 | 32.3333 | 45.3333 | 57 | 65 | 78.5 | 90.5 | 104 | 114.8333 | 124.8333 | 137.1667 | 151.6667 | 3 | 3 | 4 | 3 | 1.5 | 5 | 4 | 1.5 | 1.3333 | 1 | 2 | 3 | 2 | 2 | 5 | 4 | 6 | 2 | 2 | 1.6667 | 2 | 1.3333 | 1.6667 | 3 | 4 | 1 | 6 | 2.5 | 1.5 | 2.5 | 5 | 3 | 3 | 6 | 1.5 | 3 | 2 | 6 | 1.5 | 1.3333 | 2 | 2 | 3 | 3 | 5 | 1.6667 | 4 | 1.6667 | 5 | 6 | 2 | 1.5
192 | 21 | 15.3333 | 29 | 41 | 48.3333 | 56.3333 | 71.8333 | 77.6667 | 88.6667 | 94.3333 | 111.3333 | 121.8333 | 136.6667 | 146.6667 | 1.6667 | 6 | 1.6667 | 6 | 4 | 1.6667 | 2 | 6 | 5 | 4 | 2 | 1 | 3 | 1.3333 | 2 | 1 | 3 | 2 | 1 | 2 | 4 | 4 | 6 | 1.5 | 1.6667 | 1.6667 | 1 | 1.5 | 1 | 2 | 6 | 2 | 1.6667 | 1.6667 | 1.3333 | 1 | 6 | 4 | 3 | 4 | 4 | 2 | 2 | 2.5 | 6 | 6 | 1.5 | 1.3333 | 1 | 1 | 6 | 2
193 | 22.6667 | 14.6667 | 28.1667 | 37.1667 | 52.1667 | 60.1667 | 72.1667 | 79.3333 | 93.3333 | 103.6667 | 117.1667 | 130.5 | 140.5 | 151 | 5 | 6 | 2 | 1.6667 | 2 | 6 | 1.5 | 4 | 2.5 | 1.5 | 2.5 | 2.5 | 3 | 5 | 5 | 2 | 3 | 1 | 2 | 2 | 2 | 1 | 5 | 4 | 1 | 1.6667 | 2 | 2.5 | 2 | 2 | 4 | 6 | 1.3333 | 5 | 1 | 3 | 2 | 3 | 2.5 | 6 | 6 | 1.3333 | 4 | 2 | 1.3333 | 3 | 1.6667 | 4 | 2.5 | 2 | 2 | 4
194 | 12.6667 | 9.6667 | 20.6667 | 34.1667 | 42 | 55 | 60.6667 | 67.5 | 79.6667 | 97.6667 | 114.6667 | 120.5 | 132 | 144.6667 | 5 | 2 | 1.3333 | 1.3333 | 1.6667 | 1.3333 | 5 | 3 | 6 | 1.5 | 4 | 2 | 1 | 3 | 1.3333 | 2.5 | 6 | 3 | 2 | 2 | 1 | 1 | 1.6667 | 2 | 3 | 1.5 | 1 | 1.3333 | 1.6667 | 3 | 5 | 2.5 | 3 | 6 | 6 | 3 | 4 | 4 | 6 | 3 | 1.3333 | 1 | 1.5 | 2 | 4 | 3 | 3 | 1.5 | 6 | 4 | 1 | 1.6667
195 | 17 | 15 | 26 | 40.6667 | 54.6667 | 64.6667 | 78 | 88.3333 | 98.8333 | 113.3333 | 124.8333 | 134.5 | 146.3333 | 160.6667 | 3 | 3 | 6 | 3 | 1 | 1 | 5 | 4 | 2 | 1.6667 | 6 | 5 | 4 | 2 | 3 | 5 | 2 | 2 | 2 | 4 | 6 | 1.6667 | 1.6667 | 4 | 1.5 | 6 | 1.5 | 1.3333 | 1.5 | 3 | 3 | 3 | 3 | 2.5 | 6 | 3 | 2 | 6 | 1 | 2.5 | 2 | 1.6667 | 2 | 4 | 2.5 | 6 | 1.3333 | 2 | 3 | 5 | 5 | 1.3333
196 | 18 | 13 | 25 | 37.6667 | 49.6667 | 61.6667 | 67.6667 | 78.3333 | 89.3333 | 101.8333 | 116.1667 | 127.1667 | 145.6667 | 156 | 2 | 5 | 3 | 3 | 2 | 3 | 2 | 5 | 4 | 3 | 4 | 1.6667 | 4 | 2 | 1 | 5 | 4 | 1 | 4 | 3 | 1 | 1 | 3 | 1 | 2 | 1.6667 | 2 | 5 | 4 | 1 | 4 | 2 | 5 | 3 | 1.5 | 3 | 4 | 3 | 1.3333 | 6 | 4 | 3 | 3 | 1 | 5 | 5 | 2.5 | 6 | 1.6667 | 3 | 1.6667 | 4
197 | 17.8333 | 9.8333 | 22.1667 | 33.5 | 40.6667 | 46.8333 | 62.8333 | 79.1667 | 87.1667 | 95.3333 | 104.3333 | 114.5 | 126.5 | 132 | 2 | 4 | 2.5 | 1.3333 | 5 | 3 | 1.3333 | 3 | 1.6667 | 5 | 1.6667 | 3 | 1.3333 | 1.3333 | 2 | 2.5 | 1.3333 | 1.5 | 2 | 1.3333 | 6 | 2 | 3 | 5 | 6 | 3 | 1.3333 | 6 | 3 | 2 | 1.6667 | 1.3333 | 1.6667 | 2 | 1.5 | 3 | 1 | 2 | 4 | 2 | 2.5 | 1.6667 | 3 | 3 | 2.5 | 2.5 | 5 | 2 | 1.5 | 1 | 1 | 2
198 | 13.8333 | 10.3333 | 20.8333 | 29.1667 | 41.1667 | 49.1667 | 56.6667 | 70.6667 | 85.6667 | 97.6667 | 106.1667 | 117.8333 | 129.5 | 136.8333 | 3 | 1.3333 | 4 | 2 | 2 | 1.5 | 2 | 5 | 1.3333 | 2 | 2 | 3 | 2.5 | 1 | 6 | 2.5 | 1.3333 | 4 | 1.6667 | 1 | 1.5 | 1.6667 | 3 | 1.3333 | 2 | 6 | 2 | 4 | 6 | 5 | 1.5 | 2.5 | 1.5 | 1.5 | 3 | 6 | 1.6667 | 4 | 1.5 | 1.3333 | 2 | 1.6667 | 2 | 6 | 2 | 2 | 6 | 1.6667 | 2 | 1.3333 | 1 | 3
199 | 16 | 8.3333 | 18.8333 | 26.6667 | 43.3333 | 58 | 68.6667 | 83.6667 | 92.6667 | 104 | 114.3333 | 122.8333 | 132.1667 | 149.1667 | 3 | 1.5 | 1.3333 | 2.5 | 1.6667 | 6 | 1.5 | 1.3333 | 2.5 | 1.3333 | 3 | 1 | 6 | 4 | 1.6667 | 5 | 6 | 1.3333 | 6 | 1.3333 | 3 | 3 | 3 | 1.6667 | 6 | 1 | 6 | 2 | 4 | 2 | 1 | 2 | 3 | 3 | 1.3333 | 4 | 1.3333 | 1.5 | 6 | 1.5 | 3 | 2.5 | 1.5 | 1.5 | 2 | 4 | 1.3333 | 2 | 1 | 5 | 5 | 6
200 | 20 | 13.5 | 26 | 37.1667 | 43.1667 | 57 | 67.5 | 78 | 90.1667 | 111.1667 | 122.8333 | 129 | 143 | 153.6667 | 4 | 2.5 | 4 | 3 | 4 | 2.5 | 3 | 3 | 3 | 2.5 | 1.6667 | 4 | 2 | 1.5 | 1.5 | 1 | 6 | 5 | 1.3333 | 1.5 | 1 | 1 | 2.5 | 6 | 2 | 3 | 2.5 | 3 | 2 | 6 | 2.5 | 1.6667 | 5 | 6 | 5 | 5 | 1 | 3 | 6 | 1.6667 | 1.5 | 1.6667 | 2 | 1 | 1 | 5 | 4 | 4 | 1.6667 | 1 | 6 | 2
201 | 18.6667 | 11.6667 | 22.6667 | 32.1667 | 43.1667 | 51.1667 | 59 | 70.6667 | 82.6667 | 94 | 104 | 118 | 130 | 140.8333 | 1.6667 | 4 | 4 | 2 | 5 | 2 | 2 | 2 | 3 | 3 | 2 | 1.5 | 1.6667 | 3 | 1.3333 | 5 | 1.6667 | 3 | 1.6667 | 1.6667 | 2.5 | 1 | 3 | 1.3333 | 1.6667 | 3 | 3 | 4 | 2.5 | 2 | 5 | 2.5 | 2 | 1.3333 | 2 | 6 | 3 | 3 | 2 | 2 | 4 | 4 | 4 | 2 | 2.5 | 6 | 2 | 1.5 | 1.5 | 6 | 1.3333 | 2
202 | 19.1667 | 13.5 | 23.6667 | 30.6667 | 42.1667 | 49.1667 | 57.1667 | 66.5 | 76.8333 | 84.1667 | 93.5 | 103.8333 | 112 | 128.6667 | 3 | 5 | 4 | 1.5 | 1.6667 | 4 | 1.5 | 3 | 1.6667 | 2 | 2 | 1.3333 | 3 | 1.5 | 3 | 4 | 2 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 2 | 1.3333 | 3 | 3 | 3 | 1.3333 | 3 | 3 | 2 | 1.6667 | 2 | 1.6667 | 2 | 3 | 3 | 1.3333 | 2 | 1.3333 | 5 | 2 | 1.6667 | 2 | 2.5 | 2 | 4 | 5 | 1.6667 | 6
203 | 14.8333 | 8.8333 | 19.3333 | 32.3333 | 46.8333 | 58.8333 | 67.3333 | 83.1667 | 95.6667 | 104.6667 | 117.3333 | 126.1667 | 137.6667 | 144.6667 | 1.3333 | 4 | 1 | 2.5 | 2 | 4 | 1.5 | 3 | 2 | 2.5 | 2.5 | 6 | 3 | 6 | 2.5 | 3 | 2 | 2 | 3 | 5 | 4 | 1.5 | 1.3333 | 1.6667 | 2.5 | 6 | 1.3333 | 6 | 1.5 | 4 | 4 | 3 | 2 | 2 | 3 | 2 | 1.6667 | 1 | 6 | 4 | 2 | 1.3333 | 2.5 | 3 | 5 | 2.5 | 1.5 | 2.5 | 2 | 1 | 2 | 2
204 | 15.1667 | 11.5 | 18.5 | 26.8333 | 37 | 49.5 | 60.1667 | 72.1667 | 85.6667 | 95.8333 | 106.8333 | 126.8333 | 140.8333 | 153.8333 | 2.5 | 5 | 2 | 2 | 1.6667 | 2 | 1.6667 | 1.6667 | 3 | 2 | 1.3333 | 2 | 3 | 2.5 | 1.6667 | 3 | 2.5 | 2 | 5 | 3 | 1.6667 | 2 | 2 | 5 | 2 | 4 | 1 | 5 | 2.5 | 5 | 5 | 1 | 6 | 1.5 | 1.3333 | 1.3333 | 3 | 2 | 1 | 5 | 6 | 6 | 5 | 3 | 5 | 1 | 2 | 6 | 2 | 3 | 6 | 2
205 | 14.6667 | 9.1667 | 24.6667 | 36.1667 | 44.6667 | 56.6667 | 66.6667 | 79.3333 | 92 | 103.8333 | 115.6667 | 125.6667 | 136.6667 | 147.1667 | 4 | 1 | 2.5 | 1.6667 | 3 | 2.5 | 4 | 6 | 1.5 | 6 | 2 | 2 | 3 | 1.5 | 1 | 3 | 2 | 4 | 3 | 3 | 2.5 | 3 | 2 | 2.5 | 1.6667 | 5 | 3 | 3 | 2.5 | 6 | 1.6667 | 2.5 | 6 | 2.5 | 2 | 1.3333 | 1.5 | 3 | 6 | 1.3333 | 2 | 2.5 | 3 | 2.5 | 2.5 | 1.5 | 1 | 6 | 2 | 3 | 1.5 | 4
206 | 21 | 13 | 28.5 | 39.6667 | 53 | 64.1667 | 79.6667 | 88.5 | 99.8333 | 107.6667 | 117.3333 | 132.8333 | 144.3333 | 158.6667 | 6 | 1 | 1 | 5 | 4 | 4 | 5 | 2.5 | 5 | 2 | 2.5 | 1.6667 | 3 | 4 | 1.3333 | 5 | 5 | 1.6667 | 2 | 2.5 | 5 | 1.5 | 6 | 3 | 4 | 1 | 1.3333 | 2.5 | 2 | 6 | 1.3333 | 2 | 2 | 1.3333 | 1.5 | 3 | 1.6667 | 4 | 1 | 3 | 5 | 6 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 4 | 1.3333 | 3 | 4 | 6
207 | 14.8333 | 8.8333 | 20.8333 | 29 | 34.5 | 41.1667 | 50.6667 | 57.8333 | 65.8333 | 76.8333 | 84.8333 | 96.8333 | 109.3333 | 121.5 | 4 | 1.3333 | 2.5 | 1 | 5 | 1 | 2 | 4 | 3 | 1 | 2.5 | 1.6667 | 1.5 | 1 | 1.5 | 1.5 | 1.6667 | 2 | 1.3333 | 1.6667 | 2 | 3 | 3 | 1.5 | 3 | 1.6667 | 1.5 | 1 | 1.5 | 1.5 | 1 | 4 | 4 | 3 | 1 | 3 | 1.6667 | 3 | 2 | 1.3333 | 3 | 2 | 5 | 2 | 4 | 4 | 2.5 | 2 | 5 | 1.5 | 4 | 1.6667
208 | 12.1667 | 7.6667 | 16.8333 | 28.8333 | 41.3333 | 55.3333 | 64.1667 | 80.1667 | 88.3333 | 102.8333 | 113.6667 | 126.6667 | 137.5 | 144.8333 | 3 | 2 | 1.6667 | 1 | 1.5 | 3 | 1.6667 | 3 | 6 | 2 | 2.5 | 1.5 | 4 | 3 | 2.5 | 3 | 4 | 2 | 2 | 6 | 2.5 | 2 | 1.3333 | 3 | 4 | 6 | 4 | 2 | 2 | 1.6667 | 1.5 | 3 | 6 | 2.5 | 5 | 1 | 1.3333 | 2 | 1.5 | 6 | 6 | 2 | 2 | 3 | 2 | 2.5 | 1.3333 | 5 | 1.3333 | 3 | 1.5 | 1.5
209 | 15.8333 | 13 | 23.1667 | 33 | 46.5 | 62 | 71 | 80.5 | 88.8333 | 100.3333 | 114.3333 | 123.6667 | 131.6667 | 139.5 | 6 | 2 | 2 | 3 | 1.5 | 1.3333 | 6 | 1.3333 | 2.5 | 1.3333 | 5 | 1 | 4 | 2.5 | 2 | 5 | 3 | 2.5 | 4 | 6 | 2 | 3 | 1 | 3 | 2 | 2 | 1.5 | 4 | 2 | 2 | 3 | 1.3333 | 3 | 4 | 1.5 | 3 | 1.5 | 4 | 2.5 | 6 | 1.3333 | 2 | 2 | 4 | 1.6667 | 3 | 2 | 1.3333 | 1.3333 | 3 | 2.5 | 1
210 | 12.3333 | 8.3333 | 17 | 32 | 47.6667 | 56.1667 | 66.8333 | 79.1667 | 89.8333 | 101.8333 | 117.8333 | 131.3333 | 139.1667 | 150.6667 | 1.3333 | 3 | 2 | 2 | 1 | 3 | 1.6667 | 3 | 3 | 6 | 3 | 3 | 5 | 3 | 1.6667 | 6 | 2 | 3 | 1.5 | 2 | 1 | 3 | 1.6667 | 5 | 2.5 | 2.5 | 1.3333 | 6 | 3 | 3 | 3 | 1.6667 | 4 | 3 | 2 | 3 | 1 | 6 | 3 | 6 | 1.5 | 3 | 6 | 3 | 2 | 3 | 1.3333 | 1.5 | 3 | 2.5 | 3 | 3
211 | 10.6667 | 5 | 15.3333 | 28.6667 | 45.3333 | 55.3333 | 66.3333 | 81.3333 | 89.3333 | 99.5 | 106 | 117.5 | 130 | 142.5 | 1.5 | 1 | 1 | 1.5 | 1.6667 | 4 | 1.6667 | 3 | 5 | 1.3333 | 2 | 5 | 1.6667 | 5 | 5 | 5 | 2 | 2 | 4 | 2 | 2 | 2 | 1 | 6 | 3 | 3 | 4 | 5 | 2 | 3 | 1.5 | 1.5 | 1 | 1.6667 | 1.5 | 6 | 1.5 | 2 | 1.5 | 1.5 | 2.5 | 2 | 5 | 2 | 2.5 | 5 | 3 | 2 | 1 | 2.5 | 5 | 4
212 | 19 | 12 | 24.5 | 34.5 | 43 | 51 | 62.3333 | 75.3333 | 85.3333 | 91.6667 | 108.6667 | 120.3333 | 130.5 | 138 | 1 | 3 | 2 | 6 | 3 | 4 | 3 | 2.5 | 4 | 1.3333 | 1.6667 | 3 | 2 | 3 | 2 | 1.5 | 2 | 3 | 1 | 2 | 6 | 2 | 2 | 1.3333 | 6 | 1 | 3 | 3 | 4 | 1.5 | 2.5 | 2 | 1.3333 | 1 | 3 | 1 | 5 | 5 | 2 | 5 | 2 | 1.6667 | 2 | 6 | 1.6667 | 3 | 1.5 | 4 | 2 | 1.6667 | 2.5 | 1.3333
213 | 17.8333 | 14.5 | 24.5 | 37 | 54 | 62.6667 | 75.1667 | 82.3333 | 98.3333 | 117.3333 | 129.3333 | 140.8333 | 152.5 | 173.5 | 4 | 3 | 5 | 2.5 | 2 | 1.3333 | 5 | 1.6667 | 2 | 2.5 | 2 | 6 | 2 | 3 | 6 | 6 | 1 | 1.6667 | 5 | 1 | 2 | 4 | 2.5 | 4 | 1 | 1.5 | 1.6667 | 3 | 6 | 2 | 2 | 6 | 3 | 6 | 5 | 5 | 5 | 2 | 3 | 2 | 6 | 1.6667 | 2.5 | 1.3333 | 1.6667 | 6 | 1 | 3 | 6 | 6 | 3 | 6
214 | 17 | 7 | 19.8333 | 32.8333 | 40.6667 | 50.8333 | 62.8333 | 74.1667 | 90.1667 | 98.5 | 107 | 117.6667 | 128.1667 | 136.8333 | 3 | 1.6667 | 1 | 1.3333 | 4 | 6 | 1.3333 | 1.5 | 1.5 | 4 | 1.5 | 6 | 1.5 | 1.6667 | 3 | 1.6667 | 2.5 | 1.6667 | 4 | 2 | 1.5 | 1.5 | 3 | 6 | 2 | 6 | 1.3333 | 2 | 3 | 6 | 2 | 5 | 2.5 | 1.3333 | 3 | 1.5 | 2.5 | 1 | 2.5 | 2.5 | 1.6667 | 2 | 1 | 6 | 2.5 | 4 | 2 | 2 | 2 | 3 | 1.6667 | 2
215 | 14.5 | 11 | 18.5 | 26.6667 | 41.6667 | 55.1667 | 62.1667 | 78.6667 | 85.6667 | 97.3333 | 108.5 | 117 | 130.6667 | 142.6667 | 1 | 6 | 3 | 1 | 1 | 2.5 | 2 | 2 | 1.5 | 1.6667 | 2.5 | 2.5 | 3 | 2 | 6 | 4 | 3 | 4 | 1.5 | 5 | 1 | 3 | 1.6667 | 1.3333 | 6 | 6 | 3 | 1.5 | 2.5 | 1 | 2 | 1.5 | 2 | 1.6667 | 4 | 4 | 1.6667 | 6 | 2 | 1.5 | 1.5 | 1.6667 | 4 | 1.3333 | 3 | 4 | 5 | 1.6667 | 3 | 4 | 2.5 | 2.5
216 | 15.6667 | 12.6667 | 19.6667 | 31.1667 | 43.1667 | 51.1667 | 56.8333 | 73.8333 | 81.3333 | 93.3333 | 100.8333 | 109.5 | 119.5 | 128.6667 | 3 | 5 | 1.6667 | 3 | 1.5 | 1.5 | 1 | 3 | 2 | 2.5 | 3 | 4 | 3 | 2 | 5 | 2 | 1 | 1 | 3 | 3 | 1.5 | 1.5 | 1 | 1.6667 | 5 | 6 | 3 | 3 | 1.3333 | 2 | 1.6667 | 2.5 | 1 | 3 | 5 | 3 | 1.5 | 2 | 2.5 | 1.5 | 2.5 | 1.6667 | 2 | 2.5 | 3 | 3 | 1.5 | 2.5 | 2.5 | 1.6667 | 2 | 3
217 | 16.6667 | 8.6667 | 21.6667 | 37.6667 | 48.6667 | 55.8333 | 66 | 81 | 93 | 103.6667 | 116.1667 | 130.1667 | 141 | 154 | 4 | 1.6667 | 1.5 | 1.5 | 6 | 2 | 3 | 2 | 6 | 4 | 5 | 1 | 1.3333 | 2 | 6 | 1.6667 | 2 | 2.5 | 1.3333 | 1.3333 | 1.6667 | 1.5 | 4 | 3 | 5 | 3 | 4 | 3 | 6 | 2 | 2.5 | 1.5 | 3 | 1.3333 | 5 | 1.3333 | 6 | 1 | 2.5 | 3 | 3 | 3 | 2 | 6 | 2.5 | 4 | 3 | 1.3333 | 2 | 6 | 3 | 2
218 | 14.3333 | 9.3333 | 16.3333 | 26.6667 | 32.3333 | 40.8333 | 53.3333 | 64 | 78.5 | 85.8333 | 97.3333 | 117.3333 | 122.3333 | 130.1667 | 1.3333 | 3 | 2 | 3 | 3 | 2 | 1 | 1 | 3 | 3 | 1.3333 | 3 | 1 | 1.3333 | 2 | 1.3333 | 4 | 1.6667 | 1.3333 | 1.5 | 3 | 1.5 | 5 | 3 | 5 | 1.6667 | 3 | 1 | 3 | 1.5 | 6 | 4 | 3 | 2 | 1 | 1.3333 | 1.5 | 3 | 4 | 3 | 6 | 6 | 6 | 2 | 1 | 1 | 1 | 2 | 3 | 1 | 2.5 | 1.3333
219 | 18 | 10.5 | 23.3333 | 32.6667 | 41.1667 | 50.1667 | 59.5 | 68.5 | 76.6667 | 88.8333 | 96.6667 | 103.6667 | 112.1667 | 122.6667 | 6 | 1 | 2 | 1.5 | 5 | 2.5 | 1.3333 | 4 | 1.3333 | 3 | 3 | 2 | 1.5 | 2 | 3 | 2 | 2 | 2 | 4 | 1 | 3 | 2 | 3 | 1.3333 | 3 | 2 | 3 | 1 | 3 | 2 | 1.5 | 1.6667 | 1.6667 | 2.5 | 2 | 6 | 2.5 | 1.3333 | 2 | 2 | 1.5 | 2 | 2.5 | 1 | 2 | 3 | 1.5 | 2 | 5 | 1 | 2.5 | 2
220 | 13.3333 | 9.3333 | 16.8333 | 26.1667 | 34.5 | 54.5 | 62.6667 | 78.6667 | 90.1667 | 95.6667 | 108.6667 | 123.1667 | 133.6667 | 139.3333 | 1.5 | 1.5 | 5 | 1.3333 | 2 | 2 | 2.5 | 1 | 2 | 3 | 1.3333 | 3 | 4 | 1 | 2 | 1.3333 | 4 | 6 | 5 | 5 | 2 | 2 | 1.6667 | 2.5 | 2 | 4 | 4 | 6 | 4 | 3 | 3 | 1.5 | 1.6667 | 1 | 1.3333 | 1.5 | 3 | 4 | 2 | 4 | 1.5 | 3 | 5 | 5 | 2.5 | 3 | 3 | 2 | 1.5 | 1.6667 | 1 | 1.5
221 | 22.5 | 14.5 | 27.8333 | 42.8333 | 55.8333 | 66.3333 | 72.6667 | 84.3333 | 92.8333 | 105.5 | 115.8333 | 126.8333 | 137.5 | 148.5 | 5 | 3 | 2.5 | 4 | 6 | 2 | 4 | 1.3333 | 2.5 | 5 | 6 | 1.5 | 6 | 1 | 5 | 1 | 4 | 2.5 | 1.5 | 2.5 | 2 | 2 | 1 | 1.3333 | 3 | 6 | 1.6667 | 1 | 3 | 3 | 1 | 1.5 | 4 | 3 | 1.6667 | 4 | 5 | 2.5 | 1.3333 | 1.5 | 3 | 1.6667 | 1.3333 | 5 | 1 | 1.6667 | 5 | 3 | 2 | 5 | 2 | 2
222 | 19.8333 | 12.8333 | 23.8333 | 35.6667 | 46 | 60.1667 | 69.5 | 81 | 90.3333 | 99.6667 | 109 | 120.3333 | 137 | 151 | 1.3333 | 6 | 3 | 2.5 | 4 | 3 | 3 | 1 | 2.5 | 1.6667 | 6 | 1.6667 | 1 | 6 | 1.3333 | 2 | 6 | 1.5 | 1.6667 | 5 | 1.3333 | 1.5 | 5 | 1.5 | 1.5 | 5 | 2 | 3 | 1.5 | 1.3333 | 5 | 1.5 | 4 | 3 | 1 | 1.3333 | 5 | 1.3333 | 1.5 | 1.5 | 1 | 1.3333 | 3 | 6 | 5 | 4 | 1.6667 | 6 | 1.5 | 2.5 | 5 | 5
223 | 19.5 | 14.5 | 25.5 | 41.5 | 57.5 | 75 | 86.5 | 94.3333 | 105 | 114.3333 | 122.3333 | 136.3333 | 145.6667 | 152.1667 | 3 | 6 | 2.5 | 3 | 3 | 2 | 3 | 3 | 6 | 2.5 | 5 | 2.5 | 4 | 6 | 2 | 4 | 6 | 6 | 4 | 1.5 | 1.5 | 2 | 3 | 5 | 2.5 | 2 | 2 | 1.3333 | 1 | 2 | 1.6667 | 6 | 1.3333 | 1 | 2 | 5 | 3 | 1.3333 | 2 | 1.6667 | 2 | 4 | 6 | 2 | 4 | 1.3333 | 2 | 2 | 1.3333 | 2 | 1.5 | 1.6667
224 | 15.5 | 12.8333 | 23.5 | 38 | 51.1667 | 57.5 | 68.1667 | 82.1667 | 99.1667 | 108.6667 | 117.8333 | 124.1667 | 134.1667 | 150.1667 | 5 | 4 | 2.5 | 1.3333 | 1 | 1.6667 | 3 | 5 | 6 | 4 | 2 | 2.5 | 6 | 3 | 2.5 | 1.6667 | 1.3333 | 1 | 2.5 | 1.5 | 2.5 | 2.5 | 1.6667 | 4 | 4 | 2 | 5 | 3 | 6 | 3 | 3 | 5 | 3 | 2 | 2.5 | 2 | 2 | 2.5 | 3 | 1.6667 | 2 | 1.3333 | 1.3333 | 1.6667 | 1.5 | 1.5 | 4 | 3 | 5 | 2 | 4 | 5
225 | 21 | 16.3333 | 25 | 30 | 40.1667 | 58.1667 | 69 | 81.5 | 95.3333 | 106.3333 | 114.1667 | 127.3333 | 141.8333 | 150.3333 | 1.3333 | 6 | 5 | 4 | 3 | 1.6667 | 3 | 1 | 1 | 1 | 1 | 2 | 1.6667 | 5 | 2.5 | 1 | 6 | 4 | 3 | 5 | 1.3333 | 1.5 | 6 | 2 | 4 | 1.5 | 5 | 2 | 1.3333 | 6 | 1.5 | 5 | 6 | 2 | 1.5 | 1.5 | 1.5 | 2 | 1.3333 | 3 | 3 | 6 | 1.6667 | 2.5 | 5 | 2.5 | 2 | 5 | 2 | 3 | 1.5 | 2
226 | 19.3333 | 12.3333 | 22.3333 | 30.3333 | 48.6667 | 57.1667 | 68.1667 | 76.8333 | 87.3333 | 95.8333 | 104.5 | 112.5 | 122.5 | 131.5 | 1.3333 | 6 | 2 | 3 | 2 | 5 | 1.5 | 1.5 | 2 | 3 | 2 | 1 | 6 | 6 | 1.3333 | 5 | 2 | 2 | 2.5 | 2 | 3 | 4 | 2 | 2 | 3 | 1.5 | 1.6667 | 2.5 | 3 | 5 | 1 | 1.5 | 2 | 3 | 2 | 1.5 | 1 | 1.6667 | 2 | 4 | 2.5 | 2.5 | 1.3333 | 1.6667 | 1 | 4 | 1 | 4 | 4 | 2 | 1 | 2
227 | 13.8333 | 7.8333 | 19.8333 | 30.3333 | 44.1667 | 56.1667 | 68.3333 | 87.3333 | 96.6667 | 103.3333 | 116 | 122.3333 | 130.6667 | 141.6667 | 1 | 1.3333 | 4 | 1.5 | 4 | 2 | 3 | 3 | 1 | 2 | 1.5 | 6 | 1.3333 | 2.5 | 5 | 5 | 3 | 2 | 3 | 4 | 5 | 2.5 | 1.6667 | 3 | 6 | 4 | 4 | 5 | 1 | 1 | 1.3333 | 6 | 1 | 1 | 3 | 1.6667 | 5 | 3 | 1.6667 | 3 | 2 | 1 | 2 | 1.3333 | 4 | 2 | 1.3333 | 1 | 2 | 3 | 3 | 3
228 | 20 | 12 | 25 | 37.1667 | 45.8333 | 55.5 | 65.3333 | 74.1667 | 87.6667 | 99.6667 | 111.1667 | 118 | 139 | 148.8333 | 2 | 2 | 5 | 3 | 2 | 6 | 2 | 3 | 5 | 1.5 | 4 | 1.6667 | 1 | 4 | 2 | 1.6667 | 1.6667 | 1.3333 | 1.6667 | 5 | 2 | 2.5 | 4 | 1.3333 | 1.3333 | 3 | 1.5 | 3 | 3 | 6 | 3 | 1.5 | 2 | 3 | 4 | 3 | 1.5 | 2 | 6 | 2 | 2 | 1.3333 | 1.5 | 2 | 5 | 4 | 6 | 6 | 1.6667 | 1.6667 | 2.5 | 4
229 | 14 | 11.5 | 18 | 27.1667 | 38.3333 | 54.8333 | 60.8333 | 69.1667 | 77 | 84.6667 | 95.3333 | 102.3333 | 118.3333 | 131.6667 | 5 | 2.5 | 1 | 3 | 1.5 | 1 | 3 | 1 | 1 | 1.6667 | 1.5 | 5 | 6 | 1.6667 | 2 | 1.5 | 2.5 | 3 | 6 | 5 | 1.6667 | 2 | 1 | 1.3333 | 2 | 1 | 4 | 1.3333 | 1 | 1.3333 | 3 | 2.5 | 1 | 2 | 3 | 1.6667 | 2 | 3 | 1.6667 | 4 | 2.5 | 2 | 1.5 | 1 | 5 | 6 | 3 | 2 | 1.3333 | 5 | 4 | 3
230 | 14.8333 | 12.5 | 18.1667 | 28.1667 | 41.5 | 58.1667 | 72.6667 | 82.8333 | 96.8333 | 108.5 | 122.5 | 130.3333 | 139.3333 | 156.3333 | 4 | 2.5 | 3 | 3 | 1 | 1.3333 | 2 | 1.3333 | 3 | 2 | 2 | 3 | 1.3333 | 2 | 6 | 4 | 6 | 1.6667 | 6 | 3 | 5 | 5 | 1.5 | 3 | 2.5 | 1.6667 | 3 | 3 | 5 | 5 | 2.5 | 1.5 | 2 | 1.6667 | 5 | 3 | 3 | 3 | 5 | 3 | 2 | 1.5 | 3 | 1.3333 | 2 | 4 | 1.5 | 1.5 | 4 | 4 | 5 | 4
231 | 13 | 9 | 20.3333 | 31.8333 | 41.3333 | 51.8333 | 59.6667 | 72.3333 | 81.8333 | 101.8333 | 114.3333 | 124.1667 | 132 | 141 | 2 | 2 | 2 | 3 | 2 | 2 | 1.3333 | 6 | 3 | 3 | 2.5 | 3 | 3 | 3 | 2 | 1.5 | 3 | 3 | 1.5 | 3 | 1.3333 | 2.5 | 2 | 2 | 2 | 1.6667 | 6 | 3 | 3 | 1.5 | 4 | 1 | 5 | 3 | 6 | 6 | 2 | 1.5 | 3 | 6 | 4 | 2.5 | 1.3333 | 2 | 2 | 1.5 | 3 | 1.3333 | 1.6667 | 1.6667 | 4 | 1.6667
232 | 13.5 | 7.5 | 17.5 | 34.5 | 50.5 | 64.5 | 75.5 | 87.6667 | 99.1667 | 111.3333 | 122.8333 | 134.1667 | 147.5 | 158 | 4 | 1.5 | 1 | 1 | 4 | 2 | 1.5 | 2.5 | 2 | 5 | 4 | 6 | 6 | 3 | 3 | 4 | 2.5 | 6 | 2.5 | 3 | 2 | 1 | 2 | 6 | 1.6667 | 1.5 | 6 | 3 | 3 | 5 | 2 | 1.5 | 6 | 2 | 1.6667 | 2.5 | 2 | 2 | 5 | 2.5 | 1.3333 | 3 | 3 | 4 | 3 | 3 | 1.3333 | 6 | 4 | 2 | 2.5 | 2
233 | 15.3333 | 9.6667 | 20.8333 | 28.6667 | 39.1667 | 50.1667 | 61.8333 | 75.8333 | 83.8333 | 98.1667 | 106.8333 | 123.5 | 134.5 | 149.5 | 2 | 2 | 1.6667 | 4 | 1.6667 | 4 | 2.5 | 3 | 3 | 1.5 | 2 | 1.3333 | 1.3333 | 6 | 1.5 | 1.6667 | 2 | 4 | 4 | 1 | 2 | 5 | 1.6667 | 3 | 4 | 3 | 2 | 5 | 1.5 | 1.5 | 3 | 2 | 4 | 6 | 1.3333 | 3 | 1.5 | 4 | 1.5 | 1.6667 | 5 | 1.6667 | 4 | 6 | 1.5 | 4 | 2.5 | 3 | 5 | 2 | 5 | 3
234 | 14.1667 | 9.5 | 17.5 | 34.5 | 42 | 54.5 | 61.6667 | 70.6667 | 84.1667 | 98.1667 | 111.1667 | 119.5 | 136.5 | 148.1667 | 3 | 2 | 1.5 | 3 | 3 | 1.6667 | 1.6667 | 1.6667 | 3 | 6 | 5 | 3 | 2 | 2 | 1 | 2.5 | 1.5 | 6 | 2 | 3 | 1.5 | 1.3333 | 1.3333 | 3 | 3 | 2 | 3 | 1 | 5 | 1 | 1.5 | 6 | 3 | 2 | 4 | 5 | 2 | 6 | 3 | 2 | 1.6667 | 1.6667 | 1 | 4 | 2 | 5 | 6 | 4 | 5 | 2 | 3 | 1.6667
235 | 19 | 12 | 24 | 35 | 49 | 58.8333 | 71.1667 | 79.8333 | 91.3333 | 106.8333 | 113.8333 | 128.3333 | 137 | 150 | 1 | 2 | 5 | 4 | 2 | 5 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 6 | 2 | 2.5 | 3 | 1.3333 | 3 | 6 | 1.3333 | 2.5 | 2.5 | 3 | 2.5 | 1.5 | 1.6667 | 2 | 2 | 1.5 | 6 | 5 | 6 | 2 | 2.5 | 1.6667 | 1.3333 | 3 | 1 | 3 | 3 | 6 | 2.5 | 2.5 | 2.5 | 1.6667 | 2 | 2 | 3 | 5 | 3
236 | 16.1667 | 10.6667 | 24.1667 | 37.1667 | 47.8333 | 68.8333 | 78 | 86.6667 | 93.6667 | 106.3333 | 118.3333 | 130.1667 | 142.5 | 149.1667 | 4 | 3 | 2 | 1.6667 | 4 | 1.5 | 6 | 2 | 5 | 1 | 3 | 4 | 1.6667 | 1 | 2 | 6 | 6 | 5 | 5 | 5 | 4 | 2 | 1.5 | 1.6667 | 1 | 2 | 4 | 1.6667 | 2 | 1 | 3 | 1 | 2 | 6 | 3 | 1.6667 | 5 | 1 | 3 | 3 | 2 | 1.3333 | 2.5 | 6 | 6 | 3 | 1.3333 | 2 | 1 | 1 | 3 | 1.6667
237 | 17 | 11 | 20.3333 | 32.8333 | 43.6667 | 59.1667 | 68.5 | 78 | 89.5 | 100.8333 | 109.1667 | 118 | 128.1667 | 141.5 | 2 | 1 | 3 | 5 | 4 | 2 | 2 | 1.3333 | 2.5 | 6 | 1 | 3 | 2.5 | 2 | 1.3333 | 5 | 2.5 | 6 | 4 | 3 | 1 | 5 | 1.3333 | 2 | 3 | 1 | 1.5 | 4 | 2 | 3 | 2.5 | 4 | 4 | 4 | 1.3333 | 2 | 2 | 3 | 1.3333 | 2 | 2 | 3 | 2.5 | 1.3333 | 1.5 | 1.3333 | 6 | 1.3333 | 1.3333 | 4 | 3 | 5
238 | 11.3333 | 8 | 20.3333 | 31.3333 | 40.3333 | 53.8333 | 60.8333 | 72.3333 | 86.6667 | 98.6667 | 111 | 125.3333 | 136.6667 | 147.6667 | 1.5 | 1.5 | 3 | 2 | 2 | 1.3333 | 6 | 3 | 2 | 3 | 2 | 4 | 2 | 5 | 1 | 1 | 5 | 2 | 5 | 1.5 | 3 | 1.3333 | 1 | 1.6667 | 3 | 1.5 | 3 | 4 | 4 | 3 | 6 | 1.3333 | 2 | 3 | 6 | 1 | 2 | 3 | 6 | 1.3333 | 5 | 1.3333 | 2 | 6 | 1.6667 | 3 | 5 | 1.6667 | 3 | 1 | 2 | 5
239 | 13 | 10.3333 | 19 | 28.8333 | 34.5 | 49.5 | 64.5 | 73.5 | 87 | 104 | 115.1667 | 127.1667 | 141.8333 | 151.1667 | 2 | 2 | 1.3333 | 5 | 1.3333 | 1.3333 | 3 | 3 | 4 | 2.5 | 2 | 1.3333 | 2 | 1 | 1.6667 | 1 | 6 | 5 | 2 | 2 | 3 | 5 | 4 | 3 | 1 | 3 | 2.5 | 2.5 | 6 | 5 | 1.5 | 1 | 5 | 1 | 6 | 5 | 3 | 1.6667 | 1.5 | 5 | 2 | 1 | 6 | 3 | 2 | 6 | 1.6667 | 5 | 1.3333 | 2.5 | 3 | 2.5
240 | 17.6667 | 14.6667 | 23.6667 | 34.3333 | 50.6667 | 64.6667 | 77.3333 | 87.6667 | 98 | 108 | 117.5 | 126 | 136.6667 | 144 | 4 | 6 | 1.6667 | 3 | 1.3333 | 1.6667 | 4 | 2 | 1.5 | 2.5 | 1.6667 | 5 | 4 | 6 | 5 | 1.3333 | 2 | 4 | 5 | 3 | 2.5 | 2.5 | 6 | 1.6667 | 1 | 1.6667 | 6 | 1.6667 | 5 | 1 | 1.3333 | 3 | 2 | 1 | 1 | 6 | 4 | 2.5 | 2 | 1 | 3 | 1 | 2 | 2.5 | 2.5 | 1.6667 | 4 | 2.5 | 2 | 2 | 2 | 1.3333
241 | 16.6667 | 7.6667 | 22.6667 | 34 | 45.5 | 55.8333 | 70.5 | 80 | 93.3333 | 100.6667 | 114.5 | 123.5 | 131.5 | 142 | 2.5 | 1.6667 | 1 | 2.5 | 3 | 6 | 1 | 5 | 3 | 5 | 2 | 1.3333 | 3 | 1.5 | 3 | 4 | 1.3333 | 2 | 4 | 3 | 1 | 1.6667 | 6 | 6 | 2.5 | 1.5 | 2.5 | 3 | 2 | 5 | 1.3333 | 5 | 2.5 | 2 | 1.3333 | 1.5 | 1.3333 | 2.5 | 5 | 5 | 1.3333 | 3 | 3 | 1.6667 | 2 | 3 | 1.6667 | 1.3333 | 2 | 1.5 | 5 | 2
242 | 18.5 | 10.5 | 25.5 | 33.5 | 39.5 | 52.8333 | 65.3333 | 82.8333 | 93.8333 | 109.3333 | 121.8333 | 130.3333 | 142.6667 | 154.3333 | 6 | 1.5 | 1.3333 | 1.6667 | 4 | 4 | 3 | 4 | 1.5 | 1 | 1.5 | 4 | 1 | 1.3333 | 1.6667 | 2 | 4 | 6 | 2 | 1.3333 | 1 | 4 | 1.5 | 6 | 5 | 6 | 5 | 1.5 | 2.5 | 1 | 6 | 1.5 | 5 | 4 | 4 | 2.5 | 2 | 4 | 1.5 | 5 | 1.3333 | 4 | 1.5 | 1.6667 | 4 | 1.3333 | 1 | 6 | 3 | 5 | 1.6667 | 2
243 | 18.6667 | 10.6667 | 25.6667 | 35.3333 | 46 | 55 | 68.6667 | 76 | 87 | 100.3333 | 112.6667 | 125.3333 | 135.6667 | 144 | 2 | 1.3333 | 6 | 1.3333 | 3 | 5 | 2 | 5 | 1.6667 | 1 | 1 | 6 | 5 | 1.6667 | 2 | 2 | 2.5 | 3 | 2 | 1.5 | 6 | 2 | 4 | 1.6667 | 2 | 1 | 3 | 1.3333 | 6 | 1.5 | 2 | 1.5 | 6 | 4 | 2 | 1.3333 | 1.3333 | 5 | 4 | 2 | 1.3333 | 1.3333 | 4 | 6 | 1.3333 | 3 | 4 | 2 | 1.3333 | 3 | 1 | 3
244 | 20 | 14 | 24 | 34.1667 | 47.6667 | 58.6667 | 68 | 74.3333 | 83.3333 | 93.6667 | 106.5 | 117.1667 | 124.1667 | 134.6667 | 4 | 4 | 2 | 4 | 5 | 1 | 3 | 1 | 5 | 2 | 1.6667 | 1.5 | 3 | 5 | 3 | 2.5 | 3 | 3 | 3 | 2 | 1.3333 | 5 | 2 | 1 | 1.3333 | 1.5 | 1.5 | 2 | 3 | 1.6667 | 3 | 1.3333 | 3 | 4 | 1.6667 | 1.6667 | 4 | 1.3333 | 1.5 | 6 | 4 | 2 | 3 | 1.6667 | 2 | 2 | 2 | 1 | 2.5 | 3 | 3 | 2
245 | 13.6667 | 8.1667 | 16.3333 | 26.8333 | 33.3333 | 44.5 | 57 | 65.8333 | 76 | 86.5 | 94.5 | 103 | 112.5 | 123.6667 | 2 | 1.6667 | 2 | 2.5 | 3 | 2.5 | 1.6667 | 1 | 6 | 1.5 | 1.6667 | 1.3333 | 2 | 2 | 1 | 1.5 | 3 | 1.6667 | 4 | 2.5 | 4 | 1.5 | 4 | 3 | 1.3333 | 3 | 3 | 1.5 | 2.5 | 1.3333 | 5 | 1.3333 | 3 | 2 | 4 | 1.5 | 1 | 1.5 | 3 | 2.5 | 4 | 1.5 | 1.5 | 1.5 | 2 | 1.5 | 2 | 4 | 3 | 1.6667 | 1.5 | 5
246 | 15.1667 | 9.1667 | 20.8333 | 32.5 | 45.5 | 58.5 | 66.5 | 76.6667 | 94.6667 | 105.6667 | 120.3333 | 128 | 134.5 | 146.1667 | 3 | 1.5 | 1.6667 | 3 | 4 | 2 | 1.6667 | 4 | 1.6667 | 6 | 2.5 | 1.5 | 2 | 5 | 2 | 4 | 2.5 | 5 | 2.5 | 3 | 2 | 1 | 2 | 3 | 2.5 | 2 | 1.6667 | 4 | 4 | 5 | 5 | 4 | 4 | 2 | 3 | 2 | 6 | 5 | 2 | 1.6667 | 1.3333 | 1.3333 | 3 | 2 | 2 | 1.5 | 1.5 | 1.5 | 3 | 1.6667 | 4 | 3
247 | 19 | 12 | 23.6667 | 35.6667 | 50.3333 | 58 | 64 | 75 | 80.3333 | 91.6667 | 100.3333 | 109.6667 | 121.3333 | 134.6667 | 4 | 2 | 3 | 3 | 2 | 5 | 1.6667 | 3 | 1.3333 | 4 | 1.6667 | 5 | 5 | 5 | 3 | 1.6667 | 1.6667 | 3 | 1.6667 | 1.3333 | 1.5 | 1.5 | 2 | 1 | 4 | 3 | 2.5 | 1.5 | 1.6667 | 1 | 1 | 1.6667 | 6 | 1.5 | 1.3333 | 2.5 | 2 | 2 | 1.6667 | 3 | 1.6667 | 3 | 3 | 1.6667 | 1.6667 | 3 | 3 | 4 | 1 | 6 | 5 | 1.3333
248 | 16.3333 | 10.3333 | 19.8333 | 33.8333 | 42.3333 | 50.8333 | 58 | 67.5 | 76.8333 | 84.5 | 93.3333 | 100.8333 | 108.6667 | 119.3333 | 2.5 | 1.3333 | 4 | 2.5 | 4 | 2 | 1.5 | 2 | 2 | 5 | 2 | 5 | 1.5 | 2 | 3 | 2 | 1.6667 | 1.3333 | 1.5 | 4 | 1.3333 | 1.6667 | 1.6667 | 2.5 | 2.5 | 3 | 1 | 3 | 3 | 1.3333 | 1 | 4 | 1.6667 | 2 | 1 | 3 | 1.5 | 2 | 1.3333 | 4 | 2 | 1.5 | 2.5 | 1.5 | 1.3333 | 3 | 1 | 2.5 | 2.5 | 1.6667 | 1.5 | 5
249 | 15 | 7.6667 | 25 | 33.5 | 41.6667 | 55.6667 | 66.5 | 73.6667 | 88.6667 | 99.3333 | 109.1667 | 116 | 126 | 140.6667 | 3 | 1.5 | 1.6667 | 1.5 | 6 | 1.3333 | 6 | 4 | 3 | 3 | 1.5 | 1 | 2.5 | 1.6667 | 2 | 2 | 3 | 4 | 4 | 3 | 1.3333 | 1.5 | 2 | 6 | 1 | 2.5 | 2 | 1.6667 | 2.5 | 4 | 6 | 2.5 | 1.6667 | 1 | 3 | 5 | 1.3333 | 3 | 4 | 1.5 | 1.3333 | 1.5 | 3 | 1 | 3 | 2 | 2 | 3 | 6 | 1.6667 | 4 | 3
250 | 14 | 11 | 19.5 | 29.5 | 46.1667 | 58 | 70 | 79.5 | 90.5 | 98.1667 | 110.6667 | 122.1667 | 127.6667 | 132.8333 | 2.5 | 2 | 5 | 1.5 | 2 | 1 | 4 | 1.5 | 3 | 1 | 3 | 3 | 1.6667 | 5 | 6 | 4 | 1.3333 | 4 | 5 | 1.5 | 2 | 5 | 2 | 3 | 3 | 3 | 2.5 | 1 | 2 | 4 | 2 | 3 | 1.5 | 1.6667 | 1.5 | 3 | 2 | 2.5 | 2 | 6 | 2 | 2 | 6 | 1.5 | 1.5 | 1 | 1.6667 | 1.3333 | 1 | 1.3333 | 1.3333 | 1.5
251 | 15.3333 | 8.8333 | 23 | 37.5 | 46.1667 | 56.6667 | 69.6667 | 81.8333 | 91.5 | 102.8333 | 111 | 123 | 137.3333 | 151 | 1.3333 | 4 | 1 | 2.5 | 5 | 1.5 | 6 | 1.6667 | 5 | 5 | 1.5 | 3 | 2 | 1.6667 | 3 | 2 | 3 | 2 | 2.5 | 3 | 1 | 3 | 3 | 6 | 2.5 | 3 | 5 | 1.6667 | 1 | 5 | 2 | 1.6667 | 2 | 6 | 1.6667 | 1.6667 | 1.6667 | 1.5 | 3 | 2 | 1 | 3 | 3 | 5 | 4 | 6 | 1.3333 | 3 | 5 | 2 | 1.6667 | 5
252 | 13.8333 | 10.5 | 20.8333 | 33.3333 | 46.8333 | 53.3333 | 64.3333 | 76.3333 | 87 | 99.6667 | 111.6667 | 118.3333 | 134.3333 | 144.5 | 3 | 3 | 3 | 1.5 | 2 | 1.3333 | 5 | 2 | 2.5 | 1 | 3 | 6 | 2 | 2.5 | 6 | 3 | 2 | 1.5 | 1.6667 | 1.3333 | 2.5 | 1 | 1.5 | 6 | 1.3333 | 4 | 5 | 1.6667 | 2 | 6 | 1.3333 | 1.3333 | 6 | 1 | 1.6667 | 4 | 6 | 3 | 2 | 1 | 1 | 1.6667 | 2.5 | 1.5 | 4 | 3 | 5 | 4 | 1.3333 | 5 | 1.3333 | 2.5
253 | 20.1667 | 15.5 | 25.1667 | 34.6667 | 44.6667 | 54.3333 | 62.3333 | 79.8333 | 87.1667 | 98.1667 | 106.6667 | 119.8333 | 131.8333 | 141.1667 | 4 | 3 | 6 | 2.5 | 1.6667 | 3 | 2.5 | 2.5 | 2 | 1.5 | 2 | 4 | 2 | 1 | 6 | 1 | 1 | 6 | 1.6667 | 1 | 1 | 4 | 1 | 2 | 2.5 | 5 | 6 | 4 | 1.3333 | 3 | 2 | 1 | 5 | 3 | 1 | 2 | 2.5 | 2 | 2.5 | 1.5 | 1.6667 | 3 | 2.5 | 6 | 3 | 2 | 5 | 2 | 1.3333 | 5 | 2 | 1
254 | 20.3333 | 12.3333 | 28.3333 | 35.1667 | 49.5 | 55 | 63.5 | 74.5 | 83.8333 | 96.3333 | 105 | 118.5 | 127.5 | 139 | 1.3333 | 4 | 2 | 5 | 3 | 5 | 4 | 4 | 3 | 1 | 1.3333 | 1.5 | 1.3333 | 3 | 6 | 4 | 1.5 | 1.3333 | 1 | 1.6667 | 1.5 | 2.5 | 1.5 | 3 | 3 | 1.5 | 2.5 | 4 | 2 | 3 | 3 | 1.3333 | 2.5 | 5 | 4 | 1 | 3 | 2 | 1.6667 | 2 | 1.5 | 6 | 3 | 3 | 2.5 | 2 | 3 | 1.5 | 2 | 2.5 | 5 | 2
255 | 15.6667 | 8.3333 | 20.6667 | 28.8333 | 40.3333 | 49.8333 | 57 | 72.5 | 84.5 | 94.5 | 101.6667 | 115.6667 | 125.1667 | 136.8333 | 3 | 1.3333 | 3 | 1 | 1.3333 | 6 | 3 | 2 | 1 | 1.6667 | 4 | 1.5 | 2 | 3 | 1.5 | 5 | 2.5 | 1 | 3 | 3 | 1.6667 | 2 | 1.5 | 2 | 5 | 2.5 | 6 | 2 | 2 | 3 | 5 | 2 | 2.5 | 1.5 | 2 | 4 | 3 | 1.6667 | 1.5 | 1 | 2 | 6 | 2 | 4 | 1.5 | 1 | 2 | 5 | 6 | 3 | 1.6667 | 1
256 | 18.8333 | 11.8333 | 22.8333 | 34.1667 | 39.6667 | 51.6667 | 59 | 65.5 | 74.6667 | 83.5 | 94.3333 | 102.8333 | 114.8333 | 125.8333 | 2.5 | 4 | 1.3333 | 4 | 4 | 3 | 2 | 2 | 6 | 1.3333 | 1 | 3 | 1.3333 | 1 | 1.6667 | 1.5 | 1.6667 | 1.3333 | 6 | 3 | 3 | 2 | 1 | 1.3333 | 1 | 2 | 2 | 1.5 | 2 | 4 | 1.5 | 1.6667 | 2 | 2.5 | 1.3333 | 3 | 1.5 | 1.3333 | 3 | 5 | 1.5 | 4 | 1.5 | 1.5 | 2 | 3 | 1 | 6 | 4 | 1.5 | 2.5 | 3
257 | 20 | 8 | 26.6667 | 41.1667 | 55.6667 | 61 | 72.5 | 84.5 | 100 | 110.5 | 126.5 | 141.5 | 151.1667 | 163.1667 | 3 | 1 | 3 | 1 | 6 | 6 | 5 | 1.6667 | 2.5 | 3 | 3 | 6 | 3 | 4 | 2.5 | 5 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 1.5 | 3 | 6 | 1 | 1.3333 | 4 | 5 | 1.6667 | 2.5 | 5 | 2 | 6 | 2.5 | 2.5 | 2.5 | 3 | 4 | 3 | 3 | 6 | 4 | 2 | 3 | 6 | 3 | 1.6667 | 4 | 1 | 3 | 1.5 | 5 | 2.5
258 | 12 | 9 | 20.5 | 30.8333 | 42.5 | 57.5 | 68.5 | 79.3333 | 93.1667 | 102.1667 | 109.1667 | 118.6667 | 129.6667 | 138.8333 | 1.6667 | 2 | 4 | 1.3333 | 1.6667 | 1.3333 | 6 | 2.5 | 1.3333 | 5 | 2 | 2 | 2 | 1.6667 | 3 | 5 | 6 | 2.5 | 2.5 | 4 | 2.5 | 1 | 6 | 1.5 | 2.5 | 1.3333 | 3 | 4 | 1.3333 | 6 | 4 | 2.5 | 1.6667 | 3 | 3 | 1.3333 | 1.3333 | 2 | 2 | 1.6667 | 1.5 | 5 | 2 | 1 | 2 | 2 | 2 | 5 | 1.3333 | 1.5 | 5 | 1.3333
259 | 14.1667 | 7.1667 | 21.1667 | 40.1667 | 51.6667 | 62 | 71 | 79.8333 | 93.5 | 107 | 116.3333 | 123 | 134.5 | 145.5 | 1.5 | 3 | 1.3333 | 1.3333 | 6 | 1 | 5 | 2 | 6 | 6 | 3 | 4 | 2 | 3 | 4 | 2.5 | 2.5 | 5 | 1.3333 | 1.5 | 1.3333 | 3 | 1.6667 | 3 | 1.3333 | 1 | 2.5 | 4 | 5 | 1.6667 | 2 | 5 | 2 | 6 | 2.5 | 3 | 6 | 1 | 1 | 1.3333 | 1.5 | 2 | 1.6667 | 1.5 | 2 | 1.5 | 3 | 5 | 4 | 2 | 2 | 3
260 | 21 | 15 | 29.5 | 36.1667 | 44.3333 | 58.8333 | 65.3333 | 78.3333 | 86.1667 | 98.8333 | 114.1667 | 127.8333 | 136.8333 | 152.3333 | 5 | 2.5 | 2.5 | 5 | 5 | 1 | 2.5 | 6 | 2 | 2 | 1.6667 | 1 | 1.6667 | 3 | 2 | 1.5 | 2 | 2.5 | 5 | 5 | 2.5 | 1.6667 | 1.3333 | 1 | 5 | 2 | 3 | 3 | 2.5 | 1.3333 | 1 | 3 | 2.5 | 1.6667 | 2.5 | 6 | 1.3333 | 6 | 2 | 6 | 4 | 3 | 1.6667 | 5 | 3 | 2 | 1.5 | 2.5 | 6 | 4 | 1.5 | 4
261 | 11.5 | 9.5 | 16 | 32 | 43.1667 | 57.1667 | 71.1667 | 76.3333 | 82.3333 | 97.8333 | 108.1667 | 115.6667 | 129.1667 | 137.6667 | 1 | 4 | 3 | 1.5 | 1 | 1 | 2 | 2.5 | 6 | 1 | 4 | 5 | 2.5 | 5 | 1.6667 | 2 | 4 | 3 | 3 | 4 | 2 | 2 | 6 | 4 | 1 | 1.3333 | 1.3333 | 1.5 | 1.6667 | 1.6667 | 1.6667 | 1 | 3 | 6 | 4 | 2.5 | 1.3333 | 2 | 2 | 5 | 1.6667 | 1.3333 | 3 | 1.5 | 2.5 | 3 | 4 | 4 | 2.5 | 3 | 2 | 1
262 | 20.3333 | 12.3333 | 27.3333 | 37.6667 | 46 | 59.6667 | 74.1667 | 84.6667 | 97.8333 | 109.3333 | 118.1667 | 124.6667 | 134.5 | 145.1667 | 3 | 1.6667 | 6 | 1.6667 | 2 | 6 | 2 | 5 | 4 | 2 | 1.3333 | 3 | 2 | 1 | 1.3333 | 4 | 3 | 4 | 1.6667 | 5 | 2 | 6 | 5 | 1.5 | 1.3333 | 2.5 | 1.6667 | 5 | 2.5 | 4 | 5 | 1.6667 | 2.5 | 1 | 3 | 5 | 4 | 1.3333 | 2.5 | 1 | 1.5 | 1.5 | 2 | 1.5 | 1.5 | 1.3333 | 2 | 5 | 1.6667 | 4 | 2 | 3
263 | 12.8333 | 9 | 17.5 | 32.1667 | 47.1667 | 58.6667 | 67.1667 | 76.8333 | 87.1667 | 99.1667 | 108.1667 | 115.1667 | 125.8333 | 134.5 | 2.5 | 1.5 | 2 | 3 | 2.5 | 1.3333 | 3 | 1.6667 | 1.6667 | 6 | 2 | 5 | 6 | 3 | 3 | 3 | 3 | 4 | 3 | 1.5 | 2 | 1.5 | 2 | 3 | 4 | 3 | 1 | 1.6667 | 1.3333 | 5 | 2.5 | 1.5 | 2 | 2.5 | 6 | 1.5 | 3 | 1 | 1 | 4 | 1 | 2 | 2.5 | 1.5 | 3 | 3 | 1.6667 | 3 | 3 | 1.5 | 2.5 | 1.6667
264 | 16.5 | 10 | 19.5 | 28 | 37.5 | 51.1667 | 58.1667 | 71.1667 | 81.3333 | 90.3333 | 101.6667 | 111.6667 | 119.8333 | 134.5 | 2.5 | 2 | 4 | 1.5 | 2.5 | 4 | 1.6667 | 1.3333 | 2.5 | 1.5 | 2 | 2.5 | 2.5 | 2 | 4 | 1 | 1.6667 | 6 | 1 | 5 | 1.5 | 1 | 1.5 | 3 | 3 | 5 | 3 | 2 | 1.6667 | 5 | 2 | 1.5 | 3 | 1.6667 | 3 | 1.3333 | 1.6667 | 1.6667 | 3 | 5 | 1.3333 | 5 | 2 | 1.6667 | 1.6667 | 3 | 2 | 1.5 | 3 | 6 | 1.6667 | 4
265 | 14.6667 | 10.1667 | 23.6667 | 36.5 | 47.8333 | 55.8333 | 65.8333 | 73.3333 | 86.3333 | 97.3333 | 103.1667 | 111.1667 | 125.1667 | 134.5 | 3 | 1.6667 | 2.5 | 3 | 3 | 1.5 | 4 | 5 | 6 | 3 | 1.3333 | 2.5 | 4 | 1.6667 | 4 | 1.6667 | 2 | 2 | 2 | 2 | 5 | 1.5 | 2 | 1.5 | 3 | 1.6667 | 1.3333 | 1.5 | 5 | 1 | 3 | 4 | 3 | 5 | 1.6667 | 1.3333 | 1.5 | 2 | 1 | 1.3333 | 4 | 1.6667 | 1 | 1.3333 | 2 | 6 | 2 | 4 | 4 | 3 | 1.3333 | 1
266 | 12.8333 | 10.3333 | 20.8333 | 30.5 | 38.5 | 50.1667 | 58.8333 | 66.5 | 81.5 | 96 | 105.3333 | 116.8333 | 123 | 131.6667 | 2 | 1.3333 | 4 | 3 | 1 | 1.5 | 4 | 4 | 2 | 3 | 3 | 1.6667 | 1.6667 | 1.3333 | 4 | 1 | 1.6667 | 6 | 2 | 2 | 1.6667 | 2 | 3 | 2 | 2 | 2 | 2 | 1.6667 | 5 | 3 | 6 | 1 | 3 | 6 | 1.5 | 4 | 1 | 1.3333 | 2 | 5 | 4 | 3 | 2.5 | 2 | 1 | 1.6667 | 2 | 1.5 | 1.6667 | 3 | 3 | 1
267 | 11.8333 | 6.5 | 15.3333 | 24 | 32 | 45.6667 | 55.3333 | 69.3333 | 81.3333 | 93.3333 | 106.3333 | 121.3333 | 136.3333 | 149.6667 | 3 | 1 | 1 | 1.5 | 1.3333 | 4 | 2.5 | 1 | 2 | 2.5 | 1.6667 | 2.5 | 1.3333 | 1.6667 | 2 | 3 | 2 | 1.6667 | 5 | 5 | 1.5 | 1.6667 | 5 | 1.5 | 3 | 3 | 3 | 5 | 1.6667 | 3 | 6 | 1.3333 | 2.5 | 5 | 2.5 | 2 | 2 | 2 | 6 | 3 | 3 | 6 | 5 | 1 | 5 | 2 | 6 | 2 | 5 | 1.3333 | 1 | 6
268 | 17.5 | 14 | 21 | 31.3333 | 42.3333 | 51 | 61.6667 | 72 | 90.6667 | 101.6667 | 114.6667 | 123.1667 | 128 | 146 | 1.3333 | 1.6667 | 6 | 5 | 2 | 1.5 | 2 | 1.5 | 1.3333 | 1 | 5 | 3 | 2.5 | 2 | 1.5 | 5 | 1 | 2 | 1.6667 | 4 | 1.6667 | 4 | 2 | 3 | 3 | 1.3333 | 2 | 4 | 6 | 5 | 6 | 1.6667 | 1.6667 | 5 | 3 | 1.3333 | 4 | 6 | 1 | 2 | 3 | 1.5 | 1 | 3 | 1.3333 | 1 | 1.5 | 1 | 5 | 2 | 5 | 6
269 | 17.3333 | 8.8333 | 21.8333 | 31.3333 | 40.6667 | 52.6667 | 65.1667 | 73.1667 | 83.1667 | 92.6667 | 102.3333 | 110.8333 | 118.5 | 133.5 | 4 | 1.3333 | 1 | 2.5 | 2.5 | 6 | 3 | 1.5 | 2.5 | 1 | 3 | 3 | 1.6667 | 3 | 1.6667 | 3 | 2.5 | 2.5 | 1 | 6 | 4 | 4 | 1.5 | 3 | 2 | 2.5 | 1.5 | 2 | 1.5 | 2.5 | 2 | 4 | 2.5 | 3 | 1 | 3 | 1.6667 | 3 | 3 | 2 | 1 | 4 | 1.5 | 2 | 3 | 1.6667 | 1.5 | 1.5 | 6 | 3 | 3 | 3
270 | 19 | 13 | 23.6667 | 32.6667 | 38.1667 | 47.6667 | 60.6667 | 72.3333 | 85.3333 | 101.8333 | 114.1667 | 125.1667 | 134.6667 | 146.1667 | 3 | 2 | 3 | 5 | 3 | 3 | 1.6667 | 3 | 1.6667 | 1.3333 | 4 | 2 | 1.3333 | 1.5 | 1 | 1.6667 | 1.5 | 2 | 3 | 3 | 6 | 1 | 3 | 3 | 1.6667 | 6 | 2 | 2 | 3 | 2 | 5 | 3 | 5 | 4 | 5 | 2.5 | 1.3333 | 6 | 1 | 4 | 4 | 1 | 2 | 4 | 2 | 2.5 | 2 | 3 | 2 | 2.5 | 3 | 4
271 | 13.8333 | 10 | 22.8333 | 36.8333 | 47.8333 | 63.1667 | 80.1667 | 92 | 100.5 | 108.5 | 116.1667 | 130.6667 | 140.1667 | 151.5 | 1 | 3 | 3 | 3 | 2.5 | 1.3333 | 6 | 3 | 1 | 2 | 6 | 5 | 3 | 2 | 3 | 3 | 3 | 1.3333 | 6 | 5 | 4 | 6 | 2 | 5 | 1.5 | 6 | 1.3333 | 3 | 2 | 1.5 | 2 | 3 | 3 | 1.6667 | 1.3333 | 2 | 1.3333 | 2.5 | 2.5 | 1.3333 | 5 | 3 | 4 | 2.5 | 1.6667 | 1.3333 | 4 | 2.5 | 3 | 1.3333 | 5 | 2
272 | 12.5 | 8.5 | 16 | 28 | 41.5 | 50.8333 | 61.8333 | 73.3333 | 84.3333 | 97.8333 | 113.3333 | 122.6667 | 132.6667 | 151.6667 | 1 | 1.5 | 4 | 2 | 2 | 2 | 2 | 1.5 | 3 | 3 | 2 | 4 | 3 | 3 | 6 | 1.5 | 5 | 1 | 2 | 1.3333 | 1.5 | 3 | 4 | 2.5 | 1.5 | 6 | 1 | 3 | 1.5 | 1 | 6 | 2.5 | 1.5 | 5 | 4 | 3 | 4 | 4 | 5 | 2.5 | 2.5 | 2.5 | 1.3333 | 3 | 2 | 3 | 4 | 1 | 5 | 6 | 2 | 6
273 | 18.6667 | 12.6667 | 25 | 33.5 | 41.6667 | 57 | 69.3333 | 87.3333 | 93.5 | 104.5 | 112.5 | 128.5 | 144.5 | 154.5 | 1.6667 | 3 | 4 | 4 | 3 | 3 | 1.3333 | 5 | 3 | 1.5 | 1 | 3 | 2 | 2.5 | 1.6667 | 2 | 6 | 4 | 4 | 1.3333 | 2 | 5 | 1.3333 | 4 | 6 | 3 | 6 | 3 | 1.3333 | 2 | 1.5 | 1.3333 | 1 | 4 | 4 | 2 | 1 | 3 | 1 | 3 | 3 | 3 | 6 | 4 | 5 | 1 | 4 | 6 | 1.6667 | 5 | 1.6667 | 1.6667
274 | 21 | 13 | 24.5 | 36.1667 | 43.3333 | 50.6667 | 60.6667 | 69.6667 | 80.3333 | 94.8333 | 106.1667 | 118.8333 | 140.8333 | 151.3333 | 1.3333 | 4 | 6 | 1.6667 | 5 | 3 | 1.5 | 2 | 1.6667 | 3 | 3 | 4 | 1.5 | 1.6667 | 2.5 | 1.5 | 2 | 3 | 1.3333 | 1 | 2 | 3 | 2 | 3 | 2 | 2.5 | 1.5 | 3 | 2.5 | 1.6667 | 5 | 1.5 | 3 | 3 | 6 | 2.5 | 1.3333 | 6 | 1.5 | 2.5 | 4 | 1.3333 | 6 | 1.3333 | 6 | 5 | 6 | 5 | 2.5 | 3 | 2 | 3
275 | 16 | 12.6667 | 18.6667 | 27.8333 | 37.1667 | 55.1667 | 72.6667 | 83.8333 | 99.8333 | 110.3333 | 125.3333 | 135.3333 | 142 | 155.5 | 5 | 3 | 1.6667 | 3 | 1.6667 | 1.6667 | 1.3333 | 1.3333 | 3 | 3 | 1.5 | 1.6667 | 1.3333 | 3 | 1 | 4 | 5 | 5 | 5 | 3 | 6 | 6 | 4 | 1.5 | 1.6667 | 3 | 1.5 | 5 | 5 | 2.5 | 2.5 | 6 | 3 | 1.5 | 3 | 3 | 5 | 4 | 4 | 2 | 5 | 1.3333 | 2 | 1.6667 | 1.5 | 1.6667 | 1.5 | 2 | 4 | 2 | 5 | 2.5
276 | 21.5 | 12.5 | 27 | 34.6667 | 43.6667 | 54.6667 | 65.1667 | 74.8333 | 83 | 94.5 | 105.5 | 115.3333 | 121.5 | 135 | 1.5 | 3 | 3 | 5 | 4 | 5 | 4 | 1.5 | 1 | 2.5 | 1.6667 | 2.5 | 1 | 2 | 3 | 3 | 2 | 3 | 2 | 4 | 2.5 | 5 | 2 | 1 | 2 | 3 | 3 | 1.6667 | 3 | 2 | 1.5 | 1.6667 | 5 | 2.5 | 2 | 2 | 2 | 6 | 1 | 2 | 2 | 1.3333 | 1.5 | 5 | 2 | 1.6667 | 1.5 | 1 | 1.5 | 3 | 6 | 3
277 | 11.3333 | 8.3333 | 19.3333 | 27.5 | 41.5 | 51.6667 | 59.3333 | 68 | 75.3333 | 87 | 97.5 | 111.1667 | 119.8333 | 130.8333 | 3 | 2 | 1.3333 | 2 | 1 | 2 | 3 | 5 | 1.5 | 1.6667 | 2 | 3 | 3 | 1 | 6 | 4 | 2 | 2.5 | 1.6667 | 4 | 1.3333 | 2 | 3 | 1.3333 | 2 | 3 | 1.6667 | 2 | 2 | 1.3333 | 3 | 1 | 5 | 3 | 1.6667 | 2 | 1 | 1.5 | 2 | 6 | 4 | 2 | 1.6667 | 6 | 3 | 1 | 3 | 1.6667 | 3 | 3 | 3 | 2
278 | 17.3333 | 14.5 | 19.8333 | 30.8333 | 43.8333 | 51.8333 | 65.3333 | 74.5 | 87.8333 | 94.1667 | 109.1667 | 120.1667 | 130.8333 | 141 | 2 | 5 | 1.5 | 6 | 1.5 | 1.3333 | 1.5 | 1 | 5 | 2.5 | 2 | 1.5 | 3 | 3 | 4 | 3 | 2.5 | 1 | 1.5 | 3 | 6 | 1.5 | 2 | 4 | 5 | 1 | 1.5 | 1.6667 | 2 | 4 | 6 | 1.3333 | 1.6667 | 1.3333 | 1.6667 | 1.6667 | 2.5 | 5 | 6 | 1.5 | 2 | 6 | 1 | 2 | 4 | 2 | 3 | 1.6667 | 1 | 1.6667 | 2.5 | 5
279 | 20.6667 | 13.1667 | 25.3333 | 36 | 42.6667 | 54.5 | 61.6667 | 67.3333 | 73.5 | 81.5 | 93.5 | 101.5 | 109.5 | 120 | 2.5 | 1.6667 | 6 | 3 | 1.5 | 6 | 1.6667 | 3 | 1 | 4 | 4 | 1.6667 | 3 | 1 | 1 | 1.6667 | 1.6667 | 2.5 | 1.6667 | 6 | 2.5 | 1 | 1.6667 | 2 | 1.5 | 1.5 | 1 | 1.6667 | 1 | 1.6667 | 1.5 | 2 | 2 | 4 | 1 | 1 | 2 | 5 | 2 | 3 | 4 | 1 | 1.5 | 1.5 | 2 | 3 | 1.5 | 1.5 | 1.5 | 2 | 4 | 3
280 | 14 | 8 | 20 | 36.5 | 46.3333 | 58.8333 | 66.1667 | 77.3333 | 89 | 104.5 | 116 | 124.6667 | 132.8333 | 140.8333 | 1 | 2 | 1 | 4 | 5 | 1 | 3 | 3 | 6 | 1.5 | 3 | 6 | 1.6667 | 5 | 1.5 | 1.6667 | 3 | 1.5 | 2 | 6 | 1.5 | 2.5 | 1.6667 | 1.6667 | 6 | 1.5 | 2 | 1.6667 | 2 | 5 | 3 | 1.6667 | 5 | 4 | 5 | 1.5 | 3 | 3 | 4 | 1.5 | 1.6667 | 4 | 2 | 1 | 2 | 1.6667 | 3 | 1.5 | 5 | 1 | 1 | 1
281 | 14 | 10 | 17.3333 | 33.3333 | 43.1667 | 51.1667 | 62.1667 | 71.3333 | 82.6667 | 95.5 | 105.5 | 115 | 125.8333 | 132.8333 | 5 | 1.3333 | 2 | 1.6667 | 2.5 | 1.5 | 2 | 1.3333 | 3 | 4 | 6 | 3 | 1.5 | 1.3333 | 4 | 3 | 3 | 2 | 1 | 2 | 2 | 2 | 5 | 2 | 2 | 1.5 | 1.6667 | 4 | 6 | 2 | 2 | 1.3333 | 6 | 1.3333 | 3 | 2.5 | 5 | 1.6667 | 2 | 1.3333 | 1.5 | 1 | 4 | 3 | 1.5 | 6 | 1.3333 | 2 | 1.5 | 1.5 | 2.5 | 1.5
282 | 14.6667 | 6.6667 | 20.6667 | 27.3333 | 36.3333 | 44 | 57.6667 | 71.3333 | 82.3333 | 95.3333 | 102.8333 | 113 | 128 | 136.3333 | 1.3333 | 2 | 2 | 1.3333 | 5 | 3 | 2 | 4 | 1 | 3 | 1 | 1.6667 | 3 | 2 | 2 | 2 | 1 | 2 | 3 | 1.6667 | 3 | 5 | 4 | 1.6667 | 1.6667 | 2 | 5 | 5 | 2 | 3 | 3 | 3 | 3 | 2 | 4 | 4 | 1.3333 | 1.5 | 1.6667 | 3 | 1.5 | 3 | 4 | 1.6667 | 5 | 2 | 4 | 4 | 2 | 2.5 | 2.5 | 1.3333
283 | 14.3333 | 9.6667 | 18.3333 | 32.6667 | 40.8333 | 51.5 | 68 | 78.5 | 88.8333 | 100.3333 | 112.8333 | 121.1667 | 134.8333 | 146.3333 | 1.6667 | 1 | 2 | 5 | 3 | 1.6667 | 2 | 2 | 6 | 6 | 1 | 1.3333 | 3 | 1 | 1.6667 | 2.5 | 3 | 1.3333 | 5 | 1.3333 | 5 | 5 | 5 | 1.5 | 1.3333 | 1.5 | 6 | 1.6667 | 3 | 3 | 3 | 1.3333 | 2.5 | 1.5 | 1.5 | 6 | 1.5 | 5 | 4 | 2 | 1.6667 | 1.6667 | 2 | 3 | 1.6667 | 5 | 2 | 5 | 5 | 1.5 | 3 | 2
284 | 16.6667 | 11.1667 | 24.6667 | 39.6667 | 50.5 | 67 | 79.5 | 91.5 | 105 | 119 | 132.5 | 146 | 151 | 163 | 2 | 1.5 | 6 | 1.6667 | 2.5 | 3 | 5 | 3 | 4 | 6 | 2 | 3 | 5 | 2 | 2.5 | 1.3333 | 3 | 2.5 | 6 | 5 | 3 | 4 | 2.5 | 3 | 3 | 2 | 2 | 5 | 4 | 6 | 2 | 1.5 | 6 | 4 | 1.5 | 2.5 | 3 | 3 | 6 | 1.5 | 4 | 1.5 | 3 | 5 | 1 | 1.6667 | 1 | 1.3333 | 3 | 3 | 3 | 3
285 | 19.5 | 9.5 | 24.1667 | 35.6667 | 50.6667 | 55.8333 | 65.3333 | 80 | 95 | 103.5 | 112.5 | 119.6667 | 133.1667 | 141.6667 | 1 | 2.5 | 3 | 3 | 5 | 5 | 3 | 1.6667 | 1.5 | 1 | 6 | 3 | 5 | 3 | 4 | 3 | 1.5 | 1.3333 | 1.3333 | 1 | 2.5 | 4 | 1.5 | 1.5 | 6 | 1.6667 | 4 | 3 | 2 | 5 | 6 | 2 | 3 | 1 | 3 | 1.5 | 3 | 1.5 | 3 | 1.5 | 2 | 1.3333 | 1.3333 | 2.5 | 2.5 | 6 | 3 | 2 | 1.5 | 2 | 3 | 2
286 | 18.6667 | 14.6667 | 22.3333 | 34.1667 | 44.6667 | 56.6667 | 65.5 | 73 | 83.3333 | 91.3333 | 109.3333 | 127.3333 | 146.6667 | 156.6667 | 1.6667 | 6 | 3 | 4 | 3 | 1 | 2 | 1.6667 | 3 | 5 | 1.3333 | 2.5 | 3 | 4 | 1 | 2.5 | 3 | 2.5 | 4 | 2.5 | 4 | 1.3333 | 2.5 | 1 | 1 | 2.5 | 1.5 | 2.5 | 1.6667 | 2 | 1.6667 | 5 | 3 | 1.3333 | 1.6667 | 2 | 5 | 2 | 5 | 6 | 2 | 6 | 6 | 4 | 6 | 6 | 1.3333 | 6 | 3 | 1 | 2 | 4
287 | 25 | 14 | 33 | 46 | 54 | 65.3333 | 79.6667 | 87.1667 | 98.1667 | 107.3333 | 115.6667 | 127.1667 | 142.1667 | 151.3333 | 6 | 1.5 | 5 | 1.5 | 6 | 5 | 2 | 6 | 6 | 2.5 | 3 | 1.5 | 2.5 | 2 | 2 | 1.5 | 3 | 4 | 1.3333 | 3 | 3 | 6 | 4 | 1.3333 | 1.5 | 1.5 | 1.5 | 3 | 1 | 2 | 5 | 3 | 2.5 | 2.5 | 2.5 | 1.6667 | 1.3333 | 3 | 1 | 3 | 2.5 | 2 | 1 | 6 | 4 | 3 | 2 | 6 | 1.6667 | 2 | 3 | 2.5
288 | 13 | 8 | 19 | 36 | 50 | 60 | 70.5 | 83.6667 | 94.1667 | 110.6667 | 121.1667 | 131.8333 | 142.1667 | 150 | 1.6667 | 2 | 1.3333 | 3 | 3 | 2 | 4 | 2 | 5 | 1 | 5 | 6 | 5 | 1 | 4 | 4 | 1 | 6 | 1 | 2 | 2 | 2 | 4 | 2.5 | 6 | 3 | 1.6667 | 2.5 | 1.5 | 2 | 1 | 6 | 1.5 | 6 | 5 | 4 | 3 | 2 | 2.5 | 3 | 1.6667 | 3 | 3 | 3 | 2 | 1.3333 | 4 | 3 | 1.3333 | 1 | 2.5 | 3
289 | 9 | 6 | 16 | 25.6667 | 35.6667 | 46.5 | 53 | 61.8333 | 76.5 | 88.6667 | 101.6667 | 114.6667 | 121.3333 | 134.5 | 2 | 1.5 | 1 | 1.5 | 1.6667 | 1.3333 | 4 | 3 | 4 | 1.3333 | 3 | 1.3333 | 2 | 1 | 2 | 5 | 4 | 2.5 | 3 | 1.3333 | 1.5 | 1.6667 | 1.3333 | 2 | 1.5 | 1.6667 | 1.6667 | 4 | 4 | 3 | 6 | 1.6667 | 5 | 2.5 | 3 | 1.6667 | 6 | 3 | 1 | 3 | 2 | 3 | 6 | 2 | 1.5 | 1.5 | 2 | 1.6667 | 2.5 | 1.6667 | 6 | 3
290 | 17.8333 | 12.5 | 22.1667 | 39.1667 | 47.3333 | 56 | 62.8333 | 71.8333 | 88.3333 | 97.8333 | 108.3333 | 113.6667 | 125.1667 | 136.6667 | 4 | 1 | 5 | 2.5 | 4 | 1.3333 | 1.3333 | 3 | 6 | 5 | 5 | 1 | 2 | 2 | 2.5 | 1.6667 | 1 | 1.6667 | 5 | 1 | 2 | 1.5 | 2 | 1.3333 | 2 | 1.5 | 4 | 1.5 | 1.5 | 5 | 6 | 4 | 4 | 1 | 1.5 | 3 | 3 | 2 | 4 | 1.5 | 1 | 1 | 2 | 1.3333 | 3 | 1.5 | 4 | 3 | 3 | 5 | 1.5 | 2
291 | 17.3333 | 12 | 23 | 34.5 | 46 | 55.5 | 67 | 76.3333 | 88.8333 | 100.8333 | 108.3333 | 120.6667 | 130.8333 | 140.3333 | 2 | 6 | 3 | 1 | 1.3333 | 4 | 4 | 1.6667 | 5 | 2 | 1.5 | 3 | 4 | 1.5 | 4 | 2 | 1.5 | 2.5 | 3 | 2.5 | 3 | 1.5 | 6 | 1 | 1.3333 | 3 | 2 | 3 | 2.5 | 3 | 5 | 2 | 2.5 | 2 | 6 | 1.5 | 2.5 | 1.5 | 2.5 | 1 | 6 | 3 | 1.3333 | 2 | 1.6667 | 3 | 3 | 2.5 | 2.5 | 2.5 | 2 | 2.5
292 | 14.1667 | 9.1667 | 16.5 | 22.8333 | 30.1667 | 41.6667 | 55 | 67 | 79.5 | 89.8333 | 105.8333 | 121.5 | 131.8333 | 140.1667 | 2 | 1.6667 | 1.5 | 4 | 2.5 | 2.5 | 1.3333 | 1 | 1.3333 | 1.3333 | 2 | 1.6667 | 2 | 2 | 2 | 1.3333 | 1 | 3 | 1.5 | 6 | 6 | 4 | 2 | 1.3333 | 3 | 2 | 4 | 3 | 2 | 4 | 5 | 1.5 | 1.3333 | 3 | 3 | 3 | 4 | 3 | 3 | 6 | 5 | 4 | 5 | 1.6667 | 6 | 1.5 | 1.3333 | 1.5 | 1.3333 | 1.5 | 3 | 2.5
293 | 14.1667 | 9.1667 | 20.1667 | 27.6667 | 42.6667 | 52.6667 | 63.1667 | 75.1667 | 82.6667 | 93 | 101.8333 | 108 | 117.8333 | 128.6667 | 3 | 2 | 2.5 | 1.6667 | 3 | 2 | 3 | 3 | 1 | 1.5 | 3 | 2 | 6 | 2 | 3 | 4 | 3 | 2 | 3 | 2 | 2.5 | 1.5 | 1.5 | 5 | 2 | 2 | 5 | 3 | 3 | 2 | 1.5 | 1 | 6 | 1.3333 | 1.3333 | 1.6667 | 1.5 | 3 | 3 | 1.3333 | 1.6667 | 1 | 2 | 1.5 | 2.5 | 2 | 4 | 1.3333 | 1.3333 | 1.5 | 2 | 6
294 | 22.8333 | 12.8333 | 25.1667 | 34.1667 | 46.5 | 59 | 67.6667 | 81.6667 | 98.6667 | 108.5 | 115 | 128.3333 | 140 | 149 | 1.5 | 5 | 5 | 1.3333 | 4 | 6 | 1.3333 | 1 | 2 | 2 | 4 | 1 | 1.3333 | 4 | 6 | 1 | 2 | 4 | 4 | 2.5 | 1.5 | 4 | 1.5 | 1.6667 | 5 | 3 | 4 | 2 | 3 | 6 | 4 | 4 | 2.5 | 5 | 1.3333 | 1 | 1.5 | 2.5 | 1 | 1.5 | 1.3333 | 2 | 4 | 6 | 4 | 3 | 3 | 1.6667 | 3 | 1.5 | 1.5 | 3
295 | 14.6667 | 11.5 | 18 | 33.5 | 44.1667 | 57 | 69.6667 | 81.6667 | 92 | 103.5 | 115 | 125 | 134.8333 | 146 | 2.5 | 3 | 2 | 4 | 1.5 | 1.6667 | 2 | 1.3333 | 6 | 4 | 3 | 2.5 | 1.6667 | 2 | 3 | 4 | 3 | 1.3333 | 6 | 2.5 | 4 | 1.6667 | 4 | 3 | 3 | 6 | 2 | 1 | 1.3333 | 2 | 3 | 4 | 2 | 1.5 | 3 | 5 | 2 | 2.5 | 4 | 3 | 2 | 5 | 1 | 2 | 1.3333 | 3 | 4 | 1.5 | 2 | 2.5 | 5 | 1.6667
296 | 22.6667 | 15 | 26.6667 | 35 | 47 | 57.3333 | 66.8333 | 80.3333 | 93 | 108 | 116.6667 | 127.6667 | 134.5 | 147 | 3 | 3 | 3 | 6 | 1.6667 | 6 | 2 | 2 | 2 | 3 | 1.6667 | 1.6667 | 3 | 6 | 1.6667 | 1.3333 | 1.3333 | 2.5 | 5 | 1.5 | 1.5 | 2 | 3 | 3 | 5 | 3 | 1.5 | 4 | 1.6667 | 6 | 4 | 1 | 2 | 4 | 3 | 6 | 1.3333 | 3 | 1.3333 | 3 | 3 | 3 | 2 | 3 | 1.6667 | 1.6667 | 2 | 1.5 | 2 | 3 | 1.5 | 6
297 | 15.5 | 11 | 18.3333 | 32.1667 | 38.1667 | 45.5 | 60.5 | 70.6667 | 79.8333 | 92.8333 | 99.5 | 109 | 120 | 129 | 6 | 1.3333 | 1.6667 | 2 | 3 | 1.5 | 1.3333 | 1.5 | 1.3333 | 6 | 2.5 | 4 | 2 | 1.3333 | 1.6667 | 1 | 1.3333 | 2 | 1 | 3 | 3 | 3 | 5 | 4 | 1.5 | 1.6667 | 2 | 5 | 1.3333 | 1.5 | 5 | 1.3333 | 3 | 3 | 3 | 4 | 1.6667 | 1 | 2 | 2 | 2 | 1.5 | 3 | 3 | 3 | 3 | 1 | 4 | 3 | 1.3333 | 3 | 1.6667
298 | 16.1667 | 10.1667 | 20 | 31.6667 | 43 | 60 | 76 | 86.8333 | 96.8333 | 103.8333 | 117.3333 | 128.8333 | 134.8333 | 144.5 | 2.5 | 3 | 1.6667 | 3 | 2 | 4 | 1.3333 | 2.5 | 1.3333 | 1.3333 | 3 | 6 | 5 | 2 | 3 | 1.3333 | 3 | 5 | 6 | 3 | 5 | 3 | 3 | 5 | 2 | 1.3333 | 1.5 | 6 | 1 | 1.6667 | 6 | 1.3333 | 1.3333 | 2 | 2 | 1.6667 | 1.5 | 3 | 3 | 6 | 6 | 1.3333 | 2.5 | 1.6667 | 1.3333 | 1.3333 | 2 | 1.3333 | 1.6667 | 3 | 2.5 | 2.5
299 | 26 | 15 | 31 | 42.3333 | 56.3333 | 67.8333 | 82.8333 | 91.5 | 105 | 114 | 121.6667 | 130.1667 | 142.1667 | 159.1667 | 2 | 6 | 3 | 4 | 5 | 6 | 3 | 2 | 5 | 2 | 1.3333 | 3 | 3 | 2 | 6 | 3 | 2.5 | 2.5 | 5 | 1.5 | 3 | 4 | 2 | 6 | 1.3333 | 4 | 1.6667 | 1.6667 | 1.5 | 3 | 4 | 5 | 3 | 1.5 | 1.5 | 3 | 2 | 2 | 2 | 1.6667 | 3 | 1 | 2 | 2.5 | 6 | 1.6667 | 3 | 1.3333 | 3 | 5 | 3 | 6
300 | 20.1667 | 15.5 | 23.3333 | 33.8333 | 47.8333 | 56 | 65.5 | 77 | 85.5 | 95.8333 | 108.8333 | 117.8333 | 123 | 134.1667 | 1.5 | 6 | 3 | 5 | 1.6667 | 3 | 1.6667 | 1.5 | 3 | 3 | 2 | 2.5 | 2 | 3 | 6 | 3 | 1 | 1.6667 | 2.5 | 3 | 1.5 | 1 | 5 | 2 | 2 | 6 | 2 | 1.5 | 1.5 | 3 | 1.5 | 2.5 | 3 | 4 | 1.6667 | 1.6667 | 3 | 3 | 1 | 6 | 3 | 3 | 1.6667 | 1.3333 | 1.5 | 1 | 1 | 1.6667 | 1.6667 | 5 | 3 | 1.5
301 | 10.6667 | 7 | 14.6667 | 24.6667 | 36.6667 | 51.6667 | 60.3333 | 67.5 | 73.6667 | 87 | 97 | 107 | 114 | 122.1667 | 1 | 3 | 1 | 2 | 2 | 1.6667 | 3 | 1 | 2 | 3 | 3 | 2 | 3 | 2 | 6 | 1 | 2 | 6 | 4 | 3 | 2 | 1.6667 | 2 | 3 | 1.5 | 1.3333 | 1.3333 | 3 | 1 | 1.3333 | 1.3333 | 2.5 | 2 | 4 | 6 | 1.3333 | 2 | 3 | 1 | 4 | 1 | 2 | 1 | 6 | 3 | 1.5 | 1.5 | 1 | 3 | 2 | 1.5 | 1.6667
302 | 13.3333 | 8.6667 | 16 | 24.1667 | 37.1667 | 45.6667 | 55.1667 | 70.3333 | 84.3333 | 96.8333 | 107.3333 | 115.3333 | 126.3333 | 143 | 1.6667 | 1 | 5 | 1 | 1.6667 | 3 | 1 | 1.6667 | 1.5 | 3 | 2 | 1.6667 | 3 | 3 | 6 | 1 | 1 | 3 | 2 | 2.5 | 4 | 2 | 2 | 1.5 | 2.5 | 1.6667 | 6 | 5 | 3 | 2 | 5 | 4 | 1.5 | 4 | 3 | 4 | 1.5 | 5 | 2.5 | 1.5 | 2 | 1 | 3 | 2 | 4 | 2 | 2 | 3 | 4 | 1.6667 | 5 | 6
303 | 13.1667 | 5.6667 | 17.5 | 28 | 42 | 64 | 76.5 | 93.5 | 101.5 | 114.5 | 123.6667 | 137.6667 | 151.6667 | 165.6667 | 1 | 1 | 2 | 1.6667 | 5 | 2.5 | 1.3333 | 3 | 1 | 3 | 5 | 1.5 | 2.5 | 5 | 5 | 1.5 | 5 | 5 | 6 | 6 | 2.5 | 4 | 3 | 3 | 3 | 5 | 5 | 4 | 2 | 3 | 1.3333 | 1.6667 | 3 | 6 | 3 | 1 | 3 | 2.5 | 2 | 1.6667 | 1 | 6 | 3 | 4 | 2 | 4 | 3 | 5 | 4 | 1.5 | 6 | 2.5
304 | 13.5 | 10.6667 | 15.5 | 24.8333 | 34.6667 | 42.1667 | 54.8333 | 65.6667 | 75.5 | 86.6667 | 95.6667 | 103.6667 | 114.3333 | 120.8333 | 1.3333 | 5 | 1.3333 | 3 | 1.5 | 1.3333 | 1 | 1 | 4 | 1.3333 | 1 | 3 | 2.5 | 2 | 1.3333 | 4 | 1 | 2 | 2 | 2.5 | 2 | 6 | 1.6667 | 3 | 2.5 | 2 | 5 | 1.3333 | 1.3333 | 1 | 5 | 2.5 | 2 | 5 | 2.5 | 1.6667 | 4 | 2 | 1 | 2 | 2.5 | 2 | 1.5 | 2 | 1.6667 | 2 | 2 | 5 | 1 | 3 | 1 | 1.5
305 | 15.5 | 9.5 | 19.8333 | 32.3333 | 45 | 55.5 | 61.5 | 71.5 | 83 | 90.5 | 102.3333 | 118.6667 | 132.6667 | 144.6667 | 1.5 | 6 | 1 | 1 | 1 | 5 | 1.3333 | 3 | 1.5 | 2 | 6 | 3 | 5 | 2 | 4 | 1.6667 | 2 | 3 | 3 | 2.5 | 1.3333 | 1.5 | 1.6667 | 1.5 | 2 | 4 | 2 | 2 | 6 | 1.5 | 3 | 1 | 1.5 | 1.3333 | 1.6667 | 3 | 2.5 | 1.3333 | 4 | 4 | 6 | 5 | 1.3333 | 4 | 2 | 3 | 6 | 3 | 3 | 4 | 2 | 3
306 | 15.1667 | 10.5 | 19.3333 | 28.5 | 41.5 | 56.1667 | 62.1667 | 73.1667 | 84.1667 | 98.1667 | 111.6667 | 120.8333 | 128.6667 | 143.3333 | 2 | 1.5 | 2 | 5 | 1.6667 | 3 | 1.6667 | 2.5 | 2 | 1.5 | 4 | 1.6667 | 4 | 3 | 3 | 3 | 2 | 6 | 1.6667 | 5 | 2 | 1.6667 | 1 | 1.3333 | 1 | 3 | 3 | 4 | 4 | 1.5 | 3 | 2.5 | 3 | 3 | 6 | 2 | 3 | 6 | 3 | 1.5 | 2.5 | 1.6667 | 2 | 3 | 1.6667 | 2 | 2.5 | 1.6667 | 6 | 1.6667 | 4 | 3
307 | 13.6667 | 10 | 21.6667 | 35.3333 | 47.5 | 56 | 68.1667 | 77.8333 | 86.6667 | 102.6667 | 113.6667 | 123.6667 | 135 | 147.5 | 1.5 | 2 | 5 | 1.5 | 1.6667 | 2 | 5 | 3 | 6 | 2 | 4 | 1.6667 | 1.6667 | 5 | 3 | 2.5 | 2.5 | 1.5 | 1.5 | 3 | 2.5 | 3 | 1.6667 | 5 | 1.6667 | 5 | 1.5 | 1.5 | 3 | 1.3333 | 2.5 | 2 | 4 | 5 | 2 | 5 | 3 | 1 | 4 | 3 | 5 | 1.5 | 2 | 1.5 | 5 | 3 | 1.3333 | 2 | 1 | 1.5 | 5 | 5
308 | 16 | 13.3333 | 21 | 31 | 43.3333 | 54.6667 | 66.6667 | 84.6667 | 94 | 111 | 126 | 134 | 141 | 155.3333 | 1.3333 | 5 | 3 | 4 | 1.6667 | 1 | 3 | 2 | 2 | 1 | 4 | 3 | 2.5 | 2.5 | 6 | 1.3333 | 1.3333 | 2 | 5 | 3 | 1 | 3 | 6 | 2 | 5 | 6 | 6 | 1 | 3 | 1.6667 | 1.6667 | 3 | 5 | 5 | 5 | 2 | 2 | 3 | 4 | 6 | 3 | 1 | 3 | 1 | 1.3333 | 1.3333 | 3 | 1.3333 | 1 | 1.3333 | 6 | 6
309 | 13.5 | 9.5 | 18 | 30.5 | 46.5 | 58 | 69.5 | 84 | 93.6667 | 106.1667 | 119.6667 | 131.3333 | 136.6667 | 146 | 3 | 3 | 1 | 2.5 | 2 | 2 | 2.5 | 2 | 2.5 | 3 | 2 | 5 | 3 | 3 | 5 | 5 | 1.6667 | 6 | 2.5 | 1.3333 | 5 | 2.5 | 1 | 3 | 4 | 2 | 6 | 2.5 | 1.6667 | 4 | 2 | 2 | 3 | 4 | 3 | 2.5 | 1 | 6 | 4 | 2.5 | 1.6667 | 3 | 4 | 3 | 1 | 1 | 1.3333 | 2 | 2 | 1.3333 | 2 | 4
310 | 16.3333 | 11.3333 | 20.8333 | 31.1667 | 44.6667 | 56.1667 | 64.8333 | 78.1667 | 90.6667 | 98.1667 | 107.6667 | 121.6667 | 128.6667 | 141.1667 | 2.5 | 2.5 | 5 | 1.3333 | 3 | 2 | 2.5 | 2 | 3 | 1 | 5 | 1.3333 | 6 | 3 | 3 | 1.5 | 1.5 | 6 | 3 | 1 | 3 | 3 | 1 | 1.6667 | 1.6667 | 6 | 1.6667 | 4 | 2 | 5 | 3 | 2.5 | 1.5 | 2 | 3 | 1 | 3 | 1.5 | 3 | 2 | 5 | 1.3333 | 1.6667 | 6 | 1 | 1.6667 | 3 | 1.3333 | 3 | 2.5 | 2 | 5
311 | 20.6667 | 15.6667 | 23.3333 | 37.3333 | 46 | 55.5 | 65.5 | 74 | 88.5 | 103.1667 | 109.8333 | 119.8333 | 131.3333 | 139 | 1.6667 | 6 | 6 | 2 | 3 | 2 | 1.6667 | 1 | 1 | 3 | 6 | 4 | 1.3333 | 1.3333 | 3 | 3 | 3 | 2.5 | 2 | 2 | 1.3333 | 6 | 1.6667 | 1 | 1.5 | 2.5 | 3 | 1.5 | 4 | 2.5 | 5 | 3 | 2 | 5 | 1.6667 | 6 | 1 | 3 | 1.6667 | 1 | 1.6667 | 1.3333 | 4 | 3 | 3 | 2.5 | 5 | 1 | 2 | 1.6667 | 1 | 3
312 | 12.5 | 9.6667 | 15.1667 | 31.1667 | 43.6667 | 58.6667 | 67.8333 | 86.3333 | 96.3333 | 103 | 113 | 126.5 | 135.5 | 148.5 | 1 | 3 | 1.6667 | 4 | 1.3333 | 1.5 | 1.3333 | 1.3333 | 5 | 5 | 3 | 3 | 2 | 1.5 | 3 | 6 | 4 | 2 | 3 | 6 | 4 | 1.5 | 2 | 1.6667 | 2.5 | 4 | 6 | 6 | 1.3333 | 1.6667 | 3 | 4 | 3 | 1.3333 | 1.3333 | 1 | 2 | 3 | 2.5 | 2.5 | 2.5 | 3 | 4 | 4 | 2 | 2 | 2 | 3 | 3 | 2 | 4 | 4
313 | 12 | 9 | 16.5 | 24.1667 | 37.1667 | 48 | 56.5 | 66.1667 | 72.6667 | 80.6667 | 92.1667 | 105.6667 | 120.1667 | 135.1667 | 2 | 3 | 3 | 1 | 2 | 1 | 2 | 2.5 | 1 | 2 | 1.6667 | 3 | 2 | 2 | 6 | 3 | 5 | 1.5 | 3 | 1.3333 | 1.3333 | 4 | 1.6667 | 1.5 | 1 | 3 | 4 | 1.6667 | 1 | 2 | 2 | 1.5 | 3 | 1.3333 | 1.6667 | 2 | 2.5 | 1 | 5 | 3 | 2 | 5 | 4 | 2.5 | 5 | 5 | 1.5 | 3 | 6 | 3 | 3 | 3
314 | 14.1667 | 11.5 | 22.6667 | 32.6667 | 42.1667 | 59.1667 | 71.5 | 82.3333 | 96.5 | 103.5 | 111 | 123.5 | 132 | 141.6667 | 4 | 2 | 3 | 2.5 | 1.6667 | 1 | 6 | 2.5 | 2 | 1.6667 | 5 | 1.3333 | 2 | 2 | 2.5 | 3 | 5 | 6 | 3 | 3 | 3 | 5 | 3 | 1.3333 | 1.6667 | 2.5 | 5 | 1.6667 | 4 | 1.6667 | 2.5 | 6 | 1.3333 | 1 | 1.6667 | 3 | 1.5 | 1.5 | 3 | 1.5 | 6 | 3 | 1.5 | 2 | 2 | 2 | 2 | 2.5 | 3 | 2 | 1.6667 | 3
315 | 14.5 | 9.5 | 22.5 | 32.5 | 40.6667 | 50.6667 | 57.5 | 74.5 | 88 | 98 | 109.5 | 121.5 | 130.1667 | 140.8333 | 1.5 | 2 | 3 | 3 | 3 | 2 | 2 | 6 | 2 | 3 | 3 | 2 | 4 | 1.5 | 1.3333 | 1.3333 | 4 | 2 | 3 | 1 | 2 | 1.6667 | 1.5 | 1.6667 | 6 | 3 | 3 | 5 | 4 | 5 | 3 | 1.5 | 1.5 | 2.5 | 5 | 1 | 4 | 4 | 2.5 | 1 | 6 | 1.5 | 2 | 2.5 | 2 | 2 | 1.6667 | 3 | 5 | 2 | 2 | 1.6667
316 | 19 | 11.6667 | 26 | 38 | 60 | 77 | 88.3333 | 99.3333 | 106.8333 | 118.8333 | 126.8333 | 139.3333 | 148.8333 | 160 | 1.6667 | 3 | 4 | 3 | 6 | 1.3333 | 3 | 4 | 4 | 3 | 2 | 3 | 5 | 6 | 6 | 5 | 6 | 5 | 3 | 3 | 1 | 6 | 3 | 1.3333 | 4 | 2 | 2 | 3 | 3 | 1.5 | 1.5 | 1.5 | 2 | 2 | 3 | 5 | 2 | 1 | 2 | 3 | 2 | 2 | 2.5 | 6 | 4 | 1 | 1.5 | 3 | 5 | 1.5 | 1.6667 | 3
317 | 17.8333 | 9.8333 | 23.5 | 29.5 | 37.6667 | 50.6667 | 57.3333 | 71.8333 | 79.6667 | 87.5 | 96.5 | 105 | 112.6667 | 120.8333 | 1 | 1.3333 | 2.5 | 5 | 2 | 6 | 4 | 1.6667 | 1.5 | 1.6667 | 1.3333 | 1.5 | 3 | 2 | 1.6667 | 1.5 | 1.5 | 4 | 1.5 | 6 | 1.6667 | 1 | 2 | 2 | 6 | 2 | 4 | 2.5 | 4 | 1.5 | 1 | 1.3333 | 2 | 1.3333 | 1.5 | 3 | 3 | 1 | 3 | 2 | 2 | 1 | 3 | 2.5 | 3 | 2 | 1.3333 | 1.3333 | 4 | 1 | 1.5 | 1.6667
318 | 16.5 | 12.5 | 21 | 35.6667 | 48.1667 | 56.8333 | 71.1667 | 83.1667 | 95.1667 | 108.1667 | 121.3333 | 133.3333 | 140.5 | 159.5 | 2 | 6 | 2.5 | 2 | 1 | 3 | 3 | 1.5 | 6 | 1.6667 | 3 | 4 | 4 | 2 | 4 | 2.5 | 3 | 2 | 2 | 1.6667 | 1.6667 | 1.6667 | 5 | 6 | 1.5 | 6 | 1.5 | 3 | 1.6667 | 6 | 3 | 1.3333 | 3 | 2.5 | 6 | 1.5 | 6 | 1.6667 | 2.5 | 3 | 4 | 1 | 4 | 3 | 1 | 1.6667 | 1.5 | 3 | 1 | 6 | 6 | 6
319 | 17.1667 | 11.1667 | 23.5 | 32.1667 | 39.5 | 48.6667 | 59.8333 | 67.8333 | 77.8333 | 91.3333 | 99.3333 | 112.3333 | 122.8333 | 130.3333 | 6 | 1.6667 | 2 | 1.5 | 3 | 3 | 1.3333 | 5 | 3 | 1 | 3 | 1.6667 | 1.5 | 2 | 2.5 | 1.3333 | 1 | 1.5 | 5 | 1.6667 | 1 | 2.5 | 1.6667 | 6 | 3 | 1 | 3 | 1 | 1 | 3 | 4 | 2 | 3 | 5 | 2.5 | 3 | 3 | 1.5 | 1 | 2.5 | 1.6667 | 4 | 6 | 1.3333 | 5 | 2 | 2 | 1.5 | 1.3333 | 3 | 1.5 | 1.6667
320 | 18.3333 | 9.3333 | 22.3333 | 32.6667 | 39.6667 | 53.6667 | 64.5 | 76.5 | 88.5 | 96.3333 | 105.1667 | 115.6667 | 126.6667 | 133.6667 | 1.3333 | 4 | 1.5 | 2.5 | 4 | 5 | 2.5 | 1.5 | 2 | 1.3333 | 5 | 2 | 1.6667 | 1 | 3 | 1.3333 | 2 | 4 | 5 | 3 | 2.5 | 2 | 5 | 1.3333 | 1.5 | 6 | 2 | 2.5 | 3 | 3 | 3 | 3 | 2.5 | 2 | 1.3333 | 2 | 2.5 | 3 | 1.3333 | 2 | 3 | 3 | 2 | 2.5 | 1.5 | 2.5 | 6 | 1 | 1.5 | 2.5 | 1.6667 | 1.3333
321 | 13.5 | 7 | 16.5 | 29 | 45 | 56.5 | 66.5 | 74.1667 | 85.1667 | 96.1667 | 105 | 116.6667 | 125.8333 | 137.1667 | 1.6667 | 1 | 3 | 1.3333 | 5 | 1.5 | 2 | 1 | 6 | 2 | 1.5 | 3 | 3 | 4 | 4 | 5 | 1.5 | 6 | 3 | 1 | 2 | 2.5 | 4 | 1.5 | 2 | 1.6667 | 1 | 3 | 5 | 1 | 2 | 3 | 4 | 2 | 3 | 2 | 1.5 | 1.3333 | 3 | 3 | 6 | 1.5 | 1.6667 | 2.5 | 4 | 1.3333 | 1.3333 | 2.5 | 5 | 3 | 1.3333 | 2
322 | 13 | 8.5 | 20.3333 | 27.8333 | 39.3333 | 52.8333 | 66.5 | 78.5 | 91.8333 | 103.8333 | 117 | 123.3333 | 132.8333 | 142.3333 | 1 | 2.5 | 2 | 3 | 3 | 1.5 | 6 | 1.3333 | 1 | 1 | 3 | 2.5 | 4 | 4 | 1.5 | 2 | 4 | 1.5 | 2 | 6 | 6 | 5 | 1.6667 | 1 | 3 | 3 | 4 | 2 | 5 | 1.3333 | 5 | 2 | 1 | 2.5 | 6 | 2.5 | 1.5 | 5 | 5 | 1.6667 | 1.6667 | 1.6667 | 1.3333 | 1.6667 | 2 | 1 | 1.5 | 5 | 1.5 | 1 | 5 | 2
323 | 11.5 | 7.5 | 19 | 28.5 | 36 | 43.5 | 56.5 | 68 | 73.8333 | 81.8333 | 92.8333 | 100.8333 | 113.6667 | 124.6667 | 1 | 1.5 | 1 | 4 | 3 | 1 | 6 | 1.5 | 2 | 2 | 2.5 | 3 | 1.5 | 1.5 | 2.5 | 2 | 2 | 1 | 2 | 2.5 | 2 | 3 | 5 | 3 | 2.5 | 1.3333 | 6 | 1.6667 | 1.5 | 2 | 1.3333 | 1 | 3 | 1.5 | 1.5 | 2 | 2.5 | 2 | 2.5 | 4 | 3 | 1 | 3 | 1 | 1.3333 | 1.5 | 6 | 4 | 4 | 1 | 3 | 3
324 | 18.6667 | 14.3333 | 27.6667 | 38.1667 | 46.5 | 54.6667 | 67 | 74.1667 | 86.1667 | 95 | 106 | 122.6667 | 134 | 144 | 1.3333 | 5 | 6 | 2 | 3 | 1.3333 | 5 | 4 | 1.5 | 2 | 4 | 3 | 1.3333 | 2 | 3 | 2 | 3 | 2 | 1.5 | 1.6667 | 1.3333 | 6 | 3 | 2 | 1 | 3 | 1.5 | 1.6667 | 2 | 1.5 | 2.5 | 6 | 2 | 1.5 | 1.3333 | 4 | 4 | 2 | 4 | 1 | 6 | 4 | 1.6667 | 5 | 2 | 6 | 2 | 1.3333 | 2 | 2 | 5 | 1
325 | 14.6667 | 8.6667 | 22.6667 | 31.8333 | 43.8333 | 53.6667 | 61.5 | 72 | 84.8333 | 101.8333 | 114.1667 | 124.6667 | 139.3333 | 155.3333 | 1 | 4 | 1.6667 | 2 | 2 | 4 | 5 | 3 | 1.3333 | 4 | 1.3333 | 2.5 | 3 | 5 | 1 | 3 | 3 | 1.3333 | 3 | 2.5 | 1.3333 | 2 | 2 | 2.5 | 2 | 5 | 2.5 | 1 | 3 | 6 | 2.5 | 1.3333 | 4 | 5 | 3 | 5 | 5 | 2 | 1.3333 | 4 | 2.5 | 3 | 2 | 3 | 4 | 1.6667 | 4 | 5 | 5 | 6 | 3 | 2
326 | 17.3333 | 9.8333 | 21.3333 | 29.3333 | 42.5 | 58 | 68 | 75.5 | 85.6667 | 97 | 109.1667 | 116.5 | 127 | 140 | 5 | 1.3333 | 2 | 1.5 | 5 | 2.5 | 1 | 3 | 3 | 1.3333 | 2 | 1.6667 | 2.5 | 5 | 1.6667 | 4 | 2.5 | 5 | 6 | 2 | 2 | 1.6667 | 5 | 1.3333 | 2 | 3 | 1 | 1.5 | 3 | 2.5 | 3 | 1.6667 | 1.3333 | 2 | 2 | 6 | 5 | 4 | 1.6667 | 1.5 | 1.6667 | 1.3333 | 3 | 1.3333 | 1 | 5 | 2.5 | 2 | 3 | 5 | 3 | 2
327 | 10.1667 | 5.6667 | 13.1667 | 20.6667 | 28 | 39.5 | 48 | 62.1667 | 74.6667 | 87.6667 | 100 | 114.3333 | 129 | 139.6667 | 1.3333 | 2 | 1 | 1.3333 | 2 | 2.5 | 1.3333 | 1.6667 | 2 | 2.5 | 2 | 1 | 1.3333 | 2 | 2 | 2 | 3 | 5 | 2 | 1.5 | 2.5 | 1.5 | 2 | 2.5 | 4 | 2.5 | 1.6667 | 6 | 1 | 2.5 | 4 | 5 | 3 | 2 | 6 | 2 | 1.3333 | 4 | 3 | 4 | 1.3333 | 5 | 5 | 3 | 5 | 1.6667 | 2 | 6 | 2 | 1.6667 | 1 | 6
328 | 17 | 11 | 28 | 39.3333 | 47.5 | 57.8333 | 70.3333 | 82 | 94.6667 | 114.6667 | 123.1667 | 128.5 | 139.5 | 152.6667 | 2 | 2 | 4 | 3 | 4 | 2 | 6 | 5 | 3 | 1.3333 | 2 | 5 | 1.5 | 1.6667 | 4 | 1 | 1.6667 | 6 | 1.6667 | 1 | 2 | 2.5 | 6 | 2 | 6 | 3 | 1.3333 | 1.3333 | 2 | 1.6667 | 3 | 6 | 6 | 4 | 4 | 6 | 2.5 | 4 | 1 | 1 | 1 | 2 | 1 | 1.3333 | 3 | 2.5 | 4 | 1.5 | 2.5 | 6 | 1.6667 | 3
329 | 14.5 | 9 | 21.5 | 36.5 | 44.6667 | 53.6667 | 64.1667 | 71.8333 | 88.8333 | 95.3333 | 103.1667 | 119.8333 | 132.8333 | 141.3333 | 3 | 1 | 2.5 | 2.5 | 1.5 | 4 | 4 | 3 | 6 | 3 | 3 | 3 | 1.3333 | 1.3333 | 3 | 2.5 | 4 | 1.5 | 2 | 1.5 | 3 | 2.5 | 2 | 3 | 2.5 | 1 | 2.5 | 1.6667 | 5 | 4 | 4 | 4 | 1.6667 | 2.5 | 1 | 1.3333 | 1.3333 | 2 | 3 | 1.5 | 4 | 6 | 1.6667 | 5 | 5 | 3 | 2 | 3 | 2.5 | 2.5 | 2 | 1.5
330 | 16.5 | 12.5 | 23.5 | 37.6667 | 49.1667 | 62.1667 | 73.1667 | 86.1667 | 92.1667 | 104.1667 | 118.6667 | 126.6667 | 138.5 | 147.1667 | 6 | 2 | 1.5 | 3 | 1.5 | 2.5 | 5 | 2 | 1.6667 | 6 | 4 | 2.5 | 2.5 | 1.6667 | 6 | 1.3333 | 4 | 2 | 5 | 2 | 3 | 2 | 1 | 5 | 4 | 5 | 2 | 2 | 1.3333 | 1.6667 | 1 | 2 | 2.5 | 2.5 | 5 | 2 | 3 | 5 | 4 | 2.5 | 3 | 1.6667 | 1.6667 | 1.6667 | 6 | 3 | 1.5 | 1.3333 | 2 | 1.6667 | 3 | 2
331 | 15.5 | 11 | 20.5 | 29.8333 | 36.5 | 44.3333 | 56.5 | 69.5 | 76.6667 | 87.1667 | 94.3333 | 101.5 | 110 | 125.5 | 1.5 | 2 | 2.5 | 5 | 3 | 1.5 | 3 | 2 | 2 | 1.3333 | 5 | 1 | 2 | 1.6667 | 1.3333 | 1.6667 | 2.5 | 1.6667 | 1.6667 | 2 | 3 | 6 | 1.5 | 1.6667 | 5 | 2 | 2 | 4 | 2 | 1.6667 | 1.5 | 2 | 3 | 3 | 3 | 1.5 | 1.5 | 1.6667 | 2 | 2 | 1.6667 | 2.5 | 1 | 2 | 2 | 1.5 | 3 | 2 | 3 | 4 | 6 | 2.5
332 | 11.8333 | 8.5 | 19.8333 | 31.8333 | 39.3333 | 57 | 65.3333 | 76.5 | 91 | 97.1667 | 108.5 | 124.5 | 129.3333 | 138 | 1 | 3 | 3 | 1.5 | 2 | 1.3333 | 4 | 4 | 2.5 | 3 | 2.5 | 4 | 1 | 2 | 1.5 | 3 | 6 | 1.6667 | 5 | 5 | 4 | 1.6667 | 1.3333 | 1.3333 | 1.3333 | 2.5 | 6 | 1.3333 | 2.5 | 2 | 6 | 4 | 1.5 | 1.6667 | 1.5 | 1.5 | 5 | 4 | 1.3333 | 1 | 6 | 4 | 3 | 3 | 1 | 1.5 | 1 | 1.3333 | 3 | 2 | 2 | 1.6667
333 | 21.5 | 13 | 24.5 | 32.5 | 43.5 | 54.3333 | 64 | 80 | 94.5 | 107.8333 | 122.3333 | 136 | 146.1667 | 157.6667 | 4 | 3 | 2 | 4 | 2.5 | 6 | 1.6667 | 1.3333 | 2.5 | 2 | 1 | 2.5 | 4 | 2 | 1 | 4 | 4 | 4 | 1.5 | 1.3333 | 1.3333 | 5 | 1.3333 | 2 | 6 | 3 | 5 | 2 | 5 | 2.5 | 5 | 2 | 2 | 6 | 1.3333 | 4 | 6 | 1.5 | 5 | 2 | 6 | 1.6667 | 3 | 3 | 4 | 1.5 | 3 | 1.6667 | 2 | 2 | 6 | 1.5
334 | 18.5 | 11.5 | 23.8333 | 37.3333 | 50.8333 | 64.3333 | 72.1667 | 80.8333 | 92.3333 | 99.6667 | 107.6667 | 121.1667 | 130 | 140.3333 | 6 | 1.5 | 2.5 | 1.5 | 3 | 4 | 4 | 1.3333 | 4 | 5 | 3 | 1.5 | 6 | 3 | 2 | 2.5 | 1.5 | 5 | 4 | 3 | 1.3333 | 1 | 2.5 | 3 | 1.5 | 1.6667 | 3 | 2.5 | 1.6667 | 2.5 | 6 | 1.3333 | 2 | 1 | 3 | 1.3333 | 3 | 1.5 | 2 | 1.5 | 6 | 1 | 5 | 1.5 | 2.5 | 4 | 1.3333 | 1 | 1 | 2 | 6 | 1.3333
335 | 15.8333 | 6.8333 | 20.5 | 27.6667 | 37.5 | 51.8333 | 63.5 | 80 | 88.3333 | 106.8333 | 115 | 121 | 129.6667 | 142 | 2 | 2 | 1.5 | 1.3333 | 3 | 6 | 3 | 1.6667 | 1.5 | 1.3333 | 3 | 1.3333 | 1.5 | 2 | 1.3333 | 5 | 3 | 1.3333 | 5 | 5 | 2 | 2 | 1.6667 | 6 | 6 | 3 | 1.5 | 6 | 2 | 1.3333 | 2 | 3 | 6 | 4 | 6 | 2.5 | 2.5 | 1.5 | 1.6667 | 2.5 | 1.5 | 1.5 | 1.3333 | 1.6667 | 1.6667 | 1.5 | 2.5 | 3 | 2.5 | 1.3333 | 6 | 2.5
336 | 24 | 16 | 28 | 41.6667 | 52.8333 | 63.8333 | 73.5 | 81.5 | 91.5 | 103.1667 | 118.6667 | 129.6667 | 140.6667 | 150.6667 | 1 | 6 | 3 | 6 | 3 | 5 | 3 | 1 | 3 | 6 | 3 | 1.6667 | 5 | 2.5 | 2 | 1.6667 | 1 | 6 | 2.5 | 1.5 | 1.6667 | 2 | 3 | 3 | 3 | 1.5 | 1 | 2.5 | 2.5 | 1 | 1.5 | 5 | 1.6667 | 4 | 3 | 3 | 5 | 2 | 6 | 2.5 | 1.5 | 4 | 2.5 | 3 | 1 | 3 | 2 | 5 | 2 | 2 | 3 | 3
337 | 20.5 | 10.5 | 26.5 | 36.8333 | 48.3333 | 55 | 65 | 74 | 82.5 | 89 | 96.8333 | 109.5 | 119.5 | 126.5 | 4 | 3 | 1 | 2.5 | 4 | 6 | 5 | 1 | 1.5 | 5 | 2.5 | 1.3333 | 1 | 2.5 | 3 | 5 | 2 | 1 | 2 | 1.6667 | 2 | 4 | 1 | 3 | 2 | 3 | 2 | 2 | 2 | 2.5 | 2 | 2 | 1.5 | 2 | 1.5 | 1.5 | 1.3333 | 2.5 | 3 | 1 | 3 | 6 | 2 | 1.6667 | 2 | 4 | 2 | 2 | 1.3333 | 2.5 | 1.6667 | 1.5
338 | 15.3333 | 10.6667 | 25.3333 | 36.8333 | 47.6667 | 59.1667 | 73.1667 | 83.1667 | 89.6667 | 96.1667 | 106.6667 | 116.1667 | 127.1667 | 136.6667 | 3 | 1.6667 | 2 | 4 | 3 | 1.6667 | 6 | 4 | 2.5 | 2 | 6 | 1 | 1.3333 | 2 | 5 | 2.5 | 4 | 2.5 | 3 | 2 | 5 | 4 | 2 | 3 | 3 | 3 | 1.5 | 2.5 | 1.3333 | 1 | 2.5 | 1.6667 | 1 | 2 | 1.5 | 2 | 1.5 | 6 | 1 | 2 | 5 | 1.3333 | 1.5 | 1.6667 | 2 | 4 | 2 | 3 | 1.3333 | 5 | 1.6667 | 1.5
339 | 12.5 | 7.5 | 15.8333 | 25.5 | 36 | 53.6667 | 63.6667 | 79.3333 | 89.3333 | 100.3333 | 113.3333 | 132.3333 | 143.8333 | 154.1667 | 3 | 2 | 1.5 | 1 | 2 | 3 | 1.6667 | 1.6667 | 2 | 2 | 4 | 1.6667 | 1.5 | 3 | 1 | 5 | 6 | 6 | 4 | 1.6667 | 5 | 1.3333 | 2 | 1.6667 | 5 | 3 | 1.6667 | 6 | 2 | 3 | 2 | 3 | 4 | 3 | 2 | 2 | 2 | 2 | 4 | 5 | 6 | 3 | 6 | 4 | 4 | 3 | 3 | 1.5 | 1 | 1.3333 | 2 | 6
340 | 17.5 | 13.5 | 23 | 33.5 | 43.5 | 52 | 60.5 | 68.8333 | 78.6667 | 89.3333 | 101 | 110.8333 | 117.1667 | 127.6667 | 2.5 | 4 | 1 | 6 | 2 | 2 | 3 | 2.5 | 1.3333 | 2.5 | 1.6667 | 5 | 2 | 1.5 | 1.5 | 5 | 2 | 2.5 | 2 | 2 | 2.5 | 1.6667 | 3 | 1.3333 | 1.6667 | 2 | 3 | 1.6667 | 2.5 | 1.3333 | 3 | 3 | 3 | 2 | 4 | 1.6667 | 6 | 1.6667 | 2 | 2 | 1.3333 | 2.5 | 3 | 3 | 1.3333 | 1.5 | 1 | 2.5 | 5 | 2.5 | 1.3333 | 1.6667
341 | 22.3333 | 16.3333 | 27.8333 | 39.3333 | 44.8333 | 56.1667 | 67 | 83 | 102.5 | 112.8333 | 120.8333 | 137.3333 | 146.8333 | 161.8333 | 1.3333 | 4 | 5 | 6 | 3 | 3 | 4 | 1.5 | 6 | 2 | 1.5 | 2 | 1.5 | 1 | 2 | 1 | 1.3333 | 3 | 3 | 4 | 2 | 6 | 1.3333 | 1.5 | 1.5 | 6 | 6 | 2.5 | 6 | 6 | 2.5 | 5 | 1.3333 | 5 | 2.5 | 1.5 | 2 | 2 | 1 | 3 | 6 | 2 | 2.5 | 6 | 1 | 3 | 3 | 2.5 | 5 | 2 | 2 | 6
342 | 18.5 | 15.5 | 21.8333 | 31 | 45.5 | 56.5 | 68.1667 | 80 | 89.5 | 100.3333 | 113.3333 | 118.6667 | 131.8333 | 147.5 | 4 | 6 | 2.5 | 3 | 1 | 2 | 1.3333 | 2 | 3 | 1.5 | 3 | 1.6667 | 3 | 1.5 | 5 | 5 | 1.5 | 4 | 3 | 2.5 | 3 | 5 | 1.6667 | 2 | 3 | 1.3333 | 2.5 | 5 | 2 | 3 | 3 | 1.5 | 2.5 | 5 | 1.6667 | 1.6667 | 4 | 2 | 5 | 2 | 1 | 2 | 1.3333 | 1 | 1.6667 | 3 | 6 | 2.5 | 5 | 1.6667 | 4 | 5
343 | 11.1667 | 7.1667 | 15.5 | 27 | 40.5 | 47.5 | 63 | 73.3333 | 84 | 96 | 104.3333 | 120.8333 | 129.5 | 143.5 | 1.6667 | 1.5 | 2 | 2 | 3 | 1 | 1.3333 | 3 | 2.5 | 5 | 2.5 | 1.5 | 2.5 | 3 | 4 | 4 | 3 | 1 | 2 | 1 | 2.5 | 2 | 5 | 6 | 1 | 1.3333 | 6 | 2 | 1.6667 | 6 | 2 | 1 | 2 | 4 | 4 | 2 | 3 | 1.6667 | 2 | 1.6667 | 5 | 4 | 2.5 | 5 | 1.3333 | 4 | 2 | 1.3333 | 4 | 2.5 | 5 | 2.5
344 | 16.8333 | 8.8333 | 19.6667 | 28.3333 | 38 | 49.5 | 56.8333 | 67.8333 | 75.6667 | 94.1667 | 108.1667 | 119.5 | 132.5 | 141.8333 | 2 | 1.3333 | 4 | 1.5 | 5 | 3 | 1.5 | 1.3333 | 2 | 1 | 1.6667 | 4 | 4 | 1.6667 | 1 | 3 | 2 | 6 | 1.5 | 2 | 1.5 | 1.3333 | 2 | 2.5 | 2 | 5 | 3 | 1 | 1 | 2.5 | 3 | 1.3333 | 1.5 | 6 | 6 | 5 | 4 | 4 | 4 | 2 | 1.3333 | 3 | 2 | 5 | 2.5 | 6 | 3 | 1.5 | 1.3333 | 4 | 2 | 2
345 | 17 | 10 | 19.8333 | 28.5 | 39.8333 | 52 | 66.3333 | 80.3333 | 91.3333 | 109.3333 | 115.6667 | 126.3333 | 142 | 152 | 2 | 1.5 | 1.5 | 5 | 5 | 2 | 1.3333 | 1.5 | 1 | 1.6667 | 5 | 1 | 2 | 3 | 5 | 1.3333 | 5 | 3 | 2.5 | 1.6667 | 5 | 6 | 1.3333 | 2 | 6 | 2 | 2 | 4 | 1.3333 | 5 | 1.6667 | 3 | 6 | 6 | 3 | 3 | 1.3333 | 1 | 2 | 2 | 1 | 3 | 5 | 1.6667 | 1.6667 | 6 | 3 | 5 | 3 | 1.3333 | 1.6667 | 4
346 | 19.1667 | 13.6667 | 24.6667 | 30.5 | 40.5 | 55.5 | 66.8333 | 81.8333 | 93.1667 | 101.8333 | 112.3333 | 120.5 | 130.1667 | 145.6667 | 2 | 5 | 1.6667 | 5 | 3 | 2.5 | 2.5 | 3 | 1.3333 | 1.3333 | 1.5 | 1.6667 | 4 | 1.3333 | 3 | 1.6667 | 2 | 6 | 3 | 4 | 4 | 1.3333 | 4 | 2 | 6 | 2 | 2 | 5 | 2 | 4 | 1.3333 | 4 | 1.6667 | 3 | 2 | 2 | 2.5 | 3 | 2 | 3 | 1.5 | 2 | 1.6667 | 3 | 1.5 | 1.5 | 1.6667 | 5 | 6 | 5 | 2.5 | 2
347 | 18.5 | 15 | 21 | 31.8333 | 45.8333 | 55.6667 | 70.8333 | 82.6667 | 89.1667 | 98.1667 | 111.5 | 122 | 129.5 | 139.6667 | 4 | 2 | 6 | 3 | 1.5 | 2 | 1 | 1.5 | 3 | 5 | 1.5 | 1.3333 | 6 | 1.5 | 1.5 | 5 | 2 | 1.5 | 5 | 1.3333 | 5 | 2.5 | 6 | 1.6667 | 5 | 1.3333 | 3 | 2.5 | 1.6667 | 2 | 1.3333 | 1.5 | 3 | 3 | 1.5 | 1.5 | 6 | 1.3333 | 3 | 3 | 2 | 1 | 5 | 2.5 | 3 | 1 | 2 | 1.5 | 2 | 4 | 2.5 | 1.6667
348 | 20 | 11.5 | 24 | 33 | 46.5 | 54 | 65 | 78.5 | 84.8333 | 92.1667 | 105.1667 | 114.6667 | 122.6667 | 132.6667 | 2 | 2 | 2.5 | 5 | 6 | 2.5 | 1 | 3 | 2 | 1 | 2 | 4 | 4 | 2 | 6 | 1.5 | 3 | 1.5 | 1.6667 | 1.3333 | 1.6667 | 1.3333 | 2 | 6 | 5 | 3 | 3 | 2.5 | 2 | 1.6667 | 1.3333 | 1.3333 | 2 | 2 | 1.3333 | 2 | 4 | 5 | 2 | 2 | 2 | 3 | 2.5 | 2 | 2.5 | 2 | 1.5 | 2 | 1 | 1 | 3 | 5
349 | 20.6667 | 11.6667 | 28.6667 | 41.6667 | 54.8333 | 67.3333 | 73.5 | 86.5 | 94.5 | 101.8333 | 113.3333 | 121.3333 | 135.8333 | 149.8333 | 3 | 4 | 1.6667 | 3 | 6 | 3 | 2 | 6 | 2 | 4 | 3 | 4 | 1.5 | 5 | 1.6667 | 5 | 6 | 2 | 3 | 1.5 | 1.3333 | 2.5 | 1 | 1.3333 | 5 | 1.5 | 1.5 | 5 | 4 | 1 | 1.6667 | 1.3333 | 1.3333 | 2.5 | 1.5 | 2 | 3 | 4 | 1.5 | 3 | 4 | 1 | 1.3333 | 1.6667 | 4 | 2.5 | 2 | 6 | 3 | 6 | 2 | 3
350 | 14.5 | 10 | 20.5 | 28.5 | 38.6667 | 50.3333 | 61.1667 | 77.1667 | 87.6667 | 100.3333 | 110.3333 | 118.3333 | 126.5 | 137 | 2 | 2 | 3 | 3 | 3 | 1.5 | 3 | 3 | 1.5 | 1 | 3 | 2.5 | 4 | 1.6667 | 3 | 1.5 | 3 | 1 | 1.6667 | 6 | 5 | 1.3333 | 2.5 | 2 | 3 | 2 | 6 | 5 | 1.5 | 3 | 5 | 1 | 6 | 3 | 2 | 1.6667 | 2.5 | 3 | 2.5 | 2 | 2.5 | 1.5 | 1 | 3 | 3 | 2.5 | 1.3333 | 1.3333 | 3 | 1.5 | 4 | 2
351 | 20.3333 | 13.3333 | 26.8333 | 36.3333 | 55.8333 | 69.8333 | 79.1667 | 97.1667 | 107.6667 | 114.1667 | 127.5 | 134.3333 | 145.5 | 155 | 1.3333 | 4 | 6 | 2 | 1 | 6 | 4 | 2.5 | 1 | 2.5 | 1 | 5 | 6 | 2.5 | 5 | 6 | 2 | 6 | 5 | 1 | 3 | 3 | 2 | 1.3333 | 4 | 2 | 6 | 6 | 1.5 | 4 | 2 | 3 | 3 | 1 | 1.5 | 1 | 1.3333 | 2 | 4 | 6 | 2.5 | 1.3333 | 1.6667 | 1.3333 | 1.6667 | 3 | 1.5 | 5 | 2 | 3 | 2.5 | 2
352 | 20 | 13 | 22.6667 | 31.6667 | 39.5 | 50.1667 | 58.6667 | 73.3333 | 81.1667 | 94.5 | 108.8333 | 114.1667 | 125.3333 | 140.3333 | 5 | 2 | 4 | 2 | 4 | 3 | 1 | 1.6667 | 1 | 3 | 2 | 3 | 1.3333 | 1.5 | 2 | 3 | 2 | 1.3333 | 1.3333 | 6 | 1 | 3 | 1.5 | 3 | 3 | 1.6667 | 5 | 5 | 1.6667 | 2 | 2.5 | 1.6667 | 6 | 3 | 1.3333 | 3 | 1.3333 | 6 | 3 | 4 | 2 | 1.3333 | 1 | 1 | 1.6667 | 4 | 1.5 | 4 | 6 | 3 | 1 | 5
353 | 20 | 14 | 23.5 | 30.5 | 38.5 | 49.8333 | 56.5 | 67.8333 | 76.8333 | 89.8333 | 101.8333 | 115.3333 | 128.3333 | 136.6667 | 4 | 2 | 5 | 3 | 5 | 1 | 2 | 1.5 | 2 | 1 | 2 | 2 | 1 | 3 | 2.5 | 1.5 | 1.3333 | 2 | 2 | 6 | 2.5 | 1.3333 | 1.5 | 1.3333 | 2.5 | 1.3333 | 1.5 | 6 | 2 | 2.5 | 2 | 2.5 | 3 | 6 | 1.5 | 2.5 | 3 | 5 | 1 | 3 | 2.5 | 2 | 3 | 6 | 3 | 2 | 4 | 4 | 2 | 1.3333 | 2 | 3
354 | 12.3333 | 8.8333 | 17 | 27.5 | 33.8333 | 44.8333 | 56 | 66 | 75.6667 | 85.3333 | 92.5 | 106.5 | 121.5 | 130.5 | 1.6667 | 1.6667 | 3 | 2.5 | 1.5 | 2 | 1.6667 | 3 | 1 | 6 | 1.5 | 2 | 1 | 2.5 | 1.3333 | 1.5 | 2 | 2 | 6 | 1 | 1.6667 | 2.5 | 4 | 3 | 3 | 2 | 2 | 3 | 4 | 1.6667 | 2 | 2 | 1.6667 | 2.5 | 3 | 2.5 | 1.5 | 3 | 1 | 1.6667 | 5 | 2 | 1 | 6 | 6 | 3 | 2 | 4 | 1 | 4 | 2 | 2
355 | 15.5 | 11.5 | 20.5 | 32 | 45.5 | 56.8333 | 67.5 | 82 | 93.1667 | 105.6667 | 117.1667 | 132 | 146.5 | 156 | 1.5 | 3 | 2 | 5 | 2 | 2 | 2 | 3 | 3 | 6 | 1 | 1.5 | 1.5 | 2 | 5 | 5 | 5 | 2 | 1.3333 | 3 | 2 | 4 | 3 | 1.6667 | 2.5 | 4 | 6 | 2 | 6 | 1.5 | 2 | 1.6667 | 6 | 1 | 4 | 1.5 | 2.5 | 2 | 4 | 3 | 6 | 2.5 | 1.3333 | 5 | 6 | 3 | 3 | 2.5 | 3 | 1.5 | 2 | 3
356 | 16.5 | 11.5 | 21.5 | 27.8333 | 37.8333 | 49.8333 | 61.6667 | 72 | 80.8333 | 88.8333 | 102.8333 | 116.8333 | 130.8333 | 142.8333 | 3 | 2.5 | 2 | 4 | 3 | 2 | 3 | 2 | 1.3333 | 1.5 | 1.5 | 2 | 2 | 2.5 | 3 | 2.5 | 5 | 1.6667 | 4 | 1.3333 | 1.3333 | 3 | 5 | 2.5 | 1.3333 | 3 | 2 | 4 | 1.3333 | 2.5 | 2.5 | 2.5 | 1 | 1.5 | 4 | 1.5 | 6 | 5 | 1.3333 | 1.6667 | 3 | 5 | 2 | 4 | 3 | 1 | 5 | 5 | 1 | 2 | 6 | 3
357 | 19.5 | 14 | 23.1667 | 36.6667 | 44.6667 | 59.1667 | 71.5 | 84 | 93.1667 | 101.1667 | 112.1667 | 125.1667 | 134.3333 | 143 | 4 | 6 | 2.5 | 1.5 | 2.5 | 3 | 2 | 1.6667 | 2 | 2.5 | 5 | 4 | 3 | 1 | 1 | 3 | 1.5 | 6 | 3 | 4 | 3 | 1.6667 | 1.6667 | 6 | 2 | 6 | 2.5 | 2 | 1.6667 | 1.5 | 3 | 3 | 2 | 2 | 2 | 2 | 3 | 4 | 2 | 2 | 6 | 3 | 1 | 3 | 2 | 1.6667 | 4 | 1.5 | 2 | 1.6667 | 3 | 2
358 | 13 | 9 | 20 | 34.8333 | 42.8333 | 55.8333 | 64 | 71.5 | 82.5 | 95.6667 | 108.5 | 118.1667 | 129.5 | 139 | 1.5 | 3 | 3 | 1.5 | 2.5 | 1.5 | 5 | 2 | 2.5 | 5 | 6 | 1.3333 | 2 | 1 | 2 | 3 | 4 | 2.5 | 2.5 | 4 | 2.5 | 2 | 1.6667 | 2 | 3 | 1.5 | 1 | 2 | 1.5 | 5 | 2.5 | 2 | 2.5 | 5 | 1.6667 | 4 | 5 | 1.5 | 1.3333 | 5 | 1.6667 | 1.5 | 5 | 1.5 | 5 | 1.3333 | 2 | 3 | 3 | 1 | 3 | 2.5
359 | 20.5 | 16 | 30.5 | 39 | 54 | 67 | 76.3333 | 83 | 95.8333 | 103.5 | 113 | 119.6667 | 130.3333 | 138.1667 | 6 | 2 | 3 | 5 | 1.5 | 3 | 4 | 6 | 1 | 2 | 3 | 2.5 | 5 | 3 | 2 | 5 | 5 | 2 | 5 | 1 | 3 | 2 | 3 | 1.3333 | 1.5 | 1.6667 | 2 | 1.5 | 5 | 1.3333 | 5 | 1.5 | 1.6667 | 2 | 3 | 1 | 1.5 | 1 | 4 | 3 | 2 | 1.6667 | 1 | 2 | 3 | 1.6667 | 2 | 4 | 4 | 1 | 1.3333 | 1.5
360 | 12 | 9 | 20 | 28.8333 | 41.8333 | 48.6667 | 63.6667 | 75.3333 | 86.6667 | 96.6667 | 111.6667 | 124.5 | 141.5 | 150.1667 | 3 | 2 | 2 | 2 | 2 | 1 | 2 | 6 | 2.5 | 3 | 1.3333 | 2 | 1.5 | 3 | 6 | 2.5 | 1.6667 | 2.5 | 1 | 1.6667 | 2 | 4 | 3 | 6 | 2 | 6 | 2 | 1.6667 | 2.5 | 6 | 1.3333 | 1.5 | 6 | 1.3333 | 1.3333 | 1.3333 | 2 | 3 | 5 | 5 | 4 | 5 | 1.3333 | 2.5 | 5 | 5 | 6 | 1 | 2 | 2 | 3 | 1.6667
361 | 17.1667 | 9.1667 | 22.1667 | 33.8333 | 50.8333 | 57.5 | 67.5 | 77.1667 | 84.5 | 91.5 | 101 | 108.8333 | 119.1667 | 127.5 | 2 | 1.6667 | 3 | 2.5 | 6 | 2 | 2 | 3 | 5 | 1.3333 | 1.3333 | 4 | 3 | 2 | 6 | 6 | 1.6667 | 1.5 | 2 | 1.5 | 1.6667 | 1.3333 | 5 | 2 | 1 | 3 | 4 | 1.6667 | 1.3333 | 1.3333 | 3 | 1.6667 | 2.5 | 2 | 1.5 | 1 | 1.6667 | 1.5 | 1.3333 | 5 | 2 | 1.5 | 1.3333 | 3 | 1.5 | 2.5 | 1.3333 | 5 | 2 | 3 | 2 | 1.3333
362 | 19 | 13.5 | 23.5 | 31.6667 | 42 | 52 | 60.5 | 72.5 | 82.6667 | 96 | 103.3333 | 109 | 116.5 | 128.1667 | 3 | 6 | 2 | 2.5 | 3 | 2.5 | 2.5 | 2 | 1.5 | 1.6667 | 2 | 3 | 2 | 2 | 1.3333 | 5 | 2 | 2 | 3 | 3 | 1 | 1 | 4 | 2.5 | 2.5 | 2 | 1.5 | 6 | 1.5 | 1.6667 | 2 | 5 | 1.3333 | 5 | 4 | 3 | 1 | 1.3333 | 2 | 3 | 1.5 | 1 | 1.5 | 1.6667 | 1.5 | 2.5 | 1.5 | 2 | 1 | 1.6667 | 3 | 6
363 | 15.5 | 11 | 19.5 | 31 | 42.6667 | 55.3333 | 63.6667 | 74.6667 | 84.6667 | 92.5 | 105.1667 | 113.6667 | 120.1667 | 133.1667 | 3 | 2 | 4 | 2 | 1.5 | 3 | 2 | 2 | 2 | 1.5 | 6 | 2 | 5 | 1 | 4 | 1.6667 | 1.6667 | 4 | 4 | 3 | 1.3333 | 2 | 2 | 3 | 4 | 1.5 | 3 | 2.5 | 1.6667 | 1.3333 | 3 | 4 | 3 | 1.3333 | 2 | 1.5 | 5 | 1.6667 | 1 | 5 | 3 | 2.5 | 1.5 | 1.5 | 2 | 2 | 1 | 1.5 | 6 | 2 | 1 | 4
364 | 17.6667 | 13.1667 | 26.6667 | 37.5 | 49.1667 | 61.5 | 71.5 | 78.6667 | 90.3333 | 97.8333 | 102.8333 | 109.5 | 122 | 132 | 3 | 6 | 1.6667 | 2.5 | 1.5 | 3 | 5 | 4 | 1.3333 | 1.5 | 3 | 5 | 1.6667 | 3 | 3 | 4 | 1.3333 | 2 | 3 | 6 | 3 | 4 | 1 | 2 | 1.5 | 3 | 1.6667 | 1 | 2 | 2 | 6 | 1.6667 | 1.5 | 1 | 3 | 2 | 1.5 | 1 | 1.5 | 1 | 1.3333 | 2 | 1.3333 | 2 | 2.5 | 1.5 | 2.5 | 6 | 1 | 1.5 | 2.5 | 5
365 | 15.8333 | 9.8333 | 19.3333 | 31.8333 | 43.8333 | 53.3333 | 60.3333 | 66.8333 | 80.8333 | 92.3333 | 99.3333 | 108.8333 | 113.5 | 127 | 2 | 1.3333 | 4 | 2.5 | 3 | 3 | 2.5 | 1 | 1 | 5 | 4 | 2.5 | 3 | 3 | 2 | 4 | 2 | 2.5 | 3 | 2 | 1.3333 | 3 | 1.3333 | 1.3333 | 1.3333 | 1.6667 | 2 | 1.5 | 4 | 2 | 2 | 6 | 1.5 | 2 | 5 | 3 | 2.5 | 2 | 1.5 | 1 | 1.5 | 2 | 2 | 4 | 1.3333 | 1.3333 | 1 | 1 | 2 | 2.5 | 3 | 6
366 | 22.5 | 14.5 | 28.8333 | 44 | 54.8333 | 60.8333 | 70 | 83.5 | 90.5 | 99 | 111.5 | 125.1667 | 134 | 144.3333 | 5 | 6 | 1.5 | 2 | 4 | 4 | 5 | 1.3333 | 1.6667 | 5 | 2.5 | 6 | 1.3333 | 1.5 | 2 | 6 | 1.6667 | 1.6667 | 1.6667 | 1 | 1.5 | 2 | 1.6667 | 4 | 6 | 3 | 1.5 | 3 | 2 | 2 | 1.5 | 1.5 | 1.3333 | 2.5 | 3 | 1.6667 | 2.5 | 2 | 4 | 4 | 1.6667 | 3 | 6 | 3 | 2.5 | 3 | 1.3333 | 2 | 2 | 2 | 5 | 1.3333
367 | 14.6667 | 12.3333 | 22.6667 | 33.6667 | 43 | 57.5 | 67 | 78.6667 | 91.5 | 106.1667 | 112 | 119.1667 | 134.8333 | 146.8333 | 1.6667 | 4 | 5 | 1.6667 | 1.3333 | 1 | 2 | 6 | 1 | 2.5 | 6 | 1.5 | 1.3333 | 2 | 1 | 5 | 1 | 6 | 2.5 | 5 | 1.5 | 2 | 4 | 2 | 2 | 5 | 1.6667 | 3 | 1.3333 | 2.5 | 6 | 3 | 5 | 3 | 1.6667 | 5 | 1.5 | 1.3333 | 1.6667 | 1.3333 | 2 | 1.5 | 2 | 1.6667 | 1.6667 | 6 | 5 | 3 | 2 | 3 | 2 | 5
368 | 16.6667 | 12.1667 | 22.1667 | 32.6667 | 42 | 53.3333 | 62.8333 | 77.3333 | 89.1667 | 99 | 106.5 | 115.3333 | 129.1667 | 141.6667 | 2.5 | 2 | 1.6667 | 6 | 2.5 | 2 | 4 | 1.5 | 1.3333 | 2.5 | 1.6667 | 5 | 2 | 5 | 1.3333 | 1 | 2 | 3 | 1.3333 | 5 | 3 | 2 | 2.5 | 2 | 6 | 2 | 2.5 | 4 | 4 | 1.3333 | 5 | 1.5 | 2.5 | 4 | 1.3333 | 2 | 1 | 1 | 4 | 1.5 | 1.3333 | 3 | 2.5 | 2 | 1.3333 | 1.5 | 6 | 5 | 3 | 1.5 | 2 | 6
369 | 15.3333 | 6.3333 | 19.3333 | 31.8333 | 40.1667 | 53.1667 | 64.3333 | 79.3333 | 90.5 | 105 | 121.5 | 139.5 | 150 | 160.3333 | 1 | 2 | 2 | 1.3333 | 5 | 4 | 1 | 3 | 3 | 3 | 4 | 2.5 | 2.5 | 2.5 | 1.6667 | 1.6667 | 6 | 2 | 3 | 2 | 5 | 1.6667 | 2.5 | 2 | 3 | 3 | 3 | 6 | 2 | 1.5 | 6 | 1.6667 | 5 | 1.5 | 6 | 2 | 5 | 3 | 6 | 2.5 | 6 | 6 | 4 | 2 | 3 | 2 | 2.5 | 3 | 4 | 1.3333 | 2 | 3
370 | 16 | 10 | 19 | 33 | 42 | 53.3333 | 63.1667 | 80.1667 | 87.3333 | 94.5 | 101 | 117 | 128.3333 | 139.3333 | 4 | 1.5 | 2 | 2.5 | 5 | 1 | 1.5 | 1.5 | 6 | 2 | 1 | 5 | 1.3333 | 1.3333 | 1.3333 | 5 | 3 | 1.3333 | 2 | 5 | 1.5 | 1.6667 | 5 | 1.6667 | 6 | 5 | 3 | 3 | 1 | 1.5 | 3 | 1.6667 | 2 | 1.5 | 1.6667 | 2 | 2 | 1 | 1.5 | 2 | 3 | 6 | 5 | 2 | 3 | 1.6667 | 5 | 1.6667 | 5 | 3 | 1.5 | 1.5
371 | 19.1667 | 13.1667 | 22.6667 | 33.3333 | 44.8333 | 53.5 | 64.6667 | 81.1667 | 88.1667 | 97.3333 | 104.3333 | 113 | 129.6667 | 143.3333 | 3 | 2.5 | 6 | 1.6667 | 3 | 3 | 2 | 1.5 | 4 | 1.6667 | 3 | 2 | 2.5 | 2.5 | 4 | 2.5 | 2 | 2.5 | 1.6667 | 2.5 | 4 | 1.6667 | 2.5 | 3 | 2.5 | 6 | 3 | 5 | 1 | 1.6667 | 3 | 1.3333 | 2.5 | 3 | 1.6667 | 2 | 1.3333 | 3 | 1 | 1.6667 | 2 | 2.5 | 2.5 | 1.6667 | 3 | 6 | 1.6667 | 6 | 3 | 6 | 3 | 1.6667
372 | 15 | 11.5 | 18.5 | 25.1667 | 33.5 | 43.3333 | 58.3333 | 69 | 81.6667 | 93.5 | 110.5 | 116.1667 | 128.1667 | 135.5 | 2 | 2.5 | 2 | 5 | 2 | 1.5 | 2.5 | 1 | 2 | 1.6667 | 1 | 2 | 2 | 2 | 3 | 1.3333 | 1 | 1.3333 | 2.5 | 5 | 6 | 2 | 2 | 5 | 3 | 3 | 1.6667 | 3 | 3 | 1.6667 | 4 | 4 | 1.3333 | 6 | 1.5 | 3 | 3 | 2 | 6 | 6 | 1.5 | 1.6667 | 1.5 | 1 | 3 | 3 | 4 | 2 | 1.3333 | 1.6667 | 1.3333 | 3
373 | 16.5 | 12 | 20.1667 | 31.1667 | 45.1667 | 54.8333 | 64.3333 | 77 | 83.5 | 94.5 | 105 | 112.8333 | 127.8333 | 141.1667 | 1 | 4 | 5 | 2 | 1.5 | 3 | 2 | 1.6667 | 2 | 2 | 3 | 4 | 5 | 2 | 2 | 5 | 1 | 3 | 4 | 1.6667 | 1.5 | 2.5 | 1.5 | 4 | 1.6667 | 2 | 6 | 3 | 1 | 2.5 | 1 | 2 | 5 | 1.3333 | 1.6667 | 3 | 1 | 3 | 1.5 | 5 | 1.3333 | 1.5 | 2 | 3 | 5 | 5 | 3 | 2 | 1.6667 | 1.6667 | 6 | 4
374 | 13.5 | 9.5 | 20.8333 | 35.8333 | 49.8333 | 62.5 | 76.1667 | 88.1667 | 98.5 | 109.8333 | 122.8333 | 132 | 140.8333 | 147.8333 | 2 | 3 | 2.5 | 2 | 2 | 2 | 1.3333 | 6 | 5 | 5 | 3 | 2 | 4 | 3 | 2 | 5 | 1.6667 | 3 | 4 | 4 | 3 | 1.6667 | 5 | 4 | 5 | 1.6667 | 1.3333 | 4 | 2 | 5 | 2 | 1.3333 | 3 | 2 | 5 | 1.3333 | 1.6667 | 1.3333 | 6 | 4 | 1.6667 | 4 | 2.5 | 1 | 1 | 1.5 | 5 | 1.3333 | 1.6667 | 1.3333 | 2 | 2
375 | 14.1667 | 9.1667 | 17.5 | 28.8333 | 37 | 50.6667 | 58.1667 | 65 | 74.6667 | 86.6667 | 98 | 104.5 | 113.5 | 121 | 2.5 | 1.6667 | 2.5 | 2.5 | 2 | 3 | 1.3333 | 2 | 3 | 5 | 1.3333 | 2 | 2.5 | 2 | 1.6667 | 2 | 1.6667 | 3 | 6 | 3 | 1.5 | 2 | 3 | 1 | 1.3333 | 1.5 | 1.5 | 2.5 | 1.5 | 4 | 1.6667 | 2.5 | 4 | 4 | 1.5 | 2.5 | 5 | 1.3333 | 4 | 1 | 1 | 2 | 1.5 | 2 | 2 | 3 | 1 | 3 | 1.5 | 3 | 1 | 2
376 | 20.6667 | 14 | 25.3333 | 35.1667 | 41.8333 | 48.1667 | 57.6667 | 70.6667 | 80.5 | 91.5 | 99.5 | 107.6667 | 122.1667 | 129.6667 | 2 | 3 | 6 | 3 | 5 | 1.6667 | 3 | 1.6667 | 1.6667 | 4 | 2.5 | 1.6667 | 2.5 | 1.5 | 1 | 1.6667 | 2 | 1.3333 | 2 | 1 | 1.5 | 4 | 2 | 2 | 2.5 | 5 | 3 | 2.5 | 3 | 1.3333 | 4 | 1.5 | 1 | 6 | 2 | 2 | 1.3333 | 1 | 1.6667 | 4 | 2.5 | 3 | 1 | 1.6667 | 3 | 5 | 4 | 2.5 | 1.6667 | 1.6667 | 1.6667 | 2.5
377 | 13.8333 | 9.3333 | 18.8333 | 29.6667 | 46.6667 | 53.5 | 66.5 | 75.8333 | 88.3333 | 95.8333 | 104.3333 | 112.1667 | 120.1667 | 135.5 | 1.3333 | 4 | 2.5 | 1.5 | 2.5 | 2 | 3 | 2 | 1 | 6 | 1.3333 | 2.5 | 5 | 4 | 5 | 3 | 2 | 2.5 | 1.3333 | 1 | 1 | 4 | 5 | 3 | 1.3333 | 2 | 1 | 5 | 4 | 3 | 4 | 1.5 | 1.5 | 3 | 1.3333 | 1.6667 | 1 | 2 | 3 | 2.5 | 2.5 | 1 | 1.3333 | 3 | 1 | 3 | 3 | 1 | 6 | 2 | 1.3333 | 6
378 | 21.3333 | 16.3333 | 25.8333 | 34.3333 | 41.8333 | 53.1667 | 64.6667 | 75 | 87.5 | 94.1667 | 103.6667 | 112.5 | 120.8333 | 133.3333 | 4 | 1.3333 | 6 | 5 | 3 | 2 | 3 | 1.5 | 1 | 2.5 | 3 | 2 | 2 | 1.5 | 2.5 | 1.5 | 1.3333 | 4 | 3 | 3 | 2 | 1 | 6 | 2.5 | 6 | 2 | 1 | 1.3333 | 3 | 6 | 2 | 1.5 | 2 | 1.3333 | 2 | 1.3333 | 2 | 2 | 2.5 | 3 | 1 | 5 | 1.5 | 1.3333 | 3 | 1.6667 | 2 | 1.6667 | 2.5 | 6 | 1 | 3
379 | 21 | 15.5 | 27.3333 | 36.8333 | 50.3333 | 59.8333 | 70.8333 | 78 | 85.6667 | 92 | 99 | 111.5 | 118.1667 | 131.6667 | 2.5 | 5 | 4 | 4 | 2.5 | 3 | 5 | 1.3333 | 5 | 2.5 | 1 | 1 | 2 | 6 | 4 | 1.5 | 3 | 2 | 2.5 | 2 | 1.3333 | 5 | 1.6667 | 3 | 2.5 | 1 | 1.6667 | 2 | 1.6667 | 1 | 1 | 4 | 2 | 1 | 1.3333 | 2 | 2 | 2 | 1 | 2 | 2 | 4 | 2.5 | 4 | 2 | 1.6667 | 1.5 | 1.5 | 5 | 1.5 | 3 | 4
380 | 14.3333 | 11.1667 | 20.3333 | 30.6667 | 49.6667 | 65.6667 | 75.8333 | 86.8333 | 99.3333 | 111.8333 | 123.3333 | 134.3333 | 150.8333 | 157.8333 | 1.5 | 4 | 1.6667 | 4 | 1.5 | 1.6667 | 3 | 3 | 2 | 1.3333 | 6 | 1 | 6 | 6 | 3 | 4 | 2 | 6 | 2 | 6 | 1.6667 | 5 | 2.5 | 1 | 3 | 3 | 4 | 1 | 2.5 | 2 | 6 | 2 | 3 | 3 | 5 | 1.5 | 5 | 3 | 1.5 | 2 | 2 | 4 | 3 | 2 | 2.5 | 4 | 5 | 5 | 1.5 | 1.6667 | 2.5 | 1.3333
381 | 15.5 | 8 | 19.5 | 32.8333 | 42.8333 | 50.8333 | 62.1667 | 67.8333 | 82.1667 | 95.8333 | 106.5 | 111.8333 | 123 | 136.1667 | 1.6667 | 1.3333 | 3 | 2 | 5 | 2.5 | 2.5 | 1.5 | 6 | 4 | 1.3333 | 2 | 2 | 5 | 1.5 | 1.5 | 1 | 2 | 4 | 1 | 2 | 1.3333 | 5 | 3 | 1 | 1.3333 | 2 | 1.3333 | 6 | 6 | 1 | 1.3333 | 3 | 4 | 5 | 1.6667 | 2 | 1.3333 | 1.3333 | 6 | 2 | 1 | 1.3333 | 1 | 1.5 | 5 | 1.6667 | 3 | 1.6667 | 5 | 1.5 | 5
382 | 18 | 10 | 23 | 33.3333 | 39.1667 | 49.1667 | 63.5 | 71 | 78 | 95.5 | 103 | 119.5 | 131.8333 | 140.3333 | 2.5 | 4 | 1.5 | 2 | 6 | 2 | 2.5 | 2.5 | 1 | 3 | 1.3333 | 5 | 1 | 2 | 1.5 | 1.3333 | 4 | 1 | 3 | 2 | 4 | 4 | 1.3333 | 5 | 2 | 1 | 2.5 | 2 | 2 | 2 | 2 | 1 | 6 | 4 | 1.5 | 6 | 1.5 | 2 | 1.5 | 2.5 | 6 | 6 | 2.5 | 2 | 1 | 6 | 1.3333 | 4 | 2.5 | 3 | 1 | 2
383 | 12 | 9 | 17.5 | 26.6667 | 36 | 53 | 64.5 | 72.6667 | 88.6667 | 96 | 104 | 111.3333 | 124.3333 | 131.6667 | 1.5 | 4 | 1.5 | 2 | 2 | 1 | 3 | 2.5 | 1 | 1.6667 | 4 | 2.5 | 3 | 3 | 1.3333 | 2 | 5 | 3 | 5 | 4 | 2 | 1.5 | 6 | 2 | 2 | 1.5 | 1.6667 | 3 | 3 | 6 | 2 | 5 | 1.5 | 1.5 | 1.3333 | 3 | 1.6667 | 2.5 | 2.5 | 1.3333 | 2 | 2 | 1.3333 | 2 | 3 | 5 | 2 | 3 | 1.3333 | 1.3333 | 1.6667 | 3
384 | 19 | 10 | 30 | 47.3333 | 58.6667 | 71 | 79.3333 | 93.6667 | 112.6667 | 120.5 | 129.5 | 142.1667 | 151.1667 | 159.8333 | 3 | 1.5 | 1.5 | 4 | 3 | 6 | 5 | 6 | 6 | 4 | 6 | 1.3333 | 2 | 1.3333 | 5 | 3 | 1.3333 | 5 | 1 | 5 | 1.3333 | 1 | 3 | 3 | 4 | 6 | 3 | 1.3333 | 5 | 2 | 6 | 6 | 1.5 | 3 | 1.3333 | 2 | 5 | 2 | 1 | 1 | 4 | 1.3333 | 1.3333 | 6 | 2 | 5 | 1 | 1 | 3 | 1 | 1.6667 | 3
385 | 11.8333 | 7.5 | 19.1667 | 34.6667 | 46.8333 | 58.3333 | 75.3333 | 89.3333 | 97.8333 | 114.3333 | 123.3333 | 135.8333 | 150.6667 | 158.1667 | 1.6667 | 2.5 | 2 | 1.3333 | 1.3333 | 3 | 1.3333 | 6 | 6 | 5 | 1.5 | 3 | 5 | 1.6667 | 4 | 1.5 | 4 | 3 | 2 | 2.5 | 3 | 3 | 5 | 6 | 2 | 3 | 6 | 3 | 3 | 1 | 3 | 1.5 | 5 | 4 | 6 | 1.5 | 4 | 1.6667 | 2 | 1.3333 | 1.5 | 4 | 3 | 4 | 6 | 1.3333 | 5 | 2.5 | 2 | 1 | 2 | 2.5
386 | 15.1667 | 10.8333 | 19.1667 | 33.1667 | 43.1667 | 55.6667 | 68.8333 | 79.3333 | 92.3333 | 102.5 | 121.5 | 134.5 | 143.5 | 162.5 | 1.5 | 5 | 1.3333 | 3 | 1.3333 | 3 | 1 | 3 | 5 | 1 | 2 | 6 | 2 | 3 | 2 | 3 | 2 | 1.5 | 3 | 6 | 1.5 | 5 | 5 | 1.6667 | 4 | 1.5 | 3 | 2 | 3 | 4 | 3 | 3 | 3 | 4 | 1.6667 | 1.5 | 6 | 6 | 3 | 4 | 6 | 2.5 | 2.5 | 2 | 4 | 1 | 2 | 2 | 5 | 4 | 5 | 5
387 | 12 | 8 | 15.3333 | 23.6667 | 31 | 43 | 51.5 | 60.8333 | 68.5 | 77 | 93 | 101.5 | 117.6667 | 130.6667 | 2 | 1.3333 | 1.6667 | 3 | 1 | 3 | 1.3333 | 2 | 1.6667 | 3 | 2 | 1.6667 | 1.6667 | 2 | 2 | 1.6667 | 1 | 1 | 5 | 5 | 1.6667 | 1.5 | 4 | 1.3333 | 1.3333 | 1.6667 | 1.3333 | 5 | 2 | 3 | 1.3333 | 1.3333 | 1.5 | 2 | 2 | 3 | 4 | 5 | 4 | 3 | 1.6667 | 2.5 | 3 | 1.3333 | 6 | 1.6667 | 6 | 2.5 | 2 | 2 | 4 | 5
388 | 17 | 10 | 23.5 | 31.5 | 48.5 | 55.6667 | 66.8333 | 76.5 | 87.1667 | 99.3333 | 113.3333 | 129.8333 | 139.3333 | 148.1667 | 2 | 3 | 2 | 3 | 3 | 4 | 2.5 | 4 | 1.3333 | 3 | 2 | 1.6667 | 3 | 3 | 5 | 6 | 1.5 | 1.3333 | 3 | 1.3333 | 3 | 1.5 | 5 | 1.6667 | 1 | 5 | 2 | 1.6667 | 2 | 5 | 1.6667 | 2 | 1.6667 | 6 | 1.5 | 3 | 3 | 3 | 2 | 6 | 6 | 3 | 1.5 | 6 | 2 | 2.5 | 2 | 3 | 3 | 1.3333 | 2.5 | 2
389 | 10 | 5.5 | 19 | 28 | 40 | 49.8333 | 64.3333 | 74.3333 | 81.5 | 93 | 99.5 | 112.5 | 122.3333 | 133.5 | 2 | 1.5 | 1 | 1 | 1.5 | 3 | 5 | 4 | 3 | 3 | 2 | 1 | 6 | 3 | 1 | 2 | 3 | 1.3333 | 3 | 2.5 | 2.5 | 4 | 5 | 3 | 1 | 1.5 | 1.5 | 6 | 1.3333 | 2.5 | 1.6667 | 1.6667 | 4 | 3 | 2.5 | 2 | 1.3333 | 1.6667 | 1 | 2.5 | 1 | 5 | 3 | 4 | 1.3333 | 2 | 2.5 | 4 | 3 | 1.6667 | 4 | 2.5
390 | 18.1667 | 10.6667 | 27.1667 | 40.6667 | 51.6667 | 58 | 71.3333 | 80.3333 | 91.3333 | 103.6667 | 112.8333 | 120.3333 | 129.1667 | 136.8333 | 5 | 1.3333 | 1.3333 | 3 | 5 | 2.5 | 5 | 4 | 5 | 5 | 1.5 | 2 | 5 | 2 | 2 | 2 | 1.3333 | 1.3333 | 2 | 1.6667 | 3 | 1.3333 | 6 | 3 | 2.5 | 3 | 1 | 2.5 | 3 | 2.5 | 2.5 | 3 | 4 | 1.3333 | 6 | 1 | 3 | 1.6667 | 3 | 1.5 | 1 | 2.5 | 3 | 1 | 1 | 1.3333 | 5 | 1.5 | 1.5 | 2.5 | 2 | 1.6667
391 | 11.1667 | 8.5 | 15.1667 | 27 | 40 | 53 | 59.1667 | 74.1667 | 87.1667 | 98.5 | 113 | 132 | 141 | 147.3333 | 1.6667 | 1.3333 | 3 | 2.5 | 1.3333 | 1.3333 | 2 | 2 | 3 | 2.5 | 1.3333 | 5 | 2 | 2 | 5 | 4 | 6 | 2 | 2 | 3 | 1.3333 | 1.3333 | 1.5 | 2 | 2 | 5 | 6 | 2 | 3 | 5 | 3 | 2 | 1.6667 | 3 | 1.6667 | 5 | 5 | 3 | 4 | 2.5 | 6 | 3 | 6 | 4 | 1 | 2 | 3 | 3 | 1 | 1.5 | 2.5 | 1.3333
392 | 16.5 | 11.5 | 21 | 36.5 | 43.5 | 57 | 62.3333 | 76.3333 | 86.8333 | 100.5 | 107.8333 | 117.3333 | 132.8333 | 145.5 | 3 | 6 | 1.5 | 1 | 3 | 2 | 3 | 1.5 | 6 | 1.5 | 2 | 6 | 2.5 | 1 | 2 | 1.5 | 4 | 5 | 2 | 2.5 | 1 | 1 | 2 | 1.3333 | 5 | 4 | 3 | 2 | 3 | 3 | 2.5 | 2 | 1.6667 | 6 | 3 | 3 | 1.5 | 1.3333 | 3 | 1.5 | 5 | 2 | 1.5 | 1 | 2 | 2.5 | 5 | 6 | 4 | 5 | 2 | 1.6667
393 | 15 | 10.6667 | 19 | 35.1667 | 44.5 | 57.1667 | 65 | 81.5 | 90.1667 | 109.1667 | 119.3333 | 130.3333 | 142.8333 | 159.3333 | 2 | 2 | 5 | 1.6667 | 3 | 1.3333 | 2 | 2 | 6 | 1.6667 | 6 | 2.5 | 6 | 1.3333 | 1 | 1 | 3 | 2 | 1.6667 | 6 | 1.3333 | 1 | 3 | 2.5 | 4 | 5 | 5 | 2.5 | 3 | 1 | 1.6667 | 3 | 5 | 5 | 5 | 4 | 1.6667 | 5 | 1 | 2.5 | 1.6667 | 1.3333 | 4 | 4 | 5 | 3 | 3 | 1.5 | 6 | 2 | 2.5 | 6
394 | 14.8333 | 10.1667 | 21.3333 | 34 | 39.6667 | 48.1667 | 57.1667 | 76.1667 | 90.1667 | 99.3333 | 107.3333 | 122.6667 | 129.3333 | 137.1667 | 1 | 2.5 | 1.6667 | 5 | 1.6667 | 3 | 4 | 2.5 | 4 | 1.6667 | 5 | 2 | 1.3333 | 2 | 1.3333 | 1 | 2 | 3 | 1.5 | 2 | 1 | 5 | 1.6667 | 1.3333 | 5 | 5 | 5 | 4 | 1 | 5 | 2 | 6 | 2 | 3 | 2.5 | 1.6667 | 4 | 1 | 1.3333 | 1.6667 | 1.3333 | 6 | 6 | 2 | 1 | 1.6667 | 3 | 1 | 1.3333 | 2 | 3 | 1.5
395 | 14.5 | 11 | 21 | 32.3333 | 42 | 51.1667 | 60 | 67.8333 | 79.3333 | 87 | 99.3333 | 109.5 | 118.1667 | 128.8333 | 3 | 5 | 2 | 1 | 1.5 | 2 | 2.5 | 4 | 5 | 4 | 1 | 1.3333 | 4 | 1.6667 | 2 | 2 | 2.5 | 2 | 3 | 1.6667 | 1 | 1.3333 | 5 | 1.5 | 3 | 2 | 1.5 | 1.3333 | 4 | 1 | 4 | 2.5 | 2 | 3 | 1.6667 | 1 | 1.6667 | 1.6667 | 3 | 6 | 2.5 | 1.6667 | 3 | 3 | 2 | 2 | 3 | 1.6667 | 1.6667 | 1 | 6 | 2
396 | 19.3333 | 11.3333 | 26.3333 | 43.3333 | 59.3333 | 67.6667 | 78.8333 | 91.3333 | 107 | 123 | 131.5 | 147 | 161 | 166.6667 | 1.3333 | 2 | 3 | 5 | 5 | 3 | 3 | 4 | 3 | 5 | 3 | 6 | 5 | 2 | 3 | 6 | 2 | 1 | 4 | 1.3333 | 2.5 | 6 | 1.3333 | 1.3333 | 6 | 1 | 3 | 2.5 | 1.6667 | 3 | 6 | 5 | 5 | 1 | 4 | 6 | 2 | 2 | 2 | 2.5 | 2 | 6 | 1.5 | 6 | 2.5 | 2.5 | 6 | 3 | 1.5 | 1.3333 | 1.5 | 1.3333
397 | 17.3333 | 11.8333 | 21.1667 | 33.1667 | 41.3333 | 52.8333 | 63.1667 | 75.6667 | 84 | 89.6667 | 98.6667 | 114.6667 | 124.6667 | 131.1667 | 1.5 | 4 | 5 | 1.3333 | 3 | 2.5 | 1.3333 | 2.5 | 4 | 2 | 4 | 2 | 2.5 | 2 | 2 | 1.6667 | 5 | 3 | 2.5 | 1 | 3 | 1.3333 | 2 | 4 | 3 | 1.5 | 3 | 5 | 1.6667 | 1.6667 | 3 | 2 | 1.3333 | 1 | 1.6667 | 1.6667 | 3 | 1.5 | 3 | 1.5 | 2 | 6 | 5 | 3 | 2 | 3 | 3 | 2 | 1.5 | 1 | 2.5 | 1.5
398 | 16.6667 | 12.6667 | 19.8333 | 25.6667 | 40.6667 | 48.3333 | 58.3333 | 66.3333 | 79.3333 | 86.3333 | 98.8333 | 109.1667 | 117.5 | 127 | 1 | 1.6667 | 6 | 4 | 1 | 3 | 1.5 | 1.6667 | 1 | 1.3333 | 1.5 | 2 | 5 | 2.5 | 5 | 2.5 | 2 | 1.6667 | 3 | 1 | 1 | 6 | 2 | 1 | 2 | 2.5 | 1.5 | 2 | 1.6667 | 6 | 4 | 1.3333 | 1.6667 | 1.3333 | 3 | 1 | 3 | 3 | 2.5 | 4 | 1.3333 | 4 | 3 | 2 | 1.6667 | 2 | 3 | 1.6667 | 1.5 | 3 | 2 | 3
399 | 15.8333 | 8.5 | 21.3333 | 31.3333 | 38.5 | 50 | 57.6667 | 66.1667 | 82.1667 | 97.6667 | 107.1667 | 119.1667 | 134.1667 | 146.8333 | 2.5 | 2.5 | 1.5 | 2 | 6 | 1.3333 | 1.5 | 4 | 1.3333 | 1.6667 | 2 | 5 | 1.5 | 1.6667 | 3 | 1 | 3 | 2.5 | 1 | 5 | 1.6667 | 2 | 3 | 1 | 3 | 1 | 2.5 | 2 | 6 | 6 | 2 | 2 | 4 | 4 | 1.5 | 6 | 1.5 | 5 | 1.5 | 1.5 | 4 | 2.5 | 1.5 | 4 | 6 | 5 | 2 | 2 | 2 | 1.6667 | 3 | 6
400 | 21.8333 | 16.3333 | 28.8333 | 38.3333 | 49 | 57.3333 | 65.5 | 75.1667 | 89.1667 | 99.6667 | 109.1667 | 122.5 | 132.8333 | 141 | 6 | 1.3333 | 6 | 3 | 4 | 1.5 | 6 | 1 | 2 | 1 | 1.5 | 5 | 3 | 1.6667 | 4 | 2 | 2 | 1.6667 | 3 | 1.6667 | 1.6667 | 3 | 1.5 | 2 | 1.3333 | 1.3333 | 5 | 2 | 3 | 1 | 4 | 6 | 2.5 | 1.3333 | 5 | 1.6667 | 4 | 2 | 1.5 | 2 | 6 | 1.6667 | 4 | 1.6667 | 2 | 1.3333 | 1 | 6 | 1 | 2.5 | 3 | 1.6667
401 | 21.6667 | 10.6667 | 27.6667 | 34 | 47 | 60.3333 | 71.3333 | 83.8333 | 91 | 97.3333 | 107.3333 | 115.5 | 124 | 138 | 1.6667 | 3 | 3 | 3 | 6 | 5 | 4 | 2 | 2.5 | 1.3333 | 1 | 1.5 | 2 | 4 | 4 | 3 | 2 | 4 | 6 | 1.3333 | 2 | 5 | 1 | 3 | 2 | 1.5 | 6 | 3 | 3 | 1 | 1.6667 | 1.5 | 2 | 1 | 1.3333 | 2 | 3 | 2.5 | 3 | 1.5 | 2 | 1.6667 | 3 | 1.5 | 2.5 | 1.6667 | 1.3333 | 3 | 6 | 1 | 3 | 4
402 | 14 | 9.5 | 21.5 | 32 | 47 | 56.1667 | 75.1667 | 82.1667 | 98.1667 | 112.5 | 124 | 137.5 | 150.5 | 156.1667 | 1 | 5 | 1.5 | 2 | 1.5 | 3 | 6 | 1.5 | 3 | 3 | 1.5 | 3 | 4 | 5 | 3 | 3 | 1.6667 | 3 | 2.5 | 2 | 6 | 3 | 6 | 4 | 1.3333 | 1.6667 | 3 | 1 | 3 | 3 | 6 | 4 | 3 | 4 | 6 | 1.3333 | 4 | 2 | 1.5 | 4 | 4 | 2 | 2.5 | 5 | 4 | 3 | 3 | 3 | 1 | 1.3333 | 2 | 1.3333
403 | 18.8333 | 14.3333 | 26.3333 | 35.3333 | 49.3333 | 61.8333 | 74.8333 | 83.1667 | 98.1667 | 106.1667 | 118.6667 | 133.1667 | 149.6667 | 158.1667 | 1.3333 | 6 | 1 | 6 | 2 | 2.5 | 5 | 2.5 | 2.5 | 1.5 | 1 | 4 | 1 | 5 | 2 | 6 | 4 | 2.5 | 4 | 2 | 6 | 3 | 2 | 2 | 2 | 3 | 1.3333 | 2 | 3 | 5 | 3 | 4 | 1 | 1 | 3 | 3 | 3 | 2.5 | 4 | 3 | 1.5 | 1 | 6 | 6 | 6 | 2.5 | 5 | 3 | 3 | 1.5 | 2 | 2
404 | 15 | 9 | 26 | 40 | 49.8333 | 60.5 | 76 | 84 | 94.1667 | 108.8333 | 119.5 | 129.1667 | 139.5 | 149.5 | 1.6667 | 3 | 3 | 1.3333 | 1 | 5 | 6 | 5 | 1 | 2 | 6 | 5 | 2.5 | 4 | 1.3333 | 2 | 4 | 1.6667 | 2 | 3 | 2 | 5 | 6 | 2.5 | 1 | 1 | 3 | 3 | 1.3333 | 6 | 1.5 | 1.3333 | 5 | 2 | 1.6667 | 6 | 4 | 2 | 1.6667 | 3 | 3 | 2 | 1.6667 | 3 | 6 | 1.3333 | 1.6667 | 1.3333 | 2 | 2 | 3 | 3
405 | 15 | 10.6667 | 18 | 25 | 34.1667 | 43.5 | 53.1667 | 65.6667 | 75.6667 | 88.6667 | 97.8333 | 109 | 119 | 127.3333 | 1.6667 | 1.5 | 1.5 | 6 | 3 | 1.3333 | 1.3333 | 1.6667 | 2 | 1.5 | 2.5 | 1 | 2 | 1.6667 | 2.5 | 3 | 1 | 3 | 4 | 1.3333 | 1.6667 | 2 | 3 | 3 | 2 | 4 | 5 | 1.5 | 1.5 | 5 | 1.5 | 2 | 3 | 2 | 6 | 2 | 2.5 | 3 | 1.6667 | 2 | 2.5 | 1.6667 | 1 | 6 | 2 | 5 | 1.6667 | 1.3333 | 3 | 1 | 1.3333 | 3
406 | 22 | 15 | 32 | 39 | 48.5 | 59.3333 | 76.3333 | 85.6667 | 107.6667 | 119.6667 | 130.6667 | 142.1667 | 150.3333 | 158 | 1 | 6 | 5 | 3 | 5 | 2 | 4 | 6 | 2 | 2 | 1.5 | 1.5 | 3 | 3 | 1.5 | 2 | 2.5 | 3 | 1.3333 | 4 | 2 | 5 | 5 | 5 | 4 | 1.3333 | 2 | 2 | 6 | 6 | 5 | 5 | 3 | 4 | 3 | 2 | 2 | 2.5 | 2.5 | 4 | 4 | 1.5 | 2 | 4 | 1 | 3 | 1.6667 | 2.5 | 2 | 2 | 2 | 1.6667
407 | 18.6667 | 12.6667 | 22.6667 | 28.8333 | 38.5 | 54.5 | 71.5 | 83 | 94 | 101.5 | 108.6667 | 123.6667 | 139.6667 | 152.5 | 5 | 3 | 1.6667 | 3 | 3 | 3 | 2.5 | 1.5 | 1 | 1.6667 | 2 | 1.5 | 4 | 3 | 1.3333 | 1.3333 | 1 | 6 | 6 | 3 | 5 | 6 | 3 | 3 | 5 | 3 | 2 | 1.5 | 2 | 4 | 3 | 2 | 1.6667 | 1.5 | 3 | 1.3333 | 1.5 | 1.6667 | 3 | 1 | 3 | 5 | 6 | 1 | 6 | 1 | 5 | 4 | 1.5 | 5 | 5 | 1.3333
408 | 19 | 11 | 22.5 | 34 | 46.1667 | 57.1667 | 69.6667 | 79 | 93.6667 | 106.3333 | 112 | 121.8333 | 134.3333 | 142.3333 | 1.6667 | 1.3333 | 5 | 3 | 3 | 5 | 2 | 1.5 | 1 | 6 | 2.5 | 2 | 1.6667 | 2.5 | 3 | 5 | 2 | 3 | 3 | 3 | 2.5 | 4 | 4 | 2 | 1.5 | 4 | 2.5 | 1.3333 | 3 | 5 | 1.6667 | 5 | 1.6667 | 3 | 6 | 2 | 1 | 1.6667 | 1.5 | 1.5 | 4 | 2.5 | 1.3333 | 2 | 5 | 2.5 | 3 | 2 | 3 | 1.3333 | 2 | 1.6667
409 | 10.8333 | 8.3333 | 16.8333 | 24.3333 | 30.8333 | 48.1667 | 59.1667 | 66.8333 | 79.8333 | 92.3333 | 106.3333 | 118.3333 | 129 | 140 | 1.3333 | 3 | 1.5 | 2.5 | 1 | 1.5 | 5 | 1 | 1 | 1.5 | 2 | 3 | 1.6667 | 2 | 1.3333 | 1.5 | 5 | 6 | 1.3333 | 5 | 3 | 1 | 2 | 5 | 1.3333 | 3 | 2 | 1.3333 | 5 | 1 | 4 | 3 | 1.5 | 2 | 3 | 6 | 3 | 4 | 5 | 2 | 3 | 4 | 2 | 3 | 1.6667 | 6 | 2 | 1 | 3 | 2 | 3 | 3
410 | 17.1667 | 12.8333 | 22.1667 | 33.1667 | 43.3333 | 59.3333 | 73 | 79.8333 | 90.3333 | 103 | 114.3333 | 128.8333 | 140.5 | 150 | 4 | 2.5 | 1.3333 | 5 | 1.3333 | 3 | 2 | 3 | 4 | 1 | 3 | 3 | 1.6667 | 1.5 | 3 | 4 | 5 | 6 | 2 | 3 | 6 | 4 | 1.6667 | 2 | 1.5 | 2 | 2 | 1.3333 | 1.5 | 1 | 6 | 2 | 4 | 3 | 1.6667 | 4 | 1 | 6 | 1.3333 | 3 | 4 | 6 | 1.5 | 3 | 2 | 5 | 1.6667 | 3 | 5 | 1 | 2 | 1.5
411 | 18.6667 | 12.6667 | 24.3333 | 35.3333 | 49.3333 | 64 | 78 | 89.5 | 97.1667 | 104 | 112 | 123.6667 | 137.6667 | 144.5 | 1.6667 | 6 | 3 | 2 | 3 | 3 | 1.6667 | 4 | 3 | 1.6667 | 5 | 1.3333 | 6 | 4 | 2.5 | 1.5 | 5 | 4 | 1.6667 | 4 | 1 | 4 | 5 | 4 | 4 | 1 | 1.5 | 5 | 1.6667 | 3 | 1.3333 | 1.6667 | 1.3333 | 1.6667 | 2.5 | 1.3333 | 1 | 4 | 1.5 | 1.5 | 2 | 1.6667 | 6 | 2 | 5 | 4 | 4 | 1 | 1.5 | 2 | 1.3333 | 2
412 | 21 | 14 | 24.5 | 34.8333 | 44.5 | 52.5 | 65.5 | 74.6667 | 87.6667 | 95.6667 | 105.5 | 115.1667 | 127.1667 | 135.6667 | 6 | 5 | 1 | 2 | 1 | 6 | 2.5 | 1 | 1.6667 | 2 | 5 | 1.6667 | 2 | 2 | 1.6667 | 4 | 1 | 2.5 | 2.5 | 2 | 2 | 3 | 2 | 6 | 1.6667 | 1 | 1.5 | 5 | 4 | 6 | 1.5 | 1.5 | 2 | 1 | 2.5 | 2.5 | 3 | 1.5 | 1.3333 | 4 | 3 | 2 | 1.6667 | 3 | 4 | 4 | 3 | 1 | 1.3333 | 2.5 | 3 | 1.6667
413 | 13.5 | 9.5 | 17.5 | 25.3333 | 38.6667 | 55.6667 | 62.1667 | 73.1667 | 81 | 89.5 | 97 | 115.5 | 123.5 | 133.1667 | 2 | 4 | 2 | 1.5 | 1.5 | 2.5 | 2 | 2 | 2 | 1.6667 | 2.5 | 1.6667 | 1.3333 | 6 | 3 | 3 | 5 | 2 | 5 | 5 | 1.3333 | 1.6667 | 2 | 1.5 | 2 | 2 | 3 | 4 | 1.5 | 3 | 2 | 1.3333 | 5 | 1 | 1 | 1.5 | 2 | 2 | 2 | 1.5 | 1.5 | 6 | 5 | 6 | 3 | 1.3333 | 1.6667 | 2 | 3 | 1.6667 | 2 | 3
414 | 18.8333 | 13.8333 | 23.5 | 38 | 45.5 | 53.3333 | 69.6667 | 75.8333 | 89.8333 | 103.1667 | 111.5 | 135.5 | 146.1667 | 156.1667 | 6 | 1.3333 | 1.5 | 5 | 3 | 2 | 3 | 1.6667 | 2.5 | 5 | 6 | 1 | 2 | 1.5 | 3 | 1 | 1.3333 | 4 | 1.5 | 1 | 5 | 6 | 1.3333 | 4 | 1.3333 | 2 | 1.3333 | 1.5 | 4 | 1 | 6 | 3 | 5 | 1.6667 | 5 | 1.6667 | 1.3333 | 3 | 2.5 | 1.5 | 6 | 6 | 6 | 6 | 3 | 1 | 5 | 1.6667 | 2 | 3 | 2.5 | 2.5
415 | 24 | 18 | 30 | 38 | 51 | 65.3333 | 74.8333 | 91.8333 | 107.8333 | 118.8333 | 130.3333 | 140.3333 | 149.8333 | 157.8333 | 1 | 6 | 6 | 5 | 1 | 5 | 3 | 3 | 1 | 2 | 2 | 3 | 2.5 | 2 | 2.5 | 6 | 6 | 1.3333 | 3 | 4 | 2.5 | 5 | 1 | 1 | 3 | 4 | 6 | 4 | 2 | 3 | 5 | 6 | 3 | 2 | 4 | 2 | 4 | 2 | 3 | 2.5 | 4 | 2 | 1 | 3 | 2 | 2 | 2.5 | 3 | 4 | 2 | 1 | 1
416 | 12.8333 | 6.8333 | 17.8333 | 33.1667 | 39.1667 | 50 | 62 | 79 | 88 | 103.5 | 110.5 | 118.5 | 135.1667 | 146.8333 | 2.5 | 1 | 2 | 1.3333 | 4 | 2 | 3 | 2 | 6 | 2 | 6 | 1.3333 | 1.3333 | 1.3333 | 1.3333 | 2 | 1.3333 | 6 | 1.5 | 2 | 2 | 6 | 2 | 2 | 6 | 2 | 3 | 6 | 2 | 2 | 2 | 3 | 2.5 | 6 | 4 | 3 | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 2 | 1.6667 | 6 | 6 | 3 | 1.6667 | 3 | 3 | 4
417 | 17.8333 | 14.5 | 21.8333 | 33.8333 | 43 | 55 | 64.3333 | 72.8333 | 86.8333 | 92 | 101.8333 | 113 | 122.1667 | 132.8333 | 2 | 5 | 1.5 | 6 | 2 | 1.3333 | 3 | 1 | 1.3333 | 6 | 3 | 1.6667 | 1.5 | 5 | 1 | 1.6667 | 4 | 3 | 2 | 3 | 2.5 | 4 | 1.3333 | 1.5 | 3 | 1.5 | 2 | 2 | 2 | 5 | 6 | 1 | 1.3333 | 1.5 | 1 | 1.3333 | 6 | 1.3333 | 1.5 | 1 | 5 | 1.6667 | 2 | 2.5 | 2.5 | 1 | 4 | 1.6667 | 6 | 2 | 1.6667 | 1
418 | 19.1667 | 11.6667 | 24.6667 | 33.6667 | 51.1667 | 60.3333 | 78 | 89 | 99 | 110.3333 | 122.6667 | 130.5 | 142.6667 | 154.1667 | 4 | 3 | 3 | 1.6667 | 5 | 2.5 | 3 | 2.5 | 2 | 4 | 1.6667 | 1.3333 | 6 | 2.5 | 3 | 6 | 1.5 | 2 | 1.6667 | 4 | 6 | 4 | 1.6667 | 6 | 5 | 1.6667 | 3 | 1.3333 | 5 | 1 | 3 | 1 | 2 | 1.3333 | 3 | 5 | 1.3333 | 4 | 2 | 5 | 1.5 | 1.3333 | 2 | 3 | 3 | 6 | 1.6667 | 1.5 | 1.5 | 5 | 4 | 1
419 | 17.5 | 14.1667 | 20.5 | 27.8333 | 37.3333 | 50.3333 | 56.6667 | 71.3333 | 86.3333 | 98.5 | 104.1667 | 119.1667 | 131.1667 | 141.6667 | 6 | 2.5 | 4 | 1.6667 | 2 | 1.3333 | 1.5 | 1.5 | 3 | 1.3333 | 1 | 2 | 3 | 1 | 4 | 1.5 | 1 | 5 | 3 | 4 | 1 | 1.3333 | 2.5 | 1.5 | 5 | 1.6667 | 2 | 6 | 2 | 3 | 6 | 4 | 2 | 1.6667 | 2.5 | 6 | 1.3333 | 1 | 1.3333 | 2 | 5 | 1 | 4 | 5 | 1 | 4 | 1 | 6 | 2.5 | 1.5 | 1.5 | 5
420 | 13.1667 | 7.1667 | 20.5 | 29.3333 | 43.3333 | 54.8333 | 71.8333 | 86.8333 | 95.1667 | 111.5 | 119.1667 | 128.8333 | 140.8333 | 151.8333 | 1.3333 | 1.3333 | 1.5 | 3 | 5 | 1 | 6 | 1.3333 | 1.5 | 1.3333 | 3 | 3 | 3 | 3 | 6 | 2 | 6 | 2 | 2 | 1.5 | 2 | 4 | 6 | 5 | 4 | 4 | 5 | 2 | 3 | 2 | 1.6667 | 1.6667 | 6 | 5 | 1.3333 | 4 | 1.6667 | 2.5 | 2 | 1.5 | 1 | 4 | 3 | 1.6667 | 3 | 3 | 3 | 3 | 1 | 2.5 | 1.5 | 6
421 | 15 | 8 | 21.3333 | 33.5 | 45.3333 | 52.8333 | 67.8333 | 79.3333 | 92.3333 | 108.8333 | 120.3333 | 129.5 | 136.8333 | 149.8333 | 2.5 | 1 | 2.5 | 2 | 2 | 5 | 1.3333 | 5 | 3 | 5 | 2.5 | 1.6667 | 5 | 2.5 | 1.3333 | 3 | 1.5 | 2.5 | 2 | 1.5 | 4 | 5 | 3 | 3 | 4 | 3 | 3 | 1.5 | 6 | 2 | 2 | 3 | 6 | 3 | 6 | 1.5 | 1 | 2 | 6 | 2.5 | 1 | 5 | 1.5 | 1.6667 | 2 | 2 | 2 | 1.3333 | 2.5 | 6 | 3 | 1.5
422 | 15.5 | 12 | 20.5 | 29.1667 | 42.1667 | 58.3333 | 75.3333 | 84.8333 | 99.6667 | 109.1667 | 118.6667 | 129.5 | 142.5 | 154 | 3 | 2 | 4 | 3 | 2 | 1.5 | 3 | 2 | 1.3333 | 1.6667 | 4 | 1.6667 | 4 | 3 | 4 | 2 | 2.5 | 1.6667 | 6 | 6 | 5 | 3 | 4 | 5 | 1.5 | 1 | 3 | 4 | 5 | 6 | 1.3333 | 2.5 | 1 | 4 | 3 | 1.5 | 3 | 3 | 2 | 1.5 | 1.3333 | 3 | 2.5 | 4 | 6 | 3 | 2 | 2 | 6 | 1.5 | 1.5 | 2.5
423 | 15 | 10.5 | 20.6667 | 29 | 40.3333 | 47 | 60.5 | 74.5 | 87.3333 | 98.8333 | 106.5 | 112.3333 | 126.6667 | 135.6667 | 1.3333 | 1.6667 | 5 | 2.5 | 2 | 2.5 | 1.6667 | 4 | 2 | 1.3333 | 3 | 2 | 1.3333 | 4 | 1 | 5 | 1 | 3 | 1.3333 | 1.3333 | 1.5 | 1 | 5 | 6 | 1 | 6 | 3 | 4 | 6 | 2.5 | 3 | 1.3333 | 1.5 | 1 | 6 | 3 | 1.6667 | 2 | 1 | 3 | 1.3333 | 1.5 | 1.6667 | 1.3333 | 1.3333 | 3 | 6 | 4 | 3 | 2 | 2 | 2
424 | 15.1667 | 11.1667 | 24.1667 | 38.5 | 45.3333 | 54.3333 | 65.5 | 74.8333 | 82.6667 | 92.6667 | 106 | 113.3333 | 125.3333 | 135.1667 | 1.6667 | 4 | 2.5 | 3 | 1 | 3 | 6 | 3 | 5 | 2 | 6 | 1.3333 | 2 | 1.5 | 2 | 1.3333 | 3 | 2 | 2 | 2 | 1.6667 | 5 | 2.5 | 2 | 3 | 2 | 3 | 1.3333 | 2 | 1.3333 | 2 | 2.5 | 2.5 | 1.5 | 4 | 2 | 1.3333 | 3 | 4 | 5 | 1.3333 | 2 | 3 | 1 | 3 | 4 | 2.5 | 2.5 | 5 | 1.5 | 1.3333 | 2
425 | 15 | 11.6667 | 25 | 34 | 46 | 58.3333 | 66.8333 | 80.8333 | 87.8333 | 99.3333 | 108.6667 | 120.6667 | 132 | 141.3333 | 2 | 5 | 1.6667 | 3 | 1.6667 | 1.6667 | 6 | 4 | 2 | 4 | 1.6667 | 1.3333 | 1 | 2 | 4 | 5 | 2 | 6 | 3 | 1.3333 | 1 | 2 | 4 | 1.5 | 5 | 2 | 5 | 2 | 2.5 | 1.5 | 2 | 1 | 5 | 2 | 1.5 | 3 | 3 | 3 | 1.3333 | 2 | 2 | 3 | 1 | 6 | 1.3333 | 3 | 4 | 3 | 3 | 4 | 1 | 1.3333
426 | 15.1667 | 7.8333 | 17.8333 | 26.6667 | 36.3333 | 46.6667 | 57.1667 | 69.6667 | 78.3333 | 91.8333 | 102.3333 | 113 | 123.5 | 132 | 3 | 1.3333 | 2 | 1.5 | 1.3333 | 6 | 1 | 1.6667 | 4 | 1 | 1.3333 | 2.5 | 3 | 2 | 3 | 1.6667 | 5 | 1.3333 | 3 | 1 | 1 | 4 | 3 | 2.5 | 5 | 2.5 | 2 | 3 | 3 | 2 | 2 | 1.6667 | 6 | 3 | 2.5 | 2 | 3 | 1 | 2.5 | 4 | 5 | 1.6667 | 1 | 3 | 1.6667 | 1.3333 | 2.5 | 5 | 2 | 1.5 | 2 | 3
427 | 18.6667 | 13.6667 | 21.3333 | 37.8333 | 51.8333 | 69.8333 | 81.6667 | 88.8333 | 106.8333 | 118.6667 | 126.6667 | 141.6667 | 152.3333 | 160.3333 | 3 | 1.6667 | 3 | 6 | 2 | 3 | 1.3333 | 1.3333 | 3 | 6 | 2.5 | 5 | 5 | 2 | 5 | 2 | 3 | 6 | 6 | 3 | 3 | 1.3333 | 6 | 1.5 | 1.6667 | 1.5 | 1.5 | 2.5 | 6 | 1 | 5 | 6 | 2 | 2.5 | 1.3333 | 6 | 2.5 | 2 | 2.5 | 1 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 1.6667 | 1.6667 | 2.5 | 2.5 | 1.3333
428 | 18.5 | 13.5 | 25 | 29.3333 | 41.3333 | 57.3333 | 68.3333 | 80.6667 | 93 | 98.5 | 110.1667 | 120.6667 | 132.6667 | 146.3333 | 2 | 3 | 6 | 2.5 | 2 | 3 | 4 | 2.5 | 1 | 1 | 1.3333 | 1 | 1.5 | 6 | 1.5 | 3 | 2 | 6 | 6 | 2 | 2 | 2 | 6 | 1 | 4 | 1.3333 | 2 | 5 | 1.3333 | 6 | 3 | 2 | 1 | 1.5 | 2 | 1 | 4 | 3 | 3 | 1.6667 | 2.5 | 4 | 2 | 2 | 2 | 3 | 4 | 3 | 4 | 5 | 1.6667 | 3
429 | 19.8333 | 9.8333 | 21.8333 | 33.8333 | 44.8333 | 59.5 | 66.5 | 74.8333 | 85.5 | 98.5 | 104.1667 | 111 | 117.8333 | 131.3333 | 1.5 | 1.3333 | 1 | 6 | 6 | 4 | 1 | 1 | 5 | 2 | 2 | 3 | 2.5 | 1.5 | 4 | 3 | 4 | 6 | 3 | 1.6667 | 1.3333 | 1.5 | 2.5 | 1.6667 | 2 | 4 | 1.3333 | 1 | 1.6667 | 2 | 4 | 3 | 3 | 4 | 2 | 4 | 1 | 2 | 1.3333 | 1.3333 | 2 | 1.6667 | 1.6667 | 1.5 | 1 | 2.5 | 2 | 1.3333 | 4 | 2.5 | 2 | 5
430 | 11.5 | 7.1667 | 17 | 27.5 | 35.8333 | 46.1667 | 55.5 | 63 | 78 | 89.3333 | 95.3333 | 105.3333 | 113.1667 | 121.5 | 1.6667 | 2.5 | 1.6667 | 1.3333 | 1.3333 | 3 | 4 | 1.5 | 1.5 | 2 | 2 | 5 | 1.3333 | 2.5 | 2 | 2.5 | 2.5 | 2.5 | 1.3333 | 4 | 5 | 1 | 1.3333 | 2 | 2 | 1.5 | 1 | 3 | 5 | 4 | 4 | 2 | 2 | 1.3333 | 5 | 3 | 2 | 1.6667 | 1 | 1.3333 | 3 | 2 | 2 | 3 | 3 | 1.3333 | 1.5 | 2 | 1 | 1.3333 | 1 | 5
431 | 11 | 7.5 | 23 | 30 | 37.3333 | 43.3333 | 52 | 63.8333 | 72.3333 | 78.6667 | 92.1667 | 110.1667 | 127.6667 | 137.6667 | 1.5 | 2 | 2 | 2 | 2 | 1.5 | 6 | 6 | 1 | 1.3333 | 1.6667 | 3 | 2 | 2 | 1.3333 | 2 | 1 | 3 | 1 | 1 | 3 | 3 | 1 | 1.6667 | 2 | 6 | 2.5 | 1.3333 | 1.6667 | 1.3333 | 2.5 | 3 | 1.5 | 1.3333 | 2 | 1.5 | 2.5 | 3 | 4 | 4 | 6 | 3 | 3 | 6 | 4 | 1.5 | 6 | 6 | 2.5 | 3 | 1.5 | 3
432 | 17.3333 | 12 | 25.3333 | 35.5 | 50.5 | 61.3333 | 73.8333 | 87.8333 | 97 | 108.8333 | 121.3333 | 137.8333 | 149.3333 | 161 | 2 | 4 | 3 | 3 | 1.3333 | 4 | 5 | 3 | 1.6667 | 2.5 | 3 | 3 | 5 | 1 | 3 | 6 | 5 | 1.3333 | 2 | 2.5 | 4 | 1.5 | 6 | 1 | 5 | 1 | 3 | 5 | 3 | 1.6667 | 1.5 | 3 | 4 | 2.5 | 4 | 1.3333 | 2.5 | 2 | 5 | 3 | 6 | 2.5 | 3 | 5 | 1 | 3 | 1.5 | 6 | 2 | 5 | 1.6667 | 3
433 | 21 | 13 | 23.8333 | 38.3333 | 51.1667 | 61.6667 | 71.5 | 84 | 95 | 109 | 123 | 138.6667 | 154.6667 | 165.1667 | 3 | 2 | 3 | 5 | 3 | 5 | 1.5 | 1.3333 | 5 | 3 | 5 | 1.5 | 5 | 1.3333 | 2.5 | 4 | 2 | 3 | 4 | 1.5 | 1.5 | 1.3333 | 1 | 6 | 2 | 3 | 1.5 | 6 | 1.3333 | 1.6667 | 5 | 3 | 3 | 6 | 2 | 3 | 2.5 | 2.5 | 6 | 3 | 5 | 1.6667 | 6 | 3 | 4 | 6 | 3 | 3 | 1.3333 | 6 | 1.5 | 1.6667
434 | 20.6667 | 13.6667 | 24.8333 | 33.3333 | 39.5 | 52.1667 | 64.8333 | 72.3333 | 89.3333 | 98.3333 | 111.1667 | 122.6667 | 135.6667 | 149 | 5 | 1.6667 | 2 | 5 | 4 | 3 | 1.6667 | 2.5 | 3 | 2 | 1.5 | 2 | 1.5 | 1.6667 | 1.5 | 1.5 | 4 | 3 | 4 | 1.6667 | 1.6667 | 4 | 5 | 2 | 2 | 2 | 2 | 1.5 | 6 | 2 | 6 | 3 | 1.6667 | 4 | 2 | 1.3333 | 1.3333 | 5 | 5 | 1.5 | 2 | 2 | 2.5 | 5 | 3 | 3 | 3 | 4 | 4 | 1.3333 | 6 | 2
435 | 12 | 9.1667 | 17 | 25.5 | 35 | 48 | 61.3333 | 73.3333 | 83.8333 | 91.8333 | 107.3333 | 118.3333 | 127 | 136.5 | 2.5 | 1.6667 | 2 | 3 | 1.5 | 1.3333 | 2 | 3 | 2.5 | 1.6667 | 3 | 1.3333 | 1.5 | 4 | 1 | 3 | 4 | 1 | 6 | 2 | 5 | 4 | 3 | 1.3333 | 4 | 1 | 5 | 2 | 5 | 3 | 1 | 1.5 | 2 | 1.5 | 3 | 1.5 | 1.5 | 3 | 5 | 6 | 1.3333 | 2 | 6 | 1.6667 | 2.5 | 2 | 2.5 | 1.6667 | 2.5 | 2 | 2 | 3
436 | 15.3333 | 7.6667 | 19.3333 | 30.3333 | 37.1667 | 46 | 64 | 75.6667 | 87.5 | 96.8333 | 107.6667 | 116.8333 | 124.6667 | 139.3333 | 2 | 1.6667 | 1 | 3 | 6 | 1.6667 | 1 | 3 | 4 | 1.5 | 1.5 | 4 | 2 | 2.5 | 1 | 1.3333 | 2.5 | 1.3333 | 2 | 3 | 3 | 6 | 6 | 3 | 5 | 2 | 3 | 1.6667 | 1.3333 | 2.5 | 6 | 2 | 1.3333 | 5 | 1.3333 | 1.6667 | 2.5 | 3 | 1.3333 | 4 | 1.6667 | 2.5 | 2.5 | 2.5 | 1.3333 | 2 | 2 | 2.5 | 5 | 6 | 1.6667 | 2
437 | 13.5 | 8.5 | 25.5 | 36.1667 | 47 | 57.1667 | 68.5 | 76.8333 | 85.1667 | 94.8333 | 105.8333 | 114.1667 | 122.6667 | 133 | 3 | 2 | 1 | 2.5 | 2.5 | 2.5 | 6 | 6 | 2 | 1.6667 | 6 | 1 | 1.5 | 6 | 2 | 1.3333 | 1.6667 | 1.5 | 4 | 3 | 4 | 4 | 1.6667 | 1.6667 | 1.6667 | 3 | 1.6667 | 2 | 1.6667 | 3 | 1.6667 | 2 | 5 | 1.6667 | 2 | 1 | 1 | 3 | 6 | 1 | 1.5 | 2.5 | 1.3333 | 3 | 2 | 2 | 2 | 2.5 | 1.3333 | 6 | 1.6667 | 1.3333
438 | 19.8333 | 12.3333 | 27.8333 | 42.3333 | 55.5 | 70 | 80 | 90.6667 | 98.6667 | 105.1667 | 117.1667 | 132.1667 | 145.5 | 155.5 | 3 | 1.6667 | 1.6667 | 6 | 6 | 1.5 | 3 | 5 | 3 | 4 | 6 | 1.5 | 4 | 1.6667 | 5 | 2.5 | 4 | 2.5 | 2 | 6 | 3 | 1 | 4 | 2 | 1 | 3 | 1.6667 | 5 | 2 | 2.5 | 1.5 | 2 | 1.3333 | 1.5 | 2 | 1.6667 | 4 | 2 | 3 | 3 | 2 | 3 | 6 | 4 | 3 | 6 | 3 | 1.3333 | 1 | 2 | 5 | 2
439 | 16.3333 | 11.3333 | 19.6667 | 30.1667 | 44.5 | 55.3333 | 71.3333 | 79.5 | 94.5 | 103.3333 | 112.5 | 123 | 138.6667 | 152.3333 | 1.3333 | 2.5 | 2.5 | 5 | 3 | 2 | 1.3333 | 2 | 2 | 1 | 2.5 | 5 | 5 | 3 | 5 | 1.3333 | 2.5 | 3 | 1.3333 | 4 | 3 | 6 | 4 | 3 | 1.3333 | 2.5 | 3 | 1.3333 | 2 | 4 | 3 | 6 | 3 | 3 | 1.3333 | 1.5 | 4 | 1.5 | 2 | 1.6667 | 3 | 4 | 1.5 | 2 | 6 | 1.6667 | 6 | 2 | 4 | 1.6667 | 2 | 6
440 | 14.6667 | 5.6667 | 17.3333 | 31 | 43.3333 | 55 | 66.3333 | 74.3333 | 86.3333 | 95.6667 | 105.8333 | 125.3333 | 134.1667 | 145.1667 | 1 | 1.6667 | 2 | 1 | 6 | 3 | 1 | 1.6667 | 1.6667 | 5 | 1 | 6 | 5 | 1.3333 | 4 | 2 | 2 | 5 | 1.6667 | 3 | 1.6667 | 1.6667 | 3 | 5 | 1.5 | 1 | 3 | 2.5 | 3 | 3 | 4 | 2 | 1.3333 | 5 | 1.5 | 1.5 | 3 | 1.6667 | 3 | 2.5 | 2.5 | 6 | 6 | 5 | 2.5 | 2 | 3 | 1.3333 | 2 | 3 | 4 | 2
441 | 13.3333 | 9.6667 | 17.3333 | 30.1667 | 38 | 49.6667 | 61.1667 | 73.1667 | 87.1667 | 98 | 106.3333 | 113 | 122.3333 | 129.1667 | 1 | 3 | 1.6667 | 4 | 1.6667 | 2 | 2 | 2 | 1.3333 | 2.5 | 3 | 6 | 2.5 | 2 | 2 | 1.3333 | 1.5 | 1.6667 | 6 | 2.5 | 2 | 2 | 2.5 | 5 | 2.5 | 5 | 2 | 2.5 | 3 | 1 | 5 | 5 | 3 | 1.3333 | 4 | 2.5 | 1.3333 | 1.3333 | 4 | 1.6667 | 1.6667 | 1 | 2 | 2 | 3 | 2 | 3 | 1.3333 | 1.5 | 1.5 | 2.5 | 1.3333
442 | 17.6667 | 10.6667 | 24.6667 | 32.5 | 42.8333 | 58.1667 | 69.1667 | 80.1667 | 94.6667 | 102.8333 | 116.8333 | 124.3333 | 132.1667 | 141.6667 | 3 | 2 | 4 | 1.6667 | 2 | 5 | 5 | 2 | 1 | 3 | 2.5 | 1.3333 | 2 | 1.3333 | 4 | 3 | 3 | 5 | 1.3333 | 6 | 5 | 3 | 1.3333 | 1.6667 | 1 | 5 | 2 | 3 | 1.5 | 5 | 5 | 3 | 1.6667 | 4 | 1 | 1.5 | 5 | 1 | 5 | 3 | 2.5 | 1 | 1 | 3 | 1 | 1.5 | 1.3333 | 4 | 1.3333 | 2.5 | 4 | 1.6667
443 | 16.3333 | 8.6667 | 23.3333 | 31 | 37.5 | 47.5 | 59.3333 | 74.3333 | 93.3333 | 105.8333 | 113.8333 | 122.3333 | 135 | 147.8333 | 3 | 1.3333 | 3 | 1.3333 | 1.6667 | 6 | 3 | 4 | 3 | 1 | 1.6667 | 2 | 1.6667 | 1.6667 | 1.6667 | 1.5 | 1.6667 | 6 | 1 | 1.3333 | 1.3333 | 3 | 5 | 2.5 | 6 | 2 | 4 | 3 | 6 | 6 | 4 | 3 | 1.5 | 4 | 6 | 1 | 3 | 2 | 2 | 1 | 2 | 2.5 | 2.5 | 1.5 | 1.6667 | 6 | 3 | 2 | 2.5 | 3 | 1.3333 | 6
444 | 15.5 | 10.5 | 23.1667 | 36.1667 | 51.1667 | 66.6667 | 80.8333 | 87.1667 | 93.3333 | 101.6667 | 113.6667 | 120.3333 | 130.6667 | 146.5 | 1.5 | 5 | 3 | 1 | 3 | 2 | 1.6667 | 6 | 3 | 3 | 4 | 3 | 5 | 3 | 3 | 4 | 2 | 2.5 | 6 | 5 | 5 | 1.5 | 1.6667 | 6 | 2 | 1 | 1.6667 | 1.6667 | 1 | 2 | 1.6667 | 1.5 | 3 | 1.3333 | 2 | 2 | 4 | 2 | 3 | 3 | 1.3333 | 1.3333 | 1.5 | 2.5 | 5 | 1 | 1.3333 | 3 | 6 | 6 | 2.5 | 1.3333
445 | 16.3333 | 12.5 | 19.8333 | 29.3333 | 42.5 | 55.1667 | 66.5 | 82 | 95 | 102.5 | 110.6667 | 126 | 135.5 | 142.5 | 5 | 3 | 1.5 | 3 | 1.3333 | 2.5 | 2.5 | 1 | 1.5 | 1 | 3 | 4 | 1.5 | 1.6667 | 6 | 4 | 5 | 2 | 1.6667 | 4 | 4 | 3 | 1.3333 | 3 | 6 | 1.5 | 5 | 3 | 2 | 5 | 3 | 3 | 3 | 1.6667 | 1.5 | 1.3333 | 1.5 | 1 | 1.6667 | 4 | 5 | 1.3333 | 3 | 6 | 2.5 | 2.5 | 1.5 | 3 | 1 | 3 | 1.3333 | 1.6667
446 | 14 | 10 | 19.3333 | 34.6667 | 46.8333 | 56.5 | 67 | 80 | 92.5 | 104 | 115.1667 | 125.8333 | 140.8333 | 156.3333 | 3 | 1.6667 | 4 | 1.3333 | 2 | 2 | 4 | 1.3333 | 1.3333 | 3 | 6 | 5 | 3 | 5 | 1.6667 | 2.5 | 2 | 4 | 2 | 1.6667 | 1.6667 | 1.3333 | 1.5 | 6 | 1.3333 | 1.6667 | 5 | 5 | 1 | 3 | 6 | 2.5 | 3 | 2.5 | 2 | 4 | 2.5 | 2 | 1.6667 | 5 | 1.6667 | 4 | 3 | 2 | 2 | 5 | 5 | 3 | 3 | 4 | 2.5 | 6
447 | 13.8333 | 5.8333 | 18.8333 | 33.1667 | 44.1667 | 56.1667 | 62.6667 | 71.5 | 82 | 90.5 | 98.8333 | 107.8333 | 116.8333 | 123 | 1.3333 | 1.6667 | 1.3333 | 1.5 | 4 | 4 | 3 | 2 | 6 | 1.3333 | 3 | 4 | 1 | 3 | 2 | 5 | 3 | 5 | 3 | 1 | 1 | 3 | 1.5 | 1 | 2 | 1.3333 | 1.5 | 4 | 2 | 2.5 | 3 | 3 | 1 | 2.5 | 3 | 2 | 2 | 2 | 3 | 1.3333 | 2 | 3 | 2 | 2 | 1 | 2 | 4 | 2 | 1 | 1.6667 | 1 | 2.5
448 | 14.1667 | 9.8333 | 21.1667 | 33.6667 | 44.3333 | 59.8333 | 74.8333 | 88.1667 | 102.3333 | 114.5 | 123.8333 | 130.6667 | 141 | 154 | 1.6667 | 2.5 | 1.6667 | 4 | 3 | 1.3333 | 5 | 2 | 2.5 | 3 | 4 | 3 | 1.3333 | 4 | 4 | 1.3333 | 6 | 3 | 2.5 | 4 | 3 | 4 | 2 | 6 | 1.3333 | 5 | 2 | 5 | 2.5 | 1.6667 | 4 | 6 | 4 | 1.6667 | 1.5 | 5 | 5 | 1 | 1.6667 | 1.6667 | 2 | 2.5 | 1 | 1.3333 | 4 | 1.3333 | 2 | 3 | 5 | 5 | 2 | 1
449 | 10.6667 | 7.1667 | 15.1667 | 23.6667 | 38.6667 | 52.1667 | 61.3333 | 70.1667 | 79.1667 | 94.6667 | 100.6667 | 113.6667 | 125 | 131.5 | 2 | 1.3333 | 1.3333 | 2.5 | 1 | 2.5 | 3 | 1.5 | 1.5 | 3 | 3 | 1 | 6 | 1.3333 | 6 | 1.6667 | 6 | 2 | 3 | 2.5 | 3 | 1.6667 | 2.5 | 2 | 1.3333 | 2.5 | 2 | 3 | 1.5 | 2 | 1.5 | 4 | 2 | 6 | 6 | 1.5 | 2.5 | 1 | 1.5 | 1 | 5 | 5 | 1 | 2 | 4 | 1.3333 | 4 | 2 | 1.5 | 1.5 | 2.5 | 1
450 | 12.1667 | 7.1667 | 18.1667 | 26.1667 | 35.6667 | 45.3333 | 55.8333 | 64.8333 | 71.6667 | 85.3333 | 98.6667 | 117.6667 | 128.8333 | 138.1667 | 3 | 1 | 1.5 | 1.6667 | 2 | 3 | 4 | 2 | 2 | 1 | 2 | 3 | 1 | 3 | 3 | 2.5 | 5 | 1 | 1.6667 | 2 | 3 | 1.5 | 2 | 4 | 2 | 1 | 3 | 3 | 1 | 1.5 | 1.3333 | 3 | 1.3333 | 5 | 1.3333 | 6 | 6 | 3 | 3 | 1.3333 | 5 | 6 | 6 | 2 | 4 | 2.5 | 3 | 1.6667 | 3 | 3 | 1.3333 | 2
451 | 17 | 14 | 23.3333 | 33.8333 | 48.3333 | 59.3333 | 72.6667 | 84.6667 | 100 | 109 | 120.3333 | 131.8333 | 141.5 | 147.1667 | 1.5 | 6 | 5 | 1.5 | 1 | 2 | 5 | 1.3333 | 1.3333 | 1.5 | 6 | 1.6667 | 6 | 4 | 2.5 | 2 | 4 | 4 | 1.3333 | 1.6667 | 4 | 1.3333 | 5 | 3 | 1 | 2 | 6 | 3 | 4 | 1.3333 | 4 | 6 | 1.6667 | 3 | 3 | 1.3333 | 3 | 6 | 1 | 1.3333 | 5 | 2 | 2.5 | 2 | 1 | 1.6667 | 2 | 5 | 1.3333 | 1.6667 | 1.6667 | 1
452 | 11.3333 | 5.3333 | 14 | 32 | 45.3333 | 52.1667 | 63.1667 | 75.1667 | 89.6667 | 99.5 | 110.8333 | 120.1667 | 135.6667 | 143.6667 | 1 | 1 | 1.6667 | 1.6667 | 2 | 4 | 1.6667 | 1 | 2 | 6 | 6 | 4 | 6 | 2 | 1.3333 | 4 | 1.3333 | 1.5 | 3 | 1 | 5 | 3 | 1.5 | 1.5 | 3 | 5 | 2 | 2 | 2.5 | 3 | 6 | 3 | 5 | 2.5 | 1 | 1.3333 | 1.3333 | 4 | 4 | 2 | 1 | 6 | 1.3333 | 1 | 6 | 5 | 2.5 | 2 | 1.5 | 2 | 2.5 | 2
453 | 20.6667 | 14.6667 | 27.6667 | 39.8333 | 49.8333 | 61.3333 | 72.3333 | 80.6667 | 96.6667 | 106.1667 | 116.1667 | 127.6667 | 133.5 | 145 | 3 | 6 | 1.6667 | 4 | 4 | 2 | 1 | 6 | 1.5 | 6 | 1.6667 | 3 | 1 | 1.5 | 1.5 | 6 | 2 | 2.5 | 1 | 6 | 3 | 3 | 2 | 3 | 2.5 | 1.3333 | 1.5 | 3 | 5 | 3 | 2 | 6 | 3 | 2.5 | 3 | 1 | 5 | 1 | 3 | 1 | 5 | 3 | 1.5 | 2 | 1.3333 | 1.6667 | 1.5 | 1.3333 | 4 | 3 | 3 | 1.5
454 | 19.8333 | 10.8333 | 27.1667 | 42.5 | 54.6667 | 70.6667 | 79.1667 | 88.1667 | 99.1667 | 109 | 118.1667 | 132.3333 | 146 | 161 | 1.3333 | 2.5 | 5 | 2 | 6 | 3 | 1.3333 | 6 | 5 | 3 | 6 | 1.3333 | 4 | 4 | 2.5 | 1.6667 | 6 | 4 | 1 | 5 | 4 | 1.5 | 1 | 2 | 1.5 | 3 | 3 | 1.5 | 1.5 | 2.5 | 1 | 6 | 2 | 2.5 | 1.3333 | 4 | 3 | 2 | 2.5 | 1.6667 | 6 | 2.5 | 4 | 1.6667 | 4 | 1.6667 | 5 | 3 | 4 | 2 | 3 | 6
455 | 23.8333 | 16.3333 | 29.1667 | 40.6667 | 54.1667 | 64.1667 | 72.5 | 85 | 97 | 115 | 131 | 138.5 | 146.1667 | 158.1667 | 4 | 5 | 6 | 1.3333 | 1.5 | 6 | 4 | 1.3333 | 4 | 2.5 | 1 | 4 | 5 | 1.5 | 4 | 3 | 4 | 1 | 4 | 1 | 1.3333 | 2 | 2.5 | 2.5 | 3 | 6 | 2 | 1.5 | 2.5 | 2.5 | 5 | 2 | 5 | 4 | 4 | 5 | 3 | 6 | 6 | 1 | 3 | 1 | 1 | 2.5 | 1.6667 | 1 | 3 | 2 | 3 | 2 | 5 | 2
456 | 19 | 14 | 25 | 35.5 | 42.1667 | 51.6667 | 62.6667 | 73 | 83.3333 | 96.8333 | 109 | 120.3333 | 133 | 143 | 6 | 4 | 2.5 | 1.5 | 2.5 | 2.5 | 4 | 2 | 1.5 | 1.6667 | 6 | 1.3333 | 1.6667 | 3 | 1 | 1 | 2 | 4 | 1.5 | 2 | 1.5 | 3 | 5 | 1.5 | 3 | 1.3333 | 3 | 3 | 5 | 3 | 1 | 1.3333 | 2.5 | 2 | 6 | 3 | 1.5 | 4 | 1.6667 | 5 | 6 | 1 | 3 | 1.3333 | 3 | 6 | 2 | 1.6667 | 2.5 | 1 | 1.5 | 5
457 | 15 | 10.5 | 21 | 34.5 | 46.8333 | 56.5 | 64.5 | 80.5 | 93.5 | 116.5 | 126.8333 | 141.8333 | 154.5 | 160.5 | 2 | 2.5 | 3 | 3 | 1.5 | 3 | 2 | 4 | 2 | 1.5 | 6 | 4 | 1.6667 | 1.6667 | 5 | 4 | 3 | 4 | 1 | 1.6667 | 1.3333 | 1.6667 | 2 | 3 | 5 | 3 | 5 | 3 | 2 | 1 | 4 | 6 | 6 | 5 | 6 | 6 | 6 | 1 | 2 | 1.3333 | 6 | 3 | 3 | 3 | 6 | 1.6667 | 2 | 3 | 1 | 1 | 2.5 | 1.5
458 | 12.3333 | 5.3333 | 18 | 32 | 45.5 | 56.5 | 64.8333 | 75.6667 | 83.6667 | 91.6667 | 106 | 118.5 | 127.5 | 135.5 | 1.6667 | 1 | 1 | 1.6667 | 5 | 2 | 1.6667 | 4 | 5 | 6 | 2 | 1 | 5 | 1.5 | 3 | 4 | 2 | 6 | 1.6667 | 1.3333 | 1.3333 | 3 | 1 | 3 | 1.3333 | 4 | 3 | 2.5 | 2.5 | 2 | 2 | 1.5 | 2 | 1.5 | 3 | 1.5 | 2 | 5 | 6 | 1.3333 | 1 | 5 | 4 | 2.5 | 2 | 2 | 2 | 3 | 2 | 3 | 1.6667 | 1.3333
459 | 18.3333 | 13.3333 | 23.8333 | 34.8333 | 42.6667 | 52 | 61 | 69.8333 | 82.1667 | 88.1667 | 96.5 | 105.5 | 118.1667 | 128.1667 | 1 | 1.3333 | 5 | 6 | 2 | 3 | 2.5 | 3 | 3 | 2 | 3 | 3 | 1.3333 | 1 | 3 | 2.5 | 2.5 | 2.5 | 3 | 1.3333 | 1 | 1.5 | 4 | 2.5 | 2 | 1.5 | 1.3333 | 4 | 1.3333 | 1 | 4 | 6 | 1 | 2 | 1.3333 | 1.6667 | 2 | 1.3333 | 2.5 | 2.5 | 2 | 2.5 | 2 | 2.5 | 1.6667 | 3 | 3 | 5 | 1 | 2.5 | 1.5 | 5
460 | 9.8333 | 5.6667 | 13.6667 | 24.3333 | 35 | 43.1667 | 51.1667 | 58.1667 | 66.1667 | 81.1667 | 92.5 | 101.6667 | 111.6667 | 124.1667 | 1 | 2 | 1 | 1.6667 | 2.5 | 1.6667 | 2.5 | 1.3333 | 2 | 1.6667 | 4 | 3 | 3 | 1.6667 | 3 | 3 | 2 | 2.5 | 2 | 1.6667 | 3 | 1.3333 | 1.6667 | 2 | 2 | 1.5 | 2 | 1.5 | 2 | 2 | 1 | 3 | 3 | 5 | 4 | 3 | 2 | 5 | 1.3333 | 3 | 1.5 | 3 | 3 | 1.6667 | 3 | 2 | 4 | 1 | 5 | 4 | 2 | 1.5
461 | 11.1667 | 7 | 15.1667 | 26.5 | 36.1667 | 46.1667 | 57.6667 | 63.3333 | 75.3333 | 91.3333 | 101.3333 | 110.3333 | 118.6667 | 132.1667 | 2.5 | 2 | 1 | 1.5 | 1.6667 | 2.5 | 3 | 1 | 1.3333 | 2 | 6 | 2 | 1.3333 | 1.3333 | 4 | 3 | 2 | 1 | 5 | 2 | 1 | 1.5 | 6 | 3 | 1 | 1.6667 | 1.3333 | 1.6667 | 1.3333 | 6 | 3 | 1.6667 | 3 | 2 | 5 | 6 | 2 | 4 | 3 | 1 | 1.3333 | 1.6667 | 3 | 3 | 4 | 1.6667 | 1 | 1.6667 | 3 | 2 | 2.5 | 6
462 | 17.6667 | 9.1667 | 25.6667 | 37 | 54 | 62.1667 | 70.3333 | 78.8333 | 90.3333 | 99.6667 | 111.1667 | 127.1667 | 136.1667 | 144.8333 | 2 | 2.5 | 3 | 1.6667 | 2.5 | 6 | 6 | 2 | 1.6667 | 2 | 1.6667 | 6 | 5 | 2 | 4 | 6 | 2.5 | 2 | 2 | 1.6667 | 2 | 2 | 2.5 | 1.6667 | 2 | 2.5 | 1.5 | 2.5 | 1.5 | 1 | 3 | 6 | 2 | 4 | 1.3333 | 2 | 1.5 | 3 | 5 | 2 | 5 | 6 | 2 | 3 | 4 | 2 | 1.6667 | 1.3333 | 1.6667 | 1.5 | 2.5 | 3
463 | 16.8333 | 9.8333 | 23.8333 | 32.8333 | 44.8333 | 59.8333 | 71.3333 | 82.3333 | 94.3333 | 102.3333 | 111.5 | 117.3333 | 128.8333 | 143.3333 | 1.5 | 4 | 3 | 1.3333 | 5 | 2 | 4 | 3 | 3 | 2.5 | 1.5 | 2 | 3 | 3 | 4 | 2 | 1 | 2 | 6 | 6 | 5 | 2 | 1.5 | 3 | 6 | 1.3333 | 1.6667 | 2 | 4 | 2 | 3 | 3 | 1.5 | 3 | 1.5 | 2 | 2.5 | 2 | 1.6667 | 3 | 1 | 1.5 | 1.3333 | 2 | 2 | 2 | 2.5 | 5 | 5 | 4 | 3 | 2.5
464 | 14.1667 | 10 | 16.8333 | 31.1667 | 42.1667 | 53.1667 | 65.1667 | 74.5 | 84 | 104 | 112.3333 | 120.6667 | 127.3333 | 136.1667 | 2.5 | 2 | 3 | 2.5 | 1.6667 | 2.5 | 1 | 1.6667 | 1.3333 | 6 | 5 | 2 | 1 | 1.5 | 2.5 | 6 | 2 | 5 | 2 | 2 | 1.5 | 2.5 | 6 | 2 | 4 | 1.5 | 2.5 | 1.3333 | 3 | 2 | 1.5 | 3 | 6 | 5 | 3 | 6 | 2 | 2 | 1.3333 | 3 | 5 | 1.3333 | 1 | 1 | 1.3333 | 1 | 1.3333 | 3 | 3 | 1.3333 | 3 | 1.5
465 | 14.8333 | 9.3333 | 22.3333 | 36 | 46.3333 | 54 | 66 | 78.3333 | 88.3333 | 99.8333 | 105.8333 | 115.3333 | 123.1667 | 131.1667 | 1.3333 | 2 | 3 | 3 | 2.5 | 3 | 6 | 1.5 | 3 | 1.6667 | 3 | 6 | 5 | 2 | 2 | 1.3333 | 2 | 1.6667 | 2.5 | 1.5 | 3 | 1 | 5 | 3 | 1.3333 | 6 | 3 | 2 | 1 | 2 | 6 | 1 | 2.5 | 3 | 2 | 4 | 1.5 | 1 | 2 | 1.5 | 3 | 1 | 3 | 2.5 | 3 | 1.3333 | 1.5 | 2 | 3 | 2 | 1.3333 | 1.6667
466 | 18 | 10.5 | 23 | 36.5 | 43.8333 | 51.3333 | 65 | 74.6667 | 85.1667 | 91 | 98.6667 | 117 | 128.6667 | 142 | 2.5 | 2.5 | 3 | 2.5 | 1.5 | 6 | 3 | 2 | 5 | 2 | 5 | 1.5 | 1.3333 | 1.5 | 2 | 2.5 | 2.5 | 1.5 | 2.5 | 1 | 6 | 2 | 4 | 1.6667 | 3 | 1.6667 | 2.5 | 2.5 | 2 | 3 | 3 | 2.5 | 1.5 | 1.5 | 1.3333 | 1.5 | 2.5 | 1.5 | 1.6667 | 2 | 6 | 1.3333 | 5 | 6 | 2 | 2 | 6 | 1.6667 | 1.3333 | 5 | 3 | 4
467 | 21.6667 | 14.6667 | 25.1667 | 34.6667 | 44.6667 | 60 | 74.3333 | 82.6667 | 91 | 107.5 | 122.8333 | 131.1667 | 143.6667 | 154 | 6 | 1.6667 | 2 | 5 | 2 | 5 | 2 | 1.5 | 2.5 | 2 | 3 | 2 | 2 | 1 | 2 | 5 | 5 | 5 | 1.3333 | 4 | 5 | 6 | 2 | 1.3333 | 3 | 1.6667 | 1.6667 | 2 | 1.6667 | 3 | 1.6667 | 2 | 6 | 6 | 3 | 1.5 | 6 | 5 | 1.3333 | 3 | 3 | 1.3333 | 2 | 2 | 1.5 | 5 | 3 | 3 | 1 | 1.3333 | 6 | 2
468 | 19.8333 | 14.5 | 26.8333 | 35.8333 | 46 | 58.3333 | 65.5 | 77.5 | 90.5 | 99 | 112 | 128.5 | 139 | 153 | 5 | 2.5 | 5 | 2 | 1.3333 | 4 | 3 | 4 | 3 | 1.5 | 2 | 2.5 | 1.3333 | 1.3333 | 5 | 2.5 | 4 | 1.6667 | 5 | 1.6667 | 1.6667 | 2 | 1.5 | 2 | 2.5 | 6 | 2 | 1.5 | 5 | 5 | 1.5 | 1.5 | 2.5 | 2 | 3 | 1 | 2.5 | 2 | 2.5 | 6 | 5 | 3 | 2.5 | 6 | 4 | 2.5 | 2 | 2 | 3 | 5 | 3 | 3
469 | 15.1667 | 11.5 | 24.1667 | 36.1667 | 47.1667 | 53.8333 | 69.8333 | 81.5 | 99.5 | 115 | 128 | 139.6667 | 146.5 | 156.5 | 2 | 2 | 6 | 1.5 | 2 | 1.6667 | 6 | 3 | 6 | 3 | 1.5 | 1.5 | 4 | 5 | 1 | 1 | 1.3333 | 1 | 1.3333 | 3 | 4 | 3 | 3 | 6 | 5 | 2 | 1.6667 | 3 | 3 | 6 | 5 | 4 | 5 | 2.5 | 5 | 3 | 3 | 2 | 6 | 2 | 2.5 | 1.6667 | 2.5 | 5 | 1 | 1.3333 | 2 | 2.5 | 4 | 1.6667 | 3 | 1.3333
470 | 14.1667 | 11.1667 | 17.1667 | 31.1667 | 42.5 | 52.1667 | 62 | 73.3333 | 90.3333 | 98.8333 | 112.8333 | 125.8333 | 136.3333 | 144.3333 | 1.6667 | 4 | 3 | 2.5 | 1.3333 | 1.6667 | 1 | 2 | 1 | 3 | 5 | 5 | 1.3333 | 3 | 1 | 6 | 1.6667 | 1.5 | 5 | 1.5 | 1.3333 | 2 | 1.5 | 5 | 3 | 6 | 1 | 1.3333 | 4 | 3 | 4 | 6 | 2.5 | 1.5 | 2.5 | 2 | 1.5 | 5 | 2.5 | 5 | 1 | 3 | 4 | 5 | 4 | 2 | 2 | 2.5 | 1 | 3 | 3 | 1
471 | 19.3333 | 11.3333 | 26.3333 | 45.3333 | 58.3333 | 72.6667 | 80 | 91.5 | 97.8333 | 106.5 | 115 | 121.8333 | 132.8333 | 145.8333 | 2 | 1.6667 | 1.6667 | 6 | 3 | 5 | 1 | 6 | 6 | 6 | 1 | 6 | 6 | 4 | 1 | 2 | 6 | 1.3333 | 4 | 3 | 1 | 1 | 1.3333 | 4 | 2.5 | 3 | 4 | 2 | 2 | 1 | 1.6667 | 1.6667 | 1 | 4 | 2 | 1.6667 | 3 | 1.5 | 2.5 | 1.5 | 2 | 1.6667 | 1.5 | 1.6667 | 3 | 2 | 1 | 5 | 1.6667 | 5 | 5 | 1.3333
472 | 12.8333 | 9.5 | 16.5 | 31 | 43 | 53.5 | 67.8333 | 80.5 | 89.8333 | 102.5 | 109.8333 | 123.8333 | 138.8333 | 155.3333 | 2.5 | 2 | 1 | 4 | 1.6667 | 1.6667 | 1.6667 | 2 | 5 | 5 | 3 | 1.5 | 1.3333 | 6 | 1.6667 | 3 | 3 | 3 | 3 | 1.5 | 6 | 4 | 1.3333 | 3 | 5 | 1.3333 | 5 | 1.3333 | 1.6667 | 3 | 1.6667 | 3 | 2 | 4 | 1.6667 | 5 | 1.3333 | 3 | 1 | 2 | 3 | 4 | 4 | 3 | 6 | 2 | 4 | 3 | 6 | 3 | 6 | 1.5
473 | 16.5 | 8 | 23.5 | 35.8333 | 44.5 | 59.1667 | 65.5 | 84.1667 | 95.6667 | 108.1667 | 121.6667 | 133 | 148.3333 | 162.3333 | 2.5 | 1 | 2.5 | 2 | 6 | 2.5 | 3 | 4 | 6 | 1.6667 | 3 | 1.6667 | 1.6667 | 2 | 3 | 2 | 1.6667 | 5 | 3 | 5 | 2 | 1.3333 | 1.6667 | 1.3333 | 6 | 1.6667 | 6 | 5 | 2 | 5 | 3 | 1.5 | 2.5 | 3 | 1 | 6 | 6 | 1 | 5 | 1.5 | 3 | 1 | 1.3333 | 6 | 5 | 3 | 1.3333 | 6 | 4 | 1 | 3 | 6
474 | 12 | 9 | 19 | 33.3333 | 45.6667 | 57.5 | 66 | 75.8333 | 87.8333 | 101.8333 | 115.5 | 127.8333 | 138.3333 | 148.6667 | 2 | 2 | 3 | 2 | 1.3333 | 1.6667 | 5 | 2 | 5 | 5 | 3 | 1.3333 | 5 | 4 | 1.3333 | 2 | 2.5 | 3 | 5 | 1.3333 | 2.5 | 1.5 | 2 | 2.5 | 2 | 1.3333 | 1.5 | 5 | 2 | 2 | 2 | 6 | 1.6667 | 1.3333 | 5 | 6 | 1.6667 | 3 | 5 | 4 | 6 | 3 | 1.3333 | 2 | 2.5 | 3 | 2 | 3 | 1.3333 | 3 | 3 | 3
475 | 19.6667 | 13.1667 | 23.3333 | 34.1667 | 39.8333 | 51.8333 | 63.3333 | 73.1667 | 86.6667 | 99.8333 | 107.1667 | 116.1667 | 127.1667 | 142.5 | 1.6667 | 2.5 | 4 | 5 | 1.5 | 5 | 1.6667 | 2 | 1.3333 | 5 | 3 | 1.5 | 1.3333 | 1.3333 | 1.5 | 1.5 | 1 | 6 | 2.5 | 2.5 | 2.5 | 1 | 6 | 2 | 1.6667 | 5 | 1.6667 | 1.5 | 5 | 5 | 2 | 1.5 | 4 | 5 | 1.6667 | 2.5 | 2 | 2 | 1.6667 | 1.6667 | 1 | 1.5 | 5 | 1.5 | 2 | 6 | 1 | 2 | 6 | 1.3333 | 3 | 5
476 | 11.8333 | 8.5 | 15.1667 | 26.1667 | 38 | 55 | 69.6667 | 83 | 96 | 110.6667 | 124.5 | 132.6667 | 147.6667 | 159.3333 | 1.6667 | 1.3333 | 3 | 2.5 | 1.6667 | 1.6667 | 2 | 1.3333 | 1.3333 | 6 | 2 | 1.6667 | 1.3333 | 3 | 1.5 | 6 | 6 | 2 | 3 | 6 | 6 | 1.6667 | 2 | 5 | 1.3333 | 6 | 3 | 3 | 5 | 3 | 2 | 3 | 1.6667 | 6 | 6 | 1 | 1.3333 | 6 | 2.5 | 4 | 1 | 1.6667 | 1.5 | 4 | 3 | 5 | 3 | 4 | 1.6667 | 3 | 3 | 4
477 | 12.1667 | 6.8333 | 15.1667 | 24.1667 | 31 | 41.5 | 51.3333 | 63.8333 | 72.5 | 87.5 | 102.1667 | 111.6667 | 122.8333 | 132.8333 | 1.3333 | 3 | 1 | 1.5 | 4 | 1.3333 | 2 | 1 | 3 | 3 | 2 | 1 | 1.3333 | 2.5 | 1 | 2 | 2 | 3 | 3 | 2.5 | 2 | 1.5 | 1.3333 | 5 | 3 | 6 | 1.5 | 2 | 3 | 1.6667 | 2.5 | 1.5 | 2 | 6 | 3 | 4 | 2 | 1.6667 | 6 | 5 | 3 | 2.5 | 2 | 2 | 6 | 1 | 2.5 | 1.6667 | 2 | 4 | 3 | 1
478 | 23 | 14 | 27 | 33 | 40.6667 | 50.6667 | 62 | 76.5 | 85.8333 | 102.3333 | 112.3333 | 120.3333 | 134.6667 | 145.5 | 5 | 3 | 2 | 4 | 6 | 3 | 1 | 3 | 2 | 1 | 1.6667 | 1.3333 | 1.6667 | 2 | 2 | 2 | 3 | 1.5 | 4 | 1.5 | 2.5 | 1.3333 | 1.5 | 6 | 6 | 6 | 1.5 | 1 | 1.3333 | 2 | 5 | 1 | 2.5 | 5 | 5 | 4 | 1 | 3 | 4 | 2 | 2 | 2.5 | 2.5 | 1 | 5 | 5 | 1.3333 | 3 | 1.3333 | 5 | 2.5 | 2
479 | 12.6667 | 8.5 | 21.6667 | 29.1667 | 40.6667 | 50.1667 | 66.8333 | 77.3333 | 92.8333 | 102.5 | 111.5 | 126.1667 | 140.1667 | 150.1667 | 2 | 1.5 | 2 | 3 | 1.6667 | 2.5 | 3 | 6 | 2 | 2.5 | 1 | 2 | 3 | 1 | 5 | 2.5 | 1.5 | 5 | 1.6667 | 1.3333 | 6 | 1.6667 | 6 | 3 | 4 | 1.5 | 3 | 2 | 6 | 5 | 3 | 1.5 | 1.3333 | 1 | 6 | 1.3333 | 2.5 | 1 | 4 | 1.5 | 4 | 3 | 6 | 1.6667 | 3 | 6 | 3 | 2 | 1 | 3 | 3 | 3
480 | 16.8333 | 13.1667 | 23.8333 | 40.3333 | 50.3333 | 63.3333 | 76.5 | 88 | 99.3333 | 109 | 116.5 | 130 | 140.1667 | 148.6667 | 5 | 2.5 | 1.6667 | 4 | 1.6667 | 2 | 3 | 4 | 4 | 1.5 | 6 | 5 | 2 | 2.5 | 3 | 2.5 | 5 | 3 | 2 | 3 | 2.5 | 1.6667 | 3 | 6 | 6 | 1 | 2 | 2.5 | 5 | 1.3333 | 3 | 2 | 3 | 1.6667 | 2 | 3 | 1.6667 | 1.5 | 1.3333 | 3 | 6 | 3 | 2.5 | 2 | 3 | 3 | 1.6667 | 2.5 | 3 | 1.5 | 2.5 | 1.5
481 | 14.5 | 7.5 | 20.5 | 27.8333 | 37.3333 | 43.8333 | 51.3333 | 62.6667 | 69.1667 | 78.6667 | 90.3333 | 101.6667 | 107.8333 | 118.8333 | 2 | 2 | 2.5 | 1 | 1 | 6 | 4 | 2 | 2 | 1.3333 | 1 | 3 | 1.5 | 5 | 2 | 1 | 1.6667 | 1 | 2.5 | 1.3333 | 2 | 1.5 | 3 | 1 | 3 | 2 | 1.3333 | 5 | 1.6667 | 1 | 1.3333 | 2.5 | 3 | 2.5 | 2 | 2 | 3 | 3 | 4 | 1.6667 | 1.5 | 6 | 2.5 | 1.3333 | 1.6667 | 2 | 1.5 | 1 | 3 | 1 | 2 | 5
482 | 15 | 9.5 | 18 | 33.5 | 45.5 | 59 | 68 | 80 | 94 | 103 | 111 | 118 | 128 | 137.3333 | 1.5 | 2 | 3 | 3 | 2.5 | 3 | 1.6667 | 1.3333 | 3 | 2.5 | 5 | 5 | 6 | 2 | 1 | 3 | 2 | 6 | 2.5 | 3 | 1 | 3 | 2.5 | 2.5 | 2 | 5 | 3 | 2 | 5 | 2 | 2 | 5 | 2 | 2 | 2.5 | 2.5 | 2 | 2 | 3 | 1 | 1.6667 | 1.3333 | 3 | 1 | 1.6667 | 1 | 1.3333 | 6 | 1 | 1.3333 | 2 | 5
483 | 24 | 19 | 29.6667 | 38.6667 | 49.8333 | 64.8333 | 74.3333 | 87.3333 | 97.8333 | 108.1667 | 119.6667 | 128.5 | 139.3333 | 146.1667 | 4 | 3 | 6 | 6 | 2 | 3 | 4 | 1.6667 | 2 | 1 | 4 | 2 | 2.5 | 1 | 1.6667 | 6 | 4 | 3 | 2 | 6 | 1.6667 | 2.5 | 1.3333 | 4 | 2 | 2 | 3 | 6 | 5 | 1 | 1.5 | 3 | 1.3333 | 4 | 3 | 2 | 5 | 1 | 1.5 | 4 | 2 | 1.3333 | 1.5 | 4 | 6 | 1.3333 | 1.5 | 2 | 1.5 | 3 | 1 | 1.3333
484 | 17 | 10 | 20.3333 | 32.8333 | 45.5 | 60 | 69.1667 | 81.5 | 92.8333 | 101.3333 | 106.8333 | 116.5 | 135.5 | 147.8333 | 1 | 3 | 3 | 3 | 6 | 1 | 1.3333 | 2 | 4 | 3 | 3 | 2.5 | 4 | 1.6667 | 6 | 1 | 6 | 1 | 5 | 2.5 | 3 | 1.6667 | 2 | 2.5 | 4 | 2 | 5 | 1.3333 | 1.5 | 1.3333 | 6 | 2.5 | 2 | 3 | 1 | 2.5 | 1.5 | 1.5 | 1.5 | 1 | 2 | 5 | 1.3333 | 1.3333 | 6 | 3 | 5 | 5 | 1.3333 | 3 | 3 | 5
485 | 19.5 | 15 | 27.5 | 37 | 55 | 65 | 79.3333 | 90.6667 | 97.6667 | 112.3333 | 123 | 132.6667 | 147.6667 | 154.1667 | 2 | 5 | 2 | 6 | 2.5 | 2 | 2 | 6 | 2.5 | 2 | 3 | 2 | 4 | 6 | 2 | 6 | 1.5 | 4 | 2 | 2.5 | 1.3333 | 5 | 5 | 3 | 3 | 4 | 1.3333 | 3 | 1.3333 | 2 | 2 | 1.6667 | 1.6667 | 6 | 2 | 5 | 1.6667 | 1.5 | 5 | 2.5 | 1 | 1 | 6 | 1.6667 | 6 | 1 | 2 | 6 | 2 | 1.5 | 2 | 1
486 | 9.6667 | 6.1667 | 13.3333 | 26.8333 | 37.3333 | 44.3333 | 53.5 | 70.5 | 77.6667 | 94.6667 | 104 | 116 | 126 | 138 | 2.5 | 1 | 1 | 1.6667 | 1.5 | 2 | 1.6667 | 2 | 2.5 | 6 | 3 | 2 | 2.5 | 3 | 4 | 1 | 1 | 3 | 1.5 | 1.5 | 1.5 | 3 | 1.6667 | 3 | 3 | 5 | 3 | 6 | 1 | 3 | 1.5 | 1.6667 | 6 | 3 | 2 | 6 | 2 | 1 | 1.3333 | 5 | 1.5 | 1.5 | 5 | 4 | 1.3333 | 3 | 4 | 1.6667 | 1.5 | 5 | 2.5 | 3
487 | 17.5 | 10.5 | 23 | 33.3333 | 42.5 | 53.8333 | 60.8333 | 68.8333 | 77.5 | 85.1667 | 97 | 105.3333 | 117.8333 | 131.3333 | 1 | 1.5 | 6 | 2 | 2 | 5 | 1.5 | 4 | 2 | 1.3333 | 3 | 4 | 2 | 2.5 | 3 | 1.6667 | 3 | 1.3333 | 4 | 3 | 1.6667 | 1.3333 | 1 | 3 | 1.3333 | 3 | 1.6667 | 2 | 1.6667 | 1 | 3 | 3 | 2 | 2 | 2 | 1.6667 | 2.5 | 1.3333 | 6 | 2 | 4 | 1 | 2 | 1.3333 | 2.5 | 2 | 3 | 5 | 6 | 2 | 3 | 2.5
488 | 19 | 11.5 | 24.5 | 34.8333 | 43.6667 | 55 | 63 | 75 | 87.5 | 100.1667 | 109.8333 | 122 | 138 | 152 | 2 | 1.5 | 5 | 3 | 6 | 1.5 | 2.5 | 3 | 1.3333 | 5 | 1 | 3 | 2 | 4 | 1.3333 | 1.5 | 2 | 1.3333 | 3 | 5 | 1.5 | 1 | 2.5 | 3 | 2 | 3 | 4 | 3 | 2.5 | 1 | 3 | 6 | 1.6667 | 4 | 2 | 5 | 3 | 1 | 4 | 1.6667 | 3 | 5 | 2.5 | 1.6667 | 6 | 3 | 2 | 5 | 2 | 3 | 6 | 3
489 | 10.5 | 8 | 18.5 | 32.8333 | 42.3333 | 53 | 61.5 | 66.8333 | 82.5 | 93 | 107.1667 | 117.6667 | 125.1667 | 135.8333 | 2.5 | 1.5 | 3 | 1 | 1 | 1.5 | 6 | 2 | 6 | 4 | 1.3333 | 3 | 1 | 6 | 1.5 | 1 | 4 | 3 | 1.6667 | 2 | 2.5 | 3 | 1 | 2 | 2 | 1 | 1.3333 | 1 | 1.6667 | 3 | 5 | 6 | 3 | 1 | 1.5 | 5 | 1.6667 | 2.5 | 6 | 4 | 2.5 | 5 | 2 | 1 | 1.5 | 2 | 2 | 2 | 1.6667 | 1 | 4 | 4
490 | 14 | 6 | 19 | 27.3333 | 39.3333 | 51.6667 | 67 | 78.5 | 96.5 | 107 | 116.3333 | 128.1667 | 138.3333 | 149.3333 | 1 | 1.5 | 2.5 | 1 | 4 | 4 | 2 | 3 | 4 | 1.3333 | 2 | 1 | 3 | 2 | 2 | 5 | 3 | 1.3333 | 4 | 4 | 1.3333 | 4 | 4 | 6 | 6 | 2.5 | 1.5 | 1.5 | 6 | 5 | 6 | 1 | 1.5 | 5 | 3 | 1 | 2 | 4 | 1.6667 | 1.6667 | 6 | 1.3333 | 2 | 2.5 | 1.6667 | 2.5 | 3 | 3 | 1.6667 | 2 | 1.3333 | 6
491 | 14 | 10.5 | 17 | 23.8333 | 37 | 45.8333 | 58.8333 | 73.3333 | 84 | 92.5 | 100.8333 | 111.1667 | 122.6667 | 134.3333 | 1.5 | 3 | 1 | 5 | 1.5 | 2 | 1 | 2 | 1.5 | 2 | 2 | 1.3333 | 1.6667 | 1.5 | 6 | 4 | 2.5 | 1.3333 | 3 | 2 | 3 | 6 | 1.5 | 2.5 | 5 | 2.5 | 2 | 5 | 1.6667 | 6 | 1.6667 | 1.3333 | 1.5 | 1.5 | 2.5 | 3 | 3 | 1.3333 | 2 | 2 | 6 | 1.3333 | 1.3333 | 1.6667 | 2 | 6 | 2 | 1.5 | 1 | 1.6667 | 4 | 5
492 | 19.3333 | 13 | 25.3333 | 35.3333 | 51.3333 | 63.5 | 69.6667 | 83 | 96 | 107.1667 | 118.6667 | 137.6667 | 149 | 160 | 3 | 2.5 | 1.5 | 6 | 1.3333 | 5 | 5 | 1 | 2 | 4 | 2 | 2 | 5 | 5 | 2 | 4 | 1.5 | 4 | 1.6667 | 5 | 1.6667 | 1.6667 | 1.3333 | 1.5 | 4 | 6 | 2 | 1.3333 | 6 | 3 | 3 | 1 | 1.6667 | 1.5 | 3 | 5 | 3 | 1.5 | 4 | 3 | 6 | 6 | 3 | 4 | 4 | 5 | 1.3333 | 1 | 3 | 5 | 1.5 | 1.5
493 | 16 | 12.5 | 24 | 38.5 | 48.6667 | 55.6667 | 68.5 | 78.5 | 85.6667 | 92 | 105.5 | 116.6667 | 125 | 132.5 | 3 | 3 | 4 | 2.5 | 2.5 | 1 | 5 | 3 | 2.5 | 3 | 6 | 3 | 1.3333 | 1.3333 | 2.5 | 5 | 2 | 1.5 | 2 | 1.5 | 5 | 1.3333 | 4 | 2.5 | 1 | 1.5 | 5 | 2.5 | 3 | 1.5 | 1 | 1.6667 | 1 | 1 | 3 | 1.3333 | 5 | 1.5 | 5 | 2 | 4 | 2.5 | 3 | 1.6667 | 3 | 2.5 | 1.5 | 1.3333 | 1.6667 | 3 | 1.5 | 1.3333
494 | 25 | 19 | 34 | 45.6667 | 58.5 | 70.5 | 82 | 92.6667 | 110.1667 | 122.5 | 133.8333 | 142.3333 | 160.3333 | 171.1667 | 5 | 4 | 6 | 4 | 3 | 3 | 5 | 4 | 2 | 1.6667 | 3 | 5 | 3 | 6 | 1.3333 | 2.5 | 3 | 2.5 | 4 | 2.5 | 6 | 2 | 2.5 | 1 | 1.6667 | 4 | 3 | 2 | 4 | 2.5 | 6 | 5 | 5 | 3 | 1.3333 | 3 | 2.5 | 1.3333 | 2.5 | 5 | 2 | 2 | 2 | 2.5 | 2 | 5 | 6 | 5 | 1.3333 | 1 | 2.5 | 6
495 | 14.3333 | 10.3333 | 20.3333 | 31 | 49 | 56.3333 | 69.3333 | 82 | 90.6667 | 99.6667 | 111.6667 | 122.3333 | 129.5 | 141.1667 | 1.3333 | 5 | 3 | 1 | 2 | 2 | 2 | 4 | 1.6667 | 2.5 | 4 | 2.5 | 5 | 4 | 3 | 6 | 2 | 1.5 | 1.3333 | 2.5 | 1 | 4 | 5 | 3 | 2 | 1.6667 | 3 | 6 | 2 | 2 | 1.6667 | 3 | 2.5 | 3 | 1.5 | 2 | 4 | 2 | 5 | 1 | 1.3333 | 1.3333 | 2 | 6 | 1.6667 | 2 | 1.5 | 2 | 5 | 3 | 1.6667 | 2
496 | 16 | 8.6667 | 21.5 | 38.5 | 50.1667 | 67.1667 | 73.6667 | 81.3333 | 88.6667 | 100.8333 | 108.3333 | 118 | 126.1667 | 140.5 | 3 | 2 | 1.6667 | 2 | 6 | 1.3333 | 3 | 2.5 | 3 | 5 | 4 | 5 | 3 | 3 | 4 | 1.6667 | 6 | 2 | 3 | 6 | 2 | 1.5 | 1 | 2 | 2 | 2 | 1.6667 | 2 | 1.3333 | 1 | 2 | 3 | 2.5 | 1.6667 | 4 | 4 | 2.5 | 1 | 2 | 2 | 1 | 1.6667 | 3 | 4 | 2 | 1.5 | 1.6667 | 3 | 3 | 1.3333 | 6 | 4
497 | 21.3333 | 10.3333 | 26.3333 | 36.8333 | 47.8333 | 57.3333 | 71.8333 | 78.1667 | 91.5 | 98.5 | 109 | 122.5 | 133.5 | 145 | 2.5 | 4 | 2.5 | 1.3333 | 5 | 6 | 2 | 3 | 2.5 | 2 | 4 | 2 | 1.3333 | 1.6667 | 6 | 2 | 5 | 1.5 | 1 | 2 | 5 | 1.5 | 5 | 3 | 2 | 2 | 1.3333 | 1 | 1.3333 | 5 | 3 | 4 | 2 | 1.5 | 1 | 2.5 | 5 | 1 | 3 | 1.5 | 2 | 4 | 5 | 2.5 | 2 | 2 | 1 | 6 | 1.5 | 2 | 3 | 5
498 | 16.6667 | 6.6667 | 20.1667 | 33.1667 | 40.8333 | 47.3333 | 59.6667 | 69.5 | 86 | 98.1667 | 113.1667 | 123.8333 | 138.1667 | 144.5 | 2.5 | 1.3333 | 1.5 | 1.3333 | 4 | 6 | 1.5 | 2 | 3 | 3 | 3 | 4 | 1.6667 | 1.5 | 2.5 | 2 | 1.5 | 2 | 2 | 1 | 4 | 3 | 1.3333 | 4 | 3 | 4 | 1.5 | 1.3333 | 5 | 5 | 5 | 1.5 | 1.6667 | 5 | 2.5 | 3 | 2 | 5 | 3 | 5 | 1.6667 | 2 | 4 | 3 | 1.3333 | 3 | 5 | 5 | 1.5 | 1.5 | 2 | 1.3333
499 | 15.5 | 8.5 | 22.1667 | 28.1667 | 35.5 | 47.5 | 57 | 69.6667 | 78.1667 | 92 | 104 | 116.5 | 135.5 | 149.5 | 1 | 1 | 5 | 1.5 | 6 | 1 | 1.6667 | 5 | 2.5 | 1 | 1 | 1.5 | 1 | 2 | 3 | 1.3333 | 5 | 1 | 3 | 3 | 2 | 2.5 | 3 | 2 | 1.6667 | 2 | 6 | 3 | 2.5 | 1 | 1 | 4 | 5 | 2.5 | 1.3333 | 5 | 3 | 1 | 3 | 5 | 3 | 1 | 2.5 | 6 | 5 | 5 | 5 | 4 | 2 | 3 | 5 | 4
500 | 13.8333 | 11.5 | 16.8333 | 24.6667 | 43.3333 | 50.8333 | 61.5 | 73.6667 | 85 | 98 | 118 | 131 | 143 | 153.8333 | 3 | 5 | 2 | 1.5 | 1.3333 | 1 | 2 | 1 | 1.3333 | 1.5 | 2 | 3 | 1.6667 | 5 | 6 | 6 | 1.3333 | 1.5 | 1.6667 | 3 | 2 | 3 | 1.6667 | 4 | 1.6667 | 6 | 2 | 2.5 | 2 | 3 | 5 | 1.3333 | 1.5 | 5 | 2.5 | 4 | 4 | 6 | 5 | 5 | 3 | 6 | 1 | 3 | 2 | 5 | 1 | 4 | 5 | 1.3333 | 3 | 1.5
| 6 | Sum4: 4; Sum8: 8; Sum12: 12; Sum16: 16; Sum20: 20; Sum24: 24; Sum28: 28; Sum32: 32; Sum36: 36; Sum40: 40; Sum44: 44; Sum48: 48; Sum52: 52
1% | 9.8317 | Sum4: 5.665; Sum8: 13.9967; Sum12: 22.8333; Sum16: 30.9983; Sum20: 41.3317; Sum24: 50.6583; Sum28: 58.1667; Sum32: 68.4867; Sum36: 78.6667; Sum40: 90.6633; Sum44: 99.99; Sum48: 109.4983; Sum52: 120.825
2% | 10.1667 | Sum4: 5.83; Sum8: 15.1567; Sum12: 23.83; Sum16: 31.9967; Sum20: 42.6567; Sum24: 51.4967; Sum28: 62.16; Sum32: 71.6633; Sum36: 81.5; Sum40: 92.1667; Sum44: 101.5; Sum48: 111.6533; Sum52: 121.49
3% | 10.5 | Sum4: 6.1667; Sum8: 15.1667; Sum12: 24.1667; Sum16: 33.5; Sum20: 43.3283; Sum24: 52.1667; Sum28: 62.99; Sum32: 72.6617; Sum36: 82.8333; Sum40: 93.3233; Sum44: 102.3233; Sum48: 112.5; Sum52: 122.99
4% | 10.8267 | Sum4: 6.3333; Sum8: 15.3333; Sum12: 24.66; Sum16: 34.1667; Sum20: 43.5; Sum24: 53.82; Sum28: 63.8333; Sum32: 73.8267; Sum36: 84.1667; Sum40: 94.3333; Sum44: 103.64; Sum48: 113.5; Sum52: 123.8333
5% | 11.1667 | Sum4: 6.6667; Sum8: 15.6667; Sum12: 24.9917; Sum16: 34.5; Sum20: 44.1667; Sum24: 54.8333; Sum28: 64.3167; Sum32: 74.6667; Sum36: 85.3333; Sum40: 94.825; Sum44: 104.6583; Sum48: 114.8167; Sum52: 124.9833
6% | 11.49 | Sum4: 6.99; Sum8: 15.99; Sum12: 25.5; Sum16: 34.8233; Sum20: 44.6567; Sum24: 55.3233; Sum28: 65.47; Sum32: 75.49; Sum36: 86.3033; Sum40: 95.6567; Sum44: 105.5; Sum48: 115.5; Sum52: 125.8333
7% | 11.8217 | Sum4: 7; Sum8: 16.155; Sum12: 25.8217; Sum16: 35.4767; Sum20: 45.4883; Sum24: 55.8217; Sum28: 66.155; Sum32: 76.155; Sum36: 86.6667; Sum40: 96.3333; Sum44: 105.8333; Sum48: 116.8217; Sum52: 126.965
8% | 11.9867 | Sum4: 7.1667; Sum8: 16.4867; Sum12: 26.1667; Sum16: 35.82; Sum20: 45.8333; Sum24: 56.5; Sum28: 66.5; Sum32: 76.6533; Sum36: 87.1533; Sum40: 96.82; Sum44: 106.5; Sum48: 117.6533; Sum52: 127.6533
9% | 12 | Sum4: 7.1667; Sum8: 16.6517; Sum12: 26.3183; Sum16: 36.3183; Sum20: 46; Sum24: 56.6667; Sum28: 66.985; Sum32: 76.8333; Sum36: 87.6667; Sum40: 97.1517; Sum44: 107.8183; Sum48: 118.1667; Sum52: 128.6367
10% | 12.1667 | Sum4: 7.5; Sum8: 16.8333; Sum12: 26.6667; Sum16: 36.5; Sum20: 46.1667; Sum24: 57; Sum28: 67.5; Sum32: 77.8333; Sum36: 88.6667; Sum40: 97.9833; Sum44: 108.4833; Sum48: 118.3333; Sum52: 128.9833
11% | 12.3333 | Sum4: 7.5; Sum8: 17; Sum12: 26.8333; Sum16: 36.815; Sum20: 46.8333; Sum24: 57.3333; Sum28: 67.8333; Sum32: 78.1667; Sum36: 88.9817; Sum40: 98.6667; Sum44: 108.9817; Sum48: 119.1667; Sum52: 129.6483
12% | 12.48 | Sum4: 7.6667; Sum8: 17.1467; Sum12: 27; Sum16: 37.1467; Sum20: 47.5; Sum24: 57.6667; Sum28: 68.2933; Sum32: 78.5; Sum36: 89.3333; Sum40: 98.98; Sum44: 109.48; Sum48: 119.8333; Sum52: 130.3333
13% | 12.645 | Sum4: 7.8117; Sum8: 17.3333; Sum12: 27.3117; Sum16: 37.3333; Sum20: 47.6667; Sum24: 58.1667; Sum28: 68.6667; Sum32: 79.3117; Sum36: 89.645; Sum40: 99.4783; Sum44: 109.6667; Sum48: 120; Sum52: 130.9783
14% | 12.81 | Sum4: 7.8333; Sum8: 17.5; Sum12: 27.5; Sum16: 37.5; Sum20: 48; Sum24: 58.81; Sum28: 69; Sum32: 79.6433; Sum36: 90.1433; Sum40: 100.2867; Sum44: 110.6433; Sum48: 120.4533; Sum52: 131.31
15% | 12.8333 | Sum4: 8; Sum8: 17.6417; Sum12: 27.6667; Sum16: 37.6667; Sum20: 48.1667; Sum24: 59; Sum28: 69.5; Sum32: 79.8333; Sum36: 90.6417; Sum40: 100.6667; Sum44: 110.975; Sum48: 120.8333; Sum52: 131.5
16% | 13 | Sum4: 8; Sum8: 17.8333; Sum12: 27.8333; Sum16: 38; Sum20: 48.6133; Sum24: 59.3333; Sum28: 69.8333; Sum32: 80.4733; Sum36: 91.3333; Sum40: 100.8333; Sum44: 111.3067; Sum48: 121.5; Sum52: 131.8067
17% | 13.1383 | Sum4: 8.1667; Sum8: 18; Sum12: 28; Sum16: 38.305; Sum20: 48.8333; Sum24: 59.6667; Sum28: 70.305; Sum32: 80.8333; Sum36: 91.5; Sum40: 101.2767; Sum44: 111.6667; Sum48: 121.915; Sum52: 132.1383
18% | 13.3333 | Sum4: 8.3333; Sum8: 18; Sum12: 28.3033; Sum16: 38.5; Sum20: 49.1667; Sum24: 59.8333; Sum28: 70.6667; Sum32: 81.1667; Sum36: 91.8333; Sum40: 101.6667; Sum44: 112.1667; Sum48: 122.3333; Sum52: 132.8033
19% | 13.3333 | Sum4: 8.3333; Sum8: 18.1667; Sum12: 28.5; Sum16: 38.8017; Sum20: 49.5; Sum24: 60.135; Sum28: 70.8333; Sum32: 81.3333; Sum36: 92; Sum40: 101.9683; Sum44: 112.3333; Sum48: 122.6667; Sum52: 133
20% | 13.5 | Sum4: 8.5; Sum8: 18.4667; Sum12: 28.6667; Sum16: 39; Sum20: 49.8333; Sum24: 60.3333; Sum28: 71.3; Sum32: 81.8; Sum36: 92.3; Sum40: 102.3; Sum44: 112.8333; Sum48: 122.8333; Sum52: 133.5
21% | 13.6317 | Sum4: 8.5; Sum8: 18.6317; Sum12: 28.8333; Sum16: 39.1667; Sum20: 50; Sum24: 60.5; Sum28: 71.5; Sum32: 82.1667; Sum36: 92.6317; Sum40: 102.8333; Sum44: 113; Sum48: 123.1317; Sum52: 134.0967
22% | 13.7967 | Sum4: 8.6667; Sum8: 18.8333; Sum12: 28.8333; Sum16: 39.3333; Sum20: 50.1667; Sum24: 60.8333; Sum28: 71.8333; Sum32: 82.5; Sum36: 93; Sum40: 103.1667; Sum44: 113.6667; Sum48: 123.7967; Sum52: 134.5
23% | 13.8333 | Sum4: 8.8333; Sum8: 19; Sum12: 29; Sum16: 39.5; Sum20: 50.295; Sum24: 60.9617; Sum28: 72.1283; Sum32: 82.6667; Sum36: 93.3333; Sum40: 103.9233; Sum44: 114.1667; Sum48: 124.1667; Sum52: 134.5
24% | 13.96 | Sum4: 8.8333; Sum8: 19; Sum12: 29.2933; Sum16: 39.6667; Sum20: 50.6667; Sum24: 61.3333; Sum28: 72.3333; Sum32: 82.8333; Sum36: 93.6267; Sum40: 104; Sum44: 114.5; Sum48: 124.96; Sum52: 134.92
25% | 14 | Sum4: 9; Sum8: 19.1667; Sum12: 29.4583; Sum16: 39.9583; Sum20: 50.8333; Sum24: 61.5; Sum28: 72.625; Sum32: 83.1667; Sum36: 94; Sum40: 104.2917; Sum44: 115.125; Sum48: 125.1667; Sum52: 135.5
26% | 14 | Sum4: 9; Sum8: 19.3333; Sum12: 29.6667; Sum16: 40.1667; Sum20: 50.9567; Sum24: 61.6667; Sum28: 73; Sum32: 83.3333; Sum36: 94.1667; Sum40: 104.5; Sum44: 115.3333; Sum48: 125.6233; Sum52: 135.6667
27% | 14.1667 | Sum4: 9; Sum8: 19.3333; Sum12: 30; Sum16: 40.3333; Sum20: 51.1667; Sum24: 61.955; Sum28: 73.1667; Sum32: 83.7883; Sum36: 94.455; Sum40: 105; Sum44: 115.5; Sum48: 125.8333; Sum52: 136.0767
28% | 14.1667 | Sum4: 9.1667; Sum8: 19.5; Sum12: 30.3333; Sum16: 40.6667; Sum20: 51.4533; Sum24: 62; Sum28: 73.3333; Sum32: 84; Sum36: 94.5; Sum40: 105.1667; Sum44: 115.6667; Sum48: 126; Sum52: 136.62
29% | 14.3333 | Sum4: 9.1667; Sum8: 19.6667; Sum12: 30.5; Sum16: 40.6667; Sum20: 51.6667; Sum24: 62.1667; Sum28: 73.3333; Sum32: 84; Sum36: 94.6667; Sum40: 105.5; Sum44: 116; Sum48: 126.5; Sum52: 136.6667
30% | 14.3333 | Sum4: 9.3333; Sum8: 19.8333; Sum12: 30.5; Sum16: 40.8333; Sum20: 51.8333; Sum24: 62.3333; Sum28: 73.6667; Sum32: 84.3333; Sum36: 94.8333; Sum40: 105.7833; Sum44: 116.1667; Sum48: 126.6667; Sum52: 136.8333
31% | 14.5 | Sum4: 9.3333; Sum8: 19.8333; Sum12: 30.8333; Sum16: 41.1667; Sum20: 52; Sum24: 62.6667; Sum28: 73.6667; Sum32: 84.5; Sum36: 95.115; Sum40: 105.8333; Sum44: 116.615; Sum48: 127.115; Sum52: 137.1667
32% | 14.6667 | Sum4: 9.5; Sum8: 20; Sum12: 31; Sum16: 41.3333; Sum20: 52.1667; Sum24: 62.8333; Sum28: 74; Sum32: 84.8333; Sum36: 95.5; Sum40: 106; Sum44: 116.8333; Sum48: 127.4467; Sum52: 137.6667
33% | 14.6667 | Sum4: 9.5; Sum8: 20; Sum12: 31; Sum16: 41.5; Sum20: 52.3333; Sum24: 62.945; Sum28: 74.1667; Sum32: 85.1117; Sum36: 95.6667; Sum40: 106.2783; Sum44: 117; Sum48: 127.6667; Sum52: 138
34% | 14.6667 | Sum4: 9.5; Sum8: 20.1667; Sum12: 31.1667; Sum16: 41.6667; Sum20: 52.6667; Sum24: 63.11; Sum28: 74.2767; Sum32: 85.2767; Sum36: 95.8333; Sum40: 106.4433; Sum44: 117.2767; Sum48: 128; Sum52: 138.6067
35% | 14.8333 | Sum4: 9.6667; Sum8: 20.275; Sum12: 31.275; Sum16: 41.8333; Sum20: 52.8333; Sum24: 63.1667; Sum28: 74.3333; Sum32: 85.5; Sum36: 96; Sum40: 106.6083; Sum44: 117.4417; Sum48: 128.275; Sum52: 139
36% | 14.8333 | Sum4: 9.6667; Sum8: 20.3333; Sum12: 31.44; Sum16: 42; Sum20: 53.1067; Sum24: 63.44; Sum28: 74.5; Sum32: 85.6667; Sum36: 96.1667; Sum40: 106.8333; Sum44: 117.8333; Sum48: 128.6067; Sum52: 139.44
37% | 15 | Sum4: 9.8333; Sum8: 20.3333; Sum12: 31.605; Sum16: 42; Sum20: 53.1667; Sum24: 63.605; Sum28: 74.7717; Sum32: 85.9383; Sum36: 96.605; Sum40: 107.1667; Sum44: 118; Sum48: 128.8333; Sum52: 139.605
38% | 15 | Sum4: 9.8333; Sum8: 20.5; Sum12: 31.6667; Sum16: 42.1667; Sum20: 53.3333; Sum24: 63.8333; Sum28: 74.8333; Sum32: 86.1667; Sum36: 96.8333; Sum40: 107.27; Sum44: 118.27; Sum48: 129; Sum52: 140
39% | 15 | Sum4: 10; Sum8: 20.5; Sum12: 31.8333; Sum16: 42.2683; Sum20: 53.5; Sum24: 64; Sum28: 75; Sum32: 86.3333; Sum36: 97.1667; Sum40: 107.435; Sum44: 118.3333; Sum48: 129.1667; Sum52: 140.2683
40% | 15.1667 | Sum4: 10; Sum8: 20.6667; Sum12: 31.8333; Sum16: 42.3333; Sum20: 53.6667; Sum24: 64.1; Sum28: 75.1667; Sum32: 86.6667; Sum36: 97.3333; Sum40: 107.6667; Sum44: 118.6667; Sum48: 129.5; Sum52: 140.3333
41% | 15.265 | Sum4: 10; Sum8: 20.8333; Sum12: 32; Sum16: 42.5; Sum20: 53.6667; Sum24: 64.3333; Sum28: 75.3333; Sum32: 86.9317; Sum36: 97.5; Sum40: 108.1667; Sum44: 119.03; Sum48: 129.5; Sum52: 140.765
42% | 15.3333 | Sum4: 10; Sum8: 20.8333; Sum12: 32; Sum16: 42.6667; Sum20: 54; Sum24: 64.43; Sum28: 75.6667; Sum32: 87.0967; Sum36: 97.8333; Sum40: 108.3333; Sum44: 119.43; Sum48: 129.7633; Sum52: 140.93
43% | 15.5 | Sum4: 10; Sum8: 21; Sum12: 32.1667; Sum16: 42.8333; Sum20: 54.3333; Sum24: 64.6667; Sum28: 75.8333; Sum32: 87.1667; Sum36: 98; Sum40: 108.5; Sum44: 119.6667; Sum48: 130; Sum52: 141.1667
44% | 15.5 | Sum4: 10.1667; Sum8: 21; Sum12: 32.3333; Sum16: 43; Sum20: 54.3333; Sum24: 64.8333; Sum28: 76; Sum32: 87.3333; Sum36: 98.1667; Sum40: 108.6667; Sum44: 119.8333; Sum48: 130.4267; Sum52: 141.3333
45% | 15.5917 | Sum4: 10.3333; Sum8: 21.2583; Sum12: 32.5; Sum16: 43.0917; Sum20: 54.5; Sum24: 65; Sum28: 76.3333; Sum32: 87.5; Sum36: 98.1667; Sum40: 109; Sum44: 119.8333; Sum48: 130.8333; Sum52: 141.6667
46% | 15.8333 | Sum4: 10.3333; Sum8: 21.3333; Sum12: 32.6667; Sum16: 43.1667; Sum20: 54.6667; Sum24: 65.1667; Sum28: 76.5; Sum32: 87.6667; Sum36: 98.3333; Sum40: 109.1667; Sum44: 120.1667; Sum48: 131.09; Sum52: 141.7567
47% | 15.9217 | Sum4: 10.5; Sum8: 21.5; Sum12: 32.6667; Sum16: 43.1667; Sum20: 54.8333; Sum24: 65.3333; Sum28: 76.5883; Sum32: 88; Sum36: 98.5; Sum40: 109.4217; Sum44: 120.3333; Sum48: 131.3333; Sum52: 142
48% | 16 | Sum4: 10.5; Sum8: 21.5; Sum12: 32.8333; Sum16: 43.3333; Sum20: 55; Sum24: 65.3333; Sum28: 76.8333; Sum32: 88.0867; Sum36: 98.8333; Sum40: 109.8333; Sum44: 120.5; Sum48: 131.8333; Sum52: 142.2533
49% | 16 | Sum4: 10.585; Sum8: 21.6667; Sum12: 32.8333; Sum16: 43.5; Sum20: 55; Sum24: 65.5; Sum28: 77.085; Sum32: 88.3333; Sum36: 99; Sum40: 110.1667; Sum44: 120.6667; Sum48: 132; Sum52: 142.5
50% | 16.1667 | Sum4: 10.6667; Sum8: 21.8333; Sum12: 33; Sum16: 43.6667; Sum20: 55.1667; Sum24: 65.5; Sum28: 77.3333; Sum32: 88.5; Sum36: 99.25; Sum40: 110.4167; Sum44: 120.8333; Sum48: 132.1667; Sum52: 143
51% | 16.3333 | Sum4: 10.6667; Sum8: 21.8333; Sum12: 33.1667; Sum16: 43.7483; Sum20: 55.3333; Sum24: 65.8333; Sum28: 77.5; Sum32: 88.7483; Sum36: 99.5; Sum40: 110.915; Sum44: 121.3333; Sum48: 132.5817; Sum52: 143.3333
52% | 16.3333 | Sum4: 10.6667; Sum8: 22.1667; Sum12: 33.1667; Sum16: 43.9133; Sum20: 55.5; Sum24: 66; Sum28: 77.8333; Sum32: 88.9133; Sum36: 99.6667; Sum40: 111.1667; Sum44: 121.6667; Sum48: 132.8333; Sum52: 143.58
53% | 16.5 | Sum4: 10.8333; Sum8: 22.1667; Sum12: 33.3333; Sum16: 44.1667; Sum20: 55.5; Sum24: 66.3333; Sum28: 78; Sum32: 89.1667; Sum36: 99.745; Sum40: 111.3333; Sum44: 121.9117; Sum48: 132.8333; Sum52: 144
54% | 16.5 | Sum4: 11; Sum8: 22.3333; Sum12: 33.3333; Sum16: 44.3333; Sum20: 55.6667; Sum24: 66.5; Sum28: 78.3333; Sum32: 89.1667; Sum36: 100.0767; Sum40: 111.3333; Sum44: 122.1667; Sum48: 133.2433; Sum52: 144.3333
55% | 16.6667 | Sum4: 11; Sum8: 22.5; Sum12: 33.5; Sum16: 44.5; Sum20: 55.7417; Sum24: 66.5; Sum28: 78.5; Sum32: 89.3333; Sum36: 100.3333; Sum40: 111.5; Sum44: 122.4083; Sum48: 133.575; Sum52: 144.5
56% | 16.8333 | Sum4: 11.1667; Sum8: 22.6667; Sum12: 33.5; Sum16: 44.6667; Sum20: 55.8333; Sum24: 66.74; Sum28: 78.5; Sum32: 89.6667; Sum36: 100.5733; Sum40: 111.6667; Sum44: 122.6667; Sum48: 134.1667; Sum52: 144.74
57% | 16.8333 | Sum4: 11.1667; Sum8: 22.6667; Sum12: 33.5717; Sum16: 44.6667; Sum20: 56; Sum24: 66.8333; Sum28: 78.6667; Sum32: 89.8333; Sum36: 100.8333; Sum40: 112; Sum44: 122.6667; Sum48: 134.3333; Sum52: 145
58% | 17 | Sum4: 11.3333; Sum8: 22.6667; Sum12: 33.6667; Sum16: 44.9033; Sum20: 56.1667; Sum24: 67; Sum28: 78.9033; Sum32: 90.1667; Sum36: 101.2367; Sum40: 112.2367; Sum44: 123; Sum48: 134.5; Sum52: 145.1667
59% | 17 | Sum4: 11.4017; Sum8: 22.8333; Sum12: 33.8333; Sum16: 45.0683; Sum20: 56.3333; Sum24: 67.1667; Sum28: 79.1667; Sum32: 90.3333; Sum36: 101.6667; Sum40: 112.3333; Sum44: 123.0683; Sum48: 134.5683; Sum52: 145.5
60% | 17 | Sum4: 11.5; Sum8: 23; Sum12: 33.9; Sum16: 45.3333; Sum20: 56.5; Sum24: 67.4; Sum28: 79.3333; Sum32: 90.3333; Sum36: 101.8333; Sum40: 112.5667; Sum44: 123.3333; Sum48: 134.8333; Sum52: 145.8333
61% | 17.1667 | Sum4: 11.5; Sum8: 23; Sum12: 34; Sum16: 45.3333; Sum20: 56.6667; Sum24: 67.5; Sum28: 79.3333; Sum32: 90.5; Sum36: 101.8983; Sum40: 112.8333; Sum44: 123.5; Sum48: 135.065; Sum52: 146.065
62% | 17.3333 | Sum4: 11.5; Sum8: 23.1667; Sum12: 34.1667; Sum16: 45.5; Sum20: 56.8333; Sum24: 67.73; Sum28: 79.5; Sum32: 90.6667; Sum36: 102.1667; Sum40: 113; Sum44: 123.6667; Sum48: 135.5; Sum52: 146.3333
63% | 17.5 | Sum4: 11.5; Sum8: 23.1667; Sum12: 34.3333; Sum16: 45.5; Sum20: 57; Sum24: 68; Sum28: 79.8333; Sum32: 91; Sum36: 102.3333; Sum40: 113.3333; Sum44: 123.9567; Sum48: 135.6667; Sum52: 146.7283
64% | 17.5 | Sum4: 11.6667; Sum8: 23.2267; Sum12: 34.5; Sum16: 45.5; Sum20: 57.06; Sum24: 68.06; Sum28: 80; Sum32: 91.2267; Sum36: 102.56; Sum40: 113.5; Sum44: 124.5; Sum48: 135.8333; Sum52: 147.1667
65% | 17.6667 | Sum4: 11.6667; Sum8: 23.3333; Sum12: 34.6667; Sum16: 45.8333; Sum20: 57.1667; Sum24: 68.225; Sum28: 80.1667; Sum32: 91.5; Sum36: 102.8917; Sum40: 113.725; Sum44: 124.725; Sum48: 136.3917; Sum52: 147.5583
66% | 17.8333 | Sum4: 12; Sum8: 23.5; Sum12: 34.7233; Sum16: 46; Sum20: 57.3333; Sum24: 68.5; Sum28: 80.3333; Sum32: 91.89; Sum36: 103.1667; Sum40: 114.1667; Sum44: 125.1667; Sum48: 136.6667; Sum52: 147.8333
67% | 17.8333 | Sum4: 12; Sum8: 23.5; Sum12: 35; Sum16: 46; Sum20: 57.5; Sum24: 68.555; Sum28: 80.5; Sum32: 92.2217; Sum36: 103.3883; Sum40: 114.2217; Sum44: 125.5; Sum48: 137; Sum52: 148.3333
68% | 18 | Sum4: 12; Sum8: 23.5; Sum12: 35.1667; Sum16: 46.1667; Sum20: 57.8333; Sum24: 69; Sum28: 80.6667; Sum32: 92.3333; Sum36: 103.5; Sum40: 114.3333; Sum44: 126; Sum48: 137.3867; Sum52: 148.6667
69% | 18.1667 | Sum4: 12; Sum8: 23.6667; Sum12: 35.1667; Sum16: 46.3333; Sum20: 58; Sum24: 69.2183; Sum28: 80.8333; Sum32: 92.7183; Sum36: 103.6667; Sum40: 114.8333; Sum44: 126.2183; Sum48: 137.7183; Sum52: 149
70% | 18.3333 | Sum4: 12.1667; Sum8: 23.8333; Sum12: 35.3333; Sum16: 46.5; Sum20: 58; Sum24: 69.5; Sum28: 81.1667; Sum32: 92.8833; Sum36: 103.8333; Sum40: 115; Sum44: 126.6667; Sum48: 138.2167; Sum52: 149.2167
71% | 18.5 | Sum4: 12.3333; Sum8: 23.8817; Sum12: 35.6667; Sum16: 46.8333; Sum20: 58.1667; Sum24: 69.6667; Sum28: 81.3333; Sum32: 93.1667; Sum36: 104; Sum40: 115.5; Sum44: 126.8817; Sum48: 138.6667; Sum52: 149.5483
72% | 18.5 | Sum4: 12.3333; Sum8: 24; Sum12: 35.8333; Sum16: 46.8333; Sum20: 58.3333; Sum24: 69.8333; Sum28: 81.5; Sum32: 93.3333; Sum36: 104.5; Sum40: 115.6667; Sum44: 127.1667; Sum48: 138.8333; Sum52: 150
73% | 18.6667 | Sum4: 12.5; Sum8: 24; Sum12: 35.8783; Sum16: 47; Sum20: 58.545; Sum24: 70; Sum28: 81.6667; Sum32: 93.3333; Sum36: 105; Sum40: 116; Sum44: 127.4233; Sum48: 139.045; Sum52: 150.1667
74% | 18.6667 | Sum4: 12.5; Sum8: 24.1667; Sum12: 36; Sum16: 47.0433; Sum20: 58.8333; Sum24: 70.3333; Sum28: 81.8767; Sum32: 93.5433; Sum36: 105.3767; Sum40: 116.1667; Sum44: 128; Sum48: 139.3333; Sum52: 150.3767
75% | 18.8333 | Sum4: 12.6667; Sum8: 24.5; Sum12: 36.1667; Sum16: 47.375; Sum20: 59; Sum24: 70.5; Sum28: 82.0417; Sum32: 93.8333; Sum36: 105.6667; Sum40: 116.3333; Sum44: 128.3333; Sum48: 139.7083; Sum52: 150.875
76% | 19 | Sum4: 12.6667; Sum8: 24.5; Sum12: 36.2067; Sum16: 47.7067; Sum20: 59.1667; Sum24: 70.8333; Sum28: 82.3333; Sum32: 94; Sum36: 106; Sum40: 116.8333; Sum44: 128.5; Sum48: 140.1667; Sum52: 151.2067
77% | 19 | Sum4: 12.8333; Sum8: 24.6667; Sum12: 36.5; Sum16: 47.8333; Sum20: 59.1667; Sum24: 71.0383; Sum28: 82.3717; Sum32: 94.1667; Sum36: 106.1667; Sum40: 117.1667; Sum44: 128.8333; Sum48: 140.5; Sum52: 151.5383
78% | 19 | Sum4: 13; Sum8: 24.7033; Sum12: 36.6667; Sum16: 48.3333; Sum20: 59.37; Sum24: 71.3333; Sum28: 82.7033; Sum32: 94.5; Sum36: 106.5; Sum40: 117.3333; Sum44: 129; Sum48: 140.8333; Sum52: 152
79% | 19.1667 | Sum4: 13; Sum8: 25; Sum12: 36.7017; Sum16: 48.5; Sum20: 59.8333; Sum24: 71.3333; Sum28: 83; Sum32: 94.6667; Sum36: 107; Sum40: 117.5; Sum44: 129.535; Sum48: 141; Sum52: 152.3333
80% | 19.3333 | Sum4: 13; Sum8: 25; Sum12: 36.8667; Sum16: 48.6667; Sum20: 59.8667; Sum24: 71.5; Sum28: 83; Sum32: 94.8333; Sum36: 107.2; Sum40: 117.8667; Sum44: 130.0333; Sum48: 141.3333; Sum52: 152.6667
81% | 19.3333 | Sum4: 13.1667; Sum8: 25; Sum12: 37; Sum16: 49; Sum20: 60.0317; Sum24: 71.8333; Sum28: 83.23; Sum32: 95; Sum36: 107.5; Sum40: 118.1983; Sum44: 130.1983; Sum48: 141.5317; Sum52: 153.095
82% | 19.5 | Sum4: 13.1967; Sum8: 25.1667; Sum12: 37.1667; Sum16: 49.03; Sum20: 60.3333; Sum24: 72.1667; Sum28: 83.6667; Sum32: 95.3333; Sum36: 107.8633; Sum40: 118.6667; Sum44: 130.3633; Sum48: 142; Sum52: 153.8333
83% | 19.5283 | Sum4: 13.5; Sum8: 25.3333; Sum12: 37.3333; Sum16: 49.5283; Sum20: 60.695; Sum24: 72.3617; Sum28: 84; Sum32: 95.6667; Sum36: 108.1667; Sum40: 119.1667; Sum44: 130.7233; Sum48: 142.2233; Sum52: 154
84% | 19.8333 | Sum4: 13.5267; Sum8: 25.5; Sum12: 37.5; Sum16: 49.8333; Sum20: 61.0267; Sum24: 72.6667; Sum28: 84.1667; Sum32: 96.0533; Sum36: 108.5267; Sum40: 119.6667; Sum44: 131.3333; Sum48: 142.6667; Sum52: 154.1667
85% | 20 | Sum4: 13.8333; Sum8: 25.8333; Sum12: 37.6667; Sum16: 50.1667; Sum20: 61.5; Sum24: 73.1667; Sum28: 84.5; Sum32: 96.525; Sum36: 108.8333; Sum40: 120.1917; Sum44: 131.8333; Sum48: 143; Sum52: 154.575
86% | 20 | Sum4: 14; Sum8: 26; Sum12: 37.8333; Sum16: 50.5; Sum20: 61.69; Sum24: 73.5; Sum28: 84.8567; Sum32: 97; Sum36: 109; Sum40: 120.3567; Sum44: 132; Sum48: 143.5; Sum52: 155.3567
87% | 20.1667 | Sum4: 14; Sum8: 26; Sum12: 38; Sum16: 50.6667; Sum20: 62.0217; Sum24: 73.8767; Sum28: 85.7317; Sum32: 97.355; Sum36: 109.1667; Sum40: 121.0217; Sum44: 132.1883; Sum48: 144.5; Sum52: 156
88% | 20.3333 | Sum4: 14; Sum8: 26.3333; Sum12: 38.1867; Sum16: 50.8533; Sum20: 62.3533; Sum24: 74.8333; Sum28: 86.52; Sum32: 97.8333; Sum36: 109.3533; Sum40: 121.5; Sum44: 132.52; Sum48: 145.5; Sum52: 156.3333
89% | 20.5 | Sum4: 14.185; Sum8: 26.5; Sum12: 38.3517; Sum16: 51.1667; Sum20: 62.8333; Sum24: 75.185; Sum28: 86.8333; Sum32: 98.0183; Sum36: 109.8883; Sum40: 121.8333; Sum44: 133; Sum48: 146.0183; Sum52: 156.5183
90% | 20.6667 | Sum4: 14.5; Sum8: 26.6833; Sum12: 38.5167; Sum16: 51.3333; Sum20: 63.35; Sum24: 75.6667; Sum28: 87.1667; Sum32: 98.35; Sum36: 110.6667; Sum40: 122.3333; Sum44: 134; Sum48: 146.5; Sum52: 157.8333
91% | 21 | Sum4: 14.5; Sum8: 27; Sum12: 39; Sum16: 52; Sum20: 64; Sum24: 76; Sum28: 87.3483; Sum32: 98.8333; Sum36: 111.1817; Sum40: 122.8333; Sum44: 134.3483; Sum48: 146.8333; Sum52: 158.1667
92% | 21 | Sum4: 14.6667; Sum8: 27.3333; Sum12: 39.3467; Sum16: 52.3467; Sum20: 64.18; Sum24: 76.3467; Sum28: 88; Sum32: 99.1667; Sum36: 111.8467; Sum40: 123.0133; Sum44: 135.3467; Sum48: 147.3333; Sum52: 158.7067
93% | 21.1667 | Sum4: 15; Sum8: 27.6667; Sum12: 39.845; Sum16: 53.1667; Sum20: 64.6783; Sum24: 77.0117; Sum28: 88.1783; Sum32: 99.5; Sum36: 112.845; Sum40: 123.5; Sum44: 136.3333; Sum48: 148.3683; Sum52: 159.3333
94% | 21.3433 | Sum4: 15; Sum8: 27.8333; Sum12: 40.6667; Sum16: 53.6767; Sum20: 65.3333; Sum24: 78; Sum28: 88.8433; Sum32: 100; Sum36: 114.01; Sum40: 124.51; Sum44: 137.1767; Sum48: 149.3333; Sum52: 160
95% | 21.6667 | Sum4: 15.175; Sum8: 28.1667; Sum12: 41.175; Sum16: 54.0083; Sum20: 66.3417; Sum24: 78.3333; Sum28: 89.6833; Sum32: 101.1833; Sum36: 114.3333; Sum40: 126; Sum44: 137.675; Sum48: 149.8417; Sum52: 160.5083
96% | 22.0133 | Sum4: 15.5; Sum8: 28.6667; Sum12: 41.6667; Sum16: 54.6733; Sum20: 67.1733; Sum24: 78.8467; Sum28: 91.0133; Sum32: 102.6867; Sum36: 114.84; Sum40: 126.8467; Sum44: 138.6867; Sum48: 150.6667; Sum52: 161.0067
97% | 22.6667 | Sum4: 15.6767; Sum8: 29; Sum12: 42.3333; Sum16: 55.505; Sum20: 67.8383; Sum24: 79.505; Sum28: 91.8383; Sum32: 105; Sum36: 115.3583; Sum40: 128; Sum44: 139.505; Sum48: 151.005; Sum52: 162.6717
98% | 23.01 | Sum4: 16.3333; Sum8: 29.5033; Sum12: 43.3367; Sum16: 56.0067; Sum20: 69.8333; Sum24: 80.18; Sum28: 93.5033; Sum32: 105.3633; Sum36: 118.6667; Sum40: 129.3367; Sum44: 141.5033; Sum48: 152.51; Sum52: 163.3667
99% | 24 | Sum4: 18; Sum8: 30.505; Sum12: 45.3333; Sum16: 58.5017; Sum20: 70.67; Sum24: 82.8417; Sum28: 94.345; Sum32: 107.6683; Sum36: 119.0067; Sum40: 131.17; Sum44: 142.1683; Sum48: 154.6667; Sum52: 166.0067
100% | 26 | Sum4: 20; Sum8: 34.3333; Sum12: 47.3333; Sum16: 60.8333; Sum20: 77; Sum24: 88.3333; Sum28: 99.3333; Sum32: 117; Sum36: 131.3333; Sum40: 140.6667; Sum44: 149.5; Sum48: 162.8333; Sum52: 173.5