## Instructions
Single Feature Forecaster
Always get the latest version of this spreadsheet here.
Version history:
| 1 | 2015-04-07 | Initial beta release for feedback.
| 1.01 | 2015-05-22 | Fixed validation usability errors.
| 1.1 | 2015-05-26 | Added risks and charts.
| 1.2 | 2015-06-01 | Updated instructions and charts.
| 1.3 | 2016-02-12 | Added split rate inputs.
| 1.4 | 2016-06-01 | Added actual plot.
| 1.5 | 2016-06-02 | Added story count forecast by period.
| 1.6 | 2017-06-09 | Added risk impact scores and increased risks to 10 entries
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features and stories based on range estimates.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarentee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). We will be providing a viz that gathers this data for your team. Stay tuned.
What is this: This spreadsheet helps to probabilistically forecast how long it will take to complete features based on story count range estimates and either estimated team throughput or historical team throughput samples.
How does it work? Given your estimates, this spreadsheet hypothetically completes all work 500 times. It calculates likelihood result as the number of simulated trials that finished on or before a given date. Given your desired scenario order, features are completed in order and the dates computed based on specified likelihood.
Why is this better than burndowns and traditional Agile forecasting? Most forecasting techniques give a single date result and hide the likelihood of that date. Most often the date given as the result is 50% because work is divided by an average (or median). Thats the odds of a toin-coss. This method allows the reader to choose the amount of schedule risk they wish to sign-up for. 85% is a common middle ground used in the industry.
Is it reliable? It has no mathematical errors (that we know of!), and all we guarantee is its better than intuition alone and better than simple regression models. But, help us improve it by letting us know when it misses the actual results you are seeing.
How to: Fill in the orange boxes in the Forecast worksheet and read off the dates in the results table adjacent to the likelihood/certainty you think is appropriate. 85% is a common industry level of certainty used - a good balance of better than average but not susceptible to extreme outliers.
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.

## Forecast
Forecast Completion Date | [7 empty] | Results
Duration in
1. Start Date |  |  | 2017-07-01 |  |  |  |  | Likelihood | 1 week's | Date
[8 empty] | 100% | 28 | 2018-01-13
2. How many stories are remaining to be completed? | [7 empty] | 95% | 25 | 2017-12-23
(enter the range estimate of stories. Tip: start wide and narrow as certainty increases) | [7 empty] | 90% | 24 | 2017-12-16
| Low guess |  | 50 |  | Highest guess |  | 58 | 85% | 23 | 2017-12-09
[8 empty] | 80% | 22 | 2017-12-02
3. Stories are often split before and whilst being worked on. Estimate the split rate low and high bounds. | [7 empty] | 75% | 22 | 2017-12-02
(often the throughput in the backlog is pre-split, but captured throughput post-split. Adjust for this here) | [7 empty] | 70% | 21 | 2017-11-25
| Low guess |  | 1 |  | Highest guess |  | 2 | 65% | 20 | 2017-11-18
[8 empty] | 60% | 20 | 2017-11-18
4. Throughput. How many completed stories per week or sprint do you estimate low and high bounds? | [7 empty] | 55% | 19 | 2017-11-11
[8 empty] | 50% | 19 | 2017-11-11
Throughput/velocity data or estimate is for |  |  |  | 1 week | 7 | days |  | 45% | 18 | 2017-11-04
(choose a time interval that throughput of velocity is measured in weeks from the list in the orange cell above) | [7 empty] | 40% | 18 | 2017-11-04
Use historical throughput data OR enter a low and high estimate below. Use: | [6 empty] | Estimate | 35% | 17 | 2017-10-28
[8 empty] | 30% | 16 | 2017-10-21
[8 empty] | 25% | 16 | 2017-10-21
| Low guess |  | 3 |  | Highest guess |  | 6 | 20% | 15 | 2017-10-14
[8 empty] | 15% | 15 | 2017-10-14
[8 empty] | 10% | 14 | 2017-10-07
[8 empty] | 5% | 13 | 2017-09-30
[8 empty] | 0% | 11 | 2017-09-16
Forecast Story Count Completion by Time Period
5. How long? |  | 6 | 1 weeks |  | Result: Total Pre-split Stories in 6 1 weeks
(To forecast story counts, enter the how long. |  |  |  |  | (Pre-split means, splitting IS accounted for)
To change unit, change input 4. above.) |  |  |  |  | 95% | 14.5
[5 empty] | 85% | 16.5 | <--- Tip: This is your forecasted # storiess for this period at 85% confidence
[5 empty] | 5% | 26.025
Almost certain
Somewhat certain
Less than coin-toss odds. But if you are game?
Can I use velocity rather than throughput?
Yes. If you do have estimates in story points, then you can sume all of the estimates and use that for input 2 and estimate or use historical team velocity for input 4. The benefit of using throughput (count of completed stories per week/sprint) is that the individual stories don't require estimation in story points.
Please Remember: This forecast is only as good as the estimates you enter into it. Always look for multiple ways to forecast your project and compare the outcomes, especially if making a financially critical decision. In the end - any decision to proceed with a project is YOURS.
How do I use this story count forecast?
This forecast aims to show how many stories might be completed given the team data or estimates entered above. Enter all data for inputs 3. and 4. above. This forecast simulates 500 times to determine what number of stories will be completed for the period you entered for input 5. It also creates a chart view of this forecast in the charts tab. This forecast ignores risk data, and un-necessary inputs 1 and 2 from above.
Note on I16: Troy Magennis: This is the measure of how two random groups of your sample data would align when forecasting. Anything below 25% is good, but lower is better. It grows if there is too little data, and ALSO if the process changes over time and you use too much data.

## Risks
Likelihood | Impact Low | Impact High | Description | Combined Impact (higher is worse) | Est. impact in 1 week's | Impact Rank (fix lowest first)
Calculations -
Likelihood | Impact Low | Impact High | Description | average story count | 81
30% | 10 | 15 | Server performance issues | duration at 85th P | 23
15% | 5 | 10 | Layout issues when text localized | count per period | 3.5217
20% | 5 | 15 | Layout in Safari issues
Why would I use risks?
Risks allow you to put a probability on work being expanded because of something more than plan. For eample, there might be a chance that more work is needed to improve performance characteristics. If you think there is a 20% chance, put 20 in the likelihood column. Have the team estimate the low and high story count to rectify and add these to the low and high impact columns.
Risk impact analysis
It can be hard to determine what risks are most impactful when they have different likelihoods and impacts. The risks are ranked here from most impactful (Rank = 1) to least impactful.
This is a simple ranking. It helps quickly see what is the most important to decrease likelihood or impact.

## Charts
[14 empty] | Week | Frequency
[14 empty] | 2017-09-16 | 5
[14 empty] | 2017-09-23 | 13
[14 empty] | 2017-09-30 | 21
[14 empty] | 2017-10-07 | 35
[14 empty] | 2017-10-14 | 36
[14 empty] | 2017-10-21 | 46
[14 empty] | 2017-10-28 | 32
[14 empty] | 2017-11-04 | 41
[14 empty] | 2017-11-11 | 56
[14 empty] | 2017-11-18 | 51
[14 empty] | 2017-11-25 | 36
[14 empty] | 2017-12-02 | 38
[14 empty] | 2017-12-09 | 35
[14 empty] | 2017-12-16 | 27
[14 empty] | 2017-12-23 | 13
[14 empty] | 2017-12-30 | 11
[14 empty] | 2018-01-06 | 4
[14 empty] | 2018-01-13 | 1
0
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
Story count results in table form. For the probabilities entered, how many stories for each period?
| 4 1 weeks | 8 1 weeks | 12 1 weeks | 16 1 weeks | 20 1 weeks | 24 1 weeks | 28 1 weeks | 32 1 weeks | 36 1 weeks | 40 1 weeks | 44 1 weeks | 48 1 weeks | 52 1 weeks
95% | 9 | 20.975 | 32.5 | 44 | 56.475 | 68 | 80 | 94 | 106.5 | 119.5 | 131 | 144 | 156.475
85% | 10.425 | 22.5 | 34.925 | 47.5 | 59.5 | 72.5 | 85.5 | 99.5 | 112 | 125 | 138 | 151.5 | 164
5% | 18.525 | 33.525 | 48 | 63 | 77.5 | 92 | 107.025 | 121.5 | 135.5 | 149.525 | 163.525 | 178.5 | 192.05
What is this chart?
This chart shows how many simulated trials completed on or before the x-axis date. The higher the bar, the more likely that outcome.
What is this chart?
This chart shows the simulated burn-down trends. It shows the first 50 trials and visually shows the general hotspots and outlier dates. Enter actual stories remaining in the Reamining Stories Actual worksheet to see progress.
What is this chart?
This chart shows the number of completed (pre-split) stories for a given period. Select the time period on the forecast worksheet. The forecast is shown at three confidence intervals specified on the forecast worksheet.

## Throughput Samples
Enter Samples Below | Group | Unique Rank
3 | 1 | 3
5 | 1 | 5
2 | 2 | 2
1 | 1 | 1
5 | 2 | 6
6 | 1 | 7
4 | 2 | 4
Stability Between Two Random Groups of the Samples
|  |  | Group | All | 1 | 2 | Diff
|  |  | count | 7 | 4 | 3 | 1
|  |  | min | 1 | 1 | 2
|  |  | max | 6 | 6 | 5
|  |  | avg | 3.7143 | 3.75 | 3.6667 | 0.083333
|  |  | median | 4 | 4 | 4 | 0
|  |  | avg error |  |  |  | 0.083333 | I also tried average of the mean and median error….but think average will do.
|  |  | error/range |  |  |  | 1.667% | Aim to keep this below 25%. By adding more sample data. You will see where to stop.
Transportable data formats
|  |  | Total Count |  | 7 |  |  |  |  | CSV | 3,5,2,1,5,6,4,
|  |  | Data |  | 2 | 6 | 2 | 5 | 4 | SIP 2.0 | <sip name="dist" type="CSV" ver="1.0" count="7" average="3.71428571428571" median="4">3,5,2,1,5,6,4,</sip>
|  |  | Estimate |  | 5 | 3 | 5 | 3 | 3 | Distribution | <distribution name="dist" shape="fromSamples">3,5,2,1,5,6,4,</distribution>
|  |  | Samples Or Data |  | 3 | 6 | 4 | 4 | 3
Instructions.
If you have team historic throughput samples, you can use them when forecasting forward. If not, estimate the range in the forecast sheet. When actual data becomes available, add it here and your forecast will become more indicative.
Add seven (7) minimum, and twenty five (25) maximum recent throughput samples for your team. These samples will be used as throughput values picked at random. By using your teams data, the forecast will follow the patterns your teams throughput historically follows.
Remember to set the unit of throughput measure.
No blank rows within sample range, leave rows after the last sample blank.
Data beyond 24 weeks is most likely out of date. When adding, add most recent samples to the top and remove older samples from the bottom.
These are for testing the formulas that return random ssamples from data or between the estimates. They are included here for education and reference.
These formats are to help share throughput samples with others or teams should the need arise.
CSV = simple comma separated value list
SIP 2.0 = ProbabilityManagement.org's SIP standard for sharing data
Distribution = FocusedObjective.com's distribution format for sharing and creating random data from samples in their simulation software
What is throughput? Where do I get that data? Throughput is the number of DONE stories completed by a team per week or per sprint (you choose in this spreadsheet, default is per week). Also see our Throughput and Cycle Time Calculator spreadsheet for convertinf story/item data to throughput values. Also see our tutorials on how to use Excel to calculate throughput rates.
How many amples?
You could make this spreadsheet use more historical data, but its not statistically necessary. My advice: use the most recent 15 samples if you have them to avoid using "old" data that was cptured when the team was performing differently than it is now. You should use the most recent data where the error percentage is less than 10%

## Remaining Stories Actuals
Date (week ending) | Number of Incompleted (but in scope) stories | Notes
2017-07-01 | 27
2017-07-08 | 25
2017-07-15 | 20
2017-07-22 | 19
2017-07-29
2017-08-05
2017-08-12
2017-08-19
2017-08-26
2017-09-02
2017-09-09
2017-09-16
2017-09-23
2017-09-30
2017-10-07
2017-10-14
2017-10-21
2017-10-28
2017-11-04
2017-11-11
2017-11-18
2017-11-25
2017-12-02
2017-12-09
2017-12-16
2017-12-23
2017-12-30
2018-01-06
2018-01-13
2018-01-20
2018-01-27
2018-02-03
2018-02-10
2018-02-17
2018-02-24
2018-03-03
2018-03-10
2018-03-17
2018-03-24
2018-03-31
2018-04-07
2018-04-14
2018-04-21
2018-04-28
2018-05-05
2018-05-12
2018-05-19
2018-05-26
2018-06-02
2018-06-09
2018-06-16
Instructions.
Enter the actual number of IN-COMPLETE items in the backlog in column B for the dates shown in column A. This line will be charted on the burndown chart.

## Settings
Duration name | days
1 week | 7
2 weeks | 14
3 weeks | 21
4 weeks | 28
This table converts throughput duration name to number of days. Add more or edit these here. The days is used to increment forecasting periods. Resolution of forecast will also be in increments of this value.

## Monte Carlo (hidden)
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
 | time axis 2017-07-01 to 2018-06-30
1 | 18 | 2017-11-04 | 89 | 83 | 77 | 73 | 67 | 61 | 56 | 53 | 49 | 44 | 39 | 34 | 28 | 22 | 16 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 22 | 2017-12-02 | 94 | 91 | 88 | 85 | 79 | 75 | 70 | 66 | 61 | 56 | 53 | 49 | 44 | 41 | 36 | 32 | 27 | 23 | 20 | 15 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 19 | 2017-11-11 | 87 | 82 | 78 | 74 | 68 | 63 | 58 | 54 | 48 | 45 | 41 | 38 | 34 | 31 | 26 | 20 | 16 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 20 | 2017-11-18 | 91 | 87 | 82 | 79 | 73 | 67 | 61 | 58 | 54 | 48 | 42 | 36 | 32 | 26 | 23 | 18 | 14 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 16 | 2017-10-21 | 68 | 63 | 60 | 57 | 52 | 48 | 43 | 38 | 34 | 28 | 25 | 19 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 25 | 2017-12-23 | 99 | 95 | 90 | 87 | 82 | 79 | 76 | 73 | 70 | 67 | 63 | 58 | 53 | 48 | 44 | 41 | 36 | 32 | 29 | 26 | 21 | 15 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 22 | 2017-12-02 | 100 | 94 | 88 | 84 | 78 | 74 | 68 | 63 | 60 | 57 | 53 | 47 | 42 | 37 | 34 | 29 | 26 | 22 | 17 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 20 | 2017-11-18 | 88 | 82 | 77 | 73 | 67 | 63 | 60 | 54 | 51 | 48 | 44 | 39 | 36 | 30 | 26 | 23 | 20 | 15 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 21 | 2017-11-25 | 93 | 89 | 86 | 82 | 76 | 72 | 68 | 64 | 59 | 56 | 52 | 48 | 42 | 36 | 31 | 28 | 22 | 16 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 18 | 2017-11-04 | 85 | 80 | 77 | 73 | 68 | 62 | 56 | 51 | 46 | 43 | 40 | 35 | 30 | 24 | 18 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 15 | 2017-10-14 | 69 | 64 | 58 | 52 | 46 | 41 | 35 | 29 | 23 | 20 | 17 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 21 | 2017-11-25 | 93 | 90 | 86 | 82 | 77 | 71 | 68 | 62 | 58 | 54 | 50 | 47 | 43 | 38 | 32 | 26 | 23 | 18 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 16 | 2017-10-21 | 76 | 73 | 67 | 62 | 56 | 51 | 47 | 44 | 38 | 33 | 27 | 22 | 16 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 24 | 2017-12-16 | 104 | 100 | 94 | 91 | 85 | 81 | 75 | 71 | 67 | 62 | 57 | 52 | 46 | 43 | 40 | 35 | 32 | 27 | 23 | 18 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 14 | 2017-10-07 | 63 | 59 | 53 | 50 | 45 | 39 | 33 | 28 | 24 | 20 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 19 | 2017-11-11 | 79 | 75 | 71 | 66 | 63 | 59 | 56 | 51 | 48 | 42 | 39 | 34 | 31 | 28 | 24 | 20 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 15 | 2017-10-14 | 64 | 58 | 52 | 47 | 41 | 38 | 32 | 27 | 23 | 19 | 13 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 24 | 2017-12-16 | 103 | 98 | 94 | 90 | 87 | 81 | 78 | 73 | 67 | 62 | 56 | 53 | 49 | 44 | 39 | 36 | 30 | 25 | 20 | 17 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 19 | 2017-11-11 | 78 | 73 | 67 | 64 | 59 | 54 | 51 | 48 | 45 | 42 | 37 | 34 | 30 | 26 | 21 | 18 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 17 | 2017-10-28 | 68 | 62 | 59 | 56 | 50 | 47 | 41 | 37 | 33 | 27 | 24 | 21 | 18 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 15 | 2017-10-14 | 63 | 59 | 55 | 49 | 46 | 43 | 40 | 35 | 31 | 26 | 23 | 20 | 16 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 25 | 2017-12-23 | 109 | 103 | 99 | 95 | 92 | 87 | 84 | 81 | 78 | 73 | 68 | 62 | 59 | 55 | 49 | 43 | 40 | 37 | 32 | 29 | 25 | 19 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 26 | 2017-12-30 | 110 | 104 | 99 | 96 | 92 | 86 | 82 | 76 | 72 | 68 | 65 | 61 | 56 | 50 | 47 | 44 | 40 | 34 | 31 | 28 | 25 | 19 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 25 | 2017-12-23 | 104 | 99 | 94 | 89 | 85 | 79 | 75 | 71 | 68 | 64 | 58 | 54 | 48 | 44 | 40 | 37 | 33 | 28 | 25 | 22 | 19 | 13 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 24 | 2017-12-16 | 103 | 97 | 91 | 87 | 82 | 77 | 74 | 71 | 67 | 63 | 60 | 57 | 52 | 46 | 43 | 40 | 34 | 31 | 26 | 21 | 16 | 13 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 16 | 2017-10-21 | 67 | 64 | 61 | 58 | 52 | 49 | 43 | 39 | 34 | 30 | 24 | 19 | 14 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 18 | 2017-11-04 | 77 | 73 | 68 | 64 | 59 | 56 | 53 | 47 | 41 | 36 | 33 | 30 | 27 | 24 | 19 | 15 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 16 | 2017-10-21 | 75 | 70 | 66 | 60 | 54 | 49 | 46 | 40 | 35 | 30 | 26 | 21 | 16 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 14 | 2017-10-07 | 57 | 54 | 51 | 46 | 40 | 36 | 33 | 29 | 26 | 20 | 16 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 21 | 2017-11-25 | 90 | 85 | 80 | 77 | 71 | 65 | 60 | 55 | 51 | 48 | 44 | 41 | 36 | 31 | 26 | 23 | 20 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 22 | 2017-12-02 | 104 | 100 | 94 | 91 | 86 | 81 | 77 | 72 | 66 | 61 | 57 | 51 | 48 | 45 | 42 | 37 | 31 | 25 | 19 | 15 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 20 | 2017-11-18 | 94 | 88 | 83 | 77 | 74 | 69 | 63 | 60 | 56 | 51 | 46 | 41 | 36 | 30 | 26 | 23 | 18 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 16 | 2017-10-21 | 79 | 75 | 70 | 65 | 62 | 57 | 52 | 46 | 40 | 34 | 28 | 23 | 18 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 20 | 2017-11-18 | 87 | 81 | 78 | 75 | 70 | 64 | 59 | 54 | 51 | 48 | 44 | 40 | 35 | 32 | 29 | 24 | 18 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 16 | 2017-10-21 | 60 | 57 | 54 | 51 | 47 | 44 | 40 | 35 | 32 | 27 | 23 | 20 | 17 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 20 | 2017-11-18 | 84 | 81 | 76 | 70 | 64 | 60 | 57 | 53 | 50 | 47 | 44 | 39 | 34 | 30 | 24 | 20 | 14 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 19 | 2017-11-11 | 76 | 73 | 69 | 65 | 60 | 57 | 52 | 48 | 42 | 36 | 31 | 28 | 22 | 19 | 15 | 11 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 14 | 2017-10-07 | 67 | 61 | 56 | 53 | 48 | 45 | 42 | 37 | 31 | 26 | 22 | 16 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 16 | 2017-10-21 | 75 | 70 | 67 | 63 | 59 | 55 | 50 | 44 | 38 | 34 | 28 | 23 | 18 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 23 | 2017-12-09 | 102 | 99 | 93 | 87 | 82 | 77 | 73 | 69 | 66 | 63 | 57 | 54 | 49 | 45 | 39 | 33 | 27 | 22 | 17 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 17 | 2017-10-28 | 73 | 68 | 65 | 60 | 57 | 53 | 48 | 44 | 39 | 35 | 30 | 25 | 19 | 16 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 12 | 2017-09-23 | 58 | 55 | 51 | 45 | 39 | 33 | 29 | 25 | 19 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 19 | 2017-11-11 | 79 | 75 | 72 | 67 | 63 | 60 | 55 | 52 | 46 | 41 | 36 | 31 | 28 | 24 | 18 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 20 | 2017-11-18 | 84 | 81 | 77 | 73 | 70 | 67 | 62 | 58 | 54 | 48 | 43 | 39 | 33 | 28 | 24 | 20 | 17 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 23 | 2017-12-09 | 90 | 86 | 83 | 79 | 73 | 68 | 63 | 59 | 54 | 48 | 45 | 42 | 39 | 36 | 33 | 30 | 27 | 22 | 18 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 23 | 2017-12-09 | 99 | 96 | 93 | 87 | 81 | 78 | 74 | 70 | 66 | 60 | 55 | 52 | 48 | 45 | 40 | 34 | 30 | 27 | 21 | 17 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 20 | 2017-11-18 | 83 | 77 | 71 | 66 | 61 | 57 | 54 | 51 | 47 | 42 | 38 | 34 | 30 | 27 | 21 | 18 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 24 | 2017-12-16 | 105 | 101 | 95 | 89 | 83 | 78 | 75 | 72 | 68 | 64 | 61 | 56 | 53 | 48 | 45 | 41 | 38 | 35 | 29 | 26 | 21 | 16 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 22 | 2017-12-02 | 88 | 82 | 79 | 74 | 70 | 67 | 63 | 59 | 55 | 51 | 46 | 42 | 38 | 34 | 31 | 28 | 23 | 19 | 16 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 21 | 2017-11-25 | 93 | 89 | 85 | 80 | 74 | 71 | 66 | 63 | 58 | 54 | 50 | 45 | 42 | 37 | 31 | 28 | 23 | 18 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 12 | 2017-09-23 | 53 | 47 | 42 | 37 | 33 | 28 | 25 | 21 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 19 | 2017-11-11 | 88 | 85 | 81 | 75 | 72 | 67 | 63 | 59 | 53 | 48 | 45 | 39 | 35 | 29 | 25 | 20 | 14 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 21 | 2017-11-25 | 96 | 90 | 84 | 80 | 74 | 69 | 65 | 62 | 58 | 52 | 48 | 42 | 39 | 36 | 31 | 28 | 22 | 18 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 22 | 2017-12-02 | 98 | 93 | 90 | 85 | 81 | 76 | 70 | 67 | 63 | 58 | 54 | 48 | 43 | 40 | 35 | 31 | 28 | 23 | 18 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 15 | 2017-10-14 | 63 | 59 | 55 | 49 | 45 | 41 | 38 | 33 | 30 | 26 | 23 | 18 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 16 | 2017-10-21 | 70 | 66 | 61 | 57 | 52 | 48 | 45 | 40 | 36 | 31 | 27 | 21 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 17 | 2017-10-28 | 83 | 79 | 74 | 68 | 65 | 60 | 54 | 48 | 44 | 38 | 35 | 30 | 24 | 19 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 14 | 2017-10-07 | 69 | 63 | 58 | 52 | 47 | 41 | 37 | 32 | 26 | 21 | 16 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 17 | 2017-10-28 | 66 | 63 | 59 | 54 | 50 | 46 | 43 | 38 | 34 | 31 | 27 | 23 | 20 | 15 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 20 | 2017-11-18 | 85 | 82 | 78 | 73 | 67 | 64 | 61 | 58 | 52 | 48 | 44 | 40 | 34 | 28 | 23 | 19 | 14 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 23 | 2017-12-09 | 94 | 90 | 85 | 82 | 77 | 71 | 67 | 64 | 61 | 58 | 52 | 47 | 43 | 40 | 35 | 30 | 25 | 21 | 18 | 14 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 13 | 2017-09-30 | 53 | 47 | 43 | 39 | 36 | 32 | 29 | 24 | 20 | 16 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 16 | 2017-10-21 | 69 | 63 | 58 | 52 | 47 | 44 | 38 | 34 | 30 | 25 | 22 | 17 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 25 | 2017-12-23 | 108 | 105 | 101 | 97 | 94 | 89 | 85 | 82 | 79 | 73 | 69 | 63 | 60 | 55 | 50 | 44 | 40 | 36 | 30 | 26 | 23 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 23 | 2017-12-09 | 107 | 103 | 99 | 93 | 90 | 87 | 82 | 78 | 72 | 67 | 62 | 56 | 52 | 46 | 43 | 37 | 31 | 27 | 21 | 18 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 17 | 2017-10-28 | 73 | 68 | 65 | 59 | 56 | 51 | 45 | 41 | 36 | 31 | 25 | 21 | 16 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 14 | 2017-10-07 | 63 | 59 | 55 | 49 | 45 | 40 | 35 | 32 | 26 | 22 | 19 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 20 | 2017-11-18 | 87 | 83 | 79 | 74 | 69 | 63 | 59 | 53 | 47 | 44 | 39 | 36 | 30 | 27 | 24 | 19 | 14 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 28 | 2018-01-13 | 111 | 105 | 102 | 98 | 93 | 90 | 87 | 84 | 79 | 74 | 70 | 66 | 63 | 60 | 57 | 51 | 46 | 43 | 40 | 34 | 31 | 25 | 21 | 16 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 22 | 2017-12-02 | 96 | 93 | 88 | 85 | 79 | 75 | 69 | 66 | 63 | 58 | 54 | 48 | 45 | 41 | 36 | 33 | 29 | 24 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 16 | 2017-10-21 | 67 | 61 | 57 | 54 | 49 | 45 | 40 | 37 | 31 | 27 | 24 | 21 | 15 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 13 | 2017-09-30 | 57 | 54 | 50 | 45 | 41 | 38 | 32 | 26 | 22 | 19 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 25 | 2017-12-23 | 111 | 108 | 102 | 96 | 93 | 89 | 84 | 78 | 72 | 66 | 61 | 55 | 49 | 44 | 39 | 36 | 31 | 27 | 22 | 19 | 15 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 12 | 2017-09-23 | 61 | 56 | 51 | 45 | 39 | 34 | 30 | 25 | 19 | 14 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 14 | 2017-10-07 | 62 | 59 | 53 | 48 | 44 | 39 | 34 | 29 | 26 | 21 | 16 | 13 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 18 | 2017-11-04 | 71 | 68 | 64 | 61 | 58 | 54 | 50 | 45 | 41 | 35 | 30 | 27 | 24 | 20 | 17 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 21 | 2017-11-25 | 88 | 85 | 81 | 77 | 71 | 66 | 60 | 57 | 54 | 51 | 48 | 45 | 40 | 36 | 33 | 27 | 21 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 16 | 2017-10-21 | 69 | 64 | 59 | 56 | 53 | 48 | 45 | 39 | 34 | 31 | 27 | 23 | 17 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 16 | 2017-10-21 | 69 | 65 | 59 | 56 | 50 | 47 | 41 | 36 | 32 | 29 | 24 | 18 | 15 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 22 | 2017-12-02 | 92 | 88 | 83 | 77 | 72 | 69 | 66 | 63 | 60 | 57 | 53 | 49 | 46 | 42 | 38 | 33 | 27 | 24 | 18 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 18 | 2017-11-04 | 88 | 85 | 80 | 77 | 72 | 66 | 60 | 55 | 49 | 45 | 39 | 33 | 27 | 21 | 16 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 18 | 2017-11-04 | 72 | 69 | 64 | 59 | 56 | 52 | 48 | 42 | 37 | 32 | 27 | 24 | 20 | 17 | 13 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 23 | 2017-12-09 | 99 | 93 | 88 | 82 | 78 | 74 | 69 | 64 | 60 | 57 | 51 | 48 | 42 | 38 | 35 | 30 | 24 | 21 | 18 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 16 | 2017-10-21 | 81 | 76 | 71 | 66 | 62 | 58 | 53 | 48 | 43 | 37 | 31 | 25 | 19 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 21 | 2017-11-25 | 94 | 89 | 85 | 81 | 75 | 69 | 65 | 62 | 57 | 53 | 47 | 43 | 38 | 32 | 27 | 24 | 20 | 15 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 15 | 2017-10-14 | 72 | 67 | 61 | 58 | 53 | 48 | 44 | 40 | 34 | 28 | 25 | 19 | 16 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 22 | 2017-12-02 | 103 | 98 | 92 | 86 | 81 | 77 | 71 | 68 | 62 | 58 | 52 | 49 | 43 | 38 | 33 | 29 | 25 | 19 | 16 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 17 | 2017-10-28 | 84 | 79 | 75 | 70 | 65 | 60 | 54 | 49 | 46 | 41 | 36 | 31 | 25 | 21 | 18 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 17 | 2017-10-28 | 73 | 70 | 64 | 58 | 55 | 51 | 48 | 44 | 39 | 33 | 27 | 21 | 17 | 14 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 17 | 2017-10-28 | 74 | 68 | 65 | 60 | 54 | 50 | 44 | 38 | 33 | 28 | 25 | 20 | 17 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 17 | 2017-10-28 | 69 | 65 | 62 | 57 | 54 | 48 | 43 | 39 | 34 | 29 | 24 | 21 | 15 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 22 | 2017-12-02 | 103 | 99 | 93 | 87 | 83 | 77 | 71 | 65 | 61 | 56 | 51 | 47 | 42 | 37 | 33 | 28 | 25 | 22 | 19 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 15 | 2017-10-14 | 68 | 63 | 57 | 54 | 48 | 42 | 36 | 32 | 29 | 24 | 19 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 15 | 2017-10-14 | 72 | 68 | 63 | 57 | 51 | 46 | 41 | 35 | 29 | 24 | 20 | 16 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 15 | 2017-10-14 | 60 | 55 | 51 | 48 | 45 | 42 | 37 | 31 | 28 | 24 | 20 | 17 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 12 | 2017-09-23 | 52 | 49 | 43 | 38 | 34 | 30 | 24 | 19 | 13 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 19 | 2017-11-11 | 79 | 76 | 71 | 66 | 60 | 55 | 52 | 47 | 41 | 36 | 33 | 29 | 24 | 21 | 18 | 14 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 15 | 2017-10-14 | 62 | 58 | 55 | 50 | 45 | 40 | 36 | 33 | 30 | 27 | 22 | 18 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 20 | 2017-11-18 | 85 | 82 | 78 | 75 | 69 | 64 | 61 | 57 | 51 | 46 | 41 | 36 | 33 | 30 | 26 | 22 | 16 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 22 | 2017-12-02 | 99 | 95 | 90 | 85 | 80 | 74 | 68 | 63 | 60 | 57 | 53 | 48 | 43 | 38 | 33 | 28 | 24 | 19 | 15 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 26 | 2017-12-30 | 113 | 109 | 105 | 100 | 94 | 89 | 84 | 81 | 76 | 72 | 69 | 66 | 60 | 54 | 49 | 46 | 40 | 37 | 32 | 29 | 24 | 21 | 15 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 13 | 2017-09-30 | 57 | 53 | 47 | 44 | 39 | 33 | 28 | 23 | 17 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 22 | 2017-12-02 | 103 | 99 | 95 | 89 | 85 | 79 | 75 | 69 | 64 | 59 | 56 | 53 | 48 | 42 | 39 | 34 | 30 | 24 | 20 | 15 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 19 | 2017-11-11 | 88 | 83 | 78 | 74 | 68 | 65 | 62 | 59 | 55 | 49 | 43 | 37 | 33 | 27 | 24 | 18 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 15 | 2017-10-14 | 70 | 65 | 62 | 57 | 51 | 46 | 43 | 38 | 32 | 28 | 22 | 16 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 24 | 2017-12-16 | 101 | 97 | 94 | 89 | 86 | 80 | 74 | 70 | 67 | 62 | 59 | 56 | 52 | 48 | 43 | 40 | 34 | 29 | 24 | 18 | 15 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 19 | 2017-11-11 | 82 | 77 | 74 | 71 | 68 | 63 | 57 | 51 | 46 | 42 | 37 | 33 | 27 | 23 | 18 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 21 | 2017-11-25 | 97 | 91 | 85 | 79 | 74 | 71 | 65 | 61 | 55 | 50 | 46 | 42 | 39 | 36 | 32 | 27 | 21 | 18 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 22 | 2017-12-02 | 106 | 103 | 100 | 94 | 88 | 84 | 79 | 74 | 69 | 63 | 58 | 53 | 50 | 44 | 38 | 33 | 30 | 24 | 19 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 21 | 2017-11-25 | 99 | 95 | 89 | 84 | 81 | 75 | 70 | 64 | 58 | 52 | 48 | 45 | 41 | 38 | 33 | 28 | 23 | 17 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 17 | 2017-10-28 | 79 | 74 | 69 | 66 | 61 | 55 | 52 | 49 | 43 | 38 | 34 | 28 | 23 | 18 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 15 | 2017-10-14 | 68 | 63 | 59 | 55 | 50 | 45 | 40 | 37 | 31 | 25 | 22 | 19 | 14 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 20 | 2017-11-18 | 97 | 94 | 90 | 84 | 81 | 77 | 71 | 66 | 61 | 55 | 49 | 44 | 39 | 33 | 27 | 22 | 17 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 13 | 2017-09-30 | 62 | 56 | 53 | 48 | 42 | 36 | 31 | 27 | 21 | 16 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 24 | 2017-12-16 | 115 | 110 | 104 | 101 | 96 | 90 | 87 | 82 | 76 | 70 | 66 | 60 | 54 | 49 | 46 | 40 | 37 | 32 | 28 | 25 | 22 | 18 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 14 | 2017-10-07 | 58 | 53 | 50 | 47 | 41 | 38 | 33 | 29 | 26 | 23 | 17 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 14 | 2017-10-07 | 60 | 55 | 51 | 47 | 43 | 40 | 36 | 32 | 26 | 21 | 15 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 13 | 2017-09-30 | 61 | 57 | 52 | 48 | 42 | 38 | 33 | 27 | 24 | 19 | 16 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 20 | 2017-11-18 | 94 | 88 | 85 | 79 | 75 | 69 | 65 | 62 | 56 | 50 | 45 | 41 | 36 | 30 | 27 | 21 | 16 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 19 | 2017-11-11 | 84 | 80 | 74 | 71 | 67 | 61 | 58 | 54 | 51 | 45 | 40 | 35 | 30 | 24 | 19 | 15 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 22 | 2017-12-02 | 94 | 91 | 85 | 81 | 78 | 74 | 68 | 65 | 60 | 55 | 52 | 46 | 43 | 38 | 34 | 31 | 26 | 21 | 17 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 24 | 2017-12-16 | 104 | 99 | 96 | 91 | 88 | 85 | 79 | 76 | 71 | 68 | 63 | 58 | 55 | 49 | 46 | 43 | 37 | 33 | 29 | 24 | 20 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 19 | 2017-11-11 | 90 | 84 | 79 | 74 | 68 | 63 | 60 | 54 | 50 | 47 | 43 | 37 | 34 | 28 | 23 | 18 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 16 | 2017-10-21 | 64 | 59 | 55 | 50 | 47 | 41 | 38 | 33 | 28 | 25 | 21 | 18 | 15 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 19 | 2017-11-11 | 86 | 82 | 78 | 73 | 69 | 63 | 57 | 53 | 47 | 41 | 37 | 34 | 28 | 25 | 22 | 18 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 13 | 2017-09-30 | 63 | 60 | 57 | 51 | 47 | 41 | 35 | 29 | 24 | 21 | 18 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 13 | 2017-09-30 | 54 | 49 | 46 | 41 | 35 | 31 | 28 | 25 | 20 | 15 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 12 | 2017-09-23 | 52 | 47 | 41 | 37 | 34 | 31 | 25 | 20 | 16 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 19 | 2017-11-11 | 93 | 88 | 82 | 79 | 73 | 67 | 61 | 57 | 51 | 46 | 40 | 36 | 32 | 26 | 22 | 16 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 19 | 2017-11-11 | 82 | 79 | 73 | 67 | 64 | 59 | 56 | 52 | 47 | 42 | 38 | 35 | 32 | 26 | 22 | 17 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 21 | 2017-11-25 | 94 | 88 | 82 | 77 | 74 | 68 | 65 | 62 | 58 | 52 | 46 | 40 | 37 | 34 | 30 | 26 | 22 | 16 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 22 | 2017-12-02 | 98 | 92 | 88 | 84 | 79 | 76 | 73 | 69 | 66 | 60 | 55 | 50 | 46 | 40 | 37 | 34 | 30 | 24 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 15 | 2017-10-14 | 67 | 64 | 59 | 56 | 53 | 47 | 43 | 37 | 33 | 27 | 22 | 18 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 19 | 2017-11-11 | 82 | 78 | 75 | 70 | 65 | 60 | 55 | 50 | 45 | 42 | 38 | 35 | 30 | 24 | 21 | 15 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 17 | 2017-10-28 | 74 | 69 | 64 | 61 | 56 | 51 | 48 | 44 | 40 | 34 | 30 | 26 | 23 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 23 | 2017-12-09 | 103 | 99 | 95 | 92 | 86 | 80 | 75 | 71 | 66 | 63 | 59 | 54 | 49 | 44 | 41 | 38 | 33 | 28 | 22 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 23 | 2017-12-09 | 93 | 88 | 85 | 82 | 79 | 76 | 73 | 67 | 62 | 59 | 53 | 49 | 44 | 40 | 36 | 33 | 27 | 22 | 18 | 12 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 19 | 2017-11-11 | 83 | 79 | 74 | 71 | 67 | 62 | 58 | 55 | 52 | 48 | 42 | 37 | 34 | 28 | 22 | 18 | 15 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 22 | 2017-12-02 | 97 | 94 | 91 | 86 | 81 | 76 | 73 | 70 | 66 | 61 | 57 | 52 | 49 | 43 | 37 | 34 | 28 | 22 | 16 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 18 | 2017-11-04 | 80 | 76 | 70 | 65 | 61 | 58 | 53 | 50 | 46 | 40 | 35 | 29 | 25 | 20 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 21 | 2017-11-25 | 92 | 87 | 82 | 78 | 73 | 70 | 67 | 64 | 60 | 54 | 49 | 45 | 41 | 36 | 31 | 26 | 22 | 16 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 23 | 2017-12-09 | 97 | 91 | 88 | 83 | 79 | 76 | 71 | 68 | 62 | 57 | 54 | 51 | 47 | 43 | 38 | 32 | 27 | 24 | 21 | 17 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 20 | 2017-11-18 | 86 | 82 | 79 | 74 | 70 | 67 | 61 | 58 | 52 | 49 | 44 | 39 | 34 | 30 | 27 | 21 | 15 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 12 | 2017-09-23 | 62 | 56 | 51 | 47 | 43 | 37 | 31 | 25 | 20 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 23 | 2017-12-09 | 104 | 98 | 94 | 88 | 85 | 79 | 75 | 70 | 67 | 63 | 57 | 53 | 50 | 44 | 40 | 37 | 33 | 29 | 26 | 20 | 15 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 16 | 2017-10-21 | 72 | 68 | 63 | 58 | 54 | 48 | 44 | 41 | 37 | 33 | 28 | 23 | 18 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 15 | 2017-10-14 | 70 | 65 | 62 | 56 | 53 | 48 | 44 | 38 | 34 | 28 | 25 | 19 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 13 | 2017-09-30 | 60 | 54 | 50 | 46 | 41 | 35 | 30 | 26 | 22 | 18 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 22 | 2017-12-02 | 91 | 88 | 84 | 80 | 74 | 71 | 66 | 62 | 58 | 54 | 50 | 47 | 43 | 38 | 35 | 32 | 29 | 23 | 19 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 19 | 2017-11-11 | 82 | 78 | 74 | 68 | 63 | 60 | 57 | 54 | 48 | 43 | 39 | 35 | 29 | 25 | 21 | 18 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 15 | 2017-10-14 | 70 | 67 | 63 | 58 | 53 | 48 | 43 | 38 | 33 | 29 | 24 | 20 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 18 | 2017-11-04 | 78 | 74 | 71 | 68 | 62 | 57 | 52 | 46 | 42 | 37 | 34 | 30 | 27 | 21 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 14 | 2017-10-07 | 63 | 60 | 55 | 49 | 43 | 38 | 35 | 31 | 26 | 22 | 17 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 17 | 2017-10-28 | 78 | 75 | 69 | 63 | 59 | 56 | 52 | 46 | 40 | 34 | 28 | 25 | 19 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 16 | 2017-10-21 | 68 | 65 | 59 | 55 | 50 | 46 | 41 | 38 | 32 | 28 | 25 | 19 | 15 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 25 | 2017-12-23 | 111 | 107 | 102 | 97 | 93 | 90 | 85 | 81 | 75 | 72 | 69 | 65 | 61 | 56 | 50 | 44 | 38 | 35 | 30 | 25 | 21 | 16 | 12 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 17 | 2017-10-28 | 66 | 62 | 59 | 56 | 52 | 48 | 45 | 42 | 38 | 32 | 28 | 24 | 21 | 15 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 16 | 2017-10-21 | 59 | 55 | 52 | 48 | 45 | 40 | 34 | 29 | 26 | 23 | 20 | 16 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 27 | 2018-01-06 | 105 | 102 | 97 | 92 | 89 | 83 | 80 | 76 | 73 | 69 | 65 | 60 | 56 | 53 | 49 | 45 | 42 | 36 | 33 | 30 | 26 | 21 | 15 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 18 | 2017-11-04 | 67 | 62 | 58 | 54 | 49 | 46 | 43 | 37 | 34 | 30 | 27 | 23 | 19 | 16 | 13 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 24 | 2017-12-16 | 104 | 98 | 95 | 92 | 88 | 82 | 79 | 73 | 70 | 65 | 61 | 57 | 54 | 48 | 42 | 37 | 33 | 27 | 21 | 18 | 14 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 22 | 2017-12-02 | 94 | 90 | 87 | 82 | 79 | 73 | 68 | 62 | 58 | 52 | 47 | 44 | 39 | 36 | 32 | 27 | 24 | 19 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 15 | 2017-10-14 | 74 | 68 | 62 | 57 | 51 | 48 | 43 | 37 | 31 | 25 | 19 | 16 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 21 | 2017-11-25 | 92 | 86 | 80 | 74 | 71 | 65 | 61 | 57 | 52 | 47 | 42 | 39 | 36 | 33 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 22 | 2017-12-02 | 98 | 94 | 88 | 82 | 78 | 73 | 68 | 64 | 61 | 57 | 52 | 48 | 43 | 37 | 33 | 29 | 23 | 20 | 17 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 20 | 2017-11-18 | 86 | 83 | 80 | 75 | 70 | 64 | 60 | 55 | 51 | 48 | 43 | 38 | 34 | 30 | 25 | 21 | 17 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 14 | 2017-10-07 | 65 | 59 | 56 | 50 | 45 | 39 | 34 | 29 | 25 | 21 | 18 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 11 | 2017-09-16 | 56 | 52 | 46 | 40 | 34 | 31 | 28 | 22 | 16 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 22 | 2017-12-02 | 100 | 95 | 92 | 87 | 81 | 75 | 72 | 67 | 61 | 57 | 53 | 50 | 44 | 38 | 35 | 30 | 25 | 21 | 16 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 27 | 2018-01-06 | 116 | 110 | 105 | 99 | 96 | 93 | 90 | 86 | 83 | 79 | 74 | 71 | 65 | 59 | 55 | 50 | 46 | 41 | 38 | 34 | 29 | 24 | 20 | 16 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 14 | 2017-10-07 | 65 | 60 | 54 | 48 | 44 | 41 | 35 | 32 | 26 | 21 | 16 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 17 | 2017-10-28 | 68 | 65 | 61 | 58 | 53 | 49 | 44 | 40 | 34 | 29 | 26 | 23 | 18 | 15 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 16 | 2017-10-21 | 68 | 63 | 59 | 55 | 51 | 47 | 41 | 35 | 30 | 26 | 22 | 17 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 20 | 2017-11-18 | 83 | 78 | 74 | 70 | 66 | 61 | 57 | 54 | 51 | 47 | 43 | 39 | 35 | 30 | 26 | 20 | 15 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 24 | 2017-12-16 | 105 | 99 | 95 | 90 | 85 | 80 | 76 | 71 | 66 | 62 | 58 | 53 | 50 | 47 | 44 | 41 | 36 | 30 | 26 | 21 | 17 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 18 | 2017-11-04 | 78 | 74 | 68 | 65 | 60 | 55 | 49 | 46 | 41 | 35 | 31 | 28 | 24 | 19 | 14 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 13 | 2017-09-30 | 64 | 60 | 55 | 49 | 43 | 38 | 33 | 27 | 23 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 19 | 2017-11-11 | 86 | 83 | 79 | 74 | 69 | 63 | 60 | 57 | 51 | 45 | 41 | 36 | 30 | 26 | 20 | 16 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 18 | 2017-11-04 | 79 | 74 | 70 | 64 | 58 | 53 | 50 | 47 | 43 | 40 | 34 | 30 | 25 | 20 | 17 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 12 | 2017-09-23 | 57 | 53 | 47 | 41 | 37 | 34 | 30 | 24 | 19 | 14 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 15 | 2017-10-14 | 62 | 59 | 54 | 51 | 48 | 43 | 40 | 36 | 30 | 24 | 21 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 22 | 2017-12-02 | 93 | 88 | 83 | 77 | 74 | 69 | 63 | 58 | 52 | 47 | 42 | 38 | 35 | 32 | 29 | 26 | 21 | 16 | 13 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 23 | 2017-12-09 | 95 | 91 | 87 | 83 | 79 | 76 | 71 | 66 | 63 | 57 | 54 | 51 | 48 | 42 | 37 | 33 | 27 | 23 | 18 | 14 | 11 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 19 | 2017-11-11 | 78 | 74 | 69 | 63 | 59 | 56 | 53 | 49 | 44 | 40 | 37 | 34 | 31 | 26 | 23 | 19 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 14 | 2017-10-07 | 54 | 50 | 46 | 43 | 40 | 35 | 29 | 26 | 20 | 17 | 14 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 22 | 2017-12-02 | 101 | 98 | 94 | 90 | 85 | 81 | 77 | 71 | 67 | 62 | 56 | 50 | 47 | 44 | 39 | 33 | 27 | 22 | 18 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 22 | 2017-12-02 | 106 | 100 | 96 | 93 | 89 | 83 | 77 | 71 | 65 | 59 | 53 | 47 | 44 | 38 | 35 | 29 | 24 | 20 | 16 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 16 | 2017-10-21 | 70 | 65 | 62 | 56 | 52 | 48 | 45 | 40 | 37 | 32 | 29 | 24 | 18 | 15 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 23 | 2017-12-09 | 97 | 91 | 86 | 82 | 78 | 75 | 70 | 66 | 62 | 59 | 56 | 51 | 47 | 41 | 36 | 33 | 29 | 24 | 19 | 14 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 18 | 2017-11-04 | 79 | 76 | 70 | 65 | 61 | 57 | 51 | 46 | 40 | 36 | 32 | 26 | 23 | 18 | 14 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 20 | 2017-11-18 | 85 | 81 | 78 | 72 | 67 | 62 | 58 | 54 | 48 | 43 | 40 | 35 | 31 | 28 | 23 | 19 | 15 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 19 | 2017-11-11 | 87 | 81 | 75 | 71 | 67 | 62 | 56 | 50 | 44 | 40 | 34 | 29 | 25 | 22 | 19 | 16 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 22 | 2017-12-02 | 94 | 88 | 85 | 79 | 76 | 71 | 68 | 63 | 57 | 51 | 47 | 43 | 40 | 36 | 30 | 24 | 21 | 18 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 17 | 2017-10-28 | 74 | 68 | 65 | 60 | 55 | 52 | 47 | 43 | 40 | 35 | 30 | 27 | 21 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 19 | 2017-11-11 | 89 | 83 | 79 | 73 | 69 | 64 | 61 | 57 | 51 | 45 | 40 | 36 | 31 | 25 | 21 | 17 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 18 | 2017-11-04 | 73 | 69 | 66 | 62 | 58 | 53 | 49 | 46 | 41 | 37 | 34 | 30 | 26 | 23 | 18 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 24 | 2017-12-16 | 105 | 101 | 96 | 92 | 88 | 83 | 80 | 77 | 72 | 69 | 65 | 59 | 54 | 50 | 44 | 39 | 34 | 28 | 24 | 19 | 13 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 13 | 2017-09-30 | 59 | 54 | 51 | 46 | 40 | 35 | 30 | 24 | 21 | 18 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 16 | 2017-10-21 | 62 | 58 | 54 | 51 | 47 | 42 | 38 | 33 | 30 | 25 | 22 | 18 | 14 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 18 | 2017-11-04 | 75 | 71 | 67 | 63 | 60 | 56 | 50 | 47 | 43 | 38 | 35 | 32 | 28 | 25 | 19 | 15 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 21 | 2017-11-25 | 94 | 89 | 83 | 79 | 74 | 71 | 67 | 61 | 57 | 54 | 49 | 45 | 42 | 38 | 33 | 28 | 22 | 18 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 15 | 2017-10-14 | 60 | 56 | 52 | 46 | 43 | 39 | 34 | 29 | 26 | 23 | 18 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 17 | 2017-10-28 | 74 | 70 | 65 | 60 | 54 | 51 | 47 | 41 | 36 | 31 | 27 | 22 | 16 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 24 | 2017-12-16 | 107 | 103 | 100 | 95 | 90 | 87 | 84 | 79 | 76 | 71 | 68 | 62 | 56 | 53 | 47 | 43 | 38 | 32 | 28 | 23 | 17 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 14 | 2017-10-07 | 66 | 63 | 58 | 55 | 51 | 45 | 39 | 35 | 31 | 26 | 21 | 16 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 18 | 2017-11-04 | 84 | 79 | 75 | 71 | 67 | 64 | 58 | 52 | 48 | 44 | 39 | 33 | 29 | 23 | 18 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 24 | 2017-12-16 | 111 | 106 | 102 | 97 | 91 | 85 | 81 | 77 | 71 | 67 | 62 | 57 | 53 | 49 | 45 | 39 | 36 | 32 | 29 | 23 | 18 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 20 | 2017-11-18 | 93 | 88 | 85 | 82 | 77 | 71 | 66 | 60 | 54 | 51 | 46 | 43 | 37 | 32 | 27 | 24 | 19 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 21 | 2017-11-25 | 93 | 90 | 86 | 81 | 76 | 72 | 67 | 62 | 57 | 53 | 47 | 44 | 39 | 36 | 30 | 27 | 21 | 17 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 16 | 2017-10-21 | 69 | 65 | 59 | 55 | 51 | 47 | 43 | 40 | 34 | 28 | 22 | 19 | 13 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 18 | 2017-11-04 | 71 | 65 | 60 | 54 | 51 | 48 | 45 | 39 | 36 | 32 | 28 | 24 | 21 | 18 | 15 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 22 | 2017-12-02 | 97 | 94 | 89 | 85 | 79 | 74 | 71 | 68 | 65 | 59 | 53 | 50 | 46 | 40 | 34 | 28 | 22 | 19 | 16 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 23 | 2017-12-09 | 100 | 97 | 91 | 87 | 83 | 77 | 71 | 65 | 61 | 56 | 51 | 47 | 43 | 39 | 35 | 32 | 27 | 24 | 21 | 16 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 20 | 2017-11-18 | 91 | 85 | 80 | 74 | 69 | 65 | 62 | 58 | 54 | 48 | 45 | 41 | 37 | 33 | 29 | 23 | 17 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 17 | 2017-10-28 | 76 | 70 | 64 | 60 | 55 | 51 | 46 | 43 | 37 | 31 | 27 | 21 | 16 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 13 | 2017-09-30 | 61 | 56 | 51 | 46 | 41 | 36 | 30 | 27 | 23 | 19 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 20 | 2017-11-18 | 84 | 78 | 73 | 70 | 65 | 59 | 56 | 52 | 48 | 44 | 39 | 36 | 32 | 29 | 25 | 21 | 17 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 23 | 2017-12-09 | 99 | 95 | 91 | 85 | 82 | 78 | 73 | 68 | 65 | 59 | 53 | 47 | 42 | 39 | 36 | 32 | 29 | 23 | 18 | 12 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 24 | 2017-12-16 | 96 | 93 | 90 | 87 | 83 | 79 | 76 | 73 | 70 | 64 | 59 | 53 | 48 | 43 | 39 | 36 | 32 | 28 | 24 | 18 | 15 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 18 | 2017-11-04 | 78 | 75 | 72 | 67 | 62 | 56 | 50 | 47 | 41 | 38 | 32 | 28 | 25 | 19 | 16 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 23 | 2017-12-09 | 105 | 101 | 95 | 90 | 85 | 81 | 78 | 74 | 68 | 64 | 59 | 54 | 49 | 46 | 41 | 38 | 32 | 26 | 23 | 17 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 26 | 2017-12-30 | 113 | 107 | 103 | 98 | 93 | 88 | 84 | 80 | 74 | 70 | 65 | 59 | 54 | 49 | 46 | 43 | 40 | 37 | 32 | 27 | 23 | 20 | 17 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 19 | 2017-11-11 | 73 | 68 | 65 | 59 | 56 | 52 | 49 | 43 | 39 | 36 | 31 | 26 | 23 | 20 | 17 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 18 | 2017-11-04 | 78 | 73 | 69 | 65 | 61 | 56 | 53 | 47 | 41 | 37 | 31 | 27 | 24 | 20 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 16 | 2017-10-21 | 71 | 66 | 61 | 55 | 49 | 46 | 43 | 38 | 33 | 30 | 25 | 19 | 15 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 15 | 2017-10-14 | 71 | 67 | 64 | 60 | 54 | 49 | 43 | 37 | 32 | 26 | 20 | 16 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 21 | 2017-11-25 | 86 | 82 | 78 | 74 | 70 | 64 | 59 | 55 | 50 | 46 | 42 | 39 | 35 | 32 | 28 | 25 | 20 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 18 | 2017-11-04 | 79 | 75 | 70 | 67 | 63 | 59 | 55 | 49 | 46 | 40 | 35 | 29 | 26 | 21 | 15 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 13 | 2017-09-30 | 60 | 55 | 49 | 43 | 37 | 34 | 30 | 24 | 19 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 13 | 2017-09-30 | 55 | 52 | 49 | 46 | 42 | 38 | 32 | 27 | 23 | 18 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 23 | 2017-12-09 | 99 | 93 | 90 | 85 | 81 | 77 | 74 | 70 | 66 | 60 | 54 | 48 | 43 | 38 | 34 | 28 | 25 | 19 | 16 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 24 | 2017-12-16 | 102 | 97 | 93 | 90 | 87 | 81 | 76 | 71 | 68 | 62 | 56 | 53 | 50 | 47 | 44 | 38 | 35 | 29 | 25 | 21 | 18 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 15 | 2017-10-14 | 66 | 60 | 55 | 52 | 46 | 42 | 38 | 34 | 30 | 25 | 21 | 16 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 23 | 2017-12-09 | 103 | 97 | 94 | 91 | 86 | 81 | 78 | 72 | 68 | 63 | 58 | 52 | 49 | 45 | 41 | 37 | 31 | 26 | 22 | 18 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 19 | 2017-11-11 | 85 | 80 | 75 | 70 | 64 | 58 | 52 | 49 | 46 | 43 | 39 | 36 | 30 | 24 | 21 | 16 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 15 | 2017-10-14 | 70 | 65 | 61 | 56 | 51 | 48 | 42 | 36 | 31 | 27 | 24 | 19 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 13 | 2017-09-30 | 61 | 55 | 50 | 45 | 42 | 38 | 34 | 30 | 25 | 19 | 16 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 18 | 2017-11-04 | 80 | 75 | 70 | 66 | 60 | 55 | 52 | 49 | 46 | 41 | 36 | 30 | 26 | 20 | 15 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 19 | 2017-11-11 | 85 | 81 | 78 | 72 | 69 | 65 | 60 | 56 | 53 | 48 | 42 | 38 | 32 | 26 | 21 | 17 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 23 | 2017-12-09 | 93 | 89 | 84 | 78 | 72 | 69 | 65 | 61 | 56 | 53 | 47 | 44 | 40 | 35 | 30 | 25 | 20 | 17 | 13 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 18 | 2017-11-04 | 81 | 75 | 72 | 67 | 62 | 56 | 50 | 47 | 43 | 38 | 32 | 29 | 26 | 22 | 17 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 13 | 2017-09-30 | 60 | 56 | 52 | 49 | 44 | 38 | 33 | 29 | 24 | 20 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 21 | 2017-11-25 | 94 | 89 | 85 | 82 | 78 | 74 | 69 | 63 | 58 | 53 | 47 | 41 | 37 | 34 | 28 | 25 | 22 | 17 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 14 | 2017-10-07 | 64 | 58 | 53 | 47 | 41 | 36 | 32 | 29 | 23 | 18 | 15 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 18 | 2017-11-04 | 79 | 74 | 68 | 63 | 58 | 55 | 51 | 47 | 43 | 38 | 34 | 31 | 25 | 19 | 13 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 23 | 2017-12-09 | 99 | 95 | 90 | 85 | 79 | 76 | 72 | 66 | 62 | 59 | 54 | 51 | 47 | 44 | 38 | 33 | 28 | 24 | 18 | 15 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 24 | 2017-12-16 | 96 | 93 | 87 | 84 | 81 | 77 | 73 | 68 | 65 | 61 | 57 | 54 | 51 | 46 | 41 | 35 | 32 | 27 | 23 | 18 | 14 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 20 | 2017-11-18 | 93 | 87 | 84 | 81 | 76 | 70 | 65 | 61 | 58 | 53 | 47 | 42 | 38 | 32 | 29 | 23 | 20 | 15 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 19 | 2017-11-11 | 79 | 73 | 69 | 65 | 62 | 59 | 55 | 52 | 46 | 42 | 37 | 34 | 28 | 24 | 21 | 15 | 12 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 17 | 2017-10-28 | 71 | 68 | 62 | 59 | 54 | 49 | 44 | 38 | 35 | 32 | 29 | 26 | 20 | 17 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 14 | 2017-10-07 | 63 | 57 | 52 | 48 | 45 | 39 | 36 | 32 | 29 | 23 | 18 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 23 | 2017-12-09 | 105 | 101 | 97 | 93 | 88 | 85 | 79 | 74 | 71 | 68 | 62 | 56 | 53 | 50 | 44 | 39 | 33 | 28 | 25 | 19 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 15 | 2017-10-14 | 64 | 58 | 54 | 51 | 47 | 43 | 40 | 34 | 28 | 24 | 20 | 16 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 15 | 2017-10-14 | 69 | 64 | 60 | 56 | 51 | 46 | 40 | 35 | 29 | 26 | 21 | 18 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 14 | 2017-10-07 | 75 | 71 | 65 | 59 | 56 | 51 | 45 | 40 | 34 | 28 | 22 | 16 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 20 | 2017-11-18 | 85 | 79 | 76 | 73 | 67 | 63 | 57 | 52 | 49 | 45 | 42 | 39 | 36 | 33 | 29 | 23 | 18 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 17 | 2017-10-28 | 75 | 69 | 64 | 61 | 57 | 51 | 45 | 39 | 36 | 30 | 27 | 24 | 21 | 17 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 16 | 2017-10-21 | 74 | 69 | 65 | 61 | 57 | 52 | 46 | 42 | 37 | 34 | 28 | 22 | 18 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 16 | 2017-10-21 | 68 | 64 | 58 | 55 | 49 | 45 | 40 | 34 | 29 | 26 | 22 | 17 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 12 | 2017-09-23 | 56 | 50 | 46 | 40 | 37 | 34 | 30 | 25 | 21 | 16 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 11 | 2017-09-16 | 55 | 49 | 43 | 40 | 34 | 31 | 25 | 19 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 16 | 2017-10-21 | 62 | 58 | 55 | 50 | 46 | 41 | 38 | 35 | 30 | 26 | 21 | 18 | 14 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 22 | 2017-12-02 | 98 | 94 | 88 | 84 | 81 | 75 | 71 | 68 | 62 | 58 | 53 | 49 | 43 | 39 | 35 | 30 | 27 | 21 | 17 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 19 | 2017-11-11 | 86 | 80 | 75 | 71 | 68 | 65 | 59 | 53 | 48 | 44 | 40 | 34 | 29 | 25 | 20 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 19 | 2017-11-11 | 86 | 80 | 74 | 69 | 63 | 60 | 54 | 49 | 45 | 42 | 36 | 32 | 29 | 23 | 20 | 15 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 18 | 2017-11-04 | 78 | 73 | 67 | 64 | 60 | 55 | 52 | 46 | 43 | 39 | 35 | 32 | 27 | 22 | 17 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 20 | 2017-11-18 | 89 | 84 | 81 | 77 | 74 | 69 | 63 | 57 | 53 | 50 | 45 | 41 | 36 | 33 | 27 | 21 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 13 | 2017-09-30 | 57 | 53 | 50 | 47 | 42 | 36 | 30 | 24 | 21 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 18 | 2017-11-04 | 77 | 72 | 69 | 63 | 57 | 53 | 49 | 44 | 38 | 35 | 31 | 27 | 23 | 19 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 18 | 2017-11-04 | 75 | 72 | 69 | 66 | 62 | 57 | 52 | 48 | 43 | 38 | 34 | 29 | 25 | 19 | 15 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 19 | 2017-11-11 | 83 | 78 | 72 | 68 | 64 | 59 | 54 | 50 | 46 | 42 | 38 | 34 | 29 | 24 | 19 | 15 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 15 | 2017-10-14 | 71 | 65 | 59 | 55 | 49 | 44 | 39 | 36 | 31 | 28 | 24 | 19 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 23 | 2017-12-09 | 104 | 99 | 93 | 87 | 83 | 77 | 71 | 68 | 63 | 57 | 52 | 48 | 42 | 39 | 35 | 32 | 26 | 21 | 16 | 13 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 16 | 2017-10-21 | 68 | 62 | 56 | 52 | 46 | 43 | 39 | 35 | 32 | 29 | 26 | 20 | 17 | 12 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 21 | 2017-11-25 | 90 | 84 | 78 | 74 | 71 | 65 | 60 | 56 | 51 | 47 | 42 | 38 | 35 | 31 | 27 | 21 | 16 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 20 | 2017-11-18 | 88 | 85 | 81 | 75 | 69 | 63 | 59 | 54 | 51 | 47 | 44 | 40 | 37 | 34 | 28 | 22 | 18 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 18 | 2017-11-04 | 83 | 80 | 75 | 69 | 66 | 60 | 54 | 49 | 44 | 38 | 35 | 29 | 25 | 21 | 17 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 25 | 2017-12-23 | 111 | 106 | 103 | 98 | 94 | 91 | 86 | 83 | 79 | 74 | 71 | 65 | 59 | 53 | 48 | 42 | 38 | 35 | 32 | 28 | 23 | 17 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 24 | 2017-12-16 | 106 | 103 | 100 | 96 | 93 | 90 | 84 | 80 | 74 | 69 | 63 | 59 | 56 | 50 | 46 | 43 | 39 | 34 | 28 | 22 | 19 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 16 | 2017-10-21 | 74 | 69 | 64 | 58 | 53 | 47 | 44 | 41 | 36 | 30 | 26 | 21 | 17 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 26 | 2017-12-30 | 109 | 104 | 100 | 97 | 94 | 89 | 86 | 82 | 79 | 75 | 72 | 66 | 60 | 54 | 49 | 44 | 38 | 32 | 28 | 24 | 21 | 18 | 15 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 17 | 2017-10-28 | 77 | 74 | 71 | 65 | 60 | 55 | 50 | 46 | 42 | 36 | 32 | 27 | 22 | 17 | 13 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 15 | 2017-10-14 | 62 | 59 | 55 | 50 | 47 | 44 | 38 | 34 | 29 | 24 | 20 | 16 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 18 | 2017-11-04 | 81 | 78 | 74 | 69 | 64 | 58 | 54 | 49 | 46 | 40 | 36 | 30 | 25 | 20 | 17 | 13 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 20 | 2017-11-18 | 84 | 81 | 77 | 71 | 66 | 63 | 58 | 54 | 50 | 46 | 42 | 37 | 34 | 31 | 25 | 20 | 15 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 26 | 2017-12-30 | 111 | 106 | 100 | 95 | 92 | 86 | 83 | 78 | 75 | 71 | 68 | 62 | 58 | 55 | 50 | 44 | 40 | 34 | 31 | 25 | 21 | 17 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 24 | 2017-12-16 | 105 | 102 | 96 | 93 | 88 | 85 | 81 | 77 | 71 | 67 | 63 | 58 | 53 | 47 | 44 | 40 | 35 | 30 | 27 | 23 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 18 | 2017-11-04 | 87 | 81 | 76 | 70 | 64 | 61 | 56 | 52 | 46 | 40 | 37 | 32 | 26 | 20 | 16 | 12 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 14 | 2017-10-07 | 67 | 64 | 59 | 55 | 52 | 49 | 45 | 39 | 33 | 27 | 22 | 16 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 14 | 2017-10-07 | 67 | 61 | 55 | 52 | 47 | 43 | 37 | 32 | 27 | 22 | 17 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 14 | 2017-10-07 | 61 | 56 | 51 | 46 | 42 | 36 | 32 | 26 | 20 | 17 | 13 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 26 | 2017-12-30 | 115 | 110 | 106 | 102 | 96 | 92 | 88 | 82 | 78 | 75 | 72 | 69 | 63 | 57 | 54 | 51 | 48 | 44 | 39 | 34 | 31 | 25 | 20 | 14 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 23 | 2017-12-09 | 97 | 92 | 86 | 83 | 77 | 74 | 70 | 66 | 62 | 59 | 56 | 52 | 49 | 46 | 43 | 38 | 34 | 28 | 24 | 19 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 20 | 2017-11-18 | 93 | 88 | 85 | 82 | 76 | 72 | 66 | 60 | 57 | 51 | 48 | 44 | 38 | 32 | 27 | 22 | 17 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 21 | 2017-11-25 | 87 | 81 | 76 | 73 | 70 | 65 | 62 | 58 | 54 | 48 | 44 | 40 | 36 | 31 | 25 | 21 | 18 | 14 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 20 | 2017-11-18 | 94 | 89 | 85 | 80 | 75 | 70 | 67 | 61 | 55 | 49 | 43 | 37 | 34 | 29 | 23 | 19 | 14 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 15 | 2017-10-14 | 66 | 60 | 54 | 51 | 46 | 41 | 37 | 34 | 30 | 27 | 21 | 15 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 17 | 2017-10-28 | 68 | 65 | 62 | 56 | 50 | 44 | 41 | 38 | 32 | 28 | 24 | 21 | 18 | 14 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 14 | 2017-10-07 | 55 | 52 | 49 | 46 | 42 | 36 | 33 | 27 | 24 | 19 | 13 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 23 | 2017-12-09 | 99 | 96 | 90 | 85 | 82 | 76 | 73 | 70 | 66 | 60 | 56 | 53 | 48 | 44 | 41 | 36 | 31 | 28 | 22 | 17 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 25 | 2017-12-23 | 106 | 100 | 97 | 94 | 90 | 85 | 80 | 77 | 71 | 67 | 63 | 60 | 57 | 52 | 49 | 46 | 41 | 35 | 30 | 24 | 20 | 17 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 21 | 2017-11-25 | 92 | 87 | 82 | 77 | 74 | 71 | 67 | 62 | 58 | 52 | 49 | 45 | 40 | 36 | 32 | 27 | 21 | 17 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 21 | 2017-11-25 | 97 | 93 | 89 | 85 | 81 | 78 | 75 | 71 | 67 | 61 | 57 | 54 | 48 | 42 | 36 | 31 | 27 | 21 | 16 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 14 | 2017-10-07 | 68 | 64 | 59 | 55 | 50 | 44 | 40 | 35 | 29 | 23 | 17 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 19 | 2017-11-11 | 83 | 77 | 71 | 66 | 63 | 58 | 54 | 51 | 48 | 44 | 41 | 36 | 32 | 28 | 23 | 17 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 19 | 2017-11-11 | 84 | 79 | 76 | 72 | 66 | 63 | 57 | 53 | 50 | 44 | 40 | 36 | 30 | 26 | 23 | 18 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 23 | 2017-12-09 | 101 | 96 | 90 | 85 | 82 | 76 | 73 | 67 | 61 | 57 | 54 | 50 | 44 | 38 | 33 | 29 | 24 | 21 | 18 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 21 | 2017-11-25 | 90 | 84 | 78 | 74 | 68 | 62 | 58 | 53 | 50 | 47 | 44 | 39 | 35 | 32 | 28 | 24 | 21 | 18 | 15 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 14 | 2017-10-07 | 59 | 53 | 47 | 42 | 39 | 34 | 30 | 27 | 22 | 17 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 24 | 2017-12-16 | 108 | 102 | 98 | 95 | 90 | 87 | 82 | 79 | 73 | 67 | 63 | 59 | 55 | 52 | 49 | 45 | 40 | 34 | 29 | 26 | 20 | 17 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 17 | 2017-10-28 | 78 | 75 | 72 | 67 | 62 | 59 | 53 | 48 | 43 | 40 | 35 | 30 | 25 | 19 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 16 | 2017-10-21 | 69 | 64 | 61 | 56 | 53 | 47 | 42 | 39 | 35 | 29 | 26 | 20 | 17 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 20 | 2017-11-18 | 84 | 81 | 76 | 72 | 66 | 63 | 60 | 57 | 54 | 50 | 44 | 38 | 35 | 30 | 26 | 22 | 17 | 14 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 14 | 2017-10-07 | 58 | 55 | 52 | 46 | 41 | 37 | 34 | 30 | 24 | 20 | 16 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 23 | 2017-12-09 | 101 | 96 | 93 | 89 | 84 | 78 | 74 | 69 | 65 | 62 | 58 | 52 | 49 | 44 | 40 | 34 | 31 | 27 | 21 | 17 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 19 | 2017-11-11 | 79 | 73 | 70 | 66 | 63 | 57 | 54 | 50 | 45 | 39 | 35 | 29 | 25 | 22 | 18 | 15 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 21 | 2017-11-25 | 76 | 72 | 68 | 64 | 61 | 56 | 50 | 47 | 44 | 41 | 38 | 35 | 32 | 27 | 23 | 20 | 17 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 21 | 2017-11-25 | 99 | 95 | 90 | 85 | 81 | 77 | 72 | 68 | 62 | 59 | 53 | 47 | 43 | 40 | 35 | 29 | 24 | 18 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 16 | 2017-10-21 | 65 | 62 | 56 | 53 | 48 | 44 | 40 | 37 | 32 | 29 | 26 | 22 | 18 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 18 | 2017-11-04 | 76 | 72 | 67 | 64 | 58 | 54 | 51 | 48 | 44 | 39 | 36 | 30 | 24 | 18 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 16 | 2017-10-21 | 72 | 67 | 62 | 59 | 56 | 51 | 47 | 41 | 35 | 29 | 24 | 18 | 14 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 18 | 2017-11-04 | 83 | 77 | 74 | 68 | 62 | 56 | 52 | 49 | 43 | 37 | 34 | 30 | 27 | 22 | 18 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 27 | 2018-01-06 | 104 | 101 | 98 | 94 | 91 | 88 | 83 | 77 | 74 | 69 | 65 | 59 | 55 | 51 | 48 | 43 | 40 | 36 | 33 | 30 | 27 | 22 | 17 | 14 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 16 | 2017-10-21 | 77 | 74 | 69 | 64 | 59 | 54 | 48 | 43 | 37 | 33 | 28 | 22 | 17 | 13 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 19 | 2017-11-11 | 80 | 77 | 74 | 68 | 64 | 59 | 55 | 51 | 46 | 42 | 37 | 34 | 29 | 25 | 22 | 18 | 15 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 14 | 2017-10-07 | 57 | 52 | 48 | 43 | 38 | 35 | 29 | 26 | 22 | 18 | 12 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 22 | 2017-12-02 | 105 | 99 | 93 | 88 | 85 | 80 | 76 | 72 | 67 | 61 | 55 | 51 | 46 | 41 | 37 | 31 | 27 | 21 | 17 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 12 | 2017-09-23 | 60 | 57 | 53 | 48 | 42 | 36 | 30 | 25 | 21 | 16 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 24 | 2017-12-16 | 97 | 94 | 90 | 84 | 81 | 78 | 74 | 69 | 64 | 61 | 55 | 50 | 46 | 43 | 38 | 35 | 30 | 27 | 24 | 20 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 20 | 2017-11-18 | 90 | 84 | 78 | 73 | 68 | 64 | 60 | 56 | 53 | 47 | 41 | 36 | 33 | 29 | 25 | 20 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 18 | 2017-11-04 | 86 | 80 | 77 | 71 | 67 | 64 | 59 | 53 | 48 | 42 | 38 | 32 | 26 | 20 | 16 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 16 | 2017-10-21 | 74 | 68 | 62 | 56 | 50 | 47 | 41 | 38 | 34 | 28 | 24 | 19 | 16 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 20 | 2017-11-18 | 90 | 85 | 79 | 75 | 71 | 66 | 61 | 56 | 51 | 45 | 42 | 38 | 34 | 31 | 26 | 23 | 19 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 20 | 2017-11-18 | 92 | 88 | 83 | 77 | 74 | 69 | 64 | 58 | 52 | 48 | 43 | 37 | 32 | 29 | 24 | 19 | 14 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 13 | 2017-09-30 | 57 | 51 | 47 | 43 | 39 | 34 | 31 | 27 | 21 | 18 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 22 | 2017-12-02 | 85 | 82 | 79 | 73 | 70 | 67 | 61 | 57 | 52 | 48 | 45 | 42 | 37 | 31 | 27 | 23 | 19 | 16 | 12 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 27 | 2018-01-06 | 105 | 99 | 96 | 92 | 88 | 84 | 80 | 77 | 74 | 70 | 67 | 63 | 60 | 56 | 53 | 47 | 44 | 38 | 32 | 28 | 24 | 19 | 16 | 13 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 15 | 2017-10-14 | 56 | 53 | 49 | 44 | 41 | 38 | 35 | 31 | 25 | 22 | 16 | 13 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 20 | 2017-11-18 | 77 | 73 | 68 | 64 | 61 | 56 | 52 | 48 | 44 | 41 | 36 | 33 | 29 | 25 | 22 | 19 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 26 | 2017-12-30 | 109 | 105 | 99 | 95 | 90 | 85 | 80 | 77 | 74 | 71 | 66 | 63 | 59 | 54 | 49 | 46 | 40 | 35 | 31 | 28 | 25 | 22 | 17 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 12 | 2017-09-23 | 58 | 52 | 48 | 45 | 39 | 34 | 28 | 25 | 19 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 17 | 2017-10-28 | 78 | 73 | 68 | 62 | 57 | 52 | 46 | 41 | 37 | 31 | 26 | 21 | 17 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 14 | 2017-10-07 | 61 | 55 | 51 | 48 | 43 | 39 | 33 | 27 | 23 | 19 | 14 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 24 | 2017-12-16 | 98 | 92 | 88 | 85 | 82 | 79 | 73 | 70 | 67 | 62 | 58 | 52 | 46 | 42 | 36 | 32 | 27 | 24 | 21 | 18 | 14 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 12 | 2017-09-23 | 57 | 51 | 46 | 40 | 35 | 30 | 25 | 22 | 16 | 13 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 15 | 2017-10-14 | 66 | 63 | 57 | 53 | 49 | 46 | 42 | 37 | 33 | 28 | 23 | 19 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 17 | 2017-10-28 | 69 | 66 | 63 | 60 | 57 | 52 | 46 | 40 | 37 | 34 | 28 | 23 | 20 | 14 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 26 | 2017-12-30 | 110 | 106 | 103 | 99 | 95 | 90 | 87 | 84 | 81 | 77 | 73 | 67 | 61 | 55 | 50 | 47 | 44 | 39 | 35 | 31 | 25 | 19 | 14 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 16 | 2017-10-21 | 65 | 61 | 57 | 52 | 46 | 43 | 40 | 35 | 30 | 24 | 20 | 15 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 14 | 2017-10-07 | 64 | 61 | 55 | 49 | 45 | 39 | 33 | 28 | 25 | 22 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 19 | 2017-11-11 | 84 | 80 | 75 | 70 | 64 | 60 | 54 | 51 | 45 | 42 | 37 | 32 | 29 | 24 | 19 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 16 | 2017-10-21 | 76 | 71 | 66 | 60 | 55 | 51 | 48 | 43 | 37 | 32 | 28 | 22 | 17 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 24 | 2017-12-16 | 103 | 98 | 94 | 89 | 85 | 80 | 75 | 72 | 69 | 66 | 61 | 57 | 54 | 50 | 46 | 41 | 35 | 31 | 25 | 22 | 17 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 24 | 2017-12-16 | 104 | 101 | 95 | 90 | 87 | 83 | 78 | 72 | 69 | 63 | 59 | 54 | 50 | 47 | 42 | 38 | 34 | 29 | 25 | 19 | 15 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 19 | 2017-11-11 | 85 | 81 | 78 | 72 | 69 | 63 | 59 | 55 | 49 | 44 | 39 | 33 | 30 | 24 | 20 | 14 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 21 | 2017-11-25 | 95 | 91 | 86 | 81 | 76 | 72 | 66 | 63 | 57 | 54 | 50 | 46 | 43 | 38 | 32 | 27 | 21 | 17 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 20 | 2017-11-18 | 85 | 80 | 77 | 71 | 66 | 63 | 59 | 56 | 52 | 49 | 43 | 37 | 34 | 29 | 26 | 23 | 17 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 24 | 2017-12-16 | 99 | 95 | 91 | 88 | 82 | 77 | 74 | 70 | 64 | 60 | 56 | 52 | 49 | 45 | 41 | 38 | 34 | 30 | 24 | 18 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 14 | 2017-10-07 | 60 | 55 | 52 | 46 | 40 | 34 | 30 | 25 | 21 | 18 | 13 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 15 | 2017-10-14 | 72 | 68 | 62 | 58 | 52 | 47 | 41 | 37 | 31 | 25 | 19 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 21 | 2017-11-25 | 99 | 93 | 89 | 85 | 82 | 76 | 73 | 68 | 65 | 59 | 53 | 49 | 43 | 38 | 34 | 28 | 22 | 16 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 15 | 2017-10-14 | 63 | 59 | 56 | 50 | 45 | 42 | 39 | 34 | 28 | 23 | 20 | 15 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 19 | 2017-11-11 | 88 | 85 | 81 | 75 | 71 | 65 | 59 | 54 | 50 | 46 | 41 | 37 | 31 | 26 | 22 | 16 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 16 | 2017-10-21 | 79 | 76 | 71 | 66 | 60 | 55 | 50 | 44 | 38 | 35 | 29 | 23 | 18 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 25 | 2017-12-23 | 107 | 104 | 99 | 94 | 90 | 87 | 84 | 78 | 73 | 68 | 62 | 58 | 54 | 49 | 43 | 40 | 37 | 34 | 30 | 27 | 23 | 19 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 18 | 2017-11-04 | 77 | 72 | 67 | 62 | 59 | 53 | 50 | 45 | 42 | 37 | 32 | 26 | 21 | 18 | 14 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 19 | 2017-11-11 | 83 | 80 | 75 | 71 | 66 | 62 | 58 | 54 | 51 | 46 | 41 | 38 | 32 | 27 | 23 | 18 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 19 | 2017-11-11 | 86 | 81 | 75 | 69 | 64 | 59 | 53 | 48 | 44 | 40 | 37 | 32 | 29 | 24 | 19 | 14 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 16 | 2017-10-21 | 74 | 68 | 64 | 61 | 56 | 52 | 46 | 42 | 36 | 32 | 27 | 21 | 17 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 23 | 2017-12-09 | 99 | 96 | 92 | 89 | 83 | 79 | 75 | 70 | 64 | 60 | 57 | 54 | 48 | 44 | 39 | 36 | 31 | 27 | 24 | 18 | 14 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 18 | 2017-11-04 | 82 | 79 | 73 | 69 | 64 | 59 | 53 | 50 | 46 | 41 | 36 | 30 | 25 | 20 | 17 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 19 | 2017-11-11 | 83 | 78 | 74 | 69 | 64 | 59 | 56 | 50 | 46 | 41 | 37 | 34 | 28 | 25 | 19 | 16 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 15 | 2017-10-14 | 64 | 61 | 55 | 52 | 46 | 40 | 36 | 33 | 27 | 23 | 18 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 22 | 2017-12-02 | 103 | 97 | 91 | 86 | 81 | 77 | 74 | 71 | 66 | 61 | 57 | 52 | 46 | 41 | 36 | 33 | 29 | 23 | 17 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 13 | 2017-09-30 | 60 | 56 | 50 | 44 | 40 | 34 | 28 | 25 | 20 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 17 | 2017-10-28 | 72 | 66 | 62 | 59 | 53 | 49 | 44 | 41 | 38 | 34 | 29 | 26 | 21 | 16 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 18 | 2017-11-04 | 82 | 79 | 75 | 69 | 64 | 58 | 53 | 47 | 43 | 39 | 36 | 31 | 28 | 24 | 18 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 23 | 2017-12-09 | 95 | 90 | 87 | 82 | 78 | 74 | 70 | 66 | 63 | 59 | 56 | 51 | 45 | 39 | 35 | 31 | 28 | 23 | 20 | 17 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 17 | 2017-10-28 | 74 | 70 | 66 | 60 | 56 | 53 | 48 | 43 | 37 | 33 | 29 | 24 | 21 | 17 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 15 | 2017-10-14 | 64 | 59 | 56 | 52 | 49 | 44 | 41 | 38 | 34 | 28 | 22 | 18 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 20 | 2017-11-18 | 91 | 88 | 85 | 80 | 74 | 70 | 66 | 62 | 59 | 54 | 48 | 42 | 38 | 33 | 27 | 22 | 17 | 12 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 13 | 2017-09-30 | 58 | 53 | 47 | 42 | 37 | 33 | 29 | 24 | 19 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 17 | 2017-10-28 | 78 | 74 | 69 | 64 | 59 | 56 | 50 | 45 | 42 | 37 | 33 | 30 | 25 | 20 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 14 | 2017-10-07 | 68 | 62 | 56 | 52 | 48 | 42 | 37 | 31 | 26 | 22 | 19 | 15 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 16 | 2017-10-21 | 70 | 65 | 60 | 55 | 52 | 46 | 42 | 38 | 33 | 29 | 23 | 18 | 14 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 22 | 2017-12-02 | 97 | 94 | 89 | 85 | 81 | 75 | 70 | 64 | 60 | 54 | 51 | 46 | 41 | 38 | 34 | 29 | 25 | 21 | 17 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 12 | 2017-09-23 | 60 | 56 | 51 | 46 | 40 | 37 | 31 | 25 | 19 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 23 | 2017-12-09 | 98 | 94 | 90 | 87 | 84 | 80 | 76 | 71 | 66 | 60 | 57 | 53 | 49 | 45 | 41 | 35 | 29 | 25 | 20 | 16 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 18 | 2017-11-04 | 70 | 67 | 62 | 59 | 56 | 52 | 48 | 45 | 40 | 36 | 32 | 29 | 24 | 18 | 14 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 15 | 2017-10-14 | 69 | 63 | 58 | 52 | 49 | 43 | 40 | 34 | 30 | 26 | 20 | 16 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 18 | 2017-11-04 | 75 | 71 | 67 | 62 | 56 | 52 | 47 | 42 | 39 | 34 | 30 | 27 | 21 | 18 | 15 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 16 | 2017-10-21 | 81 | 76 | 70 | 64 | 58 | 54 | 48 | 42 | 36 | 30 | 27 | 23 | 18 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 23 | 2017-12-09 | 103 | 99 | 94 | 90 | 84 | 80 | 75 | 69 | 66 | 62 | 59 | 54 | 51 | 48 | 42 | 39 | 34 | 29 | 23 | 17 | 14 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 15 | 2017-10-14 | 64 | 59 | 53 | 50 | 47 | 43 | 37 | 32 | 29 | 25 | 19 | 15 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 16 | 2017-10-21 | 60 | 57 | 51 | 48 | 45 | 42 | 36 | 32 | 29 | 24 | 21 | 18 | 12 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 25 | 2017-12-23 | 111 | 106 | 102 | 98 | 93 | 88 | 84 | 79 | 74 | 68 | 64 | 58 | 53 | 49 | 45 | 42 | 37 | 33 | 28 | 25 | 21 | 15 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 20 | 2017-11-18 | 80 | 77 | 73 | 69 | 65 | 62 | 57 | 51 | 48 | 43 | 39 | 36 | 32 | 26 | 23 | 19 | 16 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 12 | 2017-09-23 | 55 | 50 | 47 | 41 | 38 | 32 | 26 | 20 | 15 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 11 | 2017-09-16 | 52 | 46 | 40 | 34 | 28 | 24 | 18 | 14 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 16 | 2017-10-21 | 70 | 66 | 61 | 55 | 51 | 45 | 40 | 37 | 34 | 31 | 28 | 24 | 18 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 19 | 2017-11-11 | 79 | 73 | 69 | 64 | 59 | 56 | 53 | 49 | 44 | 38 | 32 | 29 | 25 | 22 | 18 | 14 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 14 | 2017-10-07 | 58 | 53 | 50 | 44 | 40 | 34 | 29 | 26 | 21 | 17 | 14 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 20 | 2017-11-18 | 85 | 82 | 79 | 75 | 70 | 66 | 63 | 58 | 54 | 48 | 42 | 36 | 33 | 27 | 21 | 18 | 14 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 20 | 2017-11-18 | 83 | 78 | 74 | 69 | 64 | 60 | 57 | 53 | 49 | 43 | 39 | 36 | 32 | 27 | 23 | 20 | 16 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 18 | 2017-11-04 | 84 | 78 | 74 | 68 | 65 | 61 | 56 | 53 | 48 | 44 | 39 | 35 | 29 | 23 | 18 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 14 | 2017-10-07 | 63 | 57 | 53 | 47 | 43 | 38 | 32 | 27 | 22 | 16 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 16 | 2017-10-21 | 70 | 66 | 61 | 58 | 52 | 48 | 45 | 39 | 35 | 30 | 27 | 24 | 19 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 16 | 2017-10-21 | 69 | 66 | 60 | 57 | 54 | 48 | 45 | 42 | 37 | 31 | 25 | 19 | 16 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 22 | 2017-12-02 | 101 | 98 | 92 | 87 | 82 | 76 | 70 | 65 | 62 | 58 | 55 | 50 | 45 | 41 | 37 | 32 | 26 | 20 | 14 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 23 | 2017-12-09 | 96 | 92 | 87 | 84 | 80 | 74 | 71 | 68 | 62 | 59 | 56 | 51 | 48 | 42 | 37 | 31 | 26 | 23 | 17 | 14 | 9 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 15 | 2017-10-14 | 67 | 63 | 57 | 51 | 47 | 41 | 36 | 30 | 24 | 20 | 16 | 13 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 15 | 2017-10-14 | 58 | 55 | 52 | 48 | 44 | 38 | 35 | 32 | 29 | 23 | 20 | 16 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 26 | 2017-12-30 | 111 | 105 | 100 | 97 | 94 | 88 | 84 | 79 | 76 | 72 | 68 | 65 | 62 | 56 | 53 | 47 | 43 | 38 | 35 | 30 | 25 | 21 | 18 | 14 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 21 | 2017-11-25 | 94 | 88 | 85 | 81 | 76 | 70 | 67 | 63 | 59 | 54 | 49 | 46 | 40 | 36 | 30 | 24 | 21 | 18 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 18 | 2017-11-04 | 80 | 74 | 68 | 65 | 59 | 53 | 49 | 44 | 41 | 36 | 31 | 27 | 23 | 19 | 16 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 13 | 2017-09-30 | 63 | 59 | 53 | 48 | 42 | 36 | 31 | 27 | 23 | 17 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 19 | 2017-11-11 | 90 | 87 | 81 | 76 | 70 | 64 | 61 | 57 | 52 | 49 | 46 | 40 | 34 | 30 | 24 | 18 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 20 | 2017-11-18 | 90 | 85 | 79 | 75 | 69 | 63 | 60 | 57 | 52 | 46 | 41 | 36 | 32 | 26 | 23 | 19 | 15 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 20 | 2017-11-18 | 81 | 75 | 72 | 68 | 64 | 59 | 55 | 52 | 47 | 42 | 39 | 34 | 30 | 24 | 21 | 17 | 13 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 19 | 2017-11-11 | 76 | 71 | 68 | 63 | 60 | 57 | 54 | 49 | 45 | 41 | 35 | 32 | 29 | 23 | 19 | 15 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 22 | 2017-12-02 | 95 | 91 | 86 | 83 | 77 | 73 | 67 | 64 | 59 | 56 | 53 | 48 | 45 | 39 | 36 | 30 | 25 | 20 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 20 | 2017-11-18 | 89 | 84 | 81 | 75 | 69 | 64 | 61 | 55 | 52 | 49 | 46 | 41 | 37 | 31 | 28 | 25 | 19 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 20 | 2017-11-18 | 91 | 87 | 82 | 76 | 71 | 68 | 63 | 59 | 56 | 50 | 44 | 38 | 35 | 29 | 23 | 19 | 16 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 20 | 2017-11-18 | 82 | 79 | 74 | 68 | 63 | 59 | 56 | 51 | 45 | 40 | 37 | 33 | 29 | 26 | 23 | 18 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 14 | 2017-10-07 | 59 | 54 | 51 | 46 | 41 | 37 | 32 | 29 | 23 | 20 | 16 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 19 | 2017-11-11 | 85 | 81 | 77 | 71 | 68 | 65 | 60 | 55 | 51 | 48 | 42 | 36 | 31 | 27 | 22 | 19 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 14 | 2017-10-07 | 62 | 58 | 54 | 48 | 42 | 38 | 33 | 30 | 25 | 20 | 17 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 23 | 2017-12-09 | 105 | 100 | 95 | 89 | 83 | 80 | 76 | 73 | 67 | 63 | 57 | 54 | 48 | 42 | 38 | 34 | 30 | 24 | 19 | 16 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 20 | 2017-11-18 | 95 | 91 | 86 | 81 | 76 | 72 | 67 | 64 | 59 | 55 | 49 | 44 | 40 | 34 | 30 | 24 | 20 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 22 | 2017-12-02 | 103 | 98 | 92 | 88 | 82 | 77 | 73 | 68 | 65 | 61 | 57 | 51 | 45 | 42 | 37 | 32 | 27 | 22 | 17 | 11 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 20 | 2017-11-18 | 99 | 93 | 87 | 81 | 77 | 72 | 68 | 65 | 59 | 54 | 49 | 43 | 37 | 32 | 26 | 23 | 17 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 19 | 2017-11-11 | 79 | 74 | 71 | 68 | 64 | 58 | 54 | 49 | 46 | 42 | 39 | 33 | 27 | 22 | 16 | 13 | 10 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 24 | 2017-12-16 | 99 | 95 | 92 | 86 | 83 | 80 | 76 | 70 | 66 | 61 | 57 | 51 | 47 | 44 | 40 | 36 | 31 | 28 | 22 | 19 | 14 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 19 | 2017-11-11 | 83 | 78 | 73 | 67 | 64 | 61 | 55 | 51 | 46 | 40 | 34 | 28 | 24 | 18 | 15 | 12 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 26 | 2017-12-30 | 108 | 105 | 102 | 98 | 95 | 91 | 86 | 80 | 75 | 70 | 67 | 64 | 58 | 53 | 50 | 46 | 42 | 38 | 32 | 28 | 23 | 18 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 19 | 2017-11-11 | 82 | 77 | 72 | 67 | 62 | 59 | 53 | 50 | 45 | 42 | 38 | 35 | 31 | 26 | 22 | 16 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 16 | 2017-10-21 | 71 | 65 | 61 | 56 | 51 | 47 | 42 | 37 | 34 | 29 | 25 | 22 | 19 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 24 | 2017-12-16 | 107 | 103 | 99 | 93 | 89 | 83 | 79 | 74 | 68 | 64 | 61 | 57 | 52 | 46 | 43 | 40 | 34 | 31 | 25 | 20 | 17 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 19 | 2017-11-11 | 84 | 81 | 76 | 72 | 68 | 62 | 56 | 51 | 46 | 43 | 39 | 35 | 30 | 24 | 20 | 17 | 13 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 15 | 2017-10-14 | 63 | 57 | 51 | 46 | 43 | 37 | 33 | 28 | 24 | 21 | 16 | 10 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 21 | 2017-11-25 | 98 | 94 | 89 | 83 | 80 | 77 | 71 | 65 | 60 | 56 | 50 | 46 | 41 | 38 | 35 | 30 | 26 | 20 | 16 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 17 | 2017-10-28 | 75 | 71 | 65 | 61 | 56 | 52 | 46 | 43 | 37 | 31 | 26 | 23 | 20 | 17 | 12 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 20 | 2017-11-18 | 83 | 77 | 72 | 66 | 62 | 59 | 56 | 52 | 49 | 46 | 42 | 38 | 32 | 27 | 23 | 20 | 17 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 21 | 2017-11-25 | 97 | 92 | 87 | 82 | 78 | 74 | 70 | 67 | 63 | 57 | 54 | 50 | 44 | 38 | 33 | 27 | 21 | 16 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 19 | 2017-11-11 | 78 | 74 | 71 | 68 | 62 | 56 | 53 | 48 | 44 | 40 | 37 | 34 | 29 | 23 | 18 | 13 | 10 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 22 | 2017-12-02 | 93 | 89 | 86 | 82 | 76 | 71 | 65 | 62 | 59 | 53 | 50 | 45 | 42 | 37 | 34 | 29 | 24 | 19 | 16 | 13 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 20 | 2017-11-18 | 89 | 86 | 82 | 79 | 76 | 73 | 68 | 62 | 56 | 51 | 47 | 41 | 38 | 32 | 27 | 24 | 21 | 15 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 22 | 2017-12-02 | 91 | 87 | 84 | 81 | 78 | 75 | 69 | 65 | 59 | 56 | 52 | 47 | 44 | 38 | 33 | 27 | 23 | 18 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 11 | 2017-09-16 | 53 | 49 | 43 | 37 | 31 | 25 | 19 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 21 | 2017-11-25 | 93 | 90 | 87 | 82 | 76 | 70 | 64 | 59 | 53 | 49 | 45 | 42 | 36 | 31 | 26 | 21 | 18 | 14 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 21 | 2017-11-25 | 98 | 94 | 88 | 84 | 81 | 75 | 72 | 66 | 62 | 59 | 53 | 47 | 41 | 38 | 34 | 30 | 27 | 22 | 16 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 17 | 2017-10-28 | 75 | 72 | 67 | 61 | 56 | 52 | 49 | 43 | 38 | 32 | 29 | 24 | 18 | 15 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 19 | 2017-11-11 | 81 | 78 | 73 | 70 | 65 | 61 | 58 | 53 | 48 | 43 | 38 | 34 | 30 | 26 | 21 | 17 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 20 | 2017-11-18 | 91 | 85 | 82 | 76 | 72 | 66 | 62 | 56 | 50 | 45 | 40 | 35 | 32 | 29 | 23 | 18 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 17 | 2017-10-28 | 77 | 72 | 67 | 63 | 59 | 54 | 51 | 47 | 42 | 37 | 33 | 27 | 24 | 19 | 15 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 19 | 2017-11-11 | 82 | 76 | 73 | 70 | 67 | 62 | 58 | 54 | 50 | 44 | 39 | 34 | 29 | 25 | 21 | 17 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 19 | 2017-11-11 | 78 | 73 | 70 | 67 | 64 | 61 | 58 | 52 | 49 | 44 | 38 | 33 | 30 | 27 | 23 | 17 | 12 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 20 | 2017-11-18 | 85 | 82 | 77 | 73 | 70 | 67 | 63 | 60 | 54 | 50 | 46 | 42 | 36 | 33 | 28 | 23 | 17 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 18 | 2017-11-04 | 71 | 66 | 62 | 58 | 55 | 52 | 48 | 44 | 39 | 35 | 31 | 28 | 23 | 20 | 17 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 25 | 2017-12-23 | 106 | 103 | 99 | 94 | 91 | 85 | 79 | 76 | 73 | 68 | 64 | 60 | 54 | 51 | 47 | 43 | 39 | 36 | 30 | 25 | 19 | 15 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 19 | 2017-11-11 | 83 | 79 | 73 | 67 | 63 | 59 | 55 | 49 | 44 | 39 | 34 | 29 | 23 | 19 | 16 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 23 | 2017-12-09 | 97 | 91 | 88 | 85 | 80 | 76 | 70 | 67 | 61 | 56 | 52 | 49 | 46 | 41 | 36 | 33 | 29 | 25 | 22 | 18 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 19 | 2017-11-11 | 74 | 69 | 66 | 61 | 55 | 50 | 47 | 44 | 41 | 38 | 35 | 30 | 26 | 23 | 19 | 15 | 11 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 20 | 2017-11-18 | 83 | 79 | 75 | 72 | 68 | 63 | 57 | 54 | 51 | 47 | 44 | 39 | 35 | 31 | 25 | 21 | 15 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 24 | 2017-12-16 | 109 | 106 | 101 | 97 | 93 | 87 | 81 | 75 | 70 | 64 | 59 | 54 | 48 | 42 | 37 | 31 | 26 | 23 | 20 | 17 | 14 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 20 | 2017-11-18 | 81 | 78 | 74 | 69 | 65 | 62 | 58 | 55 | 52 | 47 | 41 | 38 | 35 | 31 | 26 | 20 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 13 | 2017-09-30 | 61 | 58 | 52 | 46 | 41 | 37 | 31 | 27 | 21 | 17 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 26 | 2017-12-30 | 103 | 100 | 96 | 92 | 87 | 84 | 78 | 73 | 69 | 66 | 61 | 58 | 53 | 47 | 43 | 40 | 37 | 34 | 30 | 27 | 24 | 20 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 23 | 2017-12-09 | 96 | 92 | 89 | 83 | 78 | 74 | 71 | 68 | 64 | 61 | 56 | 53 | 49 | 43 | 38 | 32 | 27 | 24 | 19 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 19 | 2017-11-11 | 88 | 83 | 77 | 74 | 70 | 65 | 59 | 56 | 50 | 44 | 40 | 36 | 33 | 27 | 22 | 17 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 20 | 2017-11-18 | 89 | 85 | 79 | 76 | 71 | 68 | 62 | 58 | 55 | 51 | 45 | 39 | 33 | 28 | 22 | 18 | 14 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 21 | 2017-11-25 | 100 | 97 | 92 | 88 | 83 | 77 | 73 | 67 | 62 | 58 | 54 | 48 | 44 | 40 | 35 | 29 | 23 | 17 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 20 | 2017-11-18 | 89 | 86 | 80 | 74 | 71 | 65 | 61 | 55 | 52 | 46 | 43 | 40 | 34 | 31 | 26 | 20 | 15 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 23 | 2017-12-09 | 100 | 95 | 92 | 88 | 83 | 77 | 73 | 67 | 61 | 57 | 52 | 47 | 44 | 38 | 34 | 31 | 28 | 25 | 19 | 16 | 13 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 21 | 2017-11-25 | 92 | 88 | 84 | 81 | 76 | 72 | 67 | 62 | 57 | 52 | 47 | 43 | 37 | 34 | 30 | 24 | 21 | 16 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 25 | 2017-12-23 | 108 | 105 | 99 | 94 | 91 | 86 | 83 | 78 | 74 | 71 | 65 | 59 | 53 | 50 | 47 | 43 | 37 | 31 | 26 | 23 | 20 | 15 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 14 | 2017-10-07 | 65 | 62 | 56 | 50 | 44 | 41 | 38 | 33 | 27 | 22 | 17 | 14 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 18 | 2017-11-04 | 82 | 76 | 70 | 65 | 62 | 57 | 53 | 49 | 46 | 43 | 38 | 32 | 29 | 26 | 21 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 14 | 2017-10-07 | 64 | 60 | 54 | 48 | 42 | 39 | 36 | 32 | 26 | 22 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 16 | 2017-10-21 | 69 | 66 | 62 | 57 | 52 | 49 | 43 | 39 | 34 | 30 | 27 | 21 | 16 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 23 | 2017-12-09 | 97 | 94 | 90 | 85 | 82 | 79 | 76 | 70 | 67 | 62 | 59 | 55 | 50 | 45 | 40 | 36 | 31 | 27 | 24 | 18 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 21 | 2017-11-25 | 93 | 88 | 82 | 79 | 76 | 71 | 67 | 63 | 57 | 53 | 48 | 45 | 42 | 36 | 31 | 26 | 20 | 15 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 24 | 2017-12-16 | 103 | 97 | 91 | 87 | 84 | 81 | 75 | 70 | 67 | 62 | 59 | 55 | 52 | 49 | 43 | 37 | 31 | 26 | 23 | 18 | 13 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 18 | 2017-11-04 | 72 | 67 | 62 | 57 | 53 | 49 | 44 | 41 | 38 | 35 | 31 | 25 | 22 | 19 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 21 | 2017-11-25 | 87 | 84 | 81 | 76 | 72 | 69 | 66 | 62 | 58 | 54 | 48 | 45 | 41 | 37 | 32 | 26 | 23 | 17 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 19 | 2017-11-11 | 88 | 82 | 77 | 72 | 67 | 61 | 57 | 52 | 47 | 44 | 40 | 35 | 31 | 25 | 21 | 18 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 25 | 2017-12-23 | 103 | 99 | 96 | 92 | 89 | 84 | 79 | 73 | 69 | 63 | 57 | 52 | 46 | 41 | 38 | 35 | 31 | 28 | 23 | 18 | 15 | 12 | 8 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 22 | 2017-12-02 | 92 | 89 | 86 | 82 | 78 | 74 | 69 | 65 | 62 | 59 | 56 | 50 | 46 | 42 | 37 | 34 | 29 | 23 | 18 | 13 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 14 | 2017-10-07 | 67 | 62 | 56 | 50 | 47 | 41 | 35 | 29 | 23 | 19 | 14 | 11 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 21 | 2017-11-25 | 98 | 94 | 89 | 83 | 77 | 74 | 70 | 64 | 58 | 55 | 51 | 45 | 39 | 33 | 28 | 25 | 21 | 18 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 19 | 2017-11-11 | 80 | 76 | 72 | 67 | 64 | 59 | 55 | 51 | 46 | 40 | 37 | 33 | 30 | 24 | 20 | 17 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 21 | 2017-11-25 | 95 | 91 | 88 | 84 | 79 | 76 | 70 | 64 | 60 | 56 | 51 | 45 | 40 | 35 | 32 | 27 | 21 | 15 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 16 | 2017-10-21 | 61 | 57 | 54 | 50 | 45 | 42 | 38 | 32 | 29 | 26 | 21 | 17 | 14 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 22 | 2017-12-02 | 101 | 98 | 92 | 87 | 83 | 80 | 74 | 68 | 63 | 60 | 57 | 54 | 48 | 45 | 41 | 35 | 29 | 23 | 19 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 16 | 2017-10-21 | 66 | 63 | 59 | 55 | 52 | 49 | 43 | 37 | 34 | 29 | 24 | 21 | 18 | 12 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 22 | 2017-12-02 | 99 | 94 | 90 | 87 | 83 | 78 | 73 | 68 | 63 | 59 | 54 | 49 | 43 | 39 | 33 | 29 | 23 | 19 | 16 | 12 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 19 | 2017-11-11 | 87 | 83 | 77 | 71 | 68 | 64 | 59 | 53 | 50 | 44 | 40 | 34 | 28 | 25 | 20 | 17 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 17 | 2017-10-28 | 83 | 77 | 71 | 68 | 63 | 60 | 54 | 49 | 43 | 37 | 31 | 26 | 22 | 16 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 17 | 2017-10-28 | 75 | 72 | 66 | 60 | 55 | 52 | 48 | 44 | 40 | 36 | 31 | 26 | 22 | 17 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 22 | 2017-12-02 | 93 | 89 | 85 | 82 | 79 | 76 | 72 | 68 | 62 | 57 | 54 | 49 | 46 | 42 | 38 | 32 | 26 | 22 | 19 | 13 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 11 | 2017-09-16 | 53 | 48 | 43 | 38 | 32 | 29 | 23 | 17 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:BD2,1,[Weeks to Zero]+1),"")

## Risk Impact Monte Carlo (hidden)
 | time axis 2017-07-01 to 2018-06-30
Risk 1 - Reduce Probability
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
1 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
26 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
44 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
47 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
50 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
51 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
52 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
53 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
54 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
55 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
56 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
57 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
58 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
59 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
60 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
61 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
62 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
63 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
64 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
65 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
66 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
67 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
68 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
69 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
70 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
71 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
72 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
73 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
74 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
75 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
76 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
77 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
78 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
79 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
80 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
81 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
82 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
83 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
84 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
85 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
86 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
87 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
88 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
89 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
90 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
91 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
92 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
93 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
94 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
95 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
96 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
97 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
98 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
99 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
100 |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Risk 1 - Reduce Impact
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
1 | 16 | 2017-10-21 | 67 | 63 | 57 | 52 | 49 | 46 | 42 | 39 | 35 | 31 | 25 | 20 | 17 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 14 | 2017-10-07 | 58 | 53 | 48 | 45 | 42 | 39 | 33 | 29 | 24 | 21 | 16 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 15 | 2017-10-14 | 64 | 58 | 55 | 51 | 46 | 43 | 38 | 34 | 29 | 26 | 21 | 16 | 12 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 16 | 2017-10-21 | 71 | 65 | 61 | 58 | 53 | 47 | 43 | 37 | 33 | 27 | 24 | 18 | 12 | 7 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 14 | 2017-10-07 | 68 | 62 | 56 | 50 | 45 | 41 | 38 | 32 | 27 | 21 | 18 | 12 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 14 | 2017-10-07 | 62 | 58 | 53 | 50 | 44 | 40 | 36 | 31 | 25 | 21 | 15 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 20 | 2017-11-18 | 84 | 81 | 75 | 69 | 66 | 63 | 59 | 55 | 50 | 45 | 40 | 36 | 32 | 27 | 24 | 21 | 16 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 13 | 2017-09-30 | 58 | 55 | 50 | 47 | 41 | 35 | 29 | 25 | 21 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 16 | 2017-10-21 | 70 | 64 | 59 | 53 | 50 | 45 | 41 | 36 | 32 | 29 | 24 | 20 | 17 | 14 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 14 | 2017-10-07 | 64 | 60 | 54 | 51 | 46 | 40 | 34 | 31 | 25 | 22 | 17 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 21 | 2017-11-25 | 97 | 94 | 91 | 86 | 82 | 78 | 75 | 70 | 64 | 60 | 57 | 52 | 47 | 44 | 40 | 34 | 28 | 23 | 18 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 19 | 2017-11-11 | 84 | 78 | 74 | 71 | 66 | 63 | 57 | 53 | 50 | 45 | 42 | 36 | 33 | 28 | 24 | 18 | 13 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 22 | 2017-12-02 | 93 | 90 | 86 | 80 | 76 | 70 | 67 | 61 | 57 | 53 | 48 | 44 | 39 | 35 | 31 | 25 | 22 | 17 | 13 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 23 | 2017-12-09 | 105 | 100 | 96 | 90 | 84 | 79 | 74 | 71 | 66 | 62 | 57 | 51 | 48 | 43 | 40 | 35 | 31 | 27 | 23 | 17 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 28 | 2018-01-13 | 114 | 111 | 108 | 105 | 100 | 97 | 92 | 87 | 83 | 80 | 74 | 69 | 66 | 61 | 58 | 53 | 50 | 45 | 42 | 38 | 32 | 29 | 26 | 23 | 17 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 22 | 2017-12-02 | 92 | 87 | 84 | 78 | 74 | 68 | 63 | 60 | 55 | 52 | 46 | 42 | 38 | 35 | 31 | 28 | 25 | 22 | 17 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 17 | 2017-10-28 | 73 | 68 | 65 | 61 | 58 | 52 | 47 | 42 | 38 | 35 | 31 | 27 | 21 | 17 | 11 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 21 | 2017-11-25 | 96 | 90 | 85 | 82 | 76 | 70 | 65 | 61 | 57 | 54 | 49 | 46 | 43 | 39 | 35 | 30 | 25 | 19 | 14 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 21 | 2017-11-25 | 93 | 90 | 85 | 81 | 77 | 71 | 65 | 59 | 54 | 50 | 47 | 42 | 36 | 31 | 28 | 25 | 19 | 16 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 16 | 2017-10-21 | 81 | 75 | 69 | 63 | 58 | 52 | 47 | 41 | 38 | 33 | 28 | 25 | 19 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 21 | 2017-11-25 | 90 | 86 | 81 | 77 | 73 | 70 | 66 | 61 | 58 | 54 | 48 | 43 | 37 | 34 | 29 | 23 | 20 | 16 | 10 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 17 | 2017-10-28 | 80 | 76 | 70 | 67 | 63 | 58 | 52 | 49 | 46 | 41 | 38 | 33 | 28 | 23 | 17 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 13 | 2017-09-30 | 56 | 50 | 45 | 40 | 37 | 34 | 31 | 26 | 20 | 17 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 20 | 2017-11-18 | 87 | 84 | 79 | 75 | 71 | 68 | 63 | 58 | 52 | 49 | 43 | 40 | 34 | 29 | 26 | 21 | 15 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 13 | 2017-09-30 | 53 | 49 | 46 | 42 | 37 | 32 | 28 | 22 | 16 | 13 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 13 | 2017-09-30 | 58 | 52 | 47 | 43 | 37 | 33 | 28 | 22 | 17 | 14 | 10 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 13 | 2017-09-30 | 58 | 52 | 47 | 44 | 39 | 34 | 30 | 24 | 20 | 17 | 11 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 20 | 2017-11-18 | 99 | 93 | 88 | 82 | 78 | 72 | 66 | 61 | 55 | 50 | 45 | 40 | 34 | 31 | 25 | 21 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 21 | 2017-11-25 | 84 | 81 | 76 | 71 | 66 | 63 | 59 | 55 | 51 | 46 | 42 | 38 | 34 | 30 | 27 | 23 | 19 | 15 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 29 | 2018-01-20 | 116 | 113 | 110 | 107 | 104 | 99 | 93 | 90 | 86 | 81 | 78 | 75 | 72 | 69 | 64 | 61 | 58 | 54 | 48 | 43 | 39 | 34 | 28 | 23 | 20 | 17 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 20 | 2017-11-18 | 93 | 87 | 81 | 76 | 73 | 70 | 64 | 61 | 56 | 50 | 44 | 38 | 34 | 29 | 24 | 21 | 18 | 13 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 22 | 2017-12-02 | 89 | 84 | 78 | 75 | 72 | 69 | 66 | 63 | 59 | 53 | 50 | 45 | 42 | 38 | 33 | 28 | 25 | 21 | 16 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 21 | 2017-11-25 | 89 | 86 | 80 | 75 | 70 | 64 | 58 | 55 | 49 | 44 | 41 | 37 | 32 | 29 | 23 | 20 | 16 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 20 | 2017-11-18 | 88 | 82 | 77 | 73 | 70 | 67 | 61 | 57 | 52 | 48 | 44 | 41 | 38 | 32 | 27 | 23 | 20 | 15 | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 25 | 2017-12-23 | 110 | 106 | 103 | 98 | 93 | 89 | 85 | 79 | 73 | 69 | 65 | 59 | 53 | 48 | 45 | 39 | 35 | 30 | 25 | 22 | 18 | 14 | 11 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 15 | 2017-10-14 | 63 | 59 | 54 | 50 | 46 | 43 | 37 | 31 | 28 | 25 | 21 | 16 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 23 | 2017-12-09 | 96 | 93 | 90 | 87 | 84 | 79 | 76 | 73 | 69 | 66 | 60 | 56 | 50 | 47 | 41 | 36 | 32 | 26 | 23 | 17 | 13 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 20 | 2017-11-18 | 91 | 85 | 80 | 75 | 71 | 65 | 62 | 56 | 52 | 48 | 42 | 37 | 31 | 26 | 23 | 18 | 14 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 21 | 2017-11-25 | 93 | 87 | 83 | 78 | 73 | 68 | 65 | 62 | 56 | 51 | 48 | 44 | 40 | 36 | 33 | 27 | 22 | 17 | 11 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 17 | 2017-10-28 | 81 | 77 | 72 | 67 | 63 | 59 | 53 | 50 | 44 | 41 | 36 | 30 | 25 | 20 | 15 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 21 | 2017-11-25 | 92 | 89 | 83 | 79 | 73 | 70 | 65 | 61 | 58 | 52 | 49 | 43 | 40 | 35 | 32 | 29 | 24 | 18 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 26 | 2017-12-30 | 111 | 106 | 103 | 97 | 94 | 89 | 84 | 79 | 75 | 69 | 66 | 62 | 59 | 56 | 51 | 48 | 45 | 42 | 39 | 33 | 29 | 23 | 17 | 11 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 19 | 2017-11-11 | 90 | 84 | 80 | 75 | 70 | 66 | 60 | 54 | 48 | 45 | 39 | 34 | 31 | 27 | 22 | 17 | 14 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 22 | 2017-12-02 | 97 | 91 | 86 | 80 | 76 | 71 | 67 | 62 | 56 | 53 | 48 | 44 | 41 | 35 | 32 | 28 | 25 | 21 | 15 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 11 | 2017-09-16 | 53 | 48 | 42 | 38 | 34 | 31 | 27 | 21 | 15 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 21 | 2017-11-25 | 96 | 93 | 87 | 81 | 78 | 74 | 69 | 66 | 63 | 58 | 52 | 48 | 43 | 37 | 33 | 29 | 25 | 19 | 15 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 18 | 2017-11-04 | 85 | 81 | 75 | 70 | 67 | 61 | 56 | 50 | 45 | 42 | 36 | 32 | 26 | 23 | 19 | 15 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 23 | 2017-12-09 | 101 | 96 | 93 | 87 | 84 | 81 | 78 | 74 | 68 | 63 | 58 | 53 | 50 | 46 | 43 | 38 | 34 | 28 | 23 | 18 | 14 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 16 | 2017-10-21 | 71 | 67 | 63 | 58 | 52 | 49 | 44 | 39 | 36 | 31 | 28 | 22 | 17 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 12 | 2017-09-23 | 53 | 48 | 45 | 40 | 34 | 31 | 26 | 23 | 18 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 12 | 2017-09-23 | 56 | 52 | 46 | 40 | 34 | 30 | 24 | 18 | 15 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 13 | 2017-09-30 | 57 | 54 | 51 | 47 | 44 | 38 | 33 | 29 | 25 | 20 | 14 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 17 | 2017-10-28 | 72 | 68 | 65 | 61 | 57 | 53 | 47 | 41 | 36 | 33 | 28 | 22 | 17 | 14 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 20 | 2017-11-18 | 89 | 85 | 81 | 75 | 71 | 67 | 64 | 59 | 54 | 50 | 44 | 38 | 33 | 27 | 24 | 19 | 14 | 10 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 17 | 2017-10-28 | 73 | 68 | 64 | 58 | 52 | 49 | 46 | 41 | 35 | 31 | 28 | 24 | 21 | 17 | 12 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 22 | 2017-12-02 | 95 | 92 | 89 | 84 | 78 | 75 | 72 | 67 | 63 | 58 | 53 | 47 | 41 | 37 | 31 | 28 | 23 | 20 | 15 | 12 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 20 | 2017-11-18 | 85 | 81 | 78 | 75 | 69 | 66 | 62 | 56 | 50 | 45 | 41 | 35 | 30 | 26 | 23 | 18 | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 14 | 2017-10-07 | 58 | 52 | 49 | 45 | 41 | 38 | 34 | 29 | 25 | 22 | 17 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 17 | 2017-10-28 | 73 | 68 | 62 | 56 | 50 | 46 | 42 | 36 | 33 | 29 | 24 | 21 | 18 | 14 | 9 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 23 | 2017-12-09 | 110 | 104 | 100 | 95 | 89 | 86 | 80 | 76 | 71 | 66 | 61 | 56 | 50 | 46 | 40 | 34 | 31 | 25 | 19 | 14 | 11 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 24 | 2017-12-16 | 108 | 104 | 99 | 93 | 90 | 84 | 80 | 77 | 71 | 67 | 62 | 58 | 55 | 51 | 46 | 42 | 39 | 33 | 27 | 22 | 16 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 24 | 2017-12-16 | 102 | 98 | 93 | 89 | 84 | 80 | 76 | 73 | 70 | 67 | 62 | 59 | 55 | 52 | 48 | 42 | 36 | 32 | 28 | 22 | 18 | 15 | 11 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 13 | 2017-09-30 | 56 | 52 | 49 | 43 | 39 | 35 | 29 | 23 | 19 | 13 | 9 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 18 | 2017-11-04 | 72 | 67 | 62 | 58 | 55 | 52 | 47 | 43 | 40 | 37 | 31 | 28 | 22 | 17 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 21 | 2017-11-25 | 92 | 88 | 84 | 79 | 76 | 71 | 65 | 61 | 56 | 52 | 48 | 45 | 40 | 36 | 32 | 27 | 21 | 18 | 13 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 12 | 2017-09-23 | 54 | 51 | 48 | 42 | 39 | 35 | 29 | 25 | 19 | 14 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 24 | 2017-12-16 | 104 | 98 | 94 | 90 | 85 | 81 | 76 | 70 | 66 | 63 | 57 | 54 | 50 | 44 | 39 | 35 | 31 | 26 | 23 | 18 | 14 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 21 | 2017-11-25 | 88 | 85 | 82 | 79 | 75 | 71 | 68 | 63 | 57 | 53 | 49 | 44 | 38 | 35 | 31 | 27 | 22 | 16 | 13 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 15 | 2017-10-14 | 67 | 61 | 56 | 51 | 45 | 40 | 36 | 32 | 29 | 26 | 20 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 17 | 2017-10-28 | 76 | 73 | 67 | 62 | 59 | 55 | 49 | 45 | 40 | 34 | 31 | 26 | 21 | 17 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 14 | 2017-10-07 | 63 | 58 | 55 | 49 | 46 | 40 | 35 | 30 | 24 | 18 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 18 | 2017-11-04 | 95 | 89 | 83 | 77 | 71 | 65 | 59 | 55 | 50 | 45 | 39 | 34 | 30 | 24 | 20 | 14 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 24 | 2017-12-16 | 113 | 108 | 103 | 98 | 93 | 87 | 81 | 77 | 72 | 66 | 62 | 59 | 55 | 49 | 45 | 41 | 38 | 32 | 26 | 23 | 18 | 12 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 14 | 2017-10-07 | 56 | 52 | 47 | 42 | 38 | 32 | 29 | 26 | 22 | 18 | 14 | 11 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 17 | 2017-10-28 | 77 | 71 | 67 | 64 | 61 | 55 | 50 | 46 | 42 | 36 | 31 | 26 | 23 | 20 | 15 | 11 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 16 | 2017-10-21 | 74 | 68 | 63 | 60 | 56 | 53 | 49 | 45 | 39 | 35 | 29 | 23 | 18 | 12 | 9 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 22 | 2017-12-02 | 94 | 90 | 84 | 81 | 78 | 73 | 68 | 65 | 62 | 56 | 51 | 47 | 44 | 40 | 37 | 34 | 31 | 26 | 21 | 15 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 17 | 2017-10-28 | 76 | 70 | 66 | 61 | 56 | 51 | 48 | 45 | 42 | 36 | 32 | 27 | 23 | 19 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 15 | 2017-10-14 | 69 | 64 | 60 | 54 | 51 | 45 | 39 | 36 | 31 | 25 | 20 | 16 | 11 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 20 | 2017-11-18 | 75 | 72 | 68 | 64 | 59 | 55 | 51 | 46 | 43 | 40 | 37 | 34 | 30 | 25 | 21 | 17 | 13 | 10 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 20 | 2017-11-18 | 90 | 86 | 83 | 77 | 73 | 69 | 65 | 59 | 54 | 48 | 43 | 40 | 36 | 32 | 27 | 22 | 18 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 14 | 2017-10-07 | 57 | 53 | 48 | 45 | 42 | 38 | 32 | 26 | 20 | 17 | 13 | 9 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 22 | 2017-12-02 | 95 | 91 | 85 | 80 | 77 | 71 | 67 | 63 | 58 | 52 | 48 | 42 | 38 | 34 | 30 | 27 | 24 | 18 | 13 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 14 | 2017-10-07 | 66 | 61 | 55 | 50 | 44 | 41 | 36 | 32 | 26 | 23 | 18 | 14 | 9 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 25 | 2017-12-23 | 113 | 110 | 106 | 103 | 99 | 93 | 87 | 81 | 76 | 71 | 65 | 59 | 56 | 52 | 48 | 44 | 39 | 36 | 30 | 24 | 21 | 16 | 12 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 20 | 2017-11-18 | 85 | 82 | 77 | 73 | 67 | 64 | 59 | 56 | 53 | 48 | 43 | 37 | 34 | 29 | 26 | 22 | 16 | 11 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 20 | 2017-11-18 | 88 | 83 | 78 | 72 | 69 | 66 | 60 | 55 | 49 | 44 | 40 | 35 | 29 | 26 | 22 | 17 | 13 | 10 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 25 | 2017-12-23 | 109 | 104 | 98 | 94 | 88 | 82 | 77 | 73 | 69 | 66 | 60 | 56 | 52 | 47 | 43 | 40 | 36 | 30 | 27 | 23 | 18 | 13 | 8 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 23 | 2017-12-09 | 97 | 92 | 87 | 84 | 80 | 76 | 72 | 66 | 63 | 58 | 53 | 50 | 47 | 44 | 41 | 36 | 31 | 26 | 22 | 17 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 19 | 2017-11-11 | 77 | 73 | 69 | 66 | 60 | 57 | 54 | 50 | 44 | 41 | 35 | 31 | 28 | 24 | 18 | 15 | 10 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 14 | 2017-10-07 | 61 | 58 | 52 | 47 | 43 | 38 | 34 | 28 | 23 | 17 | 13 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 18 | 2017-11-04 | 83 | 80 | 75 | 69 | 64 | 59 | 53 | 47 | 44 | 41 | 37 | 31 | 25 | 21 | 16 | 13 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 24 | 2017-12-16 | 100 | 95 | 90 | 86 | 81 | 76 | 71 | 67 | 64 | 61 | 58 | 52 | 46 | 42 | 36 | 33 | 30 | 27 | 23 | 19 | 13 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 22 | 2017-12-02 | 92 | 89 | 86 | 80 | 75 | 72 | 68 | 64 | 60 | 56 | 53 | 49 | 44 | 38 | 32 | 28 | 25 | 21 | 15 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 16 | 2017-10-21 | 69 | 64 | 60 | 57 | 52 | 47 | 44 | 41 | 35 | 29 | 25 | 21 | 18 | 14 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 20 | 2017-11-18 | 82 | 78 | 74 | 71 | 67 | 61 | 57 | 51 | 48 | 45 | 39 | 33 | 30 | 27 | 23 | 17 | 12 | 8 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 20 | 2017-11-18 | 83 | 79 | 76 | 71 | 67 | 61 | 58 | 55 | 50 | 45 | 41 | 36 | 31 | 27 | 24 | 21 | 17 | 13 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 15 | 2017-10-14 | 69 | 64 | 59 | 54 | 50 | 46 | 40 | 37 | 34 | 29 | 24 | 19 | 13 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 22 | 2017-12-02 | 102 | 96 | 90 | 84 | 78 | 74 | 68 | 62 | 59 | 53 | 49 | 46 | 40 | 37 | 33 | 27 | 22 | 16 | 13 | 10 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 19 | 2017-11-11 | 79 | 75 | 70 | 66 | 63 | 60 | 56 | 51 | 45 | 41 | 36 | 32 | 26 | 22 | 18 | 14 | 9 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D1:BD1,1,[Weeks to Zero]+1),"")

## Throughput Monte Carlo Weeks (hidden)
Trial # | Sumx | Sum4 | Sum8 | Sum12 | Sum16 | Sum20 | Sum24 | Sum28 | Sum32 | Sum36 | Sum40 | Sum44 | Sum48 | Sum52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
1 | 19 | 12.5 | 25.5 | 37 | 52 | 62.5 | 78.5 | 87.5 | 103.5 | 117 | 130.5 | 144 | 155.5 | 168.5 | 4 | 4 | 3 | 1.5 | 2.5 | 4 | 5 | 1.5 | 2.5 | 2 | 4 | 3 | 2 | 4 | 3 | 6 | 1.5 | 1.5 | 1.5 | 6 | 5 | 6 | 2 | 3 | 2 | 3 | 1.5 | 2.5 | 5 | 4 | 5 | 2 | 2.5 | 5 | 3 | 3 | 4 | 2.5 | 5 | 2 | 6 | 1.5 | 3 | 3 | 4 | 3 | 3 | 1.5 | 3 | 2 | 5 | 3
2 | 22.5 | 14.5 | 30.5 | 46 | 56.5 | 70 | 83 | 101 | 115 | 130.5 | 143.5 | 153 | 168 | 180.5 | 2.5 | 4 | 4 | 4 | 2 | 6 | 2 | 6 | 6 | 2 | 6 | 1.5 | 3 | 3 | 1.5 | 3 | 2.5 | 2.5 | 2.5 | 6 | 3 | 3 | 5 | 2 | 3 | 3 | 6 | 6 | 3 | 3 | 4 | 4 | 4 | 4 | 6 | 1.5 | 5 | 2 | 4 | 2 | 1.5 | 3 | 3 | 2 | 5 | 1.5 | 6 | 2.5 | 2.5 | 4 | 4 | 2
3 | 22.5 | 16.5 | 34.5 | 47.5 | 59 | 70 | 79.5 | 93 | 110.5 | 126.5 | 144.5 | 159 | 175 | 187 | 1.5 | 5 | 4 | 6 | 3 | 3 | 6 | 6 | 4 | 4 | 2.5 | 2.5 | 3 | 4 | 1.5 | 3 | 3 | 3 | 2 | 3 | 4 | 2 | 1.5 | 2 | 1.5 | 5 | 5 | 2 | 6 | 3 | 6 | 2.5 | 2 | 4 | 6 | 4 | 3 | 6 | 6 | 3 | 4 | 6 | 3 | 1.5 | 6 | 2 | 3 | 5 | 2.5 | 2 | 5 | 2.5
4 | 15 | 9 | 21.5 | 36 | 49 | 58.5 | 73.5 | 90.5 | 101 | 113.5 | 127 | 141 | 159 | 166.5 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 2.5 | 3 | 1.5 | 6 | 4 | 4 | 2 | 3 | 4 | 3 | 2.5 | 1.5 | 2.5 | 2 | 3 | 5 | 5 | 5 | 6 | 2 | 4 | 2 | 2.5 | 2 | 4 | 2 | 4 | 1.5 | 5 | 1.5 | 5 | 5 | 2 | 6 | 4 | 1.5 | 2.5 | 6 | 2 | 5 | 5 | 1.5 | 2 | 2 | 2
5 | 21.5 | 13.5 | 29.5 | 39.5 | 51 | 64.5 | 78 | 96 | 109.5 | 126.5 | 144.5 | 154.5 | 169 | 177.5 | 2 | 4 | 5 | 2.5 | 3 | 5 | 2 | 6 | 1.5 | 2 | 4 | 2.5 | 3 | 2 | 1.5 | 5 | 1.5 | 6 | 3 | 3 | 4 | 3 | 1.5 | 5 | 4 | 6 | 3 | 5 | 6 | 2.5 | 2 | 3 | 5 | 3 | 5 | 4 | 4 | 3 | 5 | 6 | 1.5 | 4 | 2.5 | 2 | 1.5 | 5 | 6 | 2 | 1.5 | 3 | 1.5 | 2.5
6 | 27.5 | 19.5 | 34.5 | 48 | 61.5 | 78.5 | 91.5 | 106 | 121 | 141 | 159 | 170 | 185.5 | 200 | 6 | 5 | 2.5 | 6 | 5 | 3 | 4 | 3 | 2.5 | 4 | 2 | 5 | 5 | 4 | 3 | 1.5 | 3 | 6 | 5 | 3 | 5 | 3 | 3 | 2 | 6 | 2.5 | 2 | 4 | 3 | 6 | 3 | 3 | 6 | 5 | 4 | 5 | 3 | 6 | 3 | 6 | 3 | 1.5 | 5 | 1.5 | 4 | 3 | 6 | 2.5 | 2.5 | 3 | 6 | 3
7 | 22 | 14.5 | 28 | 37.5 | 49 | 62.5 | 72.5 | 79.5 | 93 | 105 | 116 | 126 | 139.5 | 156.5 | 3 | 6 | 1.5 | 4 | 1.5 | 6 | 2 | 4 | 1.5 | 4 | 2.5 | 1.5 | 5 | 1.5 | 3 | 2 | 3 | 3 | 5 | 2.5 | 2 | 2.5 | 1.5 | 4 | 1.5 | 1.5 | 2 | 2 | 3 | 5 | 3 | 2.5 | 2 | 2.5 | 5 | 2.5 | 5 | 1.5 | 1.5 | 3 | 3 | 3 | 1.5 | 2.5 | 4 | 1.5 | 3 | 5 | 4 | 3 | 4 | 6
8 | 19 | 13.5 | 25 | 35.5 | 54 | 69 | 82 | 94 | 110.5 | 127.5 | 139 | 151.5 | 163 | 176.5 | 3 | 5 | 4 | 1.5 | 3 | 2.5 | 3 | 3 | 3 | 3 | 3 | 1.5 | 2.5 | 6 | 5 | 5 | 5 | 3 | 3 | 4 | 3 | 5 | 2 | 3 | 3 | 2.5 | 2.5 | 4 | 6 | 2.5 | 3 | 5 | 3 | 3 | 6 | 5 | 5 | 1.5 | 2 | 3 | 3 | 3 | 2.5 | 4 | 1.5 | 6 | 2.5 | 1.5 | 2.5 | 5 | 3 | 3
9 | 18.5 | 13.5 | 24.5 | 38.5 | 51.5 | 62.5 | 79 | 93 | 107 | 119 | 130 | 143 | 151.5 | 165.5 | 2.5 | 4 | 3 | 4 | 2 | 3 | 3 | 3 | 3 | 2.5 | 6 | 2.5 | 2 | 5 | 3 | 3 | 1.5 | 4 | 3 | 2.5 | 1.5 | 4 | 6 | 5 | 2.5 | 4 | 2.5 | 5 | 5 | 2.5 | 1.5 | 5 | 3 | 2 | 3 | 4 | 1.5 | 6 | 1.5 | 2 | 5 | 4 | 1.5 | 2.5 | 1.5 | 2.5 | 1.5 | 3 | 3 | 6 | 3 | 2
10 | 17.5 | 13 | 26.5 | 39 | 55 | 69.5 | 88.5 | 104 | 119.5 | 130.5 | 144.5 | 154 | 165.5 | 175.5 | 3 | 3 | 5 | 2 | 1.5 | 3 | 6 | 3 | 6 | 2 | 1.5 | 3 | 4 | 4 | 2 | 6 | 5 | 2.5 | 5 | 2 | 4 | 4 | 6 | 5 | 3 | 1.5 | 5 | 6 | 1.5 | 4 | 5 | 5 | 2.5 | 1.5 | 2 | 5 | 3 | 2 | 4 | 5 | 3 | 1.5 | 2.5 | 2.5 | 4 | 4 | 1.5 | 2 | 3 | 3 | 1.5 | 2.5
11 | 23.5 | 19 | 27 | 38 | 53.5 | 66 | 80.5 | 92.5 | 107 | 114.5 | 128 | 141.5 | 153 | 164 | 3 | 6 | 5 | 5 | 3 | 1.5 | 2 | 1.5 | 2 | 4 | 3 | 2 | 4 | 3 | 2.5 | 6 | 2 | 6 | 1.5 | 3 | 3 | 1.5 | 4 | 6 | 4 | 2 | 3 | 3 | 4 | 1.5 | 5 | 4 | 1.5 | 3 | 1.5 | 1.5 | 4 | 5 | 3 | 1.5 | 3 | 2.5 | 6 | 2 | 1.5 | 6 | 2.5 | 1.5 | 2 | 1.5 | 6 | 1.5
12 | 19 | 13.5 | 27 | 38 | 55 | 66.5 | 78.5 | 96.5 | 107.5 | 116.5 | 130 | 145 | 156.5 | 174.5 | 5 | 3 | 1.5 | 4 | 3 | 2.5 | 5 | 3 | 3 | 2 | 2 | 4 | 5 | 3 | 6 | 3 | 4 | 2.5 | 2 | 3 | 2 | 4 | 3 | 3 | 6 | 3 | 3 | 6 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2.5 | 3 | 3 | 5 | 3 | 4 | 5 | 3 | 1.5 | 5 | 3 | 2 | 4 | 3 | 6 | 5
13 | 18.5 | 12 | 22.5 | 41.5 | 57 | 72.5 | 83.5 | 97 | 110.5 | 125.5 | 137.5 | 151.5 | 167 | 179.5 | 2.5 | 5 | 3 | 1.5 | 4 | 2.5 | 2 | 2 | 2 | 6 | 6 | 5 | 3 | 2.5 | 6 | 4 | 6 | 2.5 | 5 | 2 | 2 | 2.5 | 1.5 | 5 | 6 | 3 | 2 | 2.5 | 4 | 3 | 2.5 | 4 | 4 | 4 | 4 | 3 | 3 | 4 | 2.5 | 2.5 | 2 | 5 | 3 | 4 | 5 | 4 | 5 | 1.5 | 2.5 | 4 | 3 | 3
14 | 24 | 14 | 28 | 41.5 | 54 | 75 | 90.5 | 107.5 | 124 | 138 | 148.5 | 162.5 | 177 | 193 | 6 | 3 | 2 | 3 | 4 | 6 | 2.5 | 1.5 | 5 | 4 | 3 | 1.5 | 3 | 3 | 1.5 | 5 | 6 | 6 | 3 | 6 | 2.5 | 3 | 4 | 6 | 2 | 6 | 6 | 3 | 2.5 | 5 | 4 | 5 | 3 | 6 | 3 | 2 | 2 | 2 | 1.5 | 5 | 3 | 3 | 5 | 3 | 3 | 2.5 | 4 | 5 | 3 | 2 | 6 | 5
15 | 20 | 14 | 28 | 36 | 53.5 | 64.5 | 79.5 | 93 | 106.5 | 122 | 138 | 149 | 162 | 176.5 | 4 | 2 | 6 | 2 | 4 | 2 | 5 | 3 | 1.5 | 1.5 | 2 | 3 | 5 | 1.5 | 6 | 5 | 3 | 4 | 2 | 2 | 5 | 3 | 4 | 3 | 3 | 5 | 1.5 | 4 | 6 | 1.5 | 3 | 3 | 4 | 1.5 | 6 | 4 | 3 | 4 | 6 | 3 | 2 | 4 | 2.5 | 2.5 | 3 | 4 | 2 | 4 | 4 | 2 | 2.5 | 6
16 | 19 | 10 | 25 | 32.5 | 40.5 | 51 | 63 | 80 | 92 | 107 | 121.5 | 137.5 | 150 | 165 | 3 | 2 | 2 | 3 | 3 | 6 | 4 | 2 | 1.5 | 2 | 2 | 2 | 2.5 | 1.5 | 2 | 2 | 3 | 2 | 3 | 2.5 | 1.5 | 4 | 1.5 | 5 | 5 | 3 | 5 | 4 | 3 | 2 | 3 | 4 | 6 | 3 | 2 | 4 | 3 | 4 | 5 | 2.5 | 5 | 3 | 3 | 5 | 3 | 5 | 2.5 | 2 | 2 | 5 | 5 | 3
17 | 19 | 12 | 27 | 40 | 57 | 74.5 | 92.5 | 107 | 119.5 | 134 | 144.5 | 155.5 | 169.5 | 183 | 5 | 3 | 2.5 | 1.5 | 2 | 5 | 6 | 2 | 1.5 | 6 | 1.5 | 4 | 6 | 3 | 5 | 3 | 2.5 | 4 | 5 | 6 | 5 | 5 | 3 | 5 | 1.5 | 6 | 5 | 2 | 1.5 | 2.5 | 6 | 2.5 | 5 | 4 | 3 | 2.5 | 3 | 2 | 2.5 | 3 | 1.5 | 3 | 2.5 | 4 | 3 | 3 | 4 | 4 | 6 | 3 | 1.5 | 3
18 | 17.5 | 13.5 | 21 | 32 | 47 | 58 | 69 | 85 | 100 | 117 | 128 | 137.5 | 152.5 | 162.5 | 4 | 3 | 4 | 2.5 | 2 | 2 | 2 | 1.5 | 3 | 2 | 3 | 3 | 2.5 | 6 | 2.5 | 4 | 3 | 1.5 | 5 | 1.5 | 2.5 | 2.5 | 3 | 3 | 3 | 5 | 5 | 3 | 5 | 4 | 3 | 3 | 6 | 4 | 3 | 4 | 3 | 2 | 4 | 2 | 1.5 | 3 | 2 | 3 | 3 | 6 | 3 | 3 | 3 | 2.5 | 2 | 2.5
19 | 19 | 13 | 27 | 36 | 47.5 | 60.5 | 75.5 | 89 | 100 | 115 | 137 | 153 | 167.5 | 182.5 | 3 | 4 | 3 | 3 | 3 | 3 | 4 | 4 | 2 | 2 | 2 | 3 | 1.5 | 3 | 5 | 2 | 1.5 | 2.5 | 4 | 5 | 5 | 3 | 4 | 3 | 2.5 | 4 | 3 | 4 | 3 | 2 | 3 | 3 | 4 | 4 | 5 | 2 | 5 | 6 | 6 | 5 | 3 | 5 | 3 | 5 | 4 | 2.5 | 3 | 5 | 4 | 3 | 3 | 5
20 | 16.5 | 13 | 25.5 | 36.5 | 46.5 | 61.5 | 71 | 85 | 95.5 | 108.5 | 128.5 | 142 | 157.5 | 170.5 | 2.5 | 3 | 5 | 2.5 | 2 | 1.5 | 6 | 3 | 2.5 | 3 | 4 | 1.5 | 1.5 | 3 | 2.5 | 3 | 4 | 3 | 2 | 6 | 2 | 1.5 | 3 | 3 | 6 | 4 | 2 | 2 | 1.5 | 3 | 4 | 2 | 6 | 1.5 | 1.5 | 4 | 5 | 5 | 4 | 6 | 3 | 4 | 5 | 1.5 | 2.5 | 5 | 3 | 5 | 2 | 3 | 5 | 3
21 | 19.5 | 8.5 | 24 | 40.5 | 53.5 | 66 | 77.5 | 88 | 105 | 120 | 130 | 139 | 158 | 170 | 1.5 | 1.5 | 2.5 | 3 | 6 | 5 | 2.5 | 2 | 5 | 4 | 2.5 | 5 | 2 | 2 | 3 | 6 | 3 | 2.5 | 2 | 5 | 3 | 4 | 3 | 1.5 | 2.5 | 2.5 | 1.5 | 4 | 5 | 5 | 4 | 3 | 1.5 | 1.5 | 6 | 6 | 2 | 2 | 3 | 3 | 2 | 1.5 | 3 | 2.5 | 5 | 6 | 5 | 3 | 1.5 | 3 | 5 | 2.5
22 | 21.5 | 10.5 | 29.5 | 41 | 56 | 65 | 77 | 89.5 | 101.5 | 116 | 132 | 147 | 164 | 176.5 | 3 | 2.5 | 2.5 | 2.5 | 5 | 6 | 2 | 6 | 3 | 4 | 3 | 1.5 | 3 | 4 | 3 | 5 | 2.5 | 2 | 2.5 | 2 | 5 | 3 | 2.5 | 1.5 | 1.5 | 3 | 6 | 2 | 2 | 5 | 2.5 | 2.5 | 6 | 3 | 1.5 | 4 | 6 | 4 | 3 | 3 | 5 | 5 | 3 | 2 | 5 | 6 | 3 | 3 | 2.5 | 2 | 5 | 3
23 | 22 | 15 | 30 | 41.5 | 54.5 | 65 | 80.5 | 95.5 | 110.5 | 121 | 131.5 | 147 | 159.5 | 169 | 3 | 4 | 3 | 5 | 3 | 4 | 5 | 3 | 3 | 3 | 2.5 | 3 | 2.5 | 3 | 1.5 | 6 | 3 | 4 | 1.5 | 2 | 3 | 2.5 | 6 | 4 | 6 | 2.5 | 2.5 | 4 | 3 | 2 | 6 | 4 | 3 | 3 | 2 | 2.5 | 2.5 | 1.5 | 4 | 2.5 | 2.5 | 6 | 3 | 4 | 4 | 4 | 3 | 1.5 | 3 | 2.5 | 1.5 | 2.5
24 | 19 | 13 | 27 | 42.5 | 54 | 72 | 83.5 | 96 | 108 | 121.5 | 140.5 | 152 | 169 | 181.5 | 3 | 3 | 3 | 4 | 2 | 4 | 4 | 4 | 3 | 6 | 2.5 | 4 | 2.5 | 5 | 2 | 2 | 4 | 3 | 6 | 5 | 3 | 1.5 | 3 | 4 | 2 | 3 | 5 | 2.5 | 4 | 2.5 | 3 | 2.5 | 4 | 1.5 | 3 | 5 | 5 | 6 | 5 | 3 | 1.5 | 5 | 2.5 | 2.5 | 5 | 2 | 4 | 6 | 2 | 3 | 5 | 2.5
25 | 22 | 15.5 | 33 | 46 | 57 | 68.5 | 80 | 99 | 116.5 | 134 | 145 | 157.5 | 175 | 192 | 4 | 6 | 1.5 | 4 | 1.5 | 5 | 5 | 6 | 1.5 | 6 | 4 | 1.5 | 3 | 2 | 2 | 4 | 2 | 2 | 5 | 2.5 | 2.5 | 2.5 | 4 | 2.5 | 5 | 4 | 5 | 5 | 6 | 6 | 3 | 2.5 | 2.5 | 6 | 3 | 6 | 3 | 3 | 2 | 3 | 1.5 | 4 | 2 | 5 | 4 | 6 | 1.5 | 6 | 5 | 5 | 4 | 3
26 | 17.5 | 10 | 23.5 | 40.5 | 58 | 70.5 | 79 | 95 | 113 | 128 | 142.5 | 156 | 171 | 186.5 | 4 | 2 | 2.5 | 1.5 | 2.5 | 5 | 4 | 2 | 3 | 3 | 5 | 6 | 2.5 | 5 | 6 | 4 | 3 | 3 | 1.5 | 5 | 1.5 | 2 | 3 | 2 | 4 | 3 | 5 | 4 | 6 | 4 | 3 | 5 | 3 | 5 | 5 | 2 | 3 | 6 | 3 | 2.5 | 6 | 1.5 | 2 | 4 | 4 | 3 | 3 | 5 | 2 | 2.5 | 6 | 5
27 | 18.5 | 12 | 24 | 38 | 49 | 61.5 | 76 | 88 | 104 | 116.5 | 129 | 139.5 | 151.5 | 168.5 | 2.5 | 3 | 4 | 2.5 | 5 | 1.5 | 2.5 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 5 | 3 | 1.5 | 4 | 3 | 2.5 | 5 | 1.5 | 3 | 6 | 1.5 | 3 | 6 | 3 | 4 | 3 | 3 | 1.5 | 5 | 3 | 4 | 2.5 | 3 | 2 | 2 | 4 | 2.5 | 3 | 1.5 | 5 | 2.5 | 5 | 3 | 5 | 4
28 | 26 | 19 | 29.5 | 44 | 57 | 69.5 | 81.5 | 98.5 | 108 | 122.5 | 139 | 150.5 | 166 | 183 | 5 | 5 | 4 | 5 | 4 | 3 | 1.5 | 2 | 3 | 5 | 1.5 | 5 | 1.5 | 4 | 5 | 2.5 | 6 | 2 | 2 | 2.5 | 3 | 3 | 3 | 3 | 6 | 2 | 6 | 3 | 2 | 3 | 1.5 | 3 | 3 | 6 | 3 | 2.5 | 6 | 4 | 5 | 1.5 | 2 | 1.5 | 4 | 4 | 2.5 | 4 | 4 | 5 | 4 | 2 | 6 | 5
29 | 16.5 | 11 | 20.5 | 32 | 46 | 57 | 65 | 77 | 88.5 | 100.5 | 109 | 123 | 134 | 148.5 | 6 | 2 | 1.5 | 1.5 | 1.5 | 4 | 2 | 2 | 1.5 | 2.5 | 2.5 | 5 | 5 | 2.5 | 1.5 | 5 | 3 | 3 | 3 | 2 | 1.5 | 1.5 | 3 | 2 | 5 | 2 | 3 | 2 | 5 | 1.5 | 2 | 3 | 1.5 | 5 | 2.5 | 3 | 2 | 2 | 2 | 2.5 | 2 | 4 | 5 | 3 | 3 | 4 | 2 | 2 | 5 | 2 | 2.5 | 5
30 | 19.5 | 12.5 | 28.5 | 41.5 | 52 | 65.5 | 80.5 | 94.5 | 106.5 | 117.5 | 128 | 141 | 156 | 171 | 4 | 2.5 | 3 | 3 | 4 | 3 | 6 | 3 | 6 | 2 | 2.5 | 2.5 | 3 | 2.5 | 2 | 3 | 3 | 6 | 3 | 1.5 | 4 | 2 | 3 | 6 | 3 | 4 | 2 | 5 | 2 | 5 | 2 | 3 | 3 | 2 | 3 | 3 | 3 | 2.5 | 3 | 2 | 2.5 | 2.5 | 5 | 3 | 3 | 6 | 4 | 2 | 4 | 3 | 6 | 2
31 | 18 | 13 | 23 | 34 | 48 | 58 | 68 | 88 | 103 | 118 | 129 | 142 | 156 | 168 | 1.5 | 6 | 2.5 | 3 | 2 | 3 | 3 | 2 | 5 | 1.5 | 3 | 1.5 | 2.5 | 2.5 | 3 | 6 | 2 | 2.5 | 3 | 2.5 | 3 | 3 | 2 | 2 | 6 | 6 | 5 | 3 | 6 | 5 | 2.5 | 1.5 | 4 | 3 | 3 | 5 | 2 | 2 | 3 | 4 | 3 | 6 | 2 | 2 | 3 | 3 | 5 | 3 | 1.5 | 4 | 2.5 | 4
32 | 22 | 12 | 27 | 40.5 | 55 | 68.5 | 78 | 90 | 102.5 | 116.5 | 129 | 144.5 | 154.5 | 173.5 | 3 | 5 | 2 | 2 | 4 | 6 | 2.5 | 2.5 | 6 | 3 | 1.5 | 3 | 5 | 1.5 | 5 | 3 | 4 | 5 | 1.5 | 3 | 1.5 | 2 | 3 | 3 | 5 | 3 | 2.5 | 1.5 | 5 | 3 | 3 | 1.5 | 3 | 5 | 3 | 3 | 1.5 | 4 | 4 | 3 | 3 | 1.5 | 6 | 5 | 3 | 2 | 2 | 3 | 3 | 5 | 5 | 6
33 | 18 | 12.5 | 24 | 35.5 | 51.5 | 63 | 71.5 | 85.5 | 101 | 114.5 | 129 | 148 | 159 | 171 | 2.5 | 2 | 5 | 3 | 2.5 | 3 | 3 | 3 | 4 | 3 | 2.5 | 2 | 3 | 2 | 5 | 6 | 2.5 | 2 | 5 | 2 | 2 | 3 | 2 | 1.5 | 4 | 2 | 5 | 3 | 5 | 5 | 2.5 | 3 | 1.5 | 3 | 3 | 6 | 3 | 2.5 | 3 | 6 | 6 | 4 | 3 | 6 | 1.5 | 2.5 | 5 | 2 | 2 | 2 | 3 | 5
34 | 25 | 13 | 28.5 | 36.5 | 49.5 | 62.5 | 75 | 93.5 | 111.5 | 126.5 | 139.5 | 152 | 161 | 172 | 2.5 | 1.5 | 3 | 6 | 6 | 6 | 1.5 | 2 | 2.5 | 1.5 | 2 | 2 | 2.5 | 5 | 4 | 1.5 | 2.5 | 2.5 | 3 | 5 | 3 | 4 | 2.5 | 3 | 1.5 | 5 | 6 | 6 | 3 | 6 | 4 | 5 | 1.5 | 6 | 2.5 | 5 | 2 | 3 | 5 | 3 | 3 | 2.5 | 4 | 3 | 3 | 2 | 2 | 2 | 1.5 | 2 | 6 | 1.5
35 | 16.5 | 13 | 22.5 | 36 | 45.5 | 59.5 | 72 | 93 | 109.5 | 124.5 | 135.5 | 151.5 | 164 | 177 | 2.5 | 3 | 6 | 1.5 | 1.5 | 2 | 3 | 3 | 3 | 2.5 | 6 | 2 | 1.5 | 4 | 2.5 | 1.5 | 1.5 | 2.5 | 4 | 6 | 2.5 | 2 | 4 | 4 | 6 | 4 | 6 | 5 | 3 | 6 | 1.5 | 6 | 4 | 5 | 3 | 3 | 4 | 1.5 | 2.5 | 3 | 6 | 1.5 | 6 | 2.5 | 5 | 3 | 3 | 1.5 | 1.5 | 2.5 | 3 | 6
36 | 25 | 16 | 31.5 | 45 | 59 | 71.5 | 83 | 95 | 111 | 122 | 134.5 | 145 | 156 | 168 | 4 | 5 | 3 | 4 | 3 | 6 | 2.5 | 4 | 6 | 2.5 | 3 | 2 | 5 | 3 | 4 | 2 | 3 | 6 | 2 | 1.5 | 2.5 | 2.5 | 1.5 | 5 | 1.5 | 5 | 2.5 | 3 | 5 | 2 | 6 | 3 | 5 | 2 | 2.5 | 1.5 | 3 | 4 | 2.5 | 3 | 3 | 1.5 | 2 | 4 | 4 | 1.5 | 4 | 1.5 | 2 | 6 | 2 | 2
37 | 22.5 | 14 | 29.5 | 42 | 54 | 65.5 | 80 | 94.5 | 105 | 112.5 | 124.5 | 137 | 154 | 171 | 3 | 4 | 4 | 3 | 2.5 | 6 | 4 | 3 | 6 | 2 | 3 | 1.5 | 1.5 | 1.5 | 5 | 4 | 5 | 1.5 | 3 | 2 | 1.5 | 4 | 4 | 5 | 2.5 | 3 | 4 | 5 | 4 | 1.5 | 2 | 3 | 1.5 | 2.5 | 2 | 1.5 | 1.5 | 1.5 | 4 | 5 | 1.5 | 3 | 6 | 2 | 3 | 6 | 5 | 3 | 5 | 4 | 3 | 5
38 | 24.5 | 17.5 | 36.5 | 52 | 65.5 | 75 | 85 | 96 | 107 | 122 | 134 | 151.5 | 165.5 | 181 | 5 | 1.5 | 6 | 5 | 4 | 3 | 6 | 6 | 5 | 6 | 1.5 | 3 | 3 | 3 | 2.5 | 5 | 3 | 1.5 | 3 | 2 | 2.5 | 1.5 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 2.5 | 3 | 2.5 | 4 | 3 | 5 | 3 | 3 | 3 | 2 | 4 | 2.5 | 4 | 5 | 6 | 3 | 2 | 5 | 4 | 3 | 2.5 | 6 | 4
39 | 23 | 14 | 31.5 | 44.5 | 61 | 69 | 81.5 | 100 | 113 | 123.5 | 137.5 | 149.5 | 166.5 | 180 | 3 | 5 | 3 | 3 | 6 | 3 | 6 | 2.5 | 2 | 5 | 3 | 3 | 6 | 5 | 4 | 1.5 | 3 | 2 | 1.5 | 1.5 | 6 | 3 | 2 | 1.5 | 4 | 6 | 2.5 | 6 | 3 | 5 | 3 | 2 | 1.5 | 2.5 | 2.5 | 4 | 5 | 3 | 3 | 3 | 1.5 | 1.5 | 3 | 6 | 3 | 6 | 3 | 5 | 3 | 3 | 6 | 1.5
40 | 14 | 8 | 21.5 | 34 | 48 | 63 | 76.5 | 87.5 | 99.5 | 108 | 120 | 136.5 | 153.5 | 169.5 | 3 | 1.5 | 1.5 | 2 | 3 | 3 | 5 | 2.5 | 5 | 3 | 1.5 | 3 | 3 | 3 | 2 | 6 | 4 | 5 | 3 | 3 | 4 | 4 | 3 | 2.5 | 3 | 2 | 3 | 3 | 3 | 2.5 | 2.5 | 4 | 1.5 | 2.5 | 1.5 | 3 | 4 | 3 | 2 | 3 | 3 | 6 | 2.5 | 5 | 2.5 | 6 | 2.5 | 6 | 6 | 2.5 | 6 | 1.5
41 | 19 | 10.5 | 23.5 | 35.5 | 52.5 | 70.5 | 84.5 | 101 | 115.5 | 127 | 142 | 159 | 170.5 | 187.5 | 4 | 2.5 | 2 | 2 | 2.5 | 6 | 2.5 | 2 | 3 | 5 | 2 | 2 | 4 | 3 | 5 | 5 | 6 | 5 | 4 | 3 | 3 | 2 | 5 | 4 | 3 | 6 | 2.5 | 5 | 6 | 3 | 2.5 | 3 | 4 | 3 | 1.5 | 3 | 2 | 4 | 6 | 3 | 3 | 6 | 4 | 4 | 5 | 1.5 | 3 | 2 | 5 | 2 | 4 | 6
42 | 20 | 15.5 | 23.5 | 41 | 60 | 77 | 92 | 103.5 | 121.5 | 133 | 145.5 | 157 | 169 | 187 | 5 | 4 | 4 | 2.5 | 3 | 1.5 | 2 | 1.5 | 5 | 5 | 5 | 2.5 | 6 | 2 | 6 | 5 | 6 | 3 | 4 | 4 | 6 | 2.5 | 4 | 2.5 | 2.5 | 3 | 4 | 2 | 5 | 5 | 3 | 5 | 2 | 4 | 2.5 | 3 | 2.5 | 2 | 6 | 2 | 2 | 3 | 1.5 | 5 | 2 | 2 | 2 | 6 | 6 | 5 | 5 | 2
43 | 20.5 | 12.5 | 30.5 | 39.5 | 51 | 64.5 | 85.5 | 95.5 | 104.5 | 122.5 | 136 | 149 | 169 | 179.5 | 4 | 3 | 4 | 1.5 | 3 | 5 | 4 | 6 | 2 | 1.5 | 1.5 | 4 | 2.5 | 3 | 3 | 3 | 3 | 2.5 | 3 | 5 | 6 | 6 | 3 | 6 | 2 | 2.5 | 1.5 | 4 | 1.5 | 3 | 3 | 1.5 | 4 | 5 | 3 | 6 | 6 | 3 | 3 | 1.5 | 3 | 4 | 3 | 3 | 6 | 5 | 3 | 6 | 1.5 | 2 | 2 | 5
44 | 19 | 14 | 24.5 | 42 | 55.5 | 76.5 | 91 | 107.5 | 123.5 | 140.5 | 154 | 167.5 | 176.5 | 194.5 | 6 | 1.5 | 4 | 2.5 | 2.5 | 2.5 | 4 | 1.5 | 2.5 | 6 | 6 | 3 | 3 | 3 | 1.5 | 6 | 4 | 6 | 6 | 5 | 2 | 6 | 4 | 2.5 | 6 | 5 | 1.5 | 4 | 5 | 6 | 2 | 3 | 6 | 3 | 3 | 5 | 4 | 3 | 4 | 2.5 | 3 | 6 | 1.5 | 3 | 3 | 1.5 | 2 | 2.5 | 4 | 5 | 6 | 3
45 | 20 | 12.5 | 29 | 39 | 61 | 71 | 84.5 | 101 | 115 | 123.5 | 139 | 157 | 171.5 | 188.5 | 2.5 | 3 | 3 | 4 | 2.5 | 5 | 5 | 4 | 2.5 | 3 | 2.5 | 2 | 6 | 6 | 6 | 4 | 2 | 5 | 1.5 | 1.5 | 2.5 | 3 | 5 | 3 | 3 | 2.5 | 6 | 5 | 2.5 | 6 | 1.5 | 4 | 2 | 2.5 | 2 | 2 | 5 | 5 | 2.5 | 3 | 4 | 5 | 3 | 6 | 5 | 2.5 | 5 | 2 | 3 | 5 | 4 | 5
46 | 19.5 | 11.5 | 27.5 | 42 | 53 | 69 | 81.5 | 95 | 108.5 | 127.5 | 142.5 | 154.5 | 171 | 184 | 3 | 2.5 | 3 | 3 | 3 | 5 | 5 | 3 | 2.5 | 2 | 6 | 4 | 2.5 | 1.5 | 3 | 4 | 3 | 3 | 6 | 4 | 1.5 | 3 | 5 | 3 | 5 | 3 | 1.5 | 4 | 2 | 1.5 | 6 | 4 | 5 | 6 | 5 | 3 | 3 | 3 | 6 | 3 | 3 | 4 | 2.5 | 2.5 | 4 | 1.5 | 5 | 6 | 3 | 6 | 2.5 | 1.5
47 | 17.5 | 10 | 27.5 | 39 | 55.5 | 71 | 82.5 | 95 | 105 | 119.5 | 136.5 | 151 | 163 | 180 | 4 | 2 | 2.5 | 1.5 | 1.5 | 6 | 6 | 4 | 1.5 | 2.5 | 2.5 | 5 | 1.5 | 6 | 3 | 6 | 6 | 3 | 5 | 1.5 | 3 | 5 | 1.5 | 2 | 3 | 2.5 | 3 | 4 | 3 | 2 | 3 | 2 | 1.5 | 5 | 3 | 5 | 2 | 5 | 6 | 4 | 6 | 3 | 2.5 | 3 | 2.5 | 3 | 4 | 2.5 | 4 | 3 | 6 | 4
48 | 16.5 | 11.5 | 21 | 38 | 52.5 | 66.5 | 84.5 | 97.5 | 107 | 119.5 | 130.5 | 146 | 156 | 174.5 | 2.5 | 3 | 2 | 4 | 3 | 2 | 3 | 1.5 | 6 | 3 | 6 | 2 | 2 | 6 | 5 | 1.5 | 3 | 5 | 3 | 3 | 4 | 4 | 5 | 5 | 3 | 2 | 3 | 5 | 4 | 1.5 | 1.5 | 2.5 | 2 | 1.5 | 6 | 3 | 2 | 3 | 2 | 4 | 4 | 3 | 2.5 | 6 | 2.5 | 2 | 1.5 | 4 | 2.5 | 4 | 6 | 6
49 | 17 | 11.5 | 24 | 40 | 54 | 64 | 77.5 | 95.5 | 111 | 128 | 146 | 155.5 | 166.5 | 178.5 | 2 | 2 | 6 | 1.5 | 2.5 | 3 | 4 | 3 | 6 | 4 | 3 | 3 | 5 | 3 | 2 | 4 | 3 | 2.5 | 3 | 1.5 | 2.5 | 3 | 3 | 5 | 6 | 6 | 2 | 4 | 5 | 2 | 6 | 2.5 | 2 | 6 | 3 | 6 | 6 | 3 | 3 | 6 | 4 | 1.5 | 1.5 | 2.5 | 4 | 2 | 2 | 3 | 2.5 | 5 | 1.5 | 3
50 | 21 | 12 | 29.5 | 40 | 53.5 | 64.5 | 79.5 | 95.5 | 115 | 131 | 146.5 | 166.5 | 180 | 192 | 2 | 3 | 3 | 4 | 6 | 3 | 6 | 2.5 | 4 | 2 | 2.5 | 2 | 5 | 3 | 3 | 2.5 | 5 | 1.5 | 2.5 | 2 | 3 | 4 | 4 | 4 | 3 | 4 | 6 | 3 | 6 | 6 | 5 | 2.5 | 6 | 6 | 2.5 | 1.5 | 2 | 5 | 6 | 2.5 | 4 | 6 | 6 | 4 | 3 | 4 | 2.5 | 4 | 5 | 1.5 | 2.5 | 3
51 | 17 | 13 | 25 | 35.5 | 51 | 67.5 | 85.5 | 102 | 117 | 135.5 | 152.5 | 166 | 177.5 | 187.5 | 6 | 2 | 3 | 2 | 2 | 2 | 3 | 5 | 4 | 1.5 | 3 | 2 | 1.5 | 5 | 6 | 3 | 6 | 4 | 4 | 2.5 | 4 | 6 | 4 | 4 | 6 | 2.5 | 3 | 5 | 1.5 | 6 | 5 | 2.5 | 4 | 6 | 2.5 | 6 | 3 | 3 | 6 | 5 | 1.5 | 3 | 3 | 6 | 2 | 5 | 2 | 2.5 | 5 | 1.5 | 2 | 1.5
52 | 24.5 | 17 | 32.5 | 45 | 54.5 | 71.5 | 81.5 | 94.5 | 112.5 | 127 | 137.5 | 149.5 | 158.5 | 168.5 | 4 | 3 | 6 | 4 | 6 | 1.5 | 3 | 5 | 2 | 4 | 4 | 2.5 | 2 | 3 | 2 | 2.5 | 6 | 3 | 5 | 3 | 3 | 2.5 | 1.5 | 3 | 2 | 3 | 4 | 4 | 4 | 6 | 2 | 6 | 2 | 4 | 2.5 | 6 | 2 | 2.5 | 4 | 2 | 3 | 4 | 2 | 3 | 1.5 | 2.5 | 2 | 3 | 2 | 2 | 3 | 3
53 | 19 | 12 | 27 | 40.5 | 49.5 | 65.5 | 80 | 93 | 108 | 118 | 129.5 | 140.5 | 156.5 | 173.5 | 4 | 2.5 | 2.5 | 3 | 4 | 3 | 2 | 6 | 3 | 3 | 5 | 2.5 | 3 | 2 | 2.5 | 1.5 | 4 | 4 | 5 | 3 | 5 | 2.5 | 5 | 2 | 3 | 2 | 3 | 5 | 3 | 4 | 3 | 5 | 1.5 | 4 | 1.5 | 3 | 1.5 | 6 | 2.5 | 1.5 | 1.5 | 5 | 2 | 2.5 | 3 | 5 | 3 | 5 | 6 | 5 | 2 | 4
54 | 19 | 10.5 | 23.5 | 39.5 | 46 | 60 | 72 | 82 | 96.5 | 112 | 127.5 | 141 | 163 | 176.5 | 5 | 2 | 1.5 | 2 | 6 | 2.5 | 1.5 | 3 | 2 | 5 | 4 | 5 | 1.5 | 1.5 | 2 | 1.5 | 4 | 4 | 3 | 3 | 2 | 4 | 3 | 3 | 4 | 1.5 | 3 | 1.5 | 4 | 4 | 4 | 2.5 | 3 | 5 | 5 | 2.5 | 4 | 4 | 1.5 | 6 | 6 | 1.5 | 4 | 2 | 5 | 5 | 6 | 6 | 1.5 | 3 | 4 | 5
55 | 19 | 12.5 | 25.5 | 40 | 53.5 | 64.5 | 78.5 | 96 | 115 | 129.5 | 138.5 | 154.5 | 173.5 | 189 | 1.5 | 3 | 4 | 4 | 5 | 1.5 | 1.5 | 5 | 2 | 4 | 6 | 2.5 | 2.5 | 2.5 | 2.5 | 6 | 4 | 1.5 | 3 | 2.5 | 5 | 2 | 3 | 4 | 2.5 | 5 | 6 | 4 | 5 | 2 | 6 | 6 | 5 | 3 | 5 | 1.5 | 3 | 1.5 | 3 | 1.5 | 3 | 5 | 4 | 4 | 5 | 5 | 3 | 6 | 1.5 | 6 | 4 | 4
56 | 21 | 10 | 33 | 44.5 | 56 | 67.5 | 79.5 | 94 | 106.5 | 115.5 | 130 | 145 | 158.5 | 169.5 | 4 | 2 | 2 | 2 | 6 | 5 | 6 | 6 | 1.5 | 1.5 | 6 | 2.5 | 5 | 3 | 1.5 | 2 | 5 | 1.5 | 3 | 2 | 5 | 3 | 2.5 | 1.5 | 2.5 | 4 | 5 | 3 | 1.5 | 4 | 5 | 2 | 3 | 1.5 | 3 | 1.5 | 2.5 | 4 | 5 | 3 | 6 | 6 | 1.5 | 1.5 | 2.5 | 4 | 4 | 3 | 2 | 1.5 | 5 | 2.5
57 | 21.5 | 14.5 | 28.5 | 45 | 64 | 77.5 | 92.5 | 110.5 | 121 | 130.5 | 143 | 153.5 | 167.5 | 178.5 | 3 | 3 | 2.5 | 6 | 4 | 3 | 2 | 5 | 6 | 1.5 | 4 | 5 | 6 | 5 | 5 | 3 | 5 | 5 | 1.5 | 2 | 4 | 3 | 2 | 6 | 5 | 6 | 3 | 4 | 3 | 2.5 | 2 | 3 | 1.5 | 3 | 2 | 3 | 3 | 3 | 1.5 | 5 | 3 | 2 | 3 | 2.5 | 4 | 4 | 3 | 3 | 4 | 3 | 2.5 | 1.5
58 | 19 | 10 | 24 | 37.5 | 48.5 | 57.5 | 71 | 87.5 | 103.5 | 121 | 134 | 148.5 | 164 | 172.5 | 3 | 1.5 | 4 | 1.5 | 6 | 3 | 2.5 | 2.5 | 2.5 | 5 | 2 | 4 | 2 | 4 | 2.5 | 2.5 | 3 | 2 | 1.5 | 2.5 | 3 | 6 | 3 | 1.5 | 6 | 2.5 | 5 | 3 | 5 | 4 | 4 | 3 | 4 | 6 | 1.5 | 6 | 2.5 | 1.5 | 5 | 4 | 3 | 3 | 6 | 2.5 | 4 | 2.5 | 3 | 6 | 1.5 | 3 | 2 | 2
59 | 20.5 | 12.5 | 27.5 | 43.5 | 54.5 | 63 | 73.5 | 84 | 94 | 102.5 | 115 | 130 | 142.5 | 154 | 2.5 | 4 | 3 | 3 | 5 | 3 | 5 | 2 | 2 | 5 | 5 | 4 | 1.5 | 5 | 2.5 | 2 | 1.5 | 1.5 | 3 | 2.5 | 3 | 2 | 4 | 1.5 | 1.5 | 3 | 4 | 2 | 1.5 | 3 | 2.5 | 3 | 2 | 1.5 | 3 | 2 | 5 | 3 | 1.5 | 3 | 3 | 3 | 4 | 5 | 1.5 | 2 | 4 | 5 | 2 | 3 | 1.5 | 5
60 | 17.5 | 13 | 24 | 34.5 | 47.5 | 57.5 | 68 | 81.5 | 96 | 107.5 | 122.5 | 132.5 | 145 | 162 | 2.5 | 2.5 | 5 | 3 | 1.5 | 3 | 4 | 2.5 | 2 | 2 | 4 | 2.5 | 5 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 1.5 | 3 | 4 | 2 | 6 | 1.5 | 2 | 4 | 3 | 2.5 | 5 | 4 | 3 | 5 | 2 | 1.5 | 6 | 2 | 5 | 2 | 3 | 1.5 | 3 | 2.5 | 1.5 | 3 | 2 | 6 | 3 | 4 | 4 | 6
61 | 17.5 | 12 | 23.5 | 42.5 | 55 | 70.5 | 80.5 | 95.5 | 109 | 124.5 | 133.5 | 143.5 | 152 | 163 | 3 | 3 | 3 | 3 | 3 | 2.5 | 3 | 3 | 4 | 6 | 6 | 3 | 4 | 3 | 4 | 1.5 | 5 | 1.5 | 4 | 5 | 4 | 3 | 1.5 | 1.5 | 4 | 3 | 2 | 6 | 5 | 2.5 | 4 | 2 | 2 | 6 | 2.5 | 5 | 3 | 1.5 | 1.5 | 3 | 2 | 3 | 3 | 2 | 2 | 1.5 | 3 | 2 | 4 | 2 | 3 | 2
62 | 21 | 10 | 27 | 37 | 54 | 74 | 86 | 97.5 | 111.5 | 122 | 133.5 | 152.5 | 162 | 172 | 2 | 3 | 3 | 2 | 5 | 6 | 2 | 4 | 2 | 3 | 3 | 2 | 6 | 2 | 4 | 5 | 5 | 6 | 5 | 4 | 3 | 2 | 2 | 5 | 2.5 | 3 | 3 | 3 | 4 | 4 | 4 | 2 | 2 | 1.5 | 3 | 4 | 1.5 | 2 | 4 | 4 | 5 | 6 | 4 | 4 | 2.5 | 4 | 1.5 | 1.5 | 2 | 3 | 2 | 3
63 | 20 | 13.5 | 30 | 40.5 | 56.5 | 66 | 83.5 | 96 | 103 | 117 | 125.5 | 137 | 152 | 169 | 2.5 | 3 | 3 | 5 | 2.5 | 4 | 6 | 4 | 2 | 4 | 3 | 1.5 | 5 | 3 | 2 | 6 | 3 | 1.5 | 3 | 2 | 1.5 | 5 | 6 | 5 | 2.5 | 2.5 | 5 | 2.5 | 1.5 | 2 | 2 | 1.5 | 3 | 3 | 3 | 5 | 1.5 | 3 | 2.5 | 1.5 | 3 | 2.5 | 4 | 2 | 5 | 5 | 2 | 3 | 3 | 6 | 4 | 4
64 | 26 | 18 | 33 | 47.5 | 58.5 | 74 | 88.5 | 103.5 | 111 | 121 | 135 | 145.5 | 159.5 | 175 | 4 | 3 | 5 | 6 | 3 | 5 | 5 | 2 | 6 | 3 | 2.5 | 3 | 2.5 | 3 | 1.5 | 4 | 6 | 2 | 5 | 2.5 | 6 | 3 | 4 | 1.5 | 3 | 3 | 3 | 6 | 1.5 | 2.5 | 1.5 | 2 | 1.5 | 4 | 1.5 | 3 | 3 | 6 | 2 | 3 | 3 | 2 | 3 | 2.5 | 2 | 3 | 6 | 3 | 5 | 4 | 4 | 2.5
65 | 21.5 | 12.5 | 28 | 38.5 | 53 | 63.5 | 76 | 93.5 | 111 | 126.5 | 147.5 | 158 | 171 | 183.5 | 3 | 2.5 | 5 | 2 | 5 | 4 | 2.5 | 4 | 2 | 3 | 3 | 2.5 | 4 | 3 | 5 | 2.5 | 5 | 2.5 | 1.5 | 1.5 | 2 | 5 | 1.5 | 4 | 4 | 2.5 | 6 | 5 | 3 | 2.5 | 6 | 6 | 6 | 2 | 1.5 | 6 | 4 | 6 | 5 | 6 | 3 | 3 | 3 | 1.5 | 2 | 4 | 4 | 3 | 3 | 4 | 1.5 | 4
66 | 20 | 12.5 | 23.5 | 36 | 50 | 62 | 77.5 | 88 | 100.5 | 109 | 124 | 133 | 143.5 | 155.5 | 1.5 | 3 | 3 | 5 | 6 | 1.5 | 2 | 1.5 | 5 | 1.5 | 3 | 3 | 4 | 3 | 3 | 4 | 4 | 2 | 3 | 3 | 2.5 | 5 | 5 | 3 | 3 | 1.5 | 4 | 2 | 2 | 2.5 | 3 | 5 | 2.5 | 2.5 | 2 | 1.5 | 6 | 2.5 | 4 | 2.5 | 1.5 | 4 | 1.5 | 2 | 1.5 | 3 | 3 | 3 | 4 | 1.5 | 2.5 | 4
67 | 22.5 | 14.5 | 31.5 | 46 | 58 | 69.5 | 81.5 | 89 | 99.5 | 113.5 | 123.5 | 134 | 143 | 157.5 | 3 | 2.5 | 3 | 6 | 6 | 2 | 6 | 3 | 2.5 | 3 | 6 | 3 | 4 | 3 | 2 | 3 | 1.5 | 5 | 2 | 3 | 1.5 | 4 | 1.5 | 5 | 2.5 | 1.5 | 1.5 | 2 | 2.5 | 2 | 2 | 4 | 3 | 2 | 5 | 4 | 3 | 1.5 | 4 | 1.5 | 3 | 4 | 2 | 1.5 | 1.5 | 1.5 | 3 | 3 | 3 | 6 | 2.5 | 3
68 | 19.5 | 12.5 | 27.5 | 45 | 62 | 72.5 | 91 | 110 | 123 | 140.5 | 153 | 163.5 | 181 | 190.5 | 3 | 5 | 2 | 2.5 | 3 | 4 | 6 | 2 | 1.5 | 6 | 4 | 6 | 5 | 4 | 5 | 3 | 4 | 2 | 1.5 | 3 | 5 | 1.5 | 6 | 6 | 6 | 3 | 4 | 6 | 5 | 2 | 3 | 3 | 2.5 | 5 | 4 | 6 | 1.5 | 3 | 5 | 3 | 2 | 1.5 | 4 | 3 | 6 | 5 | 4 | 2.5 | 3 | 2 | 3 | 1.5
69 | 19.5 | 16.5 | 30.5 | 48.5 | 60.5 | 74.5 | 93.5 | 103 | 115.5 | 126.5 | 136.5 | 147 | 163 | 182 | 5 | 6 | 3 | 2.5 | 1.5 | 1.5 | 5 | 6 | 2 | 5 | 5 | 6 | 1.5 | 3 | 1.5 | 6 | 5 | 4 | 2 | 3 | 3 | 5 | 5 | 6 | 1.5 | 2 | 3 | 3 | 5 | 2 | 1.5 | 4 | 3 | 3 | 2.5 | 2.5 | 3 | 3 | 1.5 | 2.5 | 2.5 | 1.5 | 4 | 2.5 | 5 | 3 | 6 | 2 | 6 | 6 | 4 | 3
70 | 16.5 | 12.5 | 25.5 | 33 | 50.5 | 61 | 76 | 89 | 103 | 121 | 137.5 | 148 | 160.5 | 175 | 2 | 3 | 6 | 1.5 | 2 | 2 | 6 | 3 | 3 | 1.5 | 1.5 | 1.5 | 5 | 5 | 1.5 | 6 | 2 | 2.5 | 4 | 2 | 3 | 4 | 3 | 5 | 2.5 | 6 | 3 | 1.5 | 4 | 5 | 2 | 3 | 3 | 6 | 6 | 3 | 5 | 2.5 | 3 | 6 | 1.5 | 5 | 1.5 | 2.5 | 3 | 2 | 5 | 2.5 | 5 | 5 | 1.5 | 3
71 | 16.5 | 10.5 | 21 | 35.5 | 51.5 | 68.5 | 88 | 101 | 116 | 130 | 143.5 | 157.5 | 175.5 | 184.5 | 4 | 1.5 | 2 | 3 | 3 | 3 | 1.5 | 3 | 2.5 | 5 | 5 | 2 | 3 | 5 | 3 | 5 | 5 | 6 | 3 | 3 | 5 | 6 | 2.5 | 6 | 1.5 | 6 | 3 | 2.5 | 5 | 3 | 4 | 3 | 3 | 3 | 3 | 5 | 3 | 1.5 | 6 | 3 | 3 | 3 | 4 | 4 | 3 | 6 | 6 | 3 | 1.5 | 3 | 3 | 1.5
72 | 15 | 9.5 | 22.5 | 39.5 | 48 | 59 | 70.5 | 84.5 | 97.5 | 112 | 121.5 | 133 | 145.5 | 156.5 | 2.5 | 2.5 | 3 | 1.5 | 3 | 2.5 | 1.5 | 6 | 6 | 3 | 5 | 3 | 3 | 2 | 2 | 1.5 | 3 | 3 | 2 | 3 | 1.5 | 3 | 3 | 4 | 6 | 1.5 | 2.5 | 4 | 2.5 | 6 | 3 | 1.5 | 1.5 | 6 | 3 | 4 | 2.5 | 1.5 | 1.5 | 4 | 4 | 2.5 | 2 | 3 | 3 | 2.5 | 4 | 3 | 1.5 | 6 | 2 | 1.5
73 | 22 | 14 | 27.5 | 43.5 | 52.5 | 71 | 83 | 95 | 106.5 | 126.5 | 140.5 | 155 | 165 | 178 | 3 | 3 | 3 | 5 | 5 | 3 | 4 | 1.5 | 3 | 5 | 3 | 5 | 2 | 3 | 2 | 2 | 2.5 | 4 | 6 | 6 | 2 | 3 | 3 | 4 | 2 | 2 | 4 | 4 | 3 | 3 | 2.5 | 3 | 6 | 5 | 3 | 6 | 3 | 4 | 4 | 3 | 1.5 | 3 | 5 | 5 | 2 | 2 | 2 | 4 | 5 | 3 | 2 | 3
74 | 20.5 | 13.5 | 28.5 | 38.5 | 57.5 | 67 | 86 | 95.5 | 113 | 128.5 | 140 | 154.5 | 169 | 179.5 | 4 | 2 | 2.5 | 5 | 4 | 3 | 3 | 5 | 1.5 | 2.5 | 3 | 3 | 6 | 3 | 6 | 4 | 2 | 2.5 | 3 | 2 | 3 | 4 | 6 | 6 | 3 | 3 | 2 | 1.5 | 6 | 2.5 | 3 | 6 | 5 | 5 | 2.5 | 3 | 4 | 3 | 1.5 | 3 | 1.5 | 6 | 3 | 4 | 5 | 1.5 | 3 | 5 | 2 | 2.5 | 3 | 3
75 | 21.5 | 17 | 25 | 36.5 | 50.5 | 68.5 | 85 | 100 | 117 | 125.5 | 140 | 155 | 167.5 | 178 | 6 | 2 | 3 | 6 | 1.5 | 3 | 1.5 | 2 | 1.5 | 2.5 | 6 | 1.5 | 3 | 2 | 3 | 6 | 6 | 3 | 3 | 6 | 2.5 | 6 | 5 | 3 | 3 | 2 | 4 | 6 | 3 | 3 | 6 | 5 | 2 | 1.5 | 2 | 3 | 6 | 2.5 | 4 | 2 | 4 | 6 | 2.5 | 2.5 | 4 | 2.5 | 3 | 3 | 1.5 | 2.5 | 5 | 1.5
76 | 23 | 17.5 | 32 | 45.5 | 57.5 | 69 | 82.5 | 95 | 113.5 | 125 | 142 | 159 | 176 | 188.5 | 5 | 2.5 | 4 | 6 | 3 | 2.5 | 5 | 4 | 1.5 | 5 | 5 | 2 | 2 | 6 | 1.5 | 2.5 | 4 | 3 | 1.5 | 3 | 3 | 3 | 6 | 1.5 | 6 | 2 | 3 | 1.5 | 6 | 4 | 6 | 2.5 | 2.5 | 1.5 | 5 | 2.5 | 6 | 5 | 3 | 3 | 5 | 4 | 3 | 5 | 6 | 3 | 6 | 2 | 1.5 | 6 | 2 | 3
77 | 22.5 | 14 | 28 | 43 | 53.5 | 65.5 | 80.5 | 93.5 | 107.5 | 119.5 | 133 | 146 | 159.5 | 172 | 3 | 2.5 | 2.5 | 6 | 6 | 2.5 | 2.5 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 1.5 | 2.5 | 4 | 4 | 1.5 | 1.5 | 1.5 | 6 | 6 | 4 | 2.5 | 1.5 | 5 | 4 | 3 | 3 | 4 | 4 | 5 | 1.5 | 1.5 | 3 | 1.5 | 6 | 3 | 4 | 4 | 3 | 2 | 6 | 2 | 4 | 1.5 | 2.5 | 4 | 3 | 3
78 | 17.5 | 11.5 | 22.5 | 34.5 | 44 | 53 | 66.5 | 84.5 | 100.5 | 111.5 | 124.5 | 133 | 155 | 169 | 5 | 3 | 2 | 1.5 | 3 | 3 | 3 | 2 | 3 | 3 | 4 | 2 | 1.5 | 3 | 2 | 3 | 2.5 | 2 | 2 | 2.5 | 6 | 3 | 2 | 2.5 | 6 | 5 | 4 | 3 | 5 | 5 | 4 | 2 | 3 | 2.5 | 2.5 | 3 | 3 | 5 | 2 | 3 | 2 | 2 | 1.5 | 3 | 6 | 4 | 6 | 6 | 4 | 1.5 | 6 | 2.5
79 | 19.5 | 13.5 | 28.5 | 43.5 | 56.5 | 71.5 | 84 | 93 | 109.5 | 122 | 135 | 149.5 | 159.5 | 176 | 6 | 3 | 3 | 1.5 | 3 | 3 | 5 | 4 | 4 | 3 | 4 | 4 | 4 | 3 | 3 | 3 | 4 | 3 | 3 | 5 | 2 | 3 | 5 | 2.5 | 1.5 | 3 | 1.5 | 3 | 3 | 2.5 | 5 | 6 | 5 | 3 | 1.5 | 3 | 2.5 | 4 | 4 | 2.5 | 1.5 | 5 | 3 | 5 | 2.5 | 2 | 3 | 2.5 | 1.5 | 4 | 5 | 6
80 | 20.5 | 14.5 | 28 | 38.5 | 56.5 | 69 | 78.5 | 92 | 106 | 123 | 132.5 | 147 | 160 | 175 | 3 | 2.5 | 3 | 6 | 3 | 3 | 6 | 1.5 | 1.5 | 4 | 2.5 | 2.5 | 3 | 6 | 6 | 3 | 2 | 4 | 5 | 1.5 | 3 | 2 | 2 | 2.5 | 4 | 1.5 | 3 | 5 | 3 | 5 | 3 | 3 | 3 | 4 | 6 | 4 | 2.5 | 2.5 | 3 | 1.5 | 6 | 3 | 3 | 2.5 | 2 | 2 | 6 | 3 | 2 | 5 | 3 | 5
81 | 23.5 | 15.5 | 29 | 48 | 61.5 | 73 | 87 | 98.5 | 115.5 | 128.5 | 143.5 | 156 | 167 | 177.5 | 2.5 | 4 | 6 | 3 | 6 | 2 | 3 | 2.5 | 5 | 5 | 4 | 5 | 3 | 3 | 5 | 2.5 | 3 | 4 | 3 | 1.5 | 5 | 4 | 3 | 2 | 1.5 | 2 | 3 | 5 | 5 | 5 | 4 | 3 | 2.5 | 1.5 | 6 | 3 | 6 | 3 | 3 | 3 | 1.5 | 5 | 3 | 3 | 3 | 4 | 2.5 | 1.5 | 2 | 4 | 2 | 2.5
82 | 22.5 | 14.5 | 31.5 | 45.5 | 58 | 68 | 79 | 101 | 119 | 130.5 | 145 | 158.5 | 173.5 | 185.5 | 1.5 | 3 | 4 | 6 | 2 | 6 | 3 | 6 | 2 | 4 | 4 | 4 | 2 | 5 | 2.5 | 3 | 3 | 1.5 | 3 | 2.5 | 3 | 4 | 2.5 | 1.5 | 5 | 6 | 6 | 5 | 4 | 3 | 6 | 5 | 1.5 | 2 | 4 | 4 | 5 | 3 | 4 | 2.5 | 5 | 5 | 2 | 1.5 | 2.5 | 5 | 5 | 2.5 | 3 | 6 | 1.5 | 1.5
83 | 24 | 13 | 29 | 40 | 53 | 64.5 | 78.5 | 88 | 101 | 120.5 | 136.5 | 147 | 156.5 | 167.5 | 5 | 3 | 2.5 | 2.5 | 5 | 6 | 2.5 | 2.5 | 2.5 | 2.5 | 4 | 2 | 4 | 1.5 | 6 | 1.5 | 3 | 2.5 | 3 | 3 | 5 | 6 | 1.5 | 1.5 | 2.5 | 2.5 | 2.5 | 2 | 2.5 | 6 | 2 | 2.5 | 6 | 5 | 2.5 | 6 | 3 | 6 | 5 | 2 | 2 | 1.5 | 3 | 4 | 2 | 3 | 3 | 1.5 | 2 | 4 | 3 | 2
84 | 16 | 10 | 28 | 36 | 48.5 | 60 | 72.5 | 90.5 | 105.5 | 122.5 | 134.5 | 148.5 | 163.5 | 178 | 2 | 1.5 | 1.5 | 5 | 2 | 4 | 6 | 6 | 2 | 1.5 | 2 | 2.5 | 3 | 2 | 5 | 2.5 | 4 | 4 | 1.5 | 2 | 2 | 5 | 4 | 1.5 | 3 | 5 | 4 | 6 | 6 | 5 | 2.5 | 1.5 | 3 | 4 | 5 | 5 | 6 | 2.5 | 2 | 1.5 | 2 | 6 | 3 | 3 | 3 | 6 | 2 | 4 | 6 | 3 | 2.5 | 3
85 | 19 | 14.5 | 24 | 37 | 45 | 61.5 | 76.5 | 88.5 | 98.5 | 107.5 | 115 | 128.5 | 146 | 160.5 | 4 | 6 | 2.5 | 2 | 2.5 | 2 | 3 | 2 | 2 | 3 | 6 | 2 | 2.5 | 1.5 | 2 | 2 | 6 | 4 | 4 | 2.5 | 6 | 4 | 3 | 2 | 3 | 3 | 3 | 3 | 2.5 | 1.5 | 3 | 3 | 2.5 | 3 | 2 | 1.5 | 1.5 | 3 | 1.5 | 1.5 | 3 | 5 | 1.5 | 4 | 6 | 1.5 | 6 | 4 | 4 | 6 | 2.5 | 2
86 | 20.5 | 15.5 | 25 | 40.5 | 53.5 | 67.5 | 77.5 | 93 | 110.5 | 121 | 131.5 | 140 | 155.5 | 169 | 1.5 | 4 | 5 | 5 | 2 | 3 | 2.5 | 2 | 5 | 4 | 1.5 | 5 | 2 | 6 | 2 | 3 | 2.5 | 6 | 2.5 | 3 | 3 | 2.5 | 3 | 1.5 | 6 | 2.5 | 3 | 4 | 6 | 2.5 | 6 | 3 | 5 | 2 | 1.5 | 2 | 1.5 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 2.5 | 6 | 3 | 5 | 1.5 | 5 | 1.5 | 3 | 4
87 | 15.5 | 11 | 20.5 | 31.5 | 49 | 59 | 72.5 | 80 | 93 | 106.5 | 115 | 125 | 144 | 153.5 | 3 | 2 | 2 | 4 | 2 | 2.5 | 3 | 2 | 1.5 | 3 | 2.5 | 4 | 6 | 4 | 2.5 | 5 | 2.5 | 2.5 | 3 | 2 | 6 | 2.5 | 2 | 3 | 1.5 | 2 | 1.5 | 2.5 | 4 | 3 | 3 | 3 | 3 | 5 | 4 | 1.5 | 1.5 | 3 | 2 | 2 | 2 | 3 | 3 | 2 | 3 | 6 | 4 | 6 | 1.5 | 3 | 2.5 | 2.5
88 | 21.5 | 14.5 | 26 | 39 | 51.5 | 64 | 80.5 | 93.5 | 106.5 | 124 | 135.5 | 144 | 154 | 168.5 | 3 | 6 | 2.5 | 3 | 3 | 4 | 3 | 1.5 | 2.5 | 4 | 1.5 | 5 | 5 | 3 | 1.5 | 3 | 3 | 2.5 | 3 | 4 | 2.5 | 6 | 2 | 6 | 2.5 | 5 | 1.5 | 4 | 5 | 2 | 4 | 2 | 6 | 5 | 4 | 2.5 | 2 | 3 | 2.5 | 4 | 3 | 2 | 2 | 1.5 | 2.5 | 2 | 1.5 | 4 | 2 | 1.5 | 5 | 6
89 | 19.5 | 13.5 | 23.5 | 38.5 | 47 | 62 | 72 | 87.5 | 102.5 | 113 | 128.5 | 142.5 | 153.5 | 168 | 1.5 | 6 | 3 | 3 | 3 | 3 | 1.5 | 2.5 | 6 | 2 | 5 | 2 | 3 | 2 | 2 | 1.5 | 2 | 6 | 3 | 4 | 1.5 | 5 | 2 | 1.5 | 6 | 2.5 | 2 | 5 | 5 | 3 | 4 | 3 | 3 | 1.5 | 3 | 3 | 6 | 5 | 1.5 | 3 | 5 | 3 | 2 | 4 | 1.5 | 4 | 3 | 2.5 | 4 | 3 | 6 | 1.5
90 | 23.5 | 19 | 30 | 41 | 53 | 61.5 | 73.5 | 83 | 97.5 | 117.5 | 132 | 146.5 | 161.5 | 176 | 2 | 5 | 6 | 6 | 3 | 1.5 | 1.5 | 5 | 2.5 | 3 | 4 | 1.5 | 5 | 2.5 | 1.5 | 3 | 2 | 1.5 | 2 | 3 | 2.5 | 1.5 | 4 | 4 | 3 | 1.5 | 3 | 2 | 5 | 2.5 | 3 | 4 | 6 | 6 | 6 | 2 | 1.5 | 5 | 2 | 6 | 5 | 1.5 | 3 | 5 | 1.5 | 6 | 2.5 | 5 | 6 | 2.5 | 4 | 2
91 | 17.5 | 12 | 27.5 | 38 | 50 | 62 | 75.5 | 91.5 | 109 | 127 | 142.5 | 161.5 | 173.5 | 189.5 | 2.5 | 1.5 | 3 | 5 | 2.5 | 3 | 5 | 5 | 2 | 3 | 3 | 2.5 | 3 | 4 | 3 | 2 | 2.5 | 1.5 | 6 | 2 | 5 | 2.5 | 3 | 3 | 6 | 6 | 2 | 2 | 6 | 3 | 2.5 | 6 | 4 | 2 | 6 | 6 | 2 | 1.5 | 6 | 6 | 3 | 5 | 5 | 6 | 3 | 3 | 4 | 2 | 3 | 3 | 6 | 4
92 | 17.5 | 13 | 22.5 | 32 | 45 | 61.5 | 72 | 85.5 | 99 | 113 | 125.5 | 143.5 | 158 | 172.5 | 2.5 | 3 | 6 | 1.5 | 2 | 2.5 | 3 | 2 | 2.5 | 2.5 | 1.5 | 3 | 5 | 2.5 | 3 | 2.5 | 5 | 5 | 1.5 | 5 | 5 | 1.5 | 2.5 | 1.5 | 5 | 2 | 1.5 | 5 | 2 | 4 | 2.5 | 5 | 4 | 2 | 4 | 4 | 4 | 3 | 3 | 2.5 | 6 | 3 | 4 | 5 | 4 | 2.5 | 5 | 3 | 1.5 | 4 | 4 | 5
93 | 18.5 | 11 | 22 | 37 | 53.5 | 69 | 86 | 108 | 117 | 136 | 155.5 | 166.5 | 179.5 | 188 | 3 | 2.5 | 2.5 | 3 | 2.5 | 5 | 1.5 | 2 | 5 | 4 | 3 | 3 | 5 | 2.5 | 5 | 4 | 6 | 3 | 2.5 | 4 | 4 | 4 | 3 | 6 | 5 | 5 | 6 | 6 | 3 | 2.5 | 1.5 | 2 | 6 | 4 | 6 | 3 | 2.5 | 5 | 6 | 6 | 5 | 2 | 2 | 2 | 3 | 5 | 3 | 2 | 3 | 2 | 2 | 1.5
94 | 15 | 9 | 22 | 36 | 49 | 57.5 | 65 | 79.5 | 91 | 106.5 | 119.5 | 129.5 | 144.5 | 155.5 | 2.5 | 1.5 | 2.5 | 2.5 | 2 | 4 | 2 | 5 | 2 | 3 | 4 | 5 | 1.5 | 2.5 | 5 | 4 | 2 | 2.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 3 | 5 | 6 | 1.5 | 2 | 4 | 2 | 2.5 | 3 | 4 | 2.5 | 5 | 4 | 3 | 4 | 3 | 3 | 2 | 2.5 | 2.5 | 3 | 6 | 3 | 3 | 3 | 2 | 2 | 2 | 5
95 | 24.5 | 19 | 36.5 | 50 | 61 | 72.5 | 87 | 102.5 | 112.5 | 129 | 142 | 158 | 175 | 183 | 6 | 5 | 2 | 6 | 3 | 2.5 | 6 | 6 | 1.5 | 3 | 4 | 5 | 1.5 | 1.5 | 2 | 6 | 3 | 1.5 | 3 | 4 | 4 | 1.5 | 6 | 3 | 5 | 1.5 | 3 | 6 | 3 | 2.5 | 2 | 2.5 | 6 | 2 | 6 | 2.5 | 6 | 2.5 | 3 | 1.5 | 1.5 | 2.5 | 6 | 6 | 2 | 6 | 3 | 6 | 1.5 | 2 | 3 | 1.5
96 | 23 | 16.5 | 31 | 42.5 | 56 | 75 | 85.5 | 97.5 | 111.5 | 122.5 | 138 | 151 | 161 | 176 | 5 | 3 | 6 | 2.5 | 2.5 | 4 | 2 | 6 | 1.5 | 1.5 | 6 | 2.5 | 2 | 6 | 3 | 2.5 | 6 | 4 | 4 | 5 | 3 | 2.5 | 2.5 | 2.5 | 4 | 4 | 1.5 | 2.5 | 3 | 2 | 5 | 4 | 1.5 | 2.5 | 3 | 4 | 3 | 5 | 1.5 | 6 | 1.5 | 5 | 2.5 | 4 | 3 | 3 | 2.5 | 1.5 | 4 | 2 | 5 | 4
97 | 16.5 | 13 | 23.5 | 41.5 | 52.5 | 67 | 78 | 88 | 103 | 117 | 130 | 143 | 154.5 | 169 | 2.5 | 6 | 2 | 2.5 | 2 | 1.5 | 2 | 5 | 3 | 6 | 6 | 3 | 3 | 2 | 3 | 3 | 5 | 1.5 | 2 | 6 | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 2 | 3 | 6 | 3 | 3 | 3 | 6 | 3 | 2 | 2.5 | 2 | 2.5 | 6 | 2 | 3 | 5 | 3 | 2 | 5 | 3 | 1.5 | 2.5 | 6 | 3 | 3
98 | 21.5 | 14 | 25.5 | 43.5 | 59 | 80 | 90 | 108 | 122.5 | 137.5 | 151 | 160.5 | 172 | 183 | 3 | 2 | 3 | 6 | 2.5 | 5 | 2.5 | 1.5 | 2 | 6 | 6 | 4 | 4 | 2.5 | 6 | 3 | 6 | 5 | 6 | 4 | 2.5 | 2.5 | 2.5 | 2.5 | 3 | 6 | 6 | 3 | 5 | 1.5 | 2 | 6 | 6 | 2 | 3 | 4 | 4 | 2 | 2.5 | 5 | 3 | 1.5 | 2 | 3 | 4 | 2 | 4 | 1.5 | 2 | 4 | 3 | 2
99 | 23.5 | 14.5 | 30.5 | 37.5 | 56.5 | 67.5 | 80 | 90 | 108.5 | 126.5 | 140 | 153 | 171 | 181 | 2.5 | 6 | 3 | 3 | 3 | 6 | 4 | 3 | 2 | 2 | 1.5 | 1.5 | 4 | 3 | 6 | 6 | 3 | 2.5 | 2.5 | 3 | 3 | 2.5 | 2 | 5 | 3 | 2.5 | 2.5 | 2 | 6 | 2.5 | 6 | 4 | 5 | 3 | 5 | 5 | 3 | 3 | 6 | 1.5 | 4 | 4 | 2 | 3 | 6 | 3 | 4 | 5 | 3 | 2.5 | 3 | 1.5
100 | 18 | 11 | 26 | 36 | 51.5 | 62.5 | 81.5 | 92 | 102.5 | 117 | 131.5 | 147 | 160.5 | 172 | 1.5 | 5 | 3 | 1.5 | 4 | 3 | 2 | 6 | 3 | 3 | 1.5 | 2.5 | 3 | 5 | 6 | 1.5 | 2.5 | 1.5 | 4 | 3 | 4 | 6 | 4 | 5 | 2 | 3 | 3 | 2.5 | 4 | 2 | 2.5 | 2 | 2.5 | 6 | 3 | 3 | 3 | 5 | 1.5 | 5 | 5 | 3 | 5 | 2.5 | 3 | 1.5 | 6 | 3 | 3 | 4 | 3 | 1.5
101 | 16.5 | 12.5 | 21 | 36 | 45.5 | 57 | 70 | 80 | 96.5 | 109 | 124 | 136 | 151.5 | 166 | 2.5 | 4 | 3 | 3 | 2 | 2 | 3 | 1.5 | 5 | 4 | 2 | 4 | 2.5 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 4 | 3 | 4 | 3 | 3 | 3 | 2.5 | 2 | 2.5 | 1.5 | 6 | 6 | 3 | 5 | 1.5 | 3 | 3 | 3 | 4 | 4 | 4 | 2 | 6 | 2 | 2 | 3 | 5 | 5 | 2.5 | 4 | 1.5 | 4 | 5
102 | 22.5 | 14.5 | 28 | 40 | 58.5 | 75.5 | 89 | 102 | 114 | 129 | 139.5 | 152 | 164 | 179.5 | 2.5 | 3 | 6 | 3 | 5 | 3 | 2.5 | 3 | 1.5 | 3 | 2.5 | 5 | 5 | 1.5 | 6 | 6 | 5 | 5 | 5 | 2 | 2.5 | 6 | 3 | 2 | 5 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 5 | 2.5 | 1.5 | 6 | 2.5 | 4 | 2.5 | 1.5 | 5 | 1.5 | 2 | 4 | 3 | 3 | 2 | 4 | 5 | 5 | 2.5 | 3
103 | 15.5 | 11.5 | 20.5 | 30 | 42.5 | 54.5 | 66 | 80.5 | 99.5 | 118.5 | 130.5 | 142 | 157.5 | 170.5 | 5 | 1.5 | 2.5 | 2.5 | 2 | 2 | 3 | 2 | 3 | 2.5 | 2.5 | 1.5 | 3 | 4 | 2.5 | 3 | 3 | 2.5 | 4 | 2.5 | 1.5 | 2 | 6 | 2 | 1.5 | 6 | 3 | 4 | 4 | 4 | 6 | 5 | 4 | 6 | 5 | 4 | 3 | 2.5 | 2.5 | 4 | 2 | 3 | 1.5 | 5 | 5 | 3 | 2.5 | 5 | 4 | 4 | 2 | 3
104 | 28 | 20 | 32.5 | 44.5 | 54.5 | 66 | 77.5 | 96.5 | 108.5 | 124.5 | 133.5 | 150.5 | 162.5 | 177.5 | 3 | 6 | 5 | 6 | 4 | 4 | 1.5 | 3 | 1.5 | 2.5 | 3 | 5 | 2 | 3 | 3 | 2 | 3 | 3 | 2.5 | 3 | 2 | 5 | 2 | 2.5 | 6 | 6 | 5 | 2 | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 5 | 2 | 3 | 2 | 2 | 3 | 3 | 6 | 5 | 3 | 1.5 | 5 | 2.5 | 5 | 3 | 2 | 5
105 | 14.5 | 8 | 23.5 | 36.5 | 48.5 | 64.5 | 74.5 | 87 | 101 | 120 | 135 | 148 | 160.5 | 169.5 | 2 | 2 | 2 | 2 | 1.5 | 5 | 6 | 3 | 4 | 3 | 2 | 4 | 1.5 | 5 | 1.5 | 4 | 3 | 4 | 4 | 5 | 3 | 3 | 2 | 2 | 3 | 2.5 | 2 | 5 | 2 | 2 | 5 | 5 | 5 | 6 | 3 | 5 | 5 | 3 | 4 | 3 | 4 | 3 | 3 | 3 | 2.5 | 2 | 2 | 6 | 2 | 3 | 1.5 | 2.5
106 | 24 | 17 | 28.5 | 49 | 57.5 | 70 | 86 | 100.5 | 112 | 122 | 130.5 | 149.5 | 163.5 | 175.5 | 6 | 3 | 4 | 4 | 3 | 4 | 1.5 | 3 | 2.5 | 6 | 6 | 6 | 3 | 2 | 1.5 | 2 | 1.5 | 2 | 3 | 6 | 4 | 3 | 6 | 3 | 4 | 1.5 | 4 | 5 | 2 | 1.5 | 2 | 6 | 3 | 2.5 | 1.5 | 3 | 1.5 | 2 | 3 | 2 | 2 | 6 | 5 | 6 | 4 | 4 | 3 | 3 | 4 | 4 | 2 | 2
107 | 14 | 10 | 24 | 36 | 45 | 57 | 69 | 84 | 94.5 | 106 | 114.5 | 127 | 139.5 | 150.5 | 2 | 2.5 | 4 | 1.5 | 2.5 | 1.5 | 4 | 6 | 2.5 | 2.5 | 5 | 2 | 3 | 3 | 1.5 | 1.5 | 2 | 5 | 3 | 2 | 3 | 6 | 1.5 | 1.5 | 2 | 5 | 5 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 5 | 3 | 2 | 2 | 2 | 1.5 | 3 | 2 | 3 | 6 | 1.5 | 3 | 3 | 2.5 | 4 | 3 | 2.5 | 2.5 | 3
108 | 16 | 12 | 21.5 | 32.5 | 43.5 | 55.5 | 72 | 81 | 97.5 | 114.5 | 126 | 143 | 158 | 167 | 5 | 3 | 2 | 2 | 2 | 2 | 3 | 2.5 | 2.5 | 4 | 1.5 | 3 | 4 | 3 | 1.5 | 2.5 | 6 | 2.5 | 1.5 | 2 | 6 | 4 | 4 | 2.5 | 3 | 2 | 2.5 | 1.5 | 4 | 6 | 1.5 | 5 | 3 | 5 | 6 | 3 | 3 | 4 | 2.5 | 2 | 6 | 4 | 4 | 3 | 2.5 | 4 | 6 | 2.5 | 2.5 | 3 | 2 | 1.5
109 | 17.5 | 12 | 23 | 32 | 48 | 65 | 79.5 | 98 | 108.5 | 121.5 | 139 | 158 | 172 | 185.5 | 5 | 2 | 3 | 2 | 2.5 | 3 | 2.5 | 3 | 2 | 1.5 | 2.5 | 3 | 6 | 6 | 1.5 | 2.5 | 6 | 4 | 3 | 4 | 2.5 | 2 | 4 | 6 | 2.5 | 5 | 6 | 5 | 4 | 3 | 1.5 | 2 | 4 | 4 | 2 | 3 | 2.5 | 4 | 6 | 5 | 4 | 5 | 4 | 6 | 6 | 2 | 3 | 3 | 2.5 | 3 | 3 | 5
110 | 17.5 | 10.5 | 21.5 | 37.5 | 50.5 | 64 | 78 | 92 | 106.5 | 120.5 | 129 | 142.5 | 156.5 | 170.5 | 2.5 | 3 | 2 | 3 | 4 | 3 | 2 | 2 | 4 | 6 | 3 | 3 | 4 | 2 | 2 | 5 | 3 | 3 | 5 | 2.5 | 3 | 5 | 2 | 4 | 2 | 3 | 6 | 3 | 3 | 2.5 | 6 | 3 | 5 | 1.5 | 2.5 | 5 | 2.5 | 1.5 | 1.5 | 3 | 5 | 3 | 4 | 1.5 | 5 | 5 | 1.5 | 2.5 | 3 | 3 | 4 | 4
111 | 17.5 | 11 | 26 | 43.5 | 56.5 | 72 | 91 | 102.5 | 121 | 135.5 | 148 | 159 | 170 | 186 | 2.5 | 3 | 1.5 | 4 | 2.5 | 4 | 2.5 | 6 | 6 | 1.5 | 5 | 5 | 2.5 | 2.5 | 5 | 3 | 5 | 4 | 4 | 2.5 | 5 | 4 | 6 | 4 | 6 | 2 | 2 | 1.5 | 6 | 2.5 | 4 | 6 | 5 | 6 | 1.5 | 2 | 5 | 3 | 3 | 1.5 | 5 | 2 | 2 | 2 | 2.5 | 4 | 2 | 2.5 | 5 | 2 | 6 | 3
112 | 21 | 13.5 | 26.5 | 35.5 | 55 | 69 | 82 | 93.5 | 109.5 | 120.5 | 132.5 | 142.5 | 158.5 | 175 | 2 | 5 | 1.5 | 5 | 5 | 2.5 | 2.5 | 3 | 2 | 1.5 | 1.5 | 4 | 1.5 | 6 | 6 | 6 | 6 | 3 | 2.5 | 2.5 | 2.5 | 4 | 2.5 | 4 | 4 | 2 | 3 | 2.5 | 2 | 4 | 6 | 4 | 1.5 | 5 | 3 | 1.5 | 1.5 | 5 | 3 | 2.5 | 2 | 3 | 2.5 | 2.5 | 3 | 6 | 3 | 4 | 6 | 4 | 4 | 2.5
113 | 17 | 13 | 24 | 37.5 | 52 | 63.5 | 75 | 87 | 100.5 | 112 | 122.5 | 131 | 142 | 154 | 6 | 1.5 | 2.5 | 3 | 2 | 2 | 2 | 5 | 6 | 2.5 | 2.5 | 2.5 | 2.5 | 3 | 3 | 6 | 3 | 2.5 | 4 | 2 | 5 | 3 | 1.5 | 2 | 3 | 3 | 4 | 2 | 6 | 1.5 | 3 | 3 | 2 | 4 | 2.5 | 3 | 3 | 2 | 4 | 1.5 | 3 | 2 | 1.5 | 2 | 3 | 5 | 1.5 | 1.5 | 3 | 2.5 | 1.5 | 5
114 | 19.5 | 13.5 | 27 | 40 | 57 | 70.5 | 83.5 | 101 | 118.5 | 133 | 147.5 | 158 | 171 | 180.5 | 2 | 2.5 | 3 | 6 | 3 | 3 | 5 | 2.5 | 3 | 2.5 | 2.5 | 5 | 3 | 5 | 3 | 6 | 5 | 3 | 3 | 2.5 | 3 | 4 | 3 | 3 | 3 | 6 | 2.5 | 6 | 6 | 2.5 | 6 | 3 | 6 | 2 | 5 | 1.5 | 1.5 | 6 | 3 | 4 | 4 | 2.5 | 2 | 2 | 3 | 3 | 5 | 2 | 1.5 | 2 | 3 | 3
115 | 23.5 | 17.5 | 28 | 39.5 | 50.5 | 64.5 | 77 | 89 | 101 | 115.5 | 132.5 | 144.5 | 157 | 177 | 6 | 5 | 2.5 | 4 | 2 | 4 | 1.5 | 3 | 3 | 1.5 | 3 | 4 | 5 | 2.5 | 1.5 | 2 | 6 | 4 | 2 | 2 | 4 | 3 | 3 | 2.5 | 5 | 1.5 | 2.5 | 3 | 3 | 2.5 | 4 | 2.5 | 6 | 2 | 5 | 1.5 | 2.5 | 6 | 2.5 | 6 | 5 | 2.5 | 2.5 | 2 | 1.5 | 2 | 5 | 4 | 6 | 6 | 5 | 3
116 | 23 | 15 | 31.5 | 46.5 | 62.5 | 76.5 | 92 | 111.5 | 124.5 | 140.5 | 150.5 | 163.5 | 178.5 | 196.5 | 3 | 4 | 2 | 6 | 3 | 5 | 2.5 | 6 | 5 | 4 | 2 | 4 | 3 | 6 | 4 | 3 | 3 | 3 | 2 | 6 | 2.5 | 4 | 5 | 4 | 6 | 2.5 | 5 | 6 | 1.5 | 1.5 | 5 | 5 | 3 | 4 | 5 | 4 | 2 | 4 | 2 | 2 | 2.5 | 6 | 3 | 1.5 | 4 | 3 | 3 | 5 | 4 | 5 | 3 | 6
117 | 27 | 17 | 33.5 | 47 | 65 | 77 | 94.5 | 105 | 117 | 129.5 | 138.5 | 150 | 165 | 176.5 | 6 | 3 | 3 | 5 | 4 | 6 | 2.5 | 4 | 3 | 1.5 | 3 | 6 | 4 | 3 | 5 | 6 | 1.5 | 3 | 5 | 2.5 | 6 | 6 | 2.5 | 3 | 1.5 | 4 | 3 | 2 | 6 | 2 | 2.5 | 1.5 | 3 | 5 | 2.5 | 2 | 2 | 1.5 | 2.5 | 3 | 1.5 | 1.5 | 2.5 | 6 | 3 | 4 | 5 | 3 | 2 | 4 | 2.5 | 3
118 | 22 | 12 | 25.5 | 33 | 45.5 | 56 | 72 | 84 | 98 | 112.5 | 125 | 140 | 152 | 167 | 5 | 4 | 1.5 | 1.5 | 5 | 5 | 1.5 | 2 | 1.5 | 1.5 | 1.5 | 3 | 2.5 | 2 | 5 | 3 | 3 | 2 | 3 | 2.5 | 4 | 3 | 6 | 3 | 1.5 | 5 | 3 | 2.5 | 4 | 5 | 3 | 2 | 3 | 6 | 2.5 | 3 | 3 | 6 | 2 | 1.5 | 5 | 3 | 5 | 2 | 2 | 2 | 3 | 5 | 2 | 6 | 3 | 4
119 | 18.5 | 14 | 25.5 | 38.5 | 53.5 | 67.5 | 80.5 | 94.5 | 108 | 127 | 147 | 161.5 | 175.5 | 187.5 | 3 | 5 | 3 | 3 | 3 | 1.5 | 2 | 5 | 3 | 6 | 1.5 | 2.5 | 2 | 4 | 6 | 3 | 2.5 | 6 | 3 | 2.5 | 3 | 1.5 | 2.5 | 6 | 3 | 5 | 3 | 3 | 3 | 3 | 2.5 | 5 | 6 | 3 | 5 | 5 | 4 | 5 | 5 | 6 | 5 | 2.5 | 3 | 4 | 2.5 | 5 | 5 | 1.5 | 2.5 | 1.5 | 5 | 3
120 | 18 | 12 | 25.5 | 38.5 | 48 | 59.5 | 73 | 89.5 | 104.5 | 114.5 | 132 | 142 | 153.5 | 166.5 | 2.5 | 5 | 3 | 1.5 | 4 | 2 | 1.5 | 6 | 2 | 3 | 6 | 2 | 2 | 3 | 1.5 | 3 | 1.5 | 2.5 | 5 | 2.5 | 3 | 6 | 3 | 1.5 | 6 | 3 | 5 | 2.5 | 4 | 5 | 4 | 2 | 4 | 2 | 2 | 2 | 2.5 | 6 | 3 | 6 | 2 | 4 | 1.5 | 2.5 | 1.5 | 3 | 3 | 4 | 2 | 5 | 2 | 4
121 | 12 | 7 | 19 | 29.5 | 41 | 52 | 60 | 77 | 86.5 | 102.5 | 115 | 127 | 139.5 | 152.5 | 1.5 | 2 | 1.5 | 2 | 3 | 2 | 4 | 3 | 2.5 | 3 | 3 | 2 | 5 | 1.5 | 2.5 | 2.5 | 4 | 2.5 | 2.5 | 2 | 1.5 | 3 | 2 | 1.5 | 4 | 3 | 4 | 6 | 3 | 2 | 1.5 | 3 | 6 | 2 | 2 | 6 | 6 | 3 | 1.5 | 2 | 3 | 5 | 2 | 2 | 3 | 2 | 6 | 1.5 | 3 | 2 | 3 | 5
122 | 17 | 10 | 22 | 34 | 44.5 | 56.5 | 68 | 79 | 91.5 | 105.5 | 117 | 132.5 | 150 | 167 | 2 | 2 | 3 | 3 | 4 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 2 | 1.5 | 4 | 3 | 3 | 2 | 4 | 3 | 1.5 | 3 | 5 | 2 | 2 | 2 | 3 | 4 | 3 | 3 | 4 | 2.5 | 2.5 | 1.5 | 4 | 6 | 5 | 2 | 1.5 | 3 | 2.5 | 3 | 4 | 6 | 6 | 4 | 2.5 | 5 | 5 | 2 | 4 | 6
123 | 23 | 14 | 30.5 | 43 | 56 | 71.5 | 83 | 103 | 112 | 121.5 | 130.5 | 140.5 | 158 | 178 | 4 | 1.5 | 2.5 | 6 | 3 | 6 | 1.5 | 6 | 4 | 3 | 1.5 | 4 | 2 | 2 | 3 | 6 | 2.5 | 5 | 5 | 3 | 3 | 5 | 2 | 1.5 | 5 | 5 | 5 | 5 | 3 | 2 | 2 | 2 | 1.5 | 3 | 3 | 2 | 1.5 | 1.5 | 3 | 3 | 5 | 1.5 | 2 | 1.5 | 5 | 4 | 2.5 | 6 | 4 | 5 | 5 | 6
124 | 21.5 | 11.5 | 29.5 | 41 | 52 | 66 | 81 | 96 | 109.5 | 118.5 | 137 | 151 | 168.5 | 184.5 | 2.5 | 3 | 4 | 2 | 5 | 5 | 4 | 4 | 2 | 3 | 1.5 | 5 | 2 | 2 | 3 | 4 | 2 | 3 | 6 | 3 | 3 | 6 | 2 | 4 | 1.5 | 2.5 | 6 | 5 | 3 | 2.5 | 6 | 2 | 3 | 2.5 | 1.5 | 2 | 2.5 | 5 | 6 | 5 | 3 | 3 | 5 | 3 | 2.5 | 6 | 3 | 6 | 4 | 3 | 6 | 3
125 | 20.5 | 12.5 | 25.5 | 36.5 | 47.5 | 62 | 80 | 96.5 | 110.5 | 124.5 | 145.5 | 161 | 177 | 198 | 4 | 3 | 3 | 2.5 | 6 | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 2.5 | 3 | 4 | 1.5 | 5 | 4 | 2.5 | 3 | 3 | 3 | 6 | 6 | 5 | 1.5 | 4 | 6 | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 6 | 3 | 6 | 6 | 2.5 | 4 | 3 | 6 | 5 | 3 | 5 | 3 | 5 | 6 | 6 | 4
126 | 22.5 | 15 | 28 | 42.5 | 50.5 | 68 | 82.5 | 96 | 113 | 123.5 | 133.5 | 148.5 | 166 | 180.5 | 6 | 3 | 3 | 3 | 5 | 2.5 | 2.5 | 3 | 3 | 5 | 5 | 1.5 | 1.5 | 2 | 3 | 1.5 | 5 | 5 | 5 | 2.5 | 1.5 | 6 | 5 | 2 | 2.5 | 5 | 2 | 4 | 3 | 6 | 2 | 6 | 1.5 | 3 | 3 | 3 | 2.5 | 4 | 2 | 1.5 | 2 | 3 | 6 | 4 | 5 | 2.5 | 4 | 6 | 4 | 4 | 1.5 | 5
127 | 22 | 12 | 29.5 | 44 | 59.5 | 71.5 | 83 | 99 | 110.5 | 128.5 | 146.5 | 165.5 | 180 | 193 | 3 | 3 | 3 | 3 | 4 | 6 | 5 | 2.5 | 2 | 1.5 | 6 | 5 | 4 | 1.5 | 5 | 5 | 2 | 2 | 6 | 2 | 2.5 | 4 | 2 | 3 | 3 | 3 | 6 | 4 | 2.5 | 2.5 | 2.5 | 4 | 6 | 5 | 4 | 3 | 5 | 4 | 3 | 6 | 6 | 2 | 5 | 6 | 3 | 5 | 2.5 | 4 | 1.5 | 5 | 2.5 | 4
128 | 21.5 | 13.5 | 30 | 46 | 65 | 83 | 102 | 114.5 | 130 | 147.5 | 159.5 | 170.5 | 183.5 | 199.5 | 5 | 3 | 1.5 | 4 | 5 | 3 | 2.5 | 6 | 4 | 4 | 5 | 3 | 6 | 3 | 5 | 5 | 5 | 4 | 3 | 6 | 5 | 3 | 6 | 5 | 4 | 4 | 1.5 | 3 | 1.5 | 5 | 3 | 6 | 6 | 3 | 2.5 | 6 | 5 | 1.5 | 1.5 | 4 | 3 | 1.5 | 2.5 | 4 | 4 | 4 | 2 | 3 | 2 | 5 | 6 | 3
129 | 20.5 | 13 | 26 | 36.5 | 54 | 72.5 | 83.5 | 98.5 | 114.5 | 128 | 141.5 | 155.5 | 165.5 | 175 | 3 | 6 | 2.5 | 1.5 | 6 | 1.5 | 2.5 | 3 | 3 | 1.5 | 3 | 3 | 5 | 6 | 1.5 | 5 | 2.5 | 5 | 6 | 5 | 3 | 4 | 2.5 | 1.5 | 6 | 2.5 | 2.5 | 4 | 3 | 4 | 3 | 6 | 2.5 | 4 | 5 | 2 | 3 | 1.5 | 6 | 3 | 2 | 4 | 5 | 3 | 2 | 4 | 2.5 | 1.5 | 2.5 | 1.5 | 3 | 2.5
130 | 19 | 15.5 | 22 | 34.5 | 50.5 | 63.5 | 72.5 | 86 | 103.5 | 120.5 | 132.5 | 145 | 159 | 171.5 | 4 | 2.5 | 6 | 3 | 1.5 | 2 | 1.5 | 1.5 | 2.5 | 4 | 3 | 3 | 3 | 4 | 3 | 6 | 5 | 2.5 | 2.5 | 3 | 1.5 | 2.5 | 3 | 2 | 4 | 1.5 | 2 | 6 | 6 | 5 | 4 | 2.5 | 5 | 3 | 6 | 3 | 4 | 2.5 | 3 | 2.5 | 2.5 | 5 | 3 | 2 | 5 | 1.5 | 1.5 | 6 | 4 | 3 | 3 | 2.5
131 | 18.5 | 14 | 23.5 | 36.5 | 46 | 53 | 64.5 | 72 | 81.5 | 96.5 | 106 | 116.5 | 133 | 147 | 4 | 3 | 3 | 4 | 1.5 | 3 | 2 | 3 | 2 | 5 | 2 | 4 | 3 | 2 | 2 | 2.5 | 1.5 | 1.5 | 2.5 | 1.5 | 4 | 1.5 | 3 | 3 | 3 | 1.5 | 1.5 | 1.5 | 3 | 2.5 | 2 | 2 | 3 | 4 | 5 | 3 | 2.5 | 3 | 1.5 | 2.5 | 3 | 2.5 | 2 | 3 | 6 | 5 | 3 | 2.5 | 3 | 2 | 5 | 4
132 | 18 | 12.5 | 25 | 36.5 | 49 | 60.5 | 73.5 | 88 | 103.5 | 120 | 132 | 149 | 159.5 | 173 | 1.5 | 4 | 5 | 2 | 2.5 | 3 | 4 | 3 | 3 | 2.5 | 3 | 3 | 3 | 4 | 4 | 1.5 | 3 | 4 | 2.5 | 2 | 2 | 6 | 2 | 3 | 2.5 | 6 | 3 | 3 | 2.5 | 4 | 3 | 6 | 4 | 1.5 | 5 | 6 | 2.5 | 1.5 | 5 | 3 | 6 | 5 | 3 | 3 | 2 | 2.5 | 4 | 2 | 3 | 6 | 3 | 1.5
133 | 21 | 13 | 27 | 41.5 | 53.5 | 62 | 78 | 93.5 | 101 | 113.5 | 129.5 | 140 | 155.5 | 168.5 | 2 | 2 | 3 | 6 | 6 | 2 | 3 | 3 | 3 | 1.5 | 5 | 5 | 2.5 | 5 | 2.5 | 2 | 2.5 | 1.5 | 2 | 2.5 | 2.5 | 6 | 6 | 1.5 | 5 | 1.5 | 6 | 3 | 2 | 1.5 | 1.5 | 2.5 | 4 | 2.5 | 4 | 2 | 3 | 5 | 5 | 3 | 3 | 2 | 2.5 | 3 | 1.5 | 5 | 6 | 3 | 3 | 3 | 5 | 2
134 | 21.5 | 17 | 28.5 | 47 | 59 | 73 | 82.5 | 94.5 | 106.5 | 122.5 | 137 | 145.5 | 157 | 171 | 6 | 6 | 2 | 3 | 3 | 1.5 | 4 | 3 | 5 | 6 | 6 | 1.5 | 5 | 3 | 1.5 | 2.5 | 4 | 2.5 | 1.5 | 6 | 3 | 1.5 | 2 | 3 | 4 | 4 | 1.5 | 2.5 | 2.5 | 2.5 | 3 | 4 | 4 | 3 | 3 | 6 | 6 | 4 | 2.5 | 2 | 1.5 | 2 | 3 | 2 | 3 | 3 | 1.5 | 4 | 3 | 5 | 3 | 3
135 | 19.5 | 12 | 25.5 | 40.5 | 59.5 | 69.5 | 87.5 | 102 | 112.5 | 125.5 | 140 | 158 | 170.5 | 187.5 | 4 | 3 | 2 | 3 | 5 | 2.5 | 2 | 4 | 4 | 4 | 4 | 3 | 5 | 5 | 3 | 6 | 1.5 | 5 | 1.5 | 2 | 3 | 5 | 6 | 4 | 4 | 2.5 | 5 | 3 | 5 | 1.5 | 2.5 | 1.5 | 4 | 4 | 2.5 | 2.5 | 3 | 2.5 | 4 | 5 | 5 | 5 | 3 | 5 | 1.5 | 3 | 4 | 4 | 5 | 3 | 3 | 6
136 | 17 | 13 | 22 | 35 | 47.5 | 62.5 | 74.5 | 87.5 | 101 | 110 | 122.5 | 130.5 | 143.5 | 155 | 6 | 2 | 2.5 | 2.5 | 2 | 2 | 3 | 2 | 3 | 3 | 4 | 3 | 2.5 | 2 | 4 | 4 | 3 | 5 | 3 | 4 | 2 | 3 | 5 | 2 | 6 | 2 | 3 | 2 | 3 | 4 | 4 | 2.5 | 1.5 | 3 | 2.5 | 2 | 1.5 | 2 | 6 | 3 | 1.5 | 1.5 | 2 | 3 | 4 | 3 | 3 | 3 | 2 | 5 | 3 | 1.5
137 | 23 | 15.5 | 28.5 | 40.5 | 50.5 | 64 | 77 | 89 | 107 | 123 | 136.5 | 153.5 | 169.5 | 183.5 | 6 | 3 | 4 | 2.5 | 2.5 | 5 | 4 | 1.5 | 2 | 3 | 4 | 3 | 2 | 3 | 2 | 3 | 4 | 3 | 5 | 1.5 | 2.5 | 5 | 3 | 2.5 | 4 | 2.5 | 3 | 2.5 | 5 | 4 | 5 | 4 | 3 | 2 | 6 | 5 | 6 | 2.5 | 2 | 3 | 6 | 2 | 6 | 3 | 6 | 2 | 3 | 5 | 3 | 3 | 6 | 2
138 | 26 | 15 | 30.5 | 42 | 56.5 | 70.5 | 87.5 | 102.5 | 117 | 127.5 | 142.5 | 157 | 170 | 183 | 2 | 3 | 4 | 6 | 6 | 5 | 2 | 2.5 | 4 | 2.5 | 3 | 2 | 6 | 2.5 | 3 | 3 | 2 | 6 | 3 | 3 | 3 | 3 | 5 | 6 | 6 | 3 | 2 | 4 | 3 | 3 | 6 | 2.5 | 2 | 1.5 | 4 | 3 | 5 | 5 | 2.5 | 2.5 | 2 | 1.5 | 6 | 5 | 3 | 3 | 4 | 3 | 2 | 3 | 3 | 5
139 | 26.5 | 18 | 29.5 | 42 | 55 | 69.5 | 85.5 | 102.5 | 113.5 | 126 | 139 | 154.5 | 169.5 | 183 | 5 | 4 | 4 | 5 | 2.5 | 6 | 1.5 | 1.5 | 2 | 2.5 | 2 | 6 | 5 | 2 | 3 | 3 | 5 | 4 | 4 | 1.5 | 4 | 3 | 3 | 6 | 5 | 2 | 4 | 6 | 2.5 | 3 | 2.5 | 3 | 2 | 1.5 | 5 | 4 | 4 | 4 | 3 | 2 | 5 | 3 | 5 | 2.5 | 3 | 3 | 3 | 6 | 3 | 5 | 4 | 1.5
140 | 18.5 | 9.5 | 27.5 | 38 | 53.5 | 68.5 | 78.5 | 94 | 111 | 122.5 | 137 | 155 | 168.5 | 183.5 | 2.5 | 2.5 | 1.5 | 3 | 5 | 4 | 6 | 3 | 2.5 | 3 | 3 | 2 | 2.5 | 5 | 4 | 4 | 4 | 6 | 2 | 3 | 3 | 1.5 | 2.5 | 3 | 6 | 1.5 | 3 | 5 | 5 | 3 | 3 | 6 | 3 | 2.5 | 3 | 3 | 4 | 3 | 2.5 | 5 | 4 | 5 | 5 | 4 | 3 | 6 | 1.5 | 3 | 2 | 2 | 6 | 5
141 | 24 | 17 | 29.5 | 42.5 | 56 | 71 | 81.5 | 93.5 | 107 | 121.5 | 138 | 154 | 165.5 | 178.5 | 4 | 4 | 3 | 6 | 4 | 3 | 2.5 | 3 | 2 | 5 | 2 | 4 | 3 | 1.5 | 4 | 5 | 3 | 3 | 5 | 4 | 3 | 1.5 | 4 | 2 | 4 | 3 | 2 | 3 | 4 | 2 | 6 | 1.5 | 3 | 6 | 4 | 1.5 | 6 | 1.5 | 4 | 5 | 3 | 4 | 3 | 6 | 2 | 1.5 | 4 | 4 | 2 | 2.5 | 2.5 | 6
142 | 22 | 15 | 28 | 39 | 54.5 | 67 | 78 | 88 | 100 | 116.5 | 130 | 145 | 164 | 178 | 2.5 | 2.5 | 5 | 5 | 2 | 5 | 3 | 3 | 2 | 2 | 3 | 4 | 5 | 5 | 1.5 | 4 | 6 | 1.5 | 2 | 3 | 2.5 | 2.5 | 3 | 3 | 3 | 2.5 | 2.5 | 2 | 4 | 2 | 3 | 3 | 2.5 | 3 | 5 | 6 | 1.5 | 4 | 4 | 4 | 5 | 4 | 3 | 3 | 5 | 6 | 4 | 4 | 2.5 | 5 | 4 | 2.5
143 | 14.5 | 9 | 22.5 | 42 | 52.5 | 66.5 | 80 | 92 | 108 | 123 | 136 | 150.5 | 169.5 | 180 | 2 | 2.5 | 1.5 | 3 | 4 | 1.5 | 5 | 3 | 6 | 6 | 6 | 1.5 | 2 | 2 | 5 | 1.5 | 3 | 4 | 4 | 3 | 4 | 2.5 | 4 | 3 | 5 | 1.5 | 3 | 2.5 | 5 | 4 | 3 | 4 | 2 | 2 | 5 | 6 | 2 | 4 | 3 | 4 | 2 | 6 | 5 | 1.5 | 4 | 6 | 6 | 3 | 3 | 1.5 | 3 | 3
144 | 27 | 18 | 37 | 48 | 63 | 77 | 86.5 | 96.5 | 113 | 126.5 | 140 | 153.5 | 166 | 179.5 | 5 | 6 | 5 | 2 | 6 | 3 | 5 | 5 | 2.5 | 2 | 5 | 1.5 | 1.5 | 6 | 5 | 2.5 | 2 | 2 | 4 | 6 | 2 | 3 | 2.5 | 2 | 3 | 3 | 2 | 2 | 2 | 6 | 2.5 | 6 | 3 | 2.5 | 5 | 3 | 1.5 | 3 | 6 | 3 | 3 | 6 | 1.5 | 3 | 1.5 | 2 | 5 | 4 | 2.5 | 3 | 6 | 2
145 | 18 | 12 | 23 | 40 | 53 | 65.5 | 78 | 95 | 107 | 121 | 139 | 154 | 167 | 184 | 3 | 3 | 3 | 3 | 4 | 2 | 3 | 2 | 3 | 5 | 3 | 6 | 2.5 | 6 | 2 | 2.5 | 3 | 2.5 | 3 | 4 | 4 | 1.5 | 5 | 2 | 6 | 2.5 | 2.5 | 6 | 1.5 | 1.5 | 6 | 3 | 3 | 5 | 3 | 3 | 6 | 6 | 3 | 3 | 2 | 5 | 4 | 4 | 1.5 | 4 | 5 | 2.5 | 4 | 3 | 4 | 6
146 | 25 | 15 | 28.5 | 41 | 57 | 74 | 88 | 98.5 | 115.5 | 126 | 139 | 153.5 | 168 | 186 | 5 | 3 | 2 | 5 | 4 | 6 | 2 | 1.5 | 4 | 2 | 1.5 | 5 | 3 | 5 | 5 | 3 | 6 | 3 | 4 | 4 | 3 | 6 | 2 | 3 | 2.5 | 2.5 | 4 | 1.5 | 3 | 5 | 5 | 4 | 3 | 2 | 2.5 | 3 | 2.5 | 1.5 | 6 | 3 | 3 | 4 | 2.5 | 5 | 4 | 3 | 2.5 | 5 | 5 | 6 | 2 | 5
147 | 24 | 16 | 32 | 47.5 | 58.5 | 72 | 86 | 101.5 | 112.5 | 127.5 | 143 | 155.5 | 169.5 | 180 | 1.5 | 6 | 2.5 | 6 | 3 | 5 | 6 | 2 | 6 | 5 | 1.5 | 3 | 2.5 | 1.5 | 5 | 2 | 4 | 3 | 2.5 | 4 | 3 | 4 | 3 | 4 | 4 | 4 | 5 | 2.5 | 2 | 2.5 | 5 | 1.5 | 5 | 3 | 3 | 4 | 3 | 5 | 6 | 1.5 | 2.5 | 3 | 5 | 2 | 3 | 5 | 3 | 3 | 3 | 3 | 1.5 | 3
148 | 15.5 | 7.5 | 19.5 | 30 | 41.5 | 55.5 | 71.5 | 81.5 | 98.5 | 111.5 | 124 | 138 | 149.5 | 159.5 | 1.5 | 1.5 | 3 | 1.5 | 6 | 2 | 2.5 | 1.5 | 2 | 1.5 | 2 | 5 | 2 | 5 | 3 | 1.5 | 3 | 5 | 3 | 3 | 6 | 3 | 5 | 2 | 1.5 | 4 | 2 | 2.5 | 4 | 5 | 4 | 4 | 6 | 3 | 2 | 2 | 3 | 4 | 3 | 2.5 | 6 | 2 | 3 | 3 | 2 | 5 | 3 | 1.5 | 2 | 1.5 | 2.5 | 4
149 | 15 | 10.5 | 24 | 36.5 | 51.5 | 65.5 | 79 | 86 | 94.5 | 111.5 | 125.5 | 141 | 157 | 173 | 2 | 4 | 1.5 | 3 | 3 | 1.5 | 4 | 5 | 2.5 | 2 | 5 | 3 | 3 | 4 | 3 | 5 | 3 | 3 | 6 | 2 | 6 | 3 | 3 | 1.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 2 | 2 | 3 | 6 | 3 | 3 | 5 | 2 | 5 | 5 | 2 | 3 | 1.5 | 6 | 5 | 5 | 3 | 6 | 2 | 3 | 3 | 6 | 4
150 | 24.5 | 17 | 28 | 40 | 57 | 71 | 82 | 97.5 | 113.5 | 126.5 | 141 | 152 | 160.5 | 173 | 2.5 | 6 | 2.5 | 6 | 5 | 2.5 | 1.5 | 2 | 5 | 3 | 2.5 | 1.5 | 6 | 3 | 6 | 2 | 4 | 5 | 2 | 3 | 3 | 4 | 2.5 | 1.5 | 3 | 2.5 | 5 | 5 | 5 | 5 | 4 | 2 | 3 | 2 | 4 | 4 | 3 | 5 | 1.5 | 5 | 2 | 4 | 2 | 3 | 1.5 | 1.5 | 1.5 | 4 | 3 | 1.5 | 2 | 6
151 | 16 | 11.5 | 25 | 41 | 55 | 62.5 | 73.5 | 91 | 100.5 | 110 | 124.5 | 141.5 | 153.5 | 164 | 2 | 3 | 5 | 1.5 | 1.5 | 3 | 5 | 4 | 4 | 4 | 2 | 6 | 5 | 3 | 3 | 3 | 1.5 | 1.5 | 3 | 1.5 | 3 | 4 | 2.5 | 1.5 | 3 | 6 | 2.5 | 6 | 3 | 1.5 | 3 | 2 | 2 | 1.5 | 3 | 3 | 4 | 3 | 6 | 1.5 | 6 | 4 | 3 | 4 | 2 | 5 | 3 | 2 | 3 | 3 | 3 | 1.5
152 | 22 | 14 | 27.5 | 42 | 60.5 | 77 | 87.5 | 106.5 | 120 | 135.5 | 149.5 | 165 | 174.5 | 186 | 4 | 2 | 5 | 3 | 3 | 5 | 3 | 2.5 | 5 | 2.5 | 4 | 3 | 6 | 5 | 2.5 | 5 | 1.5 | 6 | 5 | 4 | 2 | 3 | 1.5 | 4 | 5 | 6 | 5 | 3 | 2.5 | 3 | 3 | 5 | 6 | 5 | 2 | 2.5 | 3 | 4 | 4 | 3 | 3 | 6 | 2.5 | 4 | 1.5 | 2.5 | 4 | 1.5 | 3 | 3 | 3 | 2.5
153 | 16.5 | 8 | 24 | 34.5 | 50 | 64 | 75 | 85 | 104 | 122 | 132 | 147.5 | 166.5 | 180.5 | 3 | 1.5 | 2 | 1.5 | 6 | 2.5 | 1.5 | 6 | 3 | 3 | 2.5 | 2 | 5 | 3 | 1.5 | 6 | 3 | 4 | 5 | 2 | 2.5 | 3 | 2.5 | 3 | 2.5 | 3 | 3 | 1.5 | 6 | 4 | 5 | 4 | 5 | 3 | 6 | 4 | 2 | 1.5 | 2.5 | 4 | 4 | 2.5 | 4 | 5 | 5 | 6 | 3 | 5 | 2 | 3 | 3 | 6
154 | 26 | 20.5 | 31 | 44 | 60 | 78 | 89 | 101.5 | 113 | 124 | 132 | 144 | 157.5 | 173.5 | 6 | 2.5 | 6 | 6 | 2.5 | 3 | 2 | 3 | 2.5 | 4 | 4 | 2.5 | 5 | 5 | 3 | 3 | 6 | 6 | 3 | 3 | 2 | 2 | 3 | 4 | 1.5 | 5 | 2 | 4 | 5 | 2 | 1.5 | 3 | 2 | 2.5 | 2.5 | 4 | 2.5 | 2 | 2 | 1.5 | 3 | 4 | 3 | 2 | 3 | 2.5 | 6 | 2 | 6 | 6 | 2.5 | 1.5
155 | 25.5 | 14.5 | 31.5 | 45.5 | 59 | 69.5 | 78 | 93 | 105 | 117.5 | 131.5 | 148.5 | 159.5 | 175.5 | 3 | 2.5 | 3 | 6 | 5 | 6 | 3 | 3 | 2 | 5 | 5 | 2 | 2.5 | 3 | 5 | 3 | 1.5 | 5 | 2 | 2 | 2 | 2 | 2.5 | 2 | 3 | 4 | 4 | 4 | 3 | 3 | 4 | 2 | 2.5 | 5 | 2 | 3 | 3 | 4 | 4 | 3 | 4 | 5 | 3 | 5 | 3 | 2 | 4 | 2 | 3 | 3 | 6 | 4
156 | 20.5 | 13.5 | 25 | 34 | 47.5 | 58.5 | 67.5 | 81 | 94 | 106 | 123 | 138.5 | 150 | 160.5 | 3 | 4 | 4 | 2.5 | 5 | 2 | 1.5 | 3 | 1.5 | 1.5 | 3 | 3 | 5 | 2 | 4 | 2.5 | 3 | 2 | 4 | 2 | 1.5 | 2 | 4 | 1.5 | 3 | 1.5 | 3 | 6 | 1.5 | 2.5 | 3 | 6 | 1.5 | 3 | 6 | 1.5 | 3 | 3 | 5 | 6 | 3 | 1.5 | 5 | 6 | 3 | 1.5 | 3 | 4 | 2 | 3 | 4 | 1.5
157 | 20.5 | 14.5 | 26.5 | 36 | 49.5 | 58 | 69.5 | 84 | 95.5 | 111.5 | 122.5 | 137 | 153 | 168 | 5 | 4 | 3 | 2.5 | 4 | 2 | 4 | 2 | 2 | 3 | 2.5 | 2 | 2 | 3 | 6 | 2.5 | 3 | 2 | 2 | 1.5 | 1.5 | 6 | 1.5 | 2.5 | 2 | 5 | 2.5 | 5 | 3 | 4 | 3 | 1.5 | 4 | 3 | 5 | 4 | 3 | 2 | 3 | 3 | 3 | 6 | 2.5 | 3 | 2 | 6 | 2 | 6 | 6 | 2 | 2 | 5
158 | 23 | 11 | 33 | 49.5 | 64.5 | 85.5 | 97.5 | 108 | 124 | 142 | 159 | 169 | 188 | 205 | 5 | 1.5 | 1.5 | 3 | 6 | 6 | 4 | 6 | 1.5 | 6 | 5 | 4 | 3 | 2 | 5 | 5 | 6 | 3 | 6 | 6 | 2 | 4 | 3 | 3 | 4 | 2 | 3 | 1.5 | 4 | 4 | 5 | 3 | 4 | 6 | 5 | 3 | 3 | 6 | 3 | 5 | 2 | 4 | 1.5 | 2.5 | 6 | 4 | 6 | 3 | 6 | 2 | 6 | 3
159 | 14.5 | 10 | 19.5 | 34.5 | 47 | 56.5 | 65.5 | 79 | 97 | 111.5 | 123.5 | 135.5 | 149.5 | 165 | 2.5 | 1.5 | 2 | 4 | 1.5 | 3 | 2 | 3 | 5 | 2 | 2 | 6 | 2 | 2 | 6 | 2.5 | 1.5 | 2.5 | 2.5 | 3 | 2 | 1.5 | 4 | 1.5 | 3 | 5 | 3 | 2.5 | 6 | 3 | 3 | 6 | 6 | 2.5 | 2 | 4 | 4 | 4 | 2.5 | 1.5 | 3 | 3 | 2 | 4 | 2.5 | 3 | 2.5 | 6 | 2.5 | 5 | 6 | 2
160 | 16.5 | 11.5 | 21.5 | 34 | 49 | 63 | 75.5 | 93.5 | 107 | 119.5 | 138 | 150 | 163.5 | 174 | 4 | 2.5 | 2 | 3 | 2 | 3 | 3 | 2 | 2 | 3 | 2.5 | 5 | 6 | 1.5 | 6 | 1.5 | 5 | 4 | 2 | 3 | 6 | 1.5 | 3 | 2 | 6 | 3 | 6 | 3 | 6 | 2 | 3 | 2.5 | 1.5 | 4 | 2 | 5 | 5 | 6 | 1.5 | 6 | 3 | 4 | 3 | 2 | 4 | 4 | 2.5 | 3 | 2 | 2.5 | 2 | 4
161 | 19 | 10 | 28 | 43 | 55 | 71 | 80 | 96 | 110 | 120.5 | 134.5 | 145.5 | 154.5 | 167.5 | 2 | 3 | 3 | 2 | 3 | 6 | 6 | 3 | 6 | 3 | 3 | 3 | 3 | 2 | 5 | 2 | 5 | 4 | 4 | 3 | 1.5 | 1.5 | 4 | 2 | 4 | 4 | 5 | 3 | 3 | 2 | 3 | 6 | 1.5 | 3 | 3 | 3 | 3 | 3 | 2 | 6 | 1.5 | 4 | 2.5 | 3 | 2 | 1.5 | 3 | 2.5 | 2.5 | 2.5 | 4 | 4
162 | 24 | 18 | 32 | 42.5 | 52.5 | 67 | 80 | 91.5 | 104 | 122.5 | 136.5 | 144.5 | 161.5 | 171.5 | 3 | 6 | 6 | 3 | 3 | 3 | 6 | 2 | 1.5 | 4 | 2 | 3 | 3 | 2.5 | 3 | 1.5 | 2 | 5 | 2.5 | 5 | 1.5 | 6 | 3 | 2.5 | 4 | 1.5 | 3 | 3 | 3 | 3 | 1.5 | 5 | 2.5 | 6 | 5 | 5 | 5 | 2 | 5 | 2 | 1.5 | 2 | 2 | 2.5 | 4 | 5 | 6 | 2 | 2.5 | 3 | 3 | 1.5
163 | 22 | 13 | 28.5 | 45.5 | 55 | 68.5 | 85 | 103 | 118.5 | 127 | 136.5 | 149 | 165 | 180.5 | 3 | 3 | 3 | 4 | 5 | 4 | 5 | 1.5 | 3 | 6 | 3 | 5 | 2 | 4 | 1.5 | 2 | 4 | 4 | 3 | 2.5 | 6 | 1.5 | 3 | 6 | 4 | 6 | 2 | 6 | 3 | 5 | 2.5 | 5 | 2 | 2 | 3 | 1.5 | 3 | 2 | 1.5 | 3 | 3 | 3 | 5 | 1.5 | 3 | 6 | 4 | 3 | 5 | 3 | 1.5 | 6
164 | 19 | 14 | 24 | 40.5 | 53 | 67.5 | 76 | 90 | 104 | 121 | 136.5 | 150 | 162.5 | 175 | 2 | 3 | 4 | 5 | 2.5 | 2.5 | 2 | 3 | 6 | 6 | 3 | 1.5 | 2.5 | 3 | 3 | 4 | 6 | 1.5 | 4 | 3 | 1.5 | 1.5 | 2.5 | 3 | 4 | 3 | 3 | 4 | 4 | 5 | 2 | 3 | 3 | 5 | 3 | 6 | 5 | 6 | 1.5 | 3 | 1.5 | 6 | 2 | 4 | 4 | 2.5 | 3 | 3 | 4 | 3 | 3 | 2.5
165 | 19.5 | 14.5 | 24.5 | 36.5 | 48.5 | 63.5 | 80.5 | 96.5 | 111.5 | 123 | 133.5 | 148 | 161.5 | 178 | 2.5 | 3 | 3 | 6 | 3 | 2 | 2 | 3 | 2 | 3 | 4 | 3 | 6 | 2 | 2.5 | 1.5 | 3 | 3 | 6 | 3 | 2 | 6 | 6 | 3 | 2 | 5 | 6 | 3 | 5 | 6 | 1.5 | 2.5 | 2 | 2 | 1.5 | 6 | 3 | 3 | 2 | 2.5 | 5 | 5 | 1.5 | 3 | 4 | 1.5 | 3 | 5 | 5 | 2.5 | 6 | 3
166 | 22 | 14 | 29 | 46 | 63 | 71.5 | 86.5 | 101 | 116 | 132 | 142 | 157 | 179 | 196.5 | 3 | 3 | 6 | 2 | 3 | 5 | 3 | 4 | 3 | 6 | 4 | 4 | 6 | 5 | 3 | 3 | 1.5 | 3 | 2.5 | 1.5 | 3 | 2 | 4 | 6 | 5 | 2.5 | 4 | 3 | 3 | 3 | 6 | 3 | 6 | 3 | 4 | 3 | 1.5 | 5 | 2 | 1.5 | 4 | 2 | 3 | 6 | 4 | 6 | 6 | 6 | 5 | 1.5 | 6 | 5
167 | 19.5 | 11.5 | 27.5 | 46.5 | 59.5 | 72 | 84 | 92.5 | 106 | 117 | 128 | 146 | 160.5 | 176 | 4 | 1.5 | 3 | 3 | 5 | 3 | 5 | 3 | 3 | 4 | 6 | 6 | 3 | 2 | 3 | 5 | 4 | 1.5 | 4 | 3 | 4 | 2 | 3 | 3 | 1.5 | 3 | 2 | 2 | 5 | 2.5 | 3 | 3 | 4 | 2 | 2.5 | 2.5 | 3 | 1.5 | 1.5 | 5 | 5 | 2 | 6 | 5 | 6 | 3 | 2.5 | 3 | 2.5 | 6 | 3 | 4
168 | 22 | 15 | 32 | 46 | 60 | 78 | 89.5 | 107.5 | 119.5 | 129 | 141.5 | 154 | 171.5 | 183.5 | 3 | 3 | 3 | 6 | 5 | 2 | 4 | 6 | 2.5 | 4 | 6 | 1.5 | 4 | 3 | 3 | 4 | 5 | 3 | 5 | 5 | 4 | 1.5 | 3 | 3 | 6 | 3 | 6 | 3 | 3 | 1.5 | 5 | 2.5 | 3 | 1.5 | 2 | 3 | 4 | 3 | 4 | 1.5 | 1.5 | 4 | 2 | 5 | 5 | 2.5 | 6 | 4 | 1.5 | 6 | 3 | 1.5
169 | 12 | 8.5 | 17.5 | 29.5 | 38 | 50.5 | 58.5 | 69 | 83 | 93 | 108 | 121 | 134.5 | 149 | 2 | 2 | 3 | 1.5 | 2 | 1.5 | 3 | 2.5 | 6 | 1.5 | 3 | 1.5 | 3 | 1.5 | 1.5 | 2.5 | 3 | 3 | 4 | 2.5 | 2 | 1.5 | 1.5 | 3 | 2.5 | 2 | 3 | 3 | 3 | 3 | 3 | 5 | 2.5 | 2 | 4 | 1.5 | 4 | 6 | 2 | 3 | 2.5 | 5 | 4 | 1.5 | 3 | 5 | 2.5 | 3 | 6 | 2.5 | 3 | 3
170 | 19 | 15.5 | 26 | 36 | 47.5 | 63.5 | 78.5 | 91 | 104.5 | 115.5 | 128.5 | 143.5 | 156.5 | 169.5 | 5 | 3 | 5 | 2.5 | 2 | 1.5 | 5 | 2 | 2 | 3 | 3 | 2 | 4 | 1.5 | 3 | 3 | 3 | 6 | 4 | 3 | 6 | 2 | 2 | 5 | 2 | 4 | 1.5 | 5 | 6 | 2 | 3 | 2.5 | 2 | 3 | 2 | 4 | 1.5 | 2.5 | 3 | 6 | 6 | 5 | 2.5 | 1.5 | 1.5 | 2.5 | 4 | 5 | 5 | 4 | 2 | 2
171 | 20 | 14.5 | 26.5 | 44 | 61 | 74.5 | 87.5 | 97 | 111 | 123.5 | 135.5 | 153 | 169.5 | 183.5 | 1.5 | 4 | 3 | 6 | 2.5 | 3 | 4 | 2.5 | 2.5 | 6 | 3 | 6 | 3 | 3 | 6 | 5 | 2.5 | 4 | 5 | 2 | 1.5 | 4 | 1.5 | 6 | 1.5 | 2 | 3 | 3 | 5 | 3 | 2 | 4 | 6 | 3 | 2 | 1.5 | 2 | 6 | 1.5 | 2.5 | 5 | 5 | 6 | 1.5 | 5 | 3 | 6 | 2.5 | 2 | 4 | 5 | 3
172 | 16.5 | 11 | 25.5 | 36 | 46 | 67 | 84.5 | 98.5 | 109 | 122.5 | 133 | 148.5 | 164.5 | 176.5 | 4 | 3 | 1.5 | 2.5 | 3 | 2.5 | 5 | 4 | 2.5 | 4 | 2 | 2 | 2.5 | 3 | 3 | 1.5 | 6 | 3 | 6 | 6 | 1.5 | 5 | 5 | 6 | 3 | 3 | 3 | 5 | 1.5 | 5 | 1.5 | 2.5 | 3 | 5 | 1.5 | 4 | 3 | 1.5 | 2 | 4 | 5 | 2.5 | 4 | 4 | 3 | 5 | 3 | 5 | 3 | 5 | 2.5 | 1.5
173 | 19 | 16 | 23 | 36.5 | 58.5 | 72 | 86 | 98 | 108.5 | 120.5 | 135.5 | 150 | 162 | 174.5 | 3 | 6 | 3 | 4 | 1.5 | 1.5 | 1.5 | 2.5 | 6 | 2.5 | 2 | 3 | 6 | 6 | 5 | 5 | 3 | 2.5 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 3 | 3 | 4 | 2.5 | 2.5 | 3 | 2.5 | 4 | 3 | 2.5 | 2.5 | 3 | 5 | 5 | 2 | 6 | 3 | 2.5 | 3 | 3 | 1.5 | 6 | 1.5 | 2.5 | 3 | 4 | 3
174 | 18 | 12 | 22 | 35.5 | 44.5 | 56 | 72 | 84.5 | 97.5 | 114.5 | 124 | 136.5 | 148.5 | 160.5 | 1.5 | 1.5 | 6 | 3 | 2 | 4 | 2.5 | 1.5 | 1.5 | 3 | 3 | 6 | 3 | 1.5 | 1.5 | 3 | 3 | 5 | 1.5 | 2 | 3 | 2 | 6 | 5 | 3 | 3 | 2.5 | 4 | 5 | 2.5 | 2.5 | 3 | 6 | 6 | 2.5 | 2.5 | 3 | 3 | 2 | 1.5 | 4 | 2 | 5 | 1.5 | 1.5 | 3 | 1.5 | 6 | 2.5 | 4 | 1.5 | 4
175 | 20.5 | 11.5 | 30.5 | 41 | 52 | 60.5 | 82.5 | 92.5 | 106 | 121 | 134 | 148 | 157.5 | 175 | 2.5 | 2.5 | 1.5 | 5 | 4 | 5 | 5 | 5 | 3 | 4 | 1.5 | 2 | 4 | 2 | 2 | 3 | 2 | 1.5 | 2 | 3 | 5 | 6 | 5 | 6 | 4 | 1.5 | 1.5 | 3 | 2 | 6 | 4 | 1.5 | 2 | 6 | 4 | 3 | 3 | 5 | 2 | 3 | 6 | 4 | 2 | 2 | 2 | 3 | 1.5 | 3 | 6 | 2.5 | 3 | 6
176 | 20 | 15.5 | 24.5 | 42.5 | 55 | 67 | 83 | 97 | 107 | 126 | 137 | 148.5 | 162 | 182 | 1.5 | 5 | 4 | 5 | 3 | 1.5 | 1.5 | 3 | 6 | 4 | 6 | 2 | 3 | 2.5 | 3 | 4 | 2 | 2 | 3 | 5 | 5 | 4 | 4 | 3 | 2.5 | 1.5 | 4 | 6 | 2 | 5 | 1.5 | 1.5 | 4 | 6 | 6 | 3 | 3 | 4 | 2.5 | 1.5 | 2 | 2.5 | 5 | 2 | 1.5 | 6 | 4 | 2 | 6 | 5 | 3 | 6
177 | 15 | 7 | 19.5 | 32 | 46.5 | 59.5 | 74 | 85 | 99 | 115 | 134 | 144.5 | 159 | 175.5 | 1.5 | 1.5 | 1.5 | 2.5 | 3 | 5 | 1.5 | 3 | 3 | 1.5 | 3 | 5 | 5 | 4 | 2.5 | 3 | 2.5 | 6 | 3 | 1.5 | 6 | 2 | 1.5 | 5 | 2.5 | 4 | 2 | 2.5 | 3 | 4 | 4 | 3 | 5 | 2 | 3 | 6 | 6 | 3 | 6 | 4 | 1.5 | 3 | 3 | 3 | 1.5 | 4 | 6 | 3 | 3 | 1.5 | 6 | 6
178 | 12 | 7.5 | 16.5 | 32.5 | 51.5 | 64.5 | 79 | 93 | 106 | 120.5 | 137 | 151 | 162.5 | 171.5 | 1.5 | 1.5 | 1.5 | 3 | 1.5 | 3 | 2.5 | 2 | 3 | 6 | 4 | 3 | 6 | 6 | 5 | 2 | 2.5 | 1.5 | 4 | 5 | 1.5 | 3 | 4 | 6 | 1.5 | 2.5 | 5 | 5 | 3 | 2 | 3 | 5 | 1.5 | 4 | 3 | 6 | 6 | 2.5 | 5 | 3 | 4 | 2 | 6 | 2 | 4 | 4 | 2 | 1.5 | 1.5 | 3 | 1.5 | 3
179 | 22 | 11 | 28 | 50 | 64 | 80 | 92 | 103.5 | 114 | 129 | 146 | 159.5 | 174.5 | 187 | 3 | 2.5 | 3 | 2.5 | 6 | 5 | 3 | 3 | 5 | 6 | 6 | 5 | 6 | 1.5 | 1.5 | 5 | 3 | 4 | 6 | 3 | 4 | 4 | 2.5 | 1.5 | 2 | 3 | 2.5 | 4 | 2.5 | 2.5 | 2.5 | 3 | 1.5 | 6 | 5 | 2.5 | 3 | 3 | 6 | 5 | 4 | 1.5 | 5 | 3 | 5 | 1.5 | 2.5 | 6 | 1.5 | 2 | 4 | 5
180 | 20.5 | 16 | 26.5 | 33.5 | 43.5 | 52.5 | 66.5 | 79.5 | 92 | 103.5 | 119.5 | 130 | 143.5 | 155.5 | 6 | 2.5 | 2.5 | 5 | 1.5 | 3 | 3 | 3 | 2 | 1.5 | 2 | 1.5 | 2 | 3 | 3 | 2 | 1.5 | 2 | 2.5 | 3 | 6 | 1.5 | 2.5 | 4 | 6 | 2 | 3 | 2 | 2.5 | 4 | 2 | 4 | 2 | 1.5 | 3 | 5 | 4 | 4 | 5 | 3 | 3 | 2.5 | 2.5 | 2.5 | 6 | 2 | 2.5 | 3 | 2 | 2 | 3 | 5
181 | 23 | 15 | 32 | 47 | 58 | 72.5 | 83 | 95.5 | 105.5 | 123 | 140 | 156.5 | 167 | 179.5 | 2 | 4 | 3 | 6 | 4 | 4 | 6 | 3 | 3 | 6 | 3 | 3 | 4 | 1.5 | 2.5 | 3 | 5 | 4 | 3 | 2.5 | 2.5 | 4 | 2 | 2 | 4 | 4 | 2.5 | 2 | 4 | 1.5 | 3 | 1.5 | 6 | 4 | 6 | 1.5 | 6 | 4 | 2 | 5 | 6 | 5 | 2.5 | 3 | 3 | 2.5 | 2 | 3 | 5 | 3 | 3 | 1.5
182 | 22 | 16 | 33 | 46.5 | 57 | 68 | 80.5 | 94.5 | 110.5 | 120 | 137 | 149.5 | 165.5 | 178 | 4 | 4 | 3 | 5 | 3 | 3 | 6 | 5 | 4 | 4 | 3 | 2.5 | 2 | 3 | 3 | 2.5 | 3 | 3 | 3 | 2 | 1.5 | 3 | 6 | 2 | 3 | 5 | 4 | 2 | 2 | 3 | 5 | 6 | 2 | 2.5 | 2 | 3 | 6 | 5 | 3 | 3 | 2.5 | 3 | 4 | 3 | 4 | 2 | 6 | 4 | 5 | 2 | 2.5 | 3
183 | 21 | 13 | 28 | 39.5 | 54.5 | 68.5 | 80.5 | 98 | 112.5 | 120.5 | 132.5 | 141 | 153 | 167.5 | 3 | 5 | 2.5 | 2.5 | 4 | 4 | 2 | 5 | 2.5 | 3 | 3 | 3 | 2.5 | 1.5 | 6 | 5 | 5 | 2.5 | 4 | 2.5 | 2 | 3 | 3 | 4 | 3 | 2.5 | 6 | 6 | 1.5 | 5 | 4 | 4 | 2.5 | 2 | 2 | 1.5 | 3 | 2.5 | 4 | 2.5 | 1.5 | 1.5 | 3 | 2.5 | 2.5 | 5 | 1.5 | 3 | 3 | 6 | 4 | 1.5
184 | 24 | 13 | 33 | 47.5 | 63 | 74.5 | 94.5 | 112.5 | 120 | 132.5 | 148 | 159.5 | 179.5 | 187.5 | 2 | 6 | 2 | 3 | 5 | 6 | 4 | 5 | 1.5 | 6 | 3 | 4 | 6 | 2.5 | 3 | 4 | 3 | 3 | 2.5 | 3 | 5 | 6 | 4 | 5 | 5 | 5 | 5 | 3 | 2 | 1.5 | 2 | 2 | 2.5 | 3 | 4 | 3 | 4 | 5 | 2.5 | 4 | 4 | 4 | 1.5 | 2 | 6 | 4 | 6 | 4 | 2.5 | 1.5 | 2.5 | 1.5
185 | 22.5 | 14 | 32.5 | 45.5 | 54 | 67 | 81.5 | 95.5 | 110.5 | 121.5 | 138 | 147 | 164 | 172.5 | 2.5 | 1.5 | 4 | 6 | 2.5 | 6 | 6 | 4 | 2.5 | 3 | 1.5 | 6 | 2.5 | 1.5 | 1.5 | 3 | 2 | 2 | 6 | 3 | 2 | 5 | 6 | 1.5 | 5 | 2 | 3 | 4 | 3 | 5 | 2 | 5 | 3 | 2 | 4 | 2 | 4 | 2.5 | 5 | 5 | 2.5 | 1.5 | 2 | 3 | 6 | 6 | 2.5 | 2.5 | 3 | 2 | 2 | 1.5
186 | 22.5 | 17.5 | 31.5 | 43 | 54.5 | 73.5 | 86.5 | 102 | 117.5 | 135.5 | 149.5 | 161.5 | 172.5 | 185 | 2.5 | 6 | 5 | 4 | 2 | 3 | 6 | 3 | 1.5 | 2 | 6 | 2 | 2.5 | 3 | 3 | 3 | 4 | 6 | 6 | 3 | 2.5 | 2.5 | 3 | 5 | 6 | 4 | 3 | 2.5 | 4 | 5 | 1.5 | 5 | 6 | 3 | 6 | 3 | 2 | 3 | 3 | 6 | 2.5 | 3 | 5 | 1.5 | 3 | 2.5 | 2.5 | 3 | 4 | 4 | 3 | 1.5
187 | 24 | 16.5 | 30 | 46 | 57 | 68.5 | 80.5 | 92 | 105 | 118 | 130.5 | 138.5 | 156 | 171 | 6 | 5 | 1.5 | 4 | 1.5 | 6 | 3 | 3 | 3 | 2 | 5 | 6 | 1.5 | 5 | 3 | 1.5 | 3 | 2.5 | 4 | 2 | 2.5 | 2.5 | 3 | 4 | 3 | 3 | 3 | 2.5 | 5 | 2 | 3 | 3 | 6 | 2 | 2 | 3 | 4 | 5 | 2 | 1.5 | 2.5 | 2.5 | 1.5 | 1.5 | 4 | 6 | 6 | 1.5 | 6 | 3 | 2 | 4
188 | 13.5 | 9 | 20.5 | 34.5 | 46.5 | 63.5 | 76.5 | 93.5 | 107.5 | 124.5 | 138.5 | 155 | 167.5 | 186 | 1.5 | 2.5 | 3 | 2 | 3 | 1.5 | 4 | 3 | 3 | 3 | 6 | 2 | 2 | 3 | 5 | 2 | 6 | 5 | 3 | 3 | 5 | 3 | 3 | 2 | 3 | 5 | 6 | 3 | 6 | 3 | 2 | 3 | 2 | 3 | 6 | 6 | 6 | 3 | 3 | 2 | 6 | 5 | 2.5 | 3 | 4 | 4 | 3 | 1.5 | 1.5 | 5 | 6 | 6
189 | 15.5 | 11 | 21 | 38 | 52.5 | 70.5 | 86.5 | 103.5 | 115.5 | 133 | 150.5 | 161.5 | 176 | 189 | 1.5 | 2.5 | 5 | 2 | 2 | 2.5 | 3 | 2.5 | 3 | 6 | 5 | 3 | 1.5 | 5 | 3 | 5 | 6 | 3 | 5 | 4 | 5 | 6 | 3 | 2 | 6 | 3 | 3 | 5 | 4 | 3 | 3 | 2 | 3 | 6 | 2.5 | 6 | 6 | 6 | 4 | 1.5 | 4 | 3 | 2 | 2 | 5 | 3 | 1.5 | 5 | 2 | 2 | 6 | 3
190 | 18 | 12 | 29 | 44.5 | 57.5 | 70.5 | 88.5 | 104 | 116.5 | 127.5 | 141.5 | 154 | 168 | 177.5 | 3 | 6 | 1.5 | 1.5 | 3 | 3 | 5 | 6 | 6 | 4 | 1.5 | 4 | 3 | 1.5 | 2.5 | 6 | 3 | 5 | 3 | 2 | 6 | 4 | 6 | 2 | 1.5 | 6 | 4 | 4 | 1.5 | 4 | 3 | 4 | 2.5 | 2.5 | 3 | 3 | 1.5 | 4 | 2.5 | 6 | 4 | 3 | 3 | 2.5 | 2.5 | 1.5 | 5 | 5 | 2 | 2.5 | 2 | 3
191 | 30 | 19 | 37 | 50 | 62.5 | 72.5 | 89 | 105.5 | 118 | 131.5 | 140.5 | 158 | 173.5 | 184.5 | 5 | 6 | 2 | 6 | 6 | 5 | 5 | 2 | 3 | 4 | 3 | 3 | 3 | 3 | 4 | 2.5 | 2.5 | 1.5 | 3 | 3 | 2 | 2.5 | 6 | 6 | 5 | 2.5 | 3 | 6 | 5 | 3 | 3 | 1.5 | 3 | 2.5 | 4 | 4 | 2 | 2.5 | 3 | 1.5 | 5 | 4 | 2.5 | 6 | 2.5 | 6 | 3 | 4 | 1.5 | 4 | 3 | 2.5
192 | 18.5 | 12.5 | 25.5 | 36 | 46 | 60 | 70 | 85 | 100 | 110.5 | 120 | 136 | 152 | 167 | 2.5 | 3 | 3 | 4 | 4 | 2 | 4 | 3 | 2.5 | 2 | 3 | 3 | 2.5 | 1.5 | 3 | 3 | 3 | 4 | 4 | 3 | 2 | 2.5 | 2.5 | 3 | 5 | 3 | 2 | 5 | 3 | 5 | 2 | 5 | 3 | 3 | 2 | 2.5 | 1.5 | 2.5 | 1.5 | 4 | 4 | 3 | 6 | 3 | 6 | 3 | 2 | 5 | 5 | 6 | 1.5 | 2.5
193 | 24 | 16.5 | 29 | 41.5 | 53 | 64.5 | 76 | 91.5 | 104 | 118.5 | 134.5 | 150.5 | 162.5 | 176.5 | 6 | 4 | 5 | 1.5 | 5 | 2.5 | 3 | 2 | 1.5 | 3 | 5 | 3 | 3 | 4 | 2.5 | 2 | 4 | 2 | 1.5 | 4 | 6 | 1.5 | 2 | 2 | 6 | 2 | 5 | 2.5 | 5 | 4 | 2 | 1.5 | 2.5 | 4 | 5 | 3 | 4 | 6 | 3 | 3 | 2.5 | 2.5 | 6 | 5 | 2 | 6 | 1.5 | 2.5 | 3 | 3 | 4 | 4
194 | 22 | 17 | 31 | 41 | 55 | 68.5 | 77 | 89 | 101.5 | 113 | 130 | 147 | 165.5 | 185.5 | 2 | 4 | 6 | 5 | 2.5 | 2.5 | 4 | 5 | 3 | 3 | 1.5 | 2.5 | 6 | 3 | 3 | 2 | 5 | 3 | 2.5 | 3 | 3 | 2 | 2 | 1.5 | 1.5 | 4 | 4 | 2.5 | 3 | 3 | 1.5 | 5 | 3 | 2.5 | 2 | 4 | 6 | 2.5 | 2.5 | 6 | 4 | 4 | 3 | 6 | 1.5 | 5 | 6 | 6 | 5 | 4 | 5 | 6
195 | 14 | 9.5 | 21.5 | 35.5 | 47.5 | 59 | 68.5 | 82 | 95 | 109 | 119.5 | 133.5 | 150 | 168 | 4 | 2.5 | 1.5 | 1.5 | 3 | 1.5 | 1.5 | 6 | 6 | 2.5 | 1.5 | 4 | 5 | 1.5 | 2.5 | 3 | 4 | 1.5 | 3 | 3 | 1.5 | 3 | 2.5 | 2.5 | 6 | 1.5 | 3 | 3 | 2 | 6 | 2.5 | 2.5 | 4 | 4 | 3 | 3 | 2 | 3 | 2.5 | 3 | 4 | 3 | 3 | 4 | 6 | 2.5 | 2 | 6 | 4 | 5 | 6 | 3
196 | 17 | 10 | 22 | 31.5 | 40 | 57 | 69 | 80.5 | 98.5 | 115.5 | 131.5 | 142.5 | 152 | 166.5 | 3 | 1.5 | 3 | 2.5 | 4 | 3 | 3 | 2 | 2 | 1.5 | 4 | 2 | 3 | 1.5 | 2.5 | 1.5 | 5 | 4 | 3 | 5 | 1.5 | 3 | 2.5 | 5 | 3 | 5 | 1.5 | 2 | 3 | 6 | 3 | 6 | 2 | 5 | 4 | 6 | 5 | 2 | 6 | 3 | 2.5 | 2 | 1.5 | 5 | 2 | 2 | 2.5 | 3 | 1.5 | 3 | 5 | 5
197 | 18 | 12 | 23.5 | 42.5 | 51 | 63.5 | 77 | 89.5 | 105 | 118 | 128 | 142.5 | 152.5 | 168.5 | 2 | 3 | 4 | 3 | 3 | 3 | 4 | 1.5 | 2 | 6 | 6 | 5 | 2.5 | 1.5 | 1.5 | 3 | 4 | 2.5 | 4 | 2 | 2 | 4 | 2.5 | 5 | 2 | 3 | 5 | 2.5 | 2.5 | 4 | 3 | 6 | 2 | 3 | 3 | 5 | 2 | 2 | 2 | 4 | 4 | 3 | 1.5 | 6 | 2 | 2 | 3 | 3 | 4 | 5 | 4 | 3
198 | 17 | 12 | 23.5 | 37 | 49.5 | 64.5 | 83.5 | 95 | 105.5 | 118.5 | 136.5 | 154 | 168.5 | 187.5 | 3 | 3 | 3 | 3 | 2 | 3 | 1.5 | 5 | 2 | 4 | 2.5 | 5 | 5 | 2 | 3 | 2.5 | 4 | 3 | 4 | 4 | 4 | 5 | 5 | 5 | 4 | 2.5 | 2 | 3 | 3 | 1.5 | 2 | 4 | 2 | 2 | 4 | 5 | 3 | 5 | 6 | 4 | 6 | 2.5 | 4 | 5 | 5 | 1.5 | 3 | 5 | 6 | 4 | 3 | 6
199 | 18 | 12.5 | 26.5 | 42 | 55.5 | 68.5 | 78.5 | 98.5 | 114 | 128.5 | 142.5 | 155.5 | 174.5 | 191.5 | 2.5 | 2 | 5 | 3 | 3 | 2.5 | 6 | 2.5 | 3 | 5 | 2.5 | 5 | 5 | 1.5 | 4 | 3 | 6 | 2.5 | 3 | 1.5 | 2.5 | 3 | 1.5 | 3 | 6 | 4 | 5 | 5 | 3 | 6 | 1.5 | 5 | 4 | 5 | 2.5 | 3 | 5 | 3 | 3 | 3 | 2 | 3 | 6 | 2 | 3 | 6 | 4 | 6 | 5 | 6 | 3 | 3
200 | 21.5 | 15.5 | 26.5 | 37 | 50.5 | 60.5 | 71 | 81 | 98 | 111 | 124 | 134.5 | 148.5 | 162.5 | 5 | 6 | 1.5 | 3 | 3 | 3 | 2.5 | 2.5 | 1.5 | 4 | 3 | 2 | 5 | 3 | 2.5 | 3 | 1.5 | 2.5 | 3 | 3 | 2 | 4 | 3 | 1.5 | 2.5 | 3 | 1.5 | 3 | 5 | 4 | 3 | 5 | 3 | 6 | 2.5 | 1.5 | 5 | 1.5 | 4 | 2.5 | 2 | 5 | 2 | 1.5 | 2.5 | 3 | 2.5 | 6 | 3 | 3 | 2 | 6
201 | 21 | 12 | 29.5 | 42.5 | 59.5 | 69.5 | 89.5 | 101.5 | 112 | 128.5 | 144.5 | 161 | 174.5 | 189.5 | 4 | 1.5 | 4 | 2.5 | 6 | 3 | 2.5 | 6 | 3 | 4 | 2 | 4 | 4 | 3 | 5 | 5 | 1.5 | 2.5 | 3 | 3 | 6 | 5 | 6 | 3 | 3 | 2 | 2 | 5 | 2.5 | 3 | 3 | 2 | 4 | 2.5 | 5 | 5 | 3 | 4 | 6 | 3 | 5 | 6 | 4 | 1.5 | 6 | 2.5 | 2.5 | 2.5 | 2.5 | 6 | 5 | 1.5
202 | 20 | 13 | 24.5 | 40 | 50.5 | 67.5 | 82.5 | 91.5 | 105 | 117 | 134 | 147.5 | 163 | 173.5 | 3 | 5 | 2 | 3 | 3 | 4 | 1.5 | 3 | 1.5 | 5 | 5 | 4 | 3 | 2 | 1.5 | 4 | 3 | 6 | 3 | 5 | 4 | 3 | 3 | 5 | 2.5 | 2 | 3 | 1.5 | 2.5 | 2.5 | 2.5 | 6 | 1.5 | 2.5 | 5 | 3 | 4 | 3 | 4 | 6 | 2 | 3 | 2.5 | 6 | 5 | 2.5 | 6 | 2 | 4 | 2 | 2 | 2.5
203 | 13.5 | 9 | 21.5 | 35.5 | 49.5 | 60 | 77 | 92 | 108 | 119.5 | 132 | 145 | 157 | 171 | 2.5 | 2 | 1.5 | 3 | 3 | 1.5 | 5 | 3 | 2.5 | 6 | 2.5 | 3 | 6 | 1.5 | 5 | 1.5 | 1.5 | 1.5 | 5 | 2.5 | 5 | 5 | 2 | 5 | 3 | 2 | 4 | 6 | 2 | 2 | 6 | 6 | 3 | 2 | 4 | 2.5 | 1.5 | 3 | 3 | 5 | 3 | 2 | 5 | 3 | 6 | 1.5 | 1.5 | 3 | 3 | 6 | 2 | 3
204 | 22 | 14.5 | 27 | 39 | 57 | 69.5 | 81.5 | 96 | 110.5 | 125.5 | 139.5 | 153 | 170.5 | 182.5 | 1.5 | 5 | 3 | 5 | 1.5 | 6 | 2 | 3 | 1.5 | 2.5 | 4 | 4 | 4 | 6 | 4 | 4 | 5 | 3 | 2.5 | 2 | 3 | 4 | 2 | 3 | 1.5 | 3 | 6 | 4 | 1.5 | 4 | 3 | 6 | 6 | 2 | 3 | 4 | 4 | 6 | 2 | 2 | 2 | 1.5 | 4 | 6 | 3 | 6 | 2.5 | 6 | 1.5 | 1.5 | 5 | 4
205 | 16 | 12.5 | 25 | 40.5 | 50.5 | 66.5 | 75.5 | 91.5 | 104.5 | 122 | 135.5 | 150 | 159.5 | 175.5 | 3 | 2.5 | 4 | 3 | 1.5 | 2 | 6 | 3 | 6 | 4 | 4 | 1.5 | 1.5 | 1.5 | 2 | 5 | 2.5 | 6 | 6 | 1.5 | 2.5 | 3 | 1.5 | 2 | 5 | 2 | 3 | 6 | 6 | 2 | 3 | 2 | 4 | 5 | 6 | 2.5 | 6 | 1.5 | 3 | 3 | 3 | 5 | 1.5 | 5 | 3 | 2.5 | 2 | 2 | 3 | 6 | 2 | 5
206 | 19 | 13 | 28 | 44 | 60 | 73.5 | 84.5 | 96.5 | 110 | 124 | 141 | 153 | 167.5 | 177.5 | 1.5 | 5 | 2.5 | 4 | 2 | 4 | 3 | 6 | 5 | 2 | 6 | 3 | 5 | 2.5 | 6 | 2.5 | 2.5 | 4 | 4 | 3 | 1.5 | 5 | 1.5 | 3 | 1.5 | 3 | 5 | 2.5 | 4 | 5 | 2.5 | 2 | 6 | 3 | 3 | 2 | 2 | 6 | 5 | 4 | 3 | 3 | 4 | 2 | 4 | 3 | 5 | 2.5 | 1.5 | 4 | 2.5 | 2
207 | 16 | 10.5 | 22 | 35.5 | 46.5 | 59.5 | 72.5 | 85 | 100.5 | 118.5 | 134.5 | 143 | 158.5 | 173.5 | 2 | 3 | 2.5 | 3 | 1.5 | 4 | 3 | 3 | 6 | 4 | 2 | 1.5 | 1.5 | 3 | 2.5 | 4 | 2.5 | 3 | 2.5 | 5 | 2 | 3 | 3 | 5 | 2.5 | 2.5 | 2.5 | 5 | 4 | 5 | 4 | 2.5 | 3 | 3 | 6 | 6 | 4 | 5 | 2 | 5 | 1.5 | 3 | 2.5 | 1.5 | 6 | 3 | 2.5 | 4 | 3 | 2 | 5 | 5
208 | 14.5 | 9 | 21.5 | 36 | 51 | 61.5 | 71 | 86.5 | 102.5 | 113.5 | 124.5 | 134 | 144.5 | 160 | 3 | 3 | 1.5 | 1.5 | 4 | 1.5 | 4 | 3 | 5 | 1.5 | 6 | 2 | 3 | 3 | 3 | 6 | 3 | 2 | 1.5 | 4 | 2 | 4 | 2 | 1.5 | 2.5 | 6 | 4 | 3 | 4 | 5 | 3 | 4 | 2 | 5 | 2 | 2 | 3 | 4 | 2.5 | 1.5 | 1.5 | 2 | 3 | 3 | 2 | 2 | 5 | 1.5 | 2.5 | 5 | 3 | 5
209 | 19 | 11 | 29 | 45 | 59.5 | 69.5 | 80.5 | 95.5 | 118.5 | 131 | 146 | 159.5 | 171 | 190 | 2 | 3 | 4 | 2 | 3 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 6 | 1.5 | 5 | 2.5 | 3 | 2.5 | 2 | 5 | 1.5 | 3 | 1.5 | 4 | 4 | 3 | 4 | 6 | 5 | 6 | 6 | 3 | 3 | 2.5 | 4 | 3 | 5 | 4 | 3 | 2.5 | 3 | 5 | 3 | 2.5 | 4 | 3 | 2 | 5 | 5 | 4 | 5
210 | 20 | 13.5 | 26.5 | 41.5 | 52.5 | 68 | 81.5 | 96 | 107.5 | 119 | 134.5 | 146.5 | 162.5 | 171 | 1.5 | 2 | 4 | 6 | 1.5 | 5 | 5 | 1.5 | 3 | 5 | 4 | 3 | 3 | 2.5 | 2.5 | 3 | 5 | 5 | 3 | 2.5 | 1.5 | 4 | 2 | 6 | 3 | 1.5 | 4 | 6 | 2 | 1.5 | 5 | 3 | 5 | 1.5 | 2 | 3 | 2.5 | 4 | 5 | 4 | 3 | 2 | 4 | 3 | 4 | 6 | 3 | 3 | 2 | 1.5 | 2.5 | 2.5
211 | 21.5 | 9.5 | 24.5 | 40 | 54 | 65 | 84 | 96 | 106.5 | 117 | 131 | 140 | 149.5 | 161 | 3 | 2.5 | 2.5 | 1.5 | 6 | 6 | 1.5 | 1.5 | 6 | 2 | 2.5 | 5 | 2.5 | 5 | 1.5 | 5 | 3 | 2 | 3 | 3 | 5 | 6 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 2.5 | 2 | 2 | 5 | 1.5 | 2 | 1.5 | 1.5 | 5 | 6 | 1.5 | 2.5 | 2 | 3 | 1.5 | 2 | 4 | 2 | 3 | 3 | 3 | 2.5
212 | 22 | 17.5 | 26.5 | 45 | 56.5 | 73 | 89 | 104 | 122.5 | 139 | 151 | 161.5 | 178.5 | 190 | 5 | 2.5 | 6 | 4 | 2 | 2.5 | 1.5 | 3 | 5 | 2.5 | 5 | 6 | 3 | 1.5 | 3 | 4 | 5 | 6 | 2.5 | 3 | 3 | 3 | 6 | 4 | 5 | 3 | 2 | 5 | 6 | 2.5 | 5 | 5 | 6 | 2.5 | 3 | 5 | 2.5 | 2.5 | 5 | 2 | 2 | 4 | 2.5 | 2 | 3 | 4 | 6 | 4 | 3 | 2.5 | 3 | 3
213 | 14 | 9 | 18.5 | 32.5 | 42.5 | 51.5 | 63.5 | 74 | 86.5 | 95.5 | 105 | 119 | 127.5 | 141.5 | 2.5 | 1.5 | 2 | 3 | 3 | 2 | 3 | 1.5 | 2 | 3 | 6 | 3 | 2.5 | 1.5 | 2 | 4 | 1.5 | 3 | 1.5 | 3 | 3 | 3 | 2 | 4 | 3 | 3 | 2 | 2.5 | 4 | 2.5 | 3 | 3 | 4 | 1.5 | 1.5 | 2 | 3 | 1.5 | 2.5 | 2.5 | 3 | 4 | 4 | 3 | 1.5 | 3 | 1.5 | 2.5 | 3 | 5 | 3 | 3
214 | 21.5 | 14.5 | 30.5 | 43 | 56 | 71 | 83.5 | 97 | 108.5 | 123.5 | 136.5 | 155.5 | 170 | 178 | 4 | 5 | 3 | 2.5 | 4 | 3 | 5 | 4 | 2 | 5 | 3 | 2.5 | 3 | 3 | 3 | 4 | 3 | 3 | 4 | 5 | 2.5 | 5 | 3 | 2 | 4 | 5 | 2.5 | 2 | 5 | 2.5 | 2 | 2 | 5 | 1.5 | 6 | 2.5 | 2.5 | 4 | 5 | 1.5 | 5 | 5 | 6 | 3 | 4 | 2 | 2.5 | 6 | 2 | 1.5 | 1.5 | 3
215 | 17.5 | 12.5 | 25.5 | 42.5 | 62.5 | 73.5 | 90.5 | 107 | 117 | 131.5 | 149.5 | 163 | 179 | 190.5 | 6 | 1.5 | 3 | 2 | 3 | 2 | 4 | 4 | 3 | 6 | 6 | 2 | 6 | 6 | 2 | 6 | 2.5 | 2.5 | 3 | 3 | 6 | 3 | 3 | 5 | 6 | 5 | 3 | 2.5 | 2.5 | 3 | 2 | 2.5 | 4 | 4 | 5 | 1.5 | 6 | 4 | 5 | 3 | 3 | 4 | 2.5 | 4 | 2 | 4 | 6 | 4 | 1.5 | 2.5 | 2.5 | 5
216 | 16.5 | 10.5 | 24 | 36 | 53 | 66.5 | 81 | 93 | 108 | 122.5 | 134.5 | 145.5 | 161 | 172.5 | 1.5 | 3 | 3 | 3 | 3 | 3 | 6 | 1.5 | 4 | 3 | 3 | 2 | 3 | 3 | 5 | 6 | 4 | 4 | 3 | 2.5 | 6 | 2 | 2.5 | 4 | 2 | 3 | 3 | 4 | 3 | 3 | 4 | 5 | 2 | 6 | 1.5 | 5 | 1.5 | 4 | 4 | 2.5 | 2.5 | 2.5 | 3 | 3 | 4 | 6 | 3 | 2.5 | 3 | 2 | 1.5 | 5
217 | 18.5 | 9.5 | 22 | 34 | 47 | 61 | 75 | 86.5 | 99.5 | 111.5 | 122.5 | 141.5 | 157.5 | 176.5 | 2.5 | 3 | 2 | 2 | 6 | 3 | 2 | 1.5 | 2 | 4 | 3 | 3 | 4 | 2 | 2 | 5 | 4 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 2 | 1.5 | 6 | 2 | 3 | 3 | 5 | 2 | 6 | 1.5 | 1.5 | 3 | 3 | 2.5 | 4 | 1.5 | 5 | 5 | 6 | 3 | 6 | 4 | 4 | 2 | 6 | 3 | 4 | 6
218 | 22 | 16 | 34 | 46.5 | 62.5 | 73.5 | 82.5 | 98 | 113 | 124 | 139.5 | 152 | 165 | 180.5 | 2 | 5 | 5 | 4 | 3 | 3 | 6 | 6 | 2 | 2.5 | 4 | 4 | 2 | 5 | 4 | 5 | 3 | 2.5 | 1.5 | 4 | 4 | 1.5 | 2 | 1.5 | 4 | 6 | 2.5 | 3 | 3 | 4 | 5 | 3 | 3 | 2 | 4 | 2 | 1.5 | 4 | 5 | 5 | 2 | 6 | 2.5 | 2 | 6 | 1.5 | 3 | 2.5 | 4 | 3 | 6 | 2.5
219 | 23.5 | 14.5 | 34.5 | 42.5 | 59 | 68.5 | 81 | 99 | 112 | 128 | 139 | 159 | 169 | 180.5 | 4 | 2.5 | 2 | 6 | 6 | 3 | 5 | 6 | 1.5 | 1.5 | 2 | 3 | 2 | 2.5 | 6 | 6 | 2.5 | 2.5 | 3 | 1.5 | 3 | 1.5 | 3 | 5 | 3 | 4 | 6 | 5 | 2 | 3 | 2 | 6 | 5 | 5 | 4 | 2 | 5 | 1.5 | 1.5 | 3 | 3 | 5 | 6 | 6 | 1.5 | 1.5 | 3 | 4 | 2.5 | 5 | 2.5 | 1.5
220 | 21.5 | 14.5 | 28 | 34 | 49 | 65 | 82.5 | 95.5 | 107 | 120 | 133.5 | 148.5 | 161.5 | 174.5 | 3 | 3 | 6 | 2.5 | 2 | 5 | 1.5 | 5 | 1.5 | 1.5 | 1.5 | 1.5 | 6 | 2.5 | 4 | 2.5 | 2 | 6 | 3 | 5 | 2.5 | 3 | 6 | 6 | 3 | 2 | 3 | 5 | 1.5 | 3 | 3 | 4 | 5 | 2 | 2 | 4 | 2.5 | 3 | 5 | 3 | 2 | 2 | 5 | 6 | 4 | 1.5 | 6 | 1.5 | 5 | 3 | 3 | 2
221 | 20.5 | 14.5 | 28.5 | 35.5 | 50 | 63.5 | 75.5 | 86.5 | 99 | 108.5 | 120.5 | 130.5 | 144 | 151.5 | 2.5 | 3 | 3 | 6 | 3 | 3 | 5 | 3 | 1.5 | 1.5 | 2.5 | 1.5 | 6 | 2 | 2.5 | 4 | 2 | 3 | 6 | 2.5 | 1.5 | 3 | 5 | 2.5 | 5 | 1.5 | 2.5 | 2 | 3 | 3 | 4 | 2.5 | 3 | 3 | 2 | 1.5 | 2 | 4 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 5 | 3 | 2.5 | 1.5 | 1.5 | 3 | 1.5
222 | 22 | 16.5 | 27.5 | 41.5 | 55 | 67 | 78 | 91 | 104 | 121.5 | 132 | 153 | 172 | 193 | 6 | 1.5 | 4 | 5 | 3 | 2.5 | 3 | 2.5 | 5 | 2 | 5 | 2 | 2.5 | 3 | 6 | 2 | 2 | 4 | 4 | 2 | 5 | 3 | 1.5 | 1.5 | 2 | 2 | 6 | 3 | 4 | 6 | 1.5 | 1.5 | 6 | 5 | 4 | 2.5 | 3 | 2.5 | 3 | 2 | 5 | 4 | 6 | 6 | 5 | 5 | 3 | 6 | 6 | 6 | 6 | 3
223 | 18.5 | 12 | 22 | 40 | 49.5 | 59 | 71.5 | 85 | 100 | 113 | 125.5 | 139 | 151 | 173 | 3 | 5 | 2 | 2 | 2.5 | 4 | 1.5 | 2 | 6 | 5 | 4 | 3 | 1.5 | 3 | 2.5 | 2.5 | 3 | 1.5 | 2.5 | 2.5 | 2 | 6 | 1.5 | 3 | 6 | 1.5 | 3 | 3 | 6 | 3 | 2 | 4 | 4 | 3 | 4 | 2 | 4 | 2.5 | 3 | 3 | 2.5 | 4 | 3 | 4 | 6 | 2.5 | 2 | 1.5 | 5 | 5 | 6 | 6
224 | 14.5 | 9.5 | 19.5 | 35 | 51 | 64 | 83.5 | 100.5 | 115 | 129 | 139 | 150.5 | 163.5 | 179 | 1.5 | 2.5 | 2.5 | 3 | 2 | 3 | 3 | 2 | 6 | 4 | 3 | 2.5 | 3 | 3 | 5 | 5 | 5 | 3 | 2 | 3 | 5 | 6 | 2.5 | 6 | 6 | 5 | 3 | 3 | 5 | 1.5 | 2 | 6 | 3 | 6 | 2.5 | 2.5 | 5 | 2 | 1.5 | 1.5 | 2 | 2.5 | 5 | 2 | 2 | 3 | 4 | 4 | 2.5 | 6 | 4 | 3
225 | 20.5 | 11.5 | 25.5 | 42.5 | 56 | 67.5 | 86.5 | 93.5 | 108 | 118.5 | 140.5 | 152 | 164 | 181 | 3 | 3 | 2.5 | 3 | 5 | 4 | 3 | 2 | 3 | 6 | 5 | 3 | 5 | 4 | 1.5 | 3 | 3 | 3 | 3 | 2.5 | 5 | 5 | 6 | 3 | 2 | 2 | 1.5 | 1.5 | 3 | 2.5 | 3 | 6 | 2 | 2 | 4 | 2.5 | 6 | 6 | 4 | 6 | 5 | 1.5 | 3 | 2 | 2 | 3 | 5 | 2 | 6 | 3 | 5 | 3
226 | 18 | 14.5 | 24 | 34.5 | 46 | 60 | 70 | 85 | 99 | 112 | 133 | 145 | 162.5 | 179.5 | 3 | 2.5 | 3 | 6 | 1.5 | 2 | 4 | 2 | 1.5 | 2 | 4 | 3 | 2 | 1.5 | 3 | 5 | 4 | 2.5 | 1.5 | 6 | 1.5 | 2.5 | 4 | 2 | 2 | 6 | 2 | 5 | 4 | 4 | 3 | 3 | 3 | 2.5 | 2.5 | 5 | 4 | 5 | 6 | 6 | 2.5 | 3 | 1.5 | 5 | 5 | 1.5 | 6 | 5 | 2.5 | 6 | 2.5 | 6
227 | 17.5 | 13 | 23.5 | 32 | 42.5 | 57 | 76 | 86.5 | 100.5 | 117.5 | 131 | 144 | 162 | 174 | 3 | 4 | 3 | 3 | 1.5 | 3 | 4 | 2 | 2.5 | 2 | 1.5 | 2.5 | 2 | 3 | 1.5 | 4 | 6 | 4 | 2.5 | 2 | 6 | 5 | 5 | 3 | 2 | 1.5 | 2 | 5 | 2.5 | 3 | 6 | 2.5 | 3 | 3 | 5 | 6 | 5 | 3 | 4 | 1.5 | 3 | 3 | 4 | 3 | 4 | 5 | 3 | 6 | 2.5 | 2.5 | 3 | 4
228 | 22.5 | 15 | 31.5 | 43.5 | 60 | 76.5 | 97.5 | 114.5 | 127.5 | 139 | 152.5 | 166.5 | 182 | 195.5 | 4 | 6 | 2.5 | 2.5 | 1.5 | 6 | 4 | 5 | 4 | 3 | 2.5 | 2.5 | 5 | 6 | 2.5 | 3 | 2.5 | 6 | 5 | 3 | 5 | 6 | 5 | 5 | 6 | 6 | 2.5 | 2.5 | 1.5 | 3 | 2.5 | 6 | 5 | 3 | 1.5 | 2 | 3 | 3 | 1.5 | 6 | 4 | 5 | 2 | 3 | 6 | 6 | 1.5 | 2 | 3 | 2.5 | 3 | 5
229 | 26 | 16 | 33 | 47.5 | 60 | 77.5 | 86.5 | 99 | 113 | 126 | 137 | 148.5 | 164.5 | 181 | 2.5 | 6 | 1.5 | 6 | 4 | 6 | 5 | 2 | 2.5 | 3 | 3 | 6 | 2.5 | 1.5 | 2.5 | 6 | 2.5 | 6 | 6 | 3 | 2 | 1.5 | 2.5 | 3 | 2 | 6 | 3 | 1.5 | 6 | 2.5 | 1.5 | 4 | 6 | 2.5 | 3 | 1.5 | 2 | 4 | 2 | 3 | 3 | 4 | 3 | 1.5 | 4 | 2 | 5 | 5 | 6 | 1.5 | 6 | 3
230 | 19.5 | 14.5 | 25.5 | 33 | 47 | 56.5 | 72 | 84 | 96 | 112.5 | 124 | 140 | 159 | 174.5 | 3 | 2.5 | 4 | 5 | 2.5 | 2.5 | 3 | 3 | 1.5 | 3 | 1.5 | 1.5 | 2.5 | 3 | 6 | 2.5 | 4 | 2.5 | 1.5 | 1.5 | 2.5 | 6 | 2 | 5 | 2.5 | 3 | 1.5 | 5 | 5 | 2 | 2.5 | 2.5 | 1.5 | 3 | 6 | 6 | 2 | 2.5 | 4 | 3 | 4 | 3 | 6 | 3 | 4 | 6 | 3 | 6 | 2.5 | 3 | 5 | 5
231 | 23.5 | 16 | 32.5 | 41 | 50.5 | 58 | 74 | 87 | 102.5 | 113.5 | 130 | 148 | 163.5 | 171.5 | 4 | 4 | 2 | 6 | 5 | 2.5 | 3 | 6 | 3 | 1.5 | 1.5 | 2.5 | 2.5 | 1.5 | 2.5 | 3 | 1.5 | 1.5 | 2 | 2.5 | 4 | 5 | 4 | 3 | 4 | 1.5 | 1.5 | 6 | 4 | 3 | 2.5 | 6 | 3 | 4 | 2.5 | 1.5 | 6 | 3 | 1.5 | 6 | 6 | 6 | 2 | 4 | 3 | 4 | 2.5 | 6 | 3 | 1.5 | 1.5 | 2
232 | 20.5 | 12.5 | 26 | 41 | 55.5 | 69 | 81 | 98 | 112 | 123.5 | 137 | 158 | 171 | 182.5 | 3 | 1.5 | 3 | 5 | 5 | 3 | 3 | 2.5 | 6 | 2 | 3 | 4 | 1.5 | 4 | 5 | 4 | 3 | 4 | 2.5 | 4 | 2.5 | 4 | 2.5 | 3 | 5 | 6 | 3 | 3 | 3 | 6 | 2 | 3 | 1.5 | 2 | 3 | 5 | 2.5 | 2.5 | 6 | 2.5 | 5 | 6 | 4 | 6 | 2 | 2.5 | 6 | 2.5 | 2 | 4 | 1.5 | 4
233 | 29.5 | 17.5 | 36 | 47.5 | 62 | 75.5 | 83 | 92 | 103 | 117.5 | 131 | 143.5 | 152.5 | 167 | 5 | 1.5 | 6 | 5 | 6 | 6 | 2.5 | 4 | 2.5 | 6 | 1.5 | 1.5 | 3 | 3 | 2.5 | 6 | 3 | 6 | 2.5 | 2 | 2.5 | 1.5 | 2 | 1.5 | 3 | 1.5 | 3 | 1.5 | 2 | 3 | 3 | 3 | 4 | 3 | 6 | 1.5 | 1.5 | 5 | 2 | 5 | 3 | 6 | 1.5 | 2 | 1.5 | 2 | 3 | 2.5 | 4 | 3 | 5 | 2.5
234 | 21 | 12.5 | 26.5 | 40.5 | 53.5 | 63.5 | 76.5 | 92.5 | 109.5 | 130 | 143.5 | 156 | 169 | 184 | 2 | 1.5 | 3 | 6 | 6 | 2.5 | 4 | 1.5 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 4 | 1.5 | 3 | 4 | 1.5 | 5 | 1.5 | 1.5 | 5 | 4 | 6 | 3 | 3 | 5 | 3 | 5 | 4 | 6 | 6 | 6 | 2.5 | 2.5 | 3 | 3 | 5 | 4 | 3 | 1.5 | 4 | 3 | 5 | 2 | 3 | 6 | 2 | 3 | 4
235 | 22.5 | 13.5 | 31.5 | 41 | 55.5 | 68.5 | 90.5 | 107.5 | 123.5 | 136 | 152.5 | 163.5 | 177 | 192 | 3 | 5 | 3 | 2.5 | 4 | 5 | 3 | 6 | 2.5 | 3 | 2 | 2 | 6 | 3 | 4 | 1.5 | 3 | 2 | 3 | 5 | 6 | 6 | 4 | 6 | 2 | 5 | 4 | 6 | 3 | 2 | 5 | 6 | 1.5 | 3 | 3 | 5 | 5 | 4 | 2.5 | 5 | 3 | 3 | 2.5 | 2.5 | 3 | 2.5 | 4 | 4 | 2 | 2 | 6 | 5
236 | 19.5 | 14 | 28.5 | 38 | 47.5 | 56.5 | 67 | 81.5 | 91 | 110 | 122 | 131.5 | 147.5 | 156 | 3 | 2 | 3 | 6 | 1.5 | 4 | 4 | 5 | 1.5 | 2.5 | 2.5 | 3 | 3 | 2.5 | 2 | 2 | 1.5 | 2 | 2.5 | 3 | 3 | 1.5 | 3 | 3 | 3 | 1.5 | 6 | 4 | 3 | 2.5 | 2.5 | 1.5 | 6 | 6 | 2 | 5 | 1.5 | 4 | 5 | 1.5 | 3 | 3 | 1.5 | 2 | 3 | 6 | 4 | 3 | 1.5 | 3 | 1.5 | 2.5
237 | 21 | 14.5 | 27.5 | 41.5 | 49 | 64 | 74.5 | 85.5 | 101.5 | 115 | 130 | 140.5 | 157 | 170 | 4 | 2.5 | 4 | 4 | 5 | 1.5 | 1.5 | 5 | 2.5 | 2.5 | 3 | 6 | 1.5 | 2 | 2 | 2 | 6 | 2 | 2 | 5 | 2 | 3 | 2.5 | 3 | 2.5 | 2.5 | 3 | 3 | 4 | 3 | 4 | 5 | 5 | 5 | 2 | 1.5 | 2 | 2 | 5 | 6 | 2.5 | 3 | 2.5 | 2.5 | 4 | 4 | 2.5 | 6 | 2 | 5 | 2 | 4
238 | 16.5 | 11 | 23 | 39 | 55 | 68 | 79.5 | 90.5 | 101.5 | 111.5 | 124 | 141 | 157 | 169 | 1.5 | 2.5 | 3 | 4 | 2.5 | 3 | 5 | 1.5 | 5 | 3 | 3 | 5 | 5 | 2 | 5 | 4 | 3 | 3 | 3 | 4 | 3 | 5 | 2 | 1.5 | 1.5 | 1.5 | 6 | 2 | 2 | 3 | 3 | 3 | 3 | 1.5 | 4 | 1.5 | 2.5 | 2 | 5 | 3 | 2 | 6 | 4 | 5 | 3 | 4 | 3 | 6 | 1.5 | 6 | 1.5 | 3
239 | 19.5 | 11.5 | 28.5 | 38 | 56.5 | 74.5 | 93.5 | 108.5 | 130.5 | 140.5 | 156.5 | 168.5 | 180.5 | 196.5 | 1.5 | 3 | 4 | 3 | 3 | 5 | 6 | 3 | 1.5 | 1.5 | 2.5 | 4 | 6 | 5 | 6 | 1.5 | 6 | 3 | 3 | 6 | 5 | 6 | 6 | 2 | 3 | 4 | 3 | 5 | 6 | 6 | 4 | 6 | 2 | 3 | 2 | 3 | 4 | 4 | 6 | 2 | 3 | 3 | 4 | 2 | 1.5 | 5 | 3 | 2.5 | 6 | 4 | 2 | 4
240 | 19 | 13 | 25 | 37.5 | 51.5 | 72.5 | 82.5 | 95.5 | 112.5 | 125.5 | 138 | 146 | 163 | 179 | 6 | 2 | 2 | 3 | 3 | 3 | 4 | 2 | 5 | 3 | 3 | 1.5 | 6 | 2 | 2 | 4 | 3 | 6 | 6 | 6 | 3 | 1.5 | 3 | 2.5 | 3 | 3 | 3 | 4 | 6 | 4 | 4 | 3 | 2.5 | 6 | 2.5 | 2 | 3 | 2.5 | 3 | 4 | 2.5 | 2 | 2 | 1.5 | 6 | 6 | 2 | 3 | 5 | 4 | 2 | 5
241 | 22 | 16.5 | 28 | 41 | 56 | 75.5 | 83.5 | 96.5 | 108.5 | 121.5 | 133 | 147 | 160.5 | 176.5 | 6 | 5 | 2.5 | 3 | 2.5 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 3 | 4 | 3 | 5 | 6 | 6 | 5 | 2.5 | 1.5 | 1.5 | 3 | 2 | 6 | 1.5 | 4 | 1.5 | 5 | 2 | 2 | 3 | 4 | 3 | 3 | 3 | 2.5 | 2.5 | 1.5 | 5 | 5 | 2 | 5 | 2 | 2 | 6 | 2.5 | 3 | 6 | 3 | 3 | 4
242 | 18.5 | 12 | 23.5 | 35 | 48.5 | 58 | 71.5 | 87 | 98.5 | 113 | 133 | 148.5 | 162.5 | 177 | 1.5 | 6 | 3 | 1.5 | 4 | 2.5 | 2 | 3 | 4 | 1.5 | 3 | 3 | 1.5 | 6 | 3 | 3 | 2 | 3 | 2 | 2.5 | 3 | 5 | 1.5 | 4 | 3 | 6 | 2.5 | 4 | 1.5 | 2 | 3 | 5 | 3 | 5 | 2.5 | 4 | 6 | 4 | 4 | 6 | 2.5 | 6 | 5 | 2 | 5 | 4 | 2 | 3 | 4 | 4 | 1.5 | 5
243 | 21 | 14 | 27.5 | 37 | 48.5 | 67 | 78.5 | 95 | 113 | 135 | 147.5 | 162 | 177.5 | 190 | 1.5 | 1.5 | 6 | 5 | 3 | 4 | 4 | 2.5 | 1.5 | 2.5 | 2.5 | 3 | 3 | 1.5 | 4 | 3 | 5 | 6 | 1.5 | 6 | 2 | 3 | 5 | 1.5 | 6 | 5 | 1.5 | 4 | 3 | 4 | 5 | 6 | 6 | 5 | 6 | 5 | 2.5 | 5 | 2 | 3 | 2.5 | 4 | 6 | 2 | 2.5 | 3 | 6 | 4 | 3 | 3 | 5 | 1.5
244 | 19.5 | 13.5 | 24 | 44 | 55.5 | 71 | 89 | 98 | 112 | 127.5 | 139.5 | 151.5 | 165.5 | 183.5 | 3 | 3 | 2.5 | 5 | 3 | 3 | 2.5 | 2 | 5 | 6 | 5 | 4 | 1.5 | 2 | 3 | 5 | 6 | 4 | 2.5 | 3 | 3 | 6 | 5 | 4 | 2 | 3 | 1.5 | 2.5 | 3 | 6 | 2.5 | 2.5 | 1.5 | 6 | 5 | 3 | 5 | 3 | 2 | 2 | 3 | 2 | 4 | 3 | 4 | 2 | 2 | 6 | 5 | 3 | 5 | 5
245 | 24.5 | 17.5 | 34.5 | 47 | 56.5 | 80.5 | 92.5 | 111.5 | 126 | 140 | 154.5 | 164.5 | 174 | 186.5 | 1.5 | 6 | 5 | 5 | 5 | 2 | 5 | 5 | 1.5 | 3 | 3 | 5 | 2 | 2.5 | 2.5 | 2.5 | 6 | 6 | 6 | 6 | 5 | 3 | 1.5 | 2.5 | 4 | 6 | 6 | 3 | 5 | 2.5 | 2 | 5 | 4 | 6 | 1.5 | 2.5 | 3 | 5 | 1.5 | 5 | 1.5 | 1.5 | 3 | 4 | 3 | 2.5 | 2.5 | 1.5 | 2.5 | 3 | 2 | 5
246 | 17.5 | 12.5 | 24.5 | 37 | 49 | 66 | 75.5 | 88 | 102.5 | 112 | 131 | 140.5 | 150.5 | 166.5 | 2.5 | 6 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 2.5 | 3 | 3 | 3 | 2.5 | 2.5 | 4 | 5 | 6 | 3 | 3 | 3 | 2.5 | 2 | 2 | 3 | 1.5 | 2 | 6 | 2 | 2.5 | 5 | 5 | 3 | 1.5 | 2.5 | 2.5 | 5 | 4 | 6 | 4 | 2 | 2.5 | 2 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 4 | 6
247 | 17.5 | 11.5 | 27.5 | 40 | 56.5 | 74.5 | 84.5 | 98 | 111.5 | 122 | 137.5 | 155.5 | 168 | 183.5 | 3 | 2.5 | 3 | 3 | 3 | 3 | 6 | 4 | 1.5 | 6 | 2.5 | 2.5 | 1.5 | 4 | 6 | 5 | 5 | 4 | 4 | 5 | 1.5 | 4 | 2.5 | 2 | 4 | 1.5 | 3 | 5 | 6 | 2 | 1.5 | 4 | 1.5 | 5 | 1.5 | 2.5 | 4 | 5 | 4 | 2.5 | 2 | 6 | 4 | 6 | 4 | 4 | 2 | 2.5 | 1.5 | 3 | 5 | 6
248 | 20.5 | 11.5 | 30.5 | 47.5 | 64.5 | 77.5 | 95 | 108 | 122.5 | 135.5 | 148 | 161.5 | 176 | 189.5 | 1.5 | 3 | 4 | 3 | 4 | 5 | 5 | 5 | 3 | 5 | 5 | 4 | 3 | 3 | 5 | 6 | 4 | 3 | 3 | 3 | 2.5 | 6 | 6 | 3 | 1.5 | 3 | 2.5 | 6 | 3 | 2.5 | 5 | 4 | 3 | 3 | 4 | 3 | 6 | 3 | 1.5 | 2 | 2 | 5 | 1.5 | 5 | 4 | 5 | 2.5 | 3 | 2 | 6 | 2.5 | 3
249 | 22.5 | 16 | 27.5 | 40.5 | 55 | 64.5 | 74.5 | 90 | 106 | 119.5 | 132 | 144 | 156.5 | 170 | 2 | 5 | 4 | 5 | 2.5 | 4 | 2 | 3 | 2.5 | 1.5 | 6 | 3 | 2.5 | 3 | 4 | 5 | 2.5 | 1.5 | 4 | 1.5 | 2 | 1.5 | 1.5 | 5 | 4 | 1.5 | 6 | 4 | 4 | 2 | 5 | 5 | 2 | 3 | 6 | 2.5 | 3 | 3 | 2.5 | 4 | 5 | 3 | 2 | 2 | 1.5 | 4 | 5 | 2 | 2.5 | 3 | 5 | 3
250 | 21 | 14.5 | 29 | 41 | 56.5 | 71.5 | 82 | 94.5 | 111.5 | 121 | 141 | 157 | 173 | 192 | 4 | 6 | 2.5 | 2 | 4 | 2.5 | 4 | 4 | 2 | 3 | 5 | 2 | 2.5 | 2 | 6 | 5 | 6 | 3 | 3 | 3 | 3 | 2 | 1.5 | 4 | 3 | 4 | 1.5 | 4 | 5 | 2 | 6 | 4 | 2 | 1.5 | 4 | 2 | 4 | 5 | 6 | 5 | 6 | 5 | 2.5 | 2.5 | 5 | 2 | 4 | 5 | 6 | 3 | 6 | 4
251 | 23 | 11 | 28.5 | 43 | 58.5 | 71 | 81.5 | 99 | 113 | 129 | 137 | 153 | 164.5 | 180 | 3 | 3 | 3 | 2 | 6 | 6 | 1.5 | 4 | 4 | 5 | 2.5 | 3 | 4 | 2.5 | 4 | 5 | 3 | 2 | 5 | 2.5 | 3 | 3 | 2.5 | 2 | 2.5 | 3 | 6 | 6 | 2.5 | 5 | 1.5 | 5 | 6 | 1.5 | 6 | 2.5 | 2 | 3 | 1.5 | 1.5 | 6 | 2 | 4 | 4 | 3 | 4 | 3 | 1.5 | 5 | 1.5 | 6 | 3
252 | 22 | 15 | 29 | 42 | 55 | 64.5 | 79 | 93.5 | 108.5 | 119.5 | 130.5 | 141.5 | 157.5 | 176.5 | 4 | 2.5 | 6 | 2.5 | 5 | 2 | 5 | 2 | 3 | 2.5 | 5 | 2.5 | 2 | 6 | 3 | 2 | 1.5 | 4 | 2.5 | 1.5 | 1.5 | 5 | 5 | 3 | 3 | 2.5 | 6 | 3 | 5 | 2 | 2 | 6 | 2.5 | 3 | 2.5 | 3 | 2 | 2.5 | 2.5 | 4 | 3 | 3 | 3 | 2 | 2 | 6 | 3 | 5 | 6 | 6 | 2 | 5
253 | 14.5 | 9 | 20.5 | 31 | 43 | 54.5 | 62.5 | 74.5 | 84 | 95 | 106.5 | 117 | 129 | 146 | 1.5 | 1.5 | 4 | 2 | 3 | 2.5 | 4 | 2 | 3 | 2 | 1.5 | 4 | 6 | 1.5 | 3 | 1.5 | 4 | 3 | 3 | 1.5 | 2 | 1.5 | 1.5 | 3 | 2.5 | 1.5 | 3 | 5 | 2.5 | 3 | 1.5 | 2.5 | 4 | 2.5 | 3 | 1.5 | 3 | 2.5 | 2 | 4 | 1.5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 4 | 6 | 5
254 | 20 | 11 | 28.5 | 41 | 55 | 68.5 | 84.5 | 97 | 112.5 | 127.5 | 140 | 152.5 | 160.5 | 171 | 3 | 2 | 2 | 4 | 6 | 3 | 2.5 | 6 | 1.5 | 4 | 2 | 5 | 6 | 3 | 2 | 3 | 4 | 2.5 | 4 | 3 | 5 | 4 | 3 | 4 | 4 | 3 | 2.5 | 3 | 2.5 | 3 | 5 | 5 | 6 | 2.5 | 1.5 | 5 | 6 | 1.5 | 2 | 3 | 2.5 | 6 | 2 | 2 | 3 | 1.5 | 1.5 | 2 | 3 | 2 | 1.5 | 4
255 | 21 | 9 | 27.5 | 39.5 | 58.5 | 72 | 83 | 99 | 112 | 124 | 139 | 154 | 168 | 182.5 | 1.5 | 2.5 | 3 | 2 | 6 | 6 | 2.5 | 4 | 1.5 | 1.5 | 3 | 6 | 2 | 5 | 6 | 6 | 3 | 1.5 | 3 | 6 | 2.5 | 4 | 2.5 | 2 | 6 | 2 | 6 | 2 | 6 | 1.5 | 4 | 1.5 | 1.5 | 6 | 1.5 | 3 | 3 | 6 | 2 | 4 | 5 | 3 | 3 | 4 | 3 | 2 | 3 | 6 | 1.5 | 4 | 4 | 5
256 | 15.5 | 9.5 | 23 | 35.5 | 53 | 68.5 | 82.5 | 101.5 | 116.5 | 126 | 139.5 | 150.5 | 162.5 | 176 | 2.5 | 4 | 1.5 | 1.5 | 2 | 4 | 5 | 2.5 | 3 | 1.5 | 5 | 3 | 5 | 1.5 | 6 | 5 | 6 | 1.5 | 4 | 4 | 3 | 3 | 6 | 2 | 6 | 4 | 3 | 6 | 6 | 3 | 3 | 3 | 3 | 1.5 | 3 | 2 | 5 | 2.5 | 3 | 3 | 3 | 1.5 | 1.5 | 5 | 5 | 3 | 1.5 | 2.5 | 2.5 | 6 | 3 | 2
257 | 18.5 | 12.5 | 26.5 | 40 | 54.5 | 72 | 87 | 100.5 | 114 | 131.5 | 143 | 157 | 166.5 | 177.5 | 4 | 3 | 3 | 2.5 | 3 | 3 | 4 | 4 | 5 | 4 | 3 | 1.5 | 2.5 | 2 | 6 | 4 | 5 | 6 | 4 | 2.5 | 6 | 3 | 3 | 3 | 2.5 | 5 | 3 | 3 | 3 | 5 | 3 | 2.5 | 6 | 6 | 2.5 | 3 | 3 | 3 | 4 | 1.5 | 2 | 5 | 4 | 3 | 1.5 | 3 | 2 | 3 | 2 | 6 | 1.5 | 1.5
258 | 27 | 17 | 32.5 | 46.5 | 61 | 72 | 87.5 | 100 | 116.5 | 127 | 144 | 157.5 | 172 | 184.5 | 2 | 3 | 6 | 6 | 4 | 6 | 3 | 2.5 | 3 | 3 | 3 | 5 | 4 | 6 | 1.5 | 3 | 1.5 | 3 | 2.5 | 4 | 4 | 2.5 | 5 | 4 | 2 | 2.5 | 5 | 3 | 6 | 1.5 | 6 | 3 | 2 | 4 | 2 | 2.5 | 2 | 5 | 4 | 6 | 6 | 3 | 2.5 | 2 | 6 | 3 | 4 | 1.5 | 2.5 | 5 | 3 | 2
259 | 16.5 | 11.5 | 25.5 | 41.5 | 53 | 70.5 | 82.5 | 95.5 | 110 | 131 | 144 | 159 | 176.5 | 190 | 2.5 | 3 | 2 | 4 | 3 | 2 | 4 | 5 | 3 | 3 | 4 | 6 | 1.5 | 2.5 | 1.5 | 6 | 6 | 2.5 | 6 | 3 | 2.5 | 3 | 2.5 | 4 | 2.5 | 2.5 | 6 | 2 | 5 | 3 | 1.5 | 5 | 6 | 6 | 3 | 6 | 2 | 3 | 6 | 2 | 4 | 3 | 2 | 6 | 4 | 1.5 | 6 | 6 | 6 | 3 | 1.5 | 3
260 | 16 | 11.5 | 21.5 | 33.5 | 44 | 57.5 | 72.5 | 82.5 | 95.5 | 107.5 | 125 | 140 | 157 | 169 | 5 | 2 | 2 | 2.5 | 2 | 2.5 | 3 | 2.5 | 5 | 1.5 | 2.5 | 3 | 3 | 3 | 3 | 1.5 | 6 | 1.5 | 4 | 2 | 5 | 3 | 3 | 4 | 3 | 3 | 2 | 2 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 5 | 5 | 4 | 6 | 2.5 | 3 | 4 | 6 | 2 | 6 | 3 | 3 | 5 | 3 | 1.5 | 6 | 1.5
261 | 15.5 | 11.5 | 23 | 33 | 49.5 | 60.5 | 73 | 85 | 103.5 | 118.5 | 132 | 143 | 156.5 | 164 | 2.5 | 4 | 3 | 2 | 2.5 | 1.5 | 5 | 2.5 | 3 | 1.5 | 4 | 1.5 | 2 | 2.5 | 6 | 6 | 5 | 1.5 | 2.5 | 2 | 3 | 1.5 | 3 | 5 | 2.5 | 2 | 5 | 2.5 | 6 | 2.5 | 4 | 6 | 6 | 3 | 3 | 3 | 3 | 2.5 | 5 | 3 | 5 | 3 | 1.5 | 1.5 | 3 | 2.5 | 5 | 3 | 2.5 | 2 | 1.5 | 1.5
262 | 15 | 12 | 21 | 33.5 | 46.5 | 60 | 73 | 89 | 101 | 108 | 125.5 | 141.5 | 151.5 | 166 | 4 | 3 | 2.5 | 2.5 | 1.5 | 1.5 | 3 | 3 | 3 | 1.5 | 3 | 5 | 3 | 3 | 4 | 3 | 3 | 6 | 3 | 1.5 | 2.5 | 5 | 2.5 | 3 | 6 | 4 | 3 | 3 | 2.5 | 1.5 | 4 | 4 | 2.5 | 1.5 | 1.5 | 1.5 | 2.5 | 4 | 6 | 5 | 3 | 2 | 5 | 6 | 2 | 2 | 3 | 3 | 3 | 5 | 4 | 2.5
263 | 15 | 12 | 21 | 33.5 | 45.5 | 57.5 | 73 | 88 | 99 | 117.5 | 131 | 145 | 155.5 | 167 | 3 | 2.5 | 2.5 | 4 | 1.5 | 1.5 | 3 | 3 | 1.5 | 5 | 3 | 3 | 2.5 | 4 | 1.5 | 4 | 3 | 3 | 4 | 2 | 3 | 5 | 5 | 2.5 | 2 | 3 | 6 | 4 | 1.5 | 5 | 1.5 | 3 | 6 | 4 | 2.5 | 6 | 4 | 4 | 1.5 | 4 | 4 | 3 | 3 | 4 | 2.5 | 2 | 2 | 4 | 5 | 1.5 | 3 | 2
264 | 17 | 9.5 | 22.5 | 35.5 | 46.5 | 58.5 | 71 | 83 | 93.5 | 105.5 | 119.5 | 132 | 145.5 | 161.5 | 3 | 1.5 | 3 | 2 | 1.5 | 6 | 3 | 2.5 | 5 | 1.5 | 1.5 | 5 | 4 | 2.5 | 1.5 | 3 | 3 | 4 | 3 | 2 | 2 | 6 | 2 | 2.5 | 2.5 | 5 | 2.5 | 2 | 4 | 2.5 | 1.5 | 2.5 | 3 | 1.5 | 5 | 2.5 | 3 | 3 | 3 | 5 | 3 | 3 | 2.5 | 4 | 2 | 2.5 | 3 | 6 | 5 | 2 | 3 | 6
265 | 20 | 14.5 | 29 | 45 | 56.5 | 71 | 82.5 | 93 | 108 | 121.5 | 130.5 | 144.5 | 153.5 | 165 | 3 | 4 | 2.5 | 5 | 1.5 | 4 | 6 | 3 | 6 | 2 | 6 | 2 | 3 | 2.5 | 4 | 2 | 5 | 2 | 5 | 2.5 | 2.5 | 3 | 3 | 3 | 5 | 2.5 | 1.5 | 1.5 | 6 | 6 | 1.5 | 1.5 | 2.5 | 6 | 2 | 3 | 1.5 | 3 | 3 | 1.5 | 5 | 3 | 4 | 2 | 1.5 | 2.5 | 2 | 3 | 3 | 5 | 1.5 | 2
266 | 24.5 | 20 | 30 | 47 | 59 | 73.5 | 89 | 97 | 118 | 127.5 | 137 | 146.5 | 160 | 174.5 | 6 | 6 | 2 | 6 | 1.5 | 3 | 3 | 2.5 | 6 | 5 | 3 | 3 | 2 | 5 | 2.5 | 2.5 | 5 | 2.5 | 2 | 5 | 3 | 1.5 | 5 | 6 | 2 | 1.5 | 2 | 2.5 | 5 | 6 | 5 | 5 | 2 | 3 | 1.5 | 3 | 2 | 1.5 | 3 | 3 | 3 | 2 | 3 | 1.5 | 2.5 | 3 | 2 | 6 | 1.5 | 3 | 4 | 6
267 | 20.5 | 11.5 | 31.5 | 47.5 | 64.5 | 78.5 | 89.5 | 102 | 115.5 | 132 | 144.5 | 155 | 163.5 | 176 | 2.5 | 3 | 3 | 3 | 5 | 4 | 5 | 6 | 2 | 6 | 3 | 5 | 5 | 6 | 3 | 3 | 4 | 2.5 | 2.5 | 5 | 1.5 | 2 | 1.5 | 6 | 2 | 1.5 | 4 | 5 | 1.5 | 3 | 5 | 4 | 3 | 6 | 5 | 2.5 | 2.5 | 6 | 1.5 | 2.5 | 4 | 1.5 | 3 | 2 | 2 | 1.5 | 3 | 2 | 5 | 2 | 1.5 | 4
268 | 20 | 14 | 27 | 39.5 | 50 | 67.5 | 83.5 | 98 | 112.5 | 122 | 135.5 | 154.5 | 166 | 178 | 3 | 4 | 3 | 4 | 4 | 2 | 5 | 2 | 6 | 1.5 | 2 | 3 | 1.5 | 5 | 1.5 | 2.5 | 5 | 6 | 1.5 | 5 | 4 | 5 | 4 | 3 | 3 | 2.5 | 3 | 6 | 2 | 4 | 6 | 2.5 | 2 | 3 | 2.5 | 2 | 3 | 2.5 | 5 | 3 | 5 | 6 | 4 | 4 | 3 | 3 | 3 | 2.5 | 4 | 2.5 | 1.5 | 4
269 | 20 | 12 | 26 | 42 | 52.5 | 62 | 73 | 87.5 | 103.5 | 121 | 134 | 149.5 | 165.5 | 180.5 | 3 | 2 | 3 | 4 | 5 | 3 | 2 | 4 | 4 | 3 | 6 | 3 | 1.5 | 3 | 3 | 3 | 2 | 1.5 | 2 | 4 | 2 | 2 | 2 | 5 | 2 | 1.5 | 5 | 6 | 5 | 4 | 4 | 3 | 3 | 2.5 | 6 | 6 | 4 | 2.5 | 1.5 | 5 | 3 | 5 | 6 | 1.5 | 5 | 3 | 5 | 3 | 4 | 6 | 3 | 2
270 | 23 | 13 | 31 | 43.5 | 49.5 | 58.5 | 70.5 | 90.5 | 104.5 | 121 | 134.5 | 143 | 154.5 | 168.5 | 5 | 3 | 2 | 3 | 6 | 4 | 4 | 4 | 6 | 2.5 | 1.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 3 | 1.5 | 2.5 | 2 | 2 | 2.5 | 2.5 | 5 | 6 | 6 | 2 | 6 | 1.5 | 5 | 6 | 1.5 | 6 | 1.5 | 3 | 6 | 6 | 2.5 | 2 | 3 | 1.5 | 2.5 | 1.5 | 3 | 3 | 3 | 3 | 2.5 | 6 | 3 | 2.5 | 2.5
271 | 20.5 | 13 | 30.5 | 42.5 | 61 | 71 | 83 | 93.5 | 109.5 | 126 | 140 | 150.5 | 162.5 | 174.5 | 4 | 5 | 2 | 2 | 6 | 1.5 | 5 | 5 | 2.5 | 6 | 1.5 | 2 | 4 | 6 | 2.5 | 6 | 3 | 1.5 | 1.5 | 4 | 4 | 4 | 2 | 2 | 3 | 3 | 1.5 | 3 | 4 | 3 | 3 | 6 | 2.5 | 5 | 6 | 3 | 4 | 4 | 4 | 2 | 3 | 2 | 3 | 2.5 | 1.5 | 3 | 2.5 | 5 | 6 | 1.5 | 3 | 1.5
272 | 13 | 8 | 18.5 | 33 | 41.5 | 59.5 | 72.5 | 82.5 | 90 | 103.5 | 118 | 131 | 146 | 159.5 | 1.5 | 1.5 | 2.5 | 2.5 | 3 | 2 | 3 | 2.5 | 2.5 | 4 | 3 | 5 | 2.5 | 1.5 | 1.5 | 3 | 4 | 5 | 3 | 6 | 2.5 | 1.5 | 4 | 5 | 3 | 1.5 | 2.5 | 3 | 1.5 | 2 | 1.5 | 2.5 | 3 | 6 | 3 | 1.5 | 6 | 3 | 1.5 | 4 | 1.5 | 6 | 2.5 | 3 | 4 | 2 | 6 | 3 | 5 | 4 | 3 | 1.5
273 | 24.5 | 18 | 36.5 | 46 | 58.5 | 72 | 87.5 | 100.5 | 112.5 | 126 | 136 | 154 | 166 | 177.5 | 6 | 5 | 3 | 4 | 1.5 | 5 | 6 | 6 | 3 | 1.5 | 3 | 2 | 2 | 6 | 3 | 1.5 | 3 | 2.5 | 3 | 5 | 2.5 | 2 | 6 | 5 | 4 | 3 | 3 | 3 | 1.5 | 5 | 3 | 2.5 | 4 | 1.5 | 3 | 5 | 3 | 2 | 3 | 2 | 5 | 5 | 2 | 6 | 4 | 1.5 | 2.5 | 4 | 4 | 2.5 | 2 | 3
274 | 27 | 19 | 32.5 | 46 | 57.5 | 69.5 | 84 | 92 | 101 | 110 | 124 | 138.5 | 152.5 | 163.5 | 6 | 2 | 6 | 5 | 5 | 3 | 4 | 1.5 | 1.5 | 5 | 5 | 2 | 3 | 3 | 3 | 2.5 | 2.5 | 2.5 | 4 | 3 | 1.5 | 4 | 6 | 3 | 1.5 | 2 | 3 | 1.5 | 3 | 1.5 | 3 | 1.5 | 2.5 | 2.5 | 2 | 2 | 5 | 3 | 3 | 3 | 6 | 3 | 2.5 | 3 | 4 | 4 | 3 | 3 | 4 | 2.5 | 3 | 1.5
275 | 23.5 | 13.5 | 27.5 | 41 | 50.5 | 66 | 79 | 93 | 104.5 | 115 | 128.5 | 145.5 | 160.5 | 175 | 4 | 3 | 1.5 | 5 | 6 | 4 | 1.5 | 2.5 | 6 | 2 | 1.5 | 4 | 2 | 3 | 3 | 1.5 | 1.5 | 6 | 2 | 6 | 3 | 3 | 3 | 4 | 2.5 | 2.5 | 6 | 3 | 2 | 2.5 | 2 | 5 | 3 | 1.5 | 3 | 3 | 6 | 2 | 3 | 2.5 | 5 | 3 | 4 | 5 | 6 | 2.5 | 4 | 2.5 | 5 | 1.5 | 4 | 4
276 | 21.5 | 12.5 | 27.5 | 40.5 | 53.5 | 68.5 | 84.5 | 95.5 | 112.5 | 125 | 139 | 150 | 163.5 | 175.5 | 1.5 | 6 | 3 | 2 | 6 | 3 | 3 | 3 | 3 | 5 | 3 | 2 | 5 | 1.5 | 2.5 | 4 | 4 | 2 | 3 | 6 | 5 | 3 | 3 | 5 | 2 | 2 | 3 | 4 | 5 | 3 | 5 | 4 | 1.5 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 3 | 1.5 | 5 | 4 | 3 | 1.5 | 1.5 | 6
277 | 26.5 | 14.5 | 32 | 44.5 | 59.5 | 73.5 | 87.5 | 96.5 | 109 | 121 | 134 | 149 | 167.5 | 179 | 3 | 4 | 5 | 2.5 | 6 | 6 | 3 | 2.5 | 6 | 2 | 3 | 1.5 | 2 | 3 | 4 | 6 | 5 | 3 | 3 | 3 | 2 | 5 | 2 | 5 | 4 | 1.5 | 1.5 | 2 | 4 | 2.5 | 2 | 4 | 1.5 | 3 | 5 | 2.5 | 6 | 3 | 1.5 | 2.5 | 2.5 | 5 | 2.5 | 5 | 5 | 5 | 2.5 | 6 | 5 | 2.5 | 1.5 | 2.5
278 | 17.5 | 9.5 | 22.5 | 35 | 52.5 | 68 | 85 | 97.5 | 109.5 | 125.5 | 137.5 | 145.5 | 156.5 | 170.5 | 4 | 2 | 2 | 1.5 | 2 | 6 | 2.5 | 2.5 | 6 | 1.5 | 3 | 2 | 3 | 6 | 2.5 | 6 | 3 | 2.5 | 6 | 4 | 2 | 3 | 6 | 6 | 3 | 1.5 | 4 | 4 | 4 | 2 | 4 | 2 | 3 | 5 | 5 | 3 | 5 | 2.5 | 2.5 | 2 | 1.5 | 2 | 2 | 2.5 | 4 | 3 | 2.5 | 1.5 | 1.5 | 5 | 2.5 | 5
279 | 17 | 13 | 21 | 36.5 | 46 | 58 | 77.5 | 90.5 | 105 | 119 | 128 | 145 | 160 | 178 | 6 | 3 | 2 | 2 | 1.5 | 2.5 | 2 | 2 | 4 | 5 | 4 | 2.5 | 2 | 1.5 | 3 | 3 | 4 | 4 | 2 | 2 | 6 | 6 | 6 | 1.5 | 4 | 5 | 2 | 2 | 4 | 2.5 | 5 | 3 | 2 | 6 | 3 | 3 | 3 | 1.5 | 3 | 1.5 | 5 | 5 | 4 | 3 | 3 | 6 | 4 | 2 | 3 | 6 | 4 | 5
280 | 16 | 11.5 | 24 | 35.5 | 57.5 | 73.5 | 86.5 | 102.5 | 111.5 | 120.5 | 137.5 | 155.5 | 177.5 | 191 | 3 | 3 | 3 | 2.5 | 2 | 2.5 | 5 | 3 | 2 | 3 | 4 | 2.5 | 6 | 5 | 5 | 6 | 4 | 3 | 3 | 6 | 1.5 | 6 | 2.5 | 3 | 6 | 5 | 2 | 3 | 2 | 4 | 1.5 | 1.5 | 2 | 2 | 2.5 | 2.5 | 6 | 3 | 2 | 6 | 2 | 6 | 4 | 6 | 6 | 5 | 6 | 5 | 5 | 2.5 | 4 | 2
281 | 20 | 14 | 27.5 | 44.5 | 56.5 | 72 | 85.5 | 99 | 108.5 | 117.5 | 125 | 141.5 | 154.5 | 169.5 | 3 | 2 | 6 | 3 | 3 | 3 | 1.5 | 6 | 5 | 5 | 4 | 3 | 1.5 | 2 | 2.5 | 6 | 1.5 | 5 | 3 | 6 | 4 | 5 | 3 | 1.5 | 4 | 5 | 3 | 1.5 | 2 | 3 | 3 | 1.5 | 3 | 2.5 | 2 | 1.5 | 2 | 1.5 | 1.5 | 2.5 | 1.5 | 6 | 3 | 6 | 4 | 4 | 2 | 3 | 2 | 2 | 5 | 6
282 | 20.5 | 9.5 | 23.5 | 36.5 | 48.5 | 62.5 | 80.5 | 91.5 | 106.5 | 121.5 | 139.5 | 156.5 | 171 | 179 | 2.5 | 2 | 2 | 3 | 6 | 5 | 1.5 | 1.5 | 3 | 4 | 3 | 3 | 2.5 | 3 | 5 | 1.5 | 3 | 3 | 5 | 3 | 6 | 4 | 6 | 2 | 4 | 3 | 2 | 2 | 5 | 5 | 2 | 3 | 4 | 5 | 4 | 2 | 3 | 5 | 5 | 5 | 5 | 3 | 3 | 6 | 6 | 1.5 | 3 | 4 | 1.5 | 3 | 2 | 1.5
283 | 14 | 10 | 22 | 41 | 50 | 67.5 | 80 | 91.5 | 107 | 120.5 | 132 | 145.5 | 160 | 172 | 2.5 | 3 | 3 | 1.5 | 2.5 | 1.5 | 3 | 5 | 6 | 4 | 6 | 3 | 1.5 | 2 | 2.5 | 3 | 6 | 6 | 1.5 | 4 | 2.5 | 2 | 2 | 6 | 2.5 | 2.5 | 1.5 | 5 | 5 | 4 | 5 | 1.5 | 2.5 | 2.5 | 2.5 | 6 | 3 | 3 | 2.5 | 3 | 4 | 2 | 5 | 2.5 | 1.5 | 6 | 3 | 4 | 3 | 3 | 4 | 2
284 | 20.5 | 13.5 | 29.5 | 39 | 54.5 | 70.5 | 84 | 92 | 108 | 118.5 | 128 | 141.5 | 154.5 | 166.5 | 1.5 | 4 | 2 | 6 | 3 | 4 | 3 | 6 | 2 | 2.5 | 2.5 | 2.5 | 1.5 | 3 | 5 | 6 | 3 | 4 | 6 | 3 | 6 | 1.5 | 4 | 2 | 1.5 | 3 | 2 | 1.5 | 2 | 3 | 6 | 5 | 3 | 1.5 | 3 | 3 | 2 | 1.5 | 2 | 4 | 1.5 | 3 | 4 | 5 | 5 | 4 | 2.5 | 1.5 | 2 | 2 | 3 | 5
285 | 21 | 12.5 | 29 | 41.5 | 52 | 66 | 74 | 86.5 | 102 | 116.5 | 133.5 | 151 | 168 | 177.5 | 2 | 2.5 | 4 | 4 | 2.5 | 6 | 5 | 3 | 3 | 3 | 5 | 1.5 | 3 | 1.5 | 3 | 3 | 4 | 6 | 1.5 | 2.5 | 2 | 1.5 | 2 | 2.5 | 3 | 5 | 3 | 1.5 | 6 | 4 | 1.5 | 4 | 3 | 2.5 | 6 | 3 | 5 | 5 | 5 | 2 | 5 | 1.5 | 6 | 5 | 3 | 3 | 6 | 5 | 1.5 | 2.5 | 2.5 | 3
286 | 18.5 | 10 | 25.5 | 38.5 | 49 | 57.5 | 68.5 | 80 | 97 | 112 | 121 | 131.5 | 144 | 158.5 | 1.5 | 4 | 1.5 | 3 | 2.5 | 6 | 3 | 4 | 2.5 | 2 | 2.5 | 6 | 3 | 3 | 2 | 2.5 | 2.5 | 1.5 | 1.5 | 3 | 2.5 | 3 | 3 | 2.5 | 1.5 | 3 | 4 | 3 | 5 | 5 | 2 | 5 | 4 | 2 | 6 | 3 | 3 | 2.5 | 1.5 | 2 | 1.5 | 2.5 | 2.5 | 4 | 2 | 4 | 5 | 1.5 | 5 | 3 | 1.5 | 5
287 | 20 | 14 | 29 | 43.5 | 62 | 75 | 96 | 104.5 | 122 | 133.5 | 148 | 156.5 | 165.5 | 180.5 | 5 | 2 | 3 | 4 | 3 | 3 | 3 | 6 | 6 | 3 | 3 | 2.5 | 6 | 5 | 5 | 2.5 | 2.5 | 5 | 1.5 | 4 | 6 | 3 | 6 | 6 | 3 | 2.5 | 1.5 | 1.5 | 4 | 6 | 6 | 1.5 | 5 | 3 | 2 | 1.5 | 1.5 | 3 | 4 | 6 | 2.5 | 1.5 | 2.5 | 2 | 2.5 | 2 | 2.5 | 2 | 2 | 4 | 3 | 6
288 | 19.5 | 15 | 25.5 | 38 | 50 | 68 | 79.5 | 89.5 | 108.5 | 123 | 143 | 156 | 171 | 185 | 2 | 4 | 6 | 3 | 1.5 | 3 | 3 | 3 | 2 | 5 | 3 | 2.5 | 3 | 3 | 3 | 3 | 6 | 2 | 4 | 6 | 3 | 3 | 2.5 | 3 | 1.5 | 2.5 | 3 | 3 | 6 | 3 | 6 | 4 | 5 | 2.5 | 3 | 4 | 6 | 6 | 2 | 6 | 6 | 2 | 2.5 | 2.5 | 6 | 2.5 | 1.5 | 5 | 4 | 3 | 4 | 3
289 | 17.5 | 9.5 | 23.5 | 35 | 44.5 | 53.5 | 61 | 78 | 94.5 | 109 | 122.5 | 132.5 | 145 | 157 | 1.5 | 3 | 2 | 3 | 4 | 4 | 3 | 3 | 2.5 | 1.5 | 2.5 | 5 | 2.5 | 3 | 1.5 | 2.5 | 1.5 | 3 | 2.5 | 2 | 2.5 | 1.5 | 1.5 | 2 | 5 | 3 | 3 | 6 | 5 | 6 | 4 | 1.5 | 1.5 | 3 | 5 | 5 | 1.5 | 4 | 5 | 3 | 1.5 | 5 | 2 | 1.5 | 3 | 4 | 1.5 | 4 | 1.5 | 3 | 6 | 1.5
290 | 25 | 19 | 30 | 44.5 | 56 | 67.5 | 76.5 | 86.5 | 99 | 110.5 | 120 | 135 | 151 | 162.5 | 3 | 6 | 5 | 5 | 3 | 3 | 3 | 2 | 2.5 | 5 | 4 | 3 | 2 | 3 | 2.5 | 4 | 2 | 2.5 | 2 | 5 | 3 | 2.5 | 2 | 1.5 | 1.5 | 3 | 1.5 | 4 | 2.5 | 3 | 4 | 3 | 1.5 | 6 | 1.5 | 2.5 | 2 | 3 | 3 | 1.5 | 3 | 3 | 3 | 6 | 3 | 5 | 5 | 3 | 3 | 2 | 2.5 | 4
291 | 22.5 | 17.5 | 28 | 42.5 | 55 | 73 | 88.5 | 99 | 109 | 126 | 138 | 152 | 162.5 | 179.5 | 2.5 | 6 | 3 | 6 | 2 | 3 | 1.5 | 4 | 1.5 | 6 | 4 | 3 | 2.5 | 4 | 3 | 3 | 6 | 3 | 4 | 5 | 1.5 | 3 | 5 | 6 | 1.5 | 3 | 3 | 3 | 2.5 | 2 | 3 | 2.5 | 5 | 3 | 6 | 3 | 2.5 | 4 | 1.5 | 4 | 2 | 2 | 6 | 4 | 3 | 2 | 1.5 | 4 | 6 | 6 | 2.5 | 2.5
292 | 26 | 17 | 34 | 46 | 56 | 67.5 | 79.5 | 91.5 | 99.5 | 115 | 126 | 138 | 150.5 | 161.5 | 3 | 6 | 2 | 6 | 6 | 3 | 3 | 5 | 2.5 | 3 | 5 | 1.5 | 3 | 3 | 1.5 | 2.5 | 1.5 | 2 | 5 | 3 | 4 | 1.5 | 4 | 2.5 | 2 | 5 | 2 | 3 | 1.5 | 3 | 1.5 | 2 | 5 | 2.5 | 5 | 3 | 3 | 2 | 3 | 3 | 3 | 4 | 2.5 | 2.5 | 3 | 2.5 | 3 | 4 | 1.5 | 3 | 2.5 | 4
293 | 16 | 8 | 23 | 33 | 49.5 | 68 | 87 | 99 | 114 | 124.5 | 137.5 | 151 | 161 | 180 | 1.5 | 3 | 1.5 | 2 | 4 | 4 | 4 | 3 | 2.5 | 2 | 1.5 | 4 | 6 | 2 | 2.5 | 6 | 5 | 5 | 6 | 2.5 | 5 | 5 | 6 | 3 | 2.5 | 2.5 | 4 | 3 | 5 | 3 | 4 | 3 | 2 | 3 | 4 | 1.5 | 1.5 | 2.5 | 6 | 3 | 4 | 2.5 | 3 | 4 | 1.5 | 2.5 | 2 | 4 | 4 | 6 | 3 | 6
294 | 22 | 18 | 30 | 47 | 56 | 72.5 | 84.5 | 102 | 115.5 | 127 | 140 | 155.5 | 171.5 | 185.5 | 6 | 6 | 4 | 2 | 2 | 2 | 6 | 2 | 6 | 2 | 4 | 5 | 1.5 | 3 | 1.5 | 3 | 2.5 | 6 | 6 | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 4 | 1.5 | 6 | 1.5 | 3 | 3 | 2 | 1.5 | 5 | 3 | 4 | 2 | 4 | 3 | 1.5 | 3 | 6 | 5 | 5 | 5 | 3 | 3 | 5 | 3 | 3 | 3
295 | 17.5 | 12 | 25.5 | 39.5 | 54.5 | 67.5 | 81 | 94 | 109 | 121 | 131.5 | 146.5 | 163.5 | 174 | 6 | 1.5 | 3 | 1.5 | 2.5 | 3 | 5 | 3 | 6 | 2 | 2 | 4 | 1.5 | 5 | 6 | 2.5 | 3 | 4 | 3 | 3 | 3 | 2.5 | 2 | 6 | 3 | 2 | 4 | 4 | 6 | 1.5 | 6 | 1.5 | 1.5 | 3 | 2.5 | 5 | 2 | 5 | 1.5 | 2 | 3 | 3 | 3 | 6 | 2 | 3 | 6 | 6 | 3 | 2 | 2.5 | 3
296 | 23 | 16 | 27.5 | 36.5 | 46.5 | 64.5 | 81 | 90.5 | 103 | 118.5 | 128 | 134 | 145.5 | 156.5 | 2 | 6 | 6 | 2 | 4 | 3 | 2.5 | 2 | 3 | 1.5 | 1.5 | 3 | 3 | 3 | 2.5 | 1.5 | 5 | 2 | 6 | 5 | 1.5 | 6 | 4 | 5 | 2 | 2 | 3 | 2.5 | 2.5 | 6 | 2.5 | 1.5 | 1.5 | 6 | 2 | 6 | 2.5 | 2.5 | 3 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 4 | 3 | 2.5 | 2 | 2 | 3 | 3 | 3
297 | 19.5 | 14 | 27 | 40 | 51 | 64 | 73.5 | 84 | 98.5 | 111 | 122.5 | 137 | 150.5 | 164.5 | 6 | 4 | 2 | 2 | 4 | 1.5 | 2.5 | 5 | 3 | 2 | 2 | 6 | 1.5 | 4 | 2.5 | 3 | 3 | 3 | 3 | 4 | 2 | 4 | 1.5 | 2 | 4 | 1.5 | 2 | 3 | 2.5 | 3 | 3 | 6 | 3 | 3 | 2.5 | 4 | 1.5 | 5 | 2 | 3 | 3 | 2.5 | 6 | 3 | 2.5 | 2.5 | 2.5 | 6 | 6 | 3 | 3 | 2
298 | 24 | 18 | 29 | 43.5 | 56.5 | 69 | 82 | 95 | 114 | 131 | 147 | 157 | 168 | 181 | 5 | 4 | 4 | 5 | 3 | 3 | 2 | 3 | 6 | 2.5 | 3 | 3 | 3 | 5 | 3 | 2 | 2.5 | 4 | 3 | 3 | 5 | 3 | 3 | 2 | 2.5 | 2.5 | 4 | 4 | 5 | 4 | 6 | 4 | 6 | 3 | 3 | 5 | 6 | 3 | 4 | 3 | 2 | 2.5 | 1.5 | 4 | 2 | 2.5 | 5 | 1.5 | 2.5 | 3 | 5 | 2.5
299 | 18 | 13 | 25.5 | 41 | 56 | 70 | 86.5 | 102 | 111.5 | 124.5 | 140 | 149 | 164 | 175.5 | 6 | 1.5 | 2.5 | 3 | 2 | 3 | 5 | 2.5 | 4 | 4 | 6 | 1.5 | 2 | 3 | 5 | 5 | 3 | 3 | 3 | 5 | 6 | 6 | 2 | 2.5 | 5 | 1.5 | 3 | 6 | 2 | 3 | 2 | 2.5 | 5 | 3 | 2.5 | 2.5 | 6 | 4 | 3 | 2.5 | 2.5 | 3 | 1.5 | 2 | 6 | 3 | 4 | 2 | 2.5 | 5 | 2.5 | 1.5
300 | 28 | 18 | 35.5 | 51 | 67 | 77 | 89 | 98.5 | 108 | 121.5 | 133 | 145.5 | 161.5 | 180.5 | 6 | 2 | 6 | 4 | 5 | 5 | 5 | 2.5 | 5 | 4 | 2.5 | 4 | 6 | 5 | 3 | 2 | 4 | 1.5 | 3 | 1.5 | 1.5 | 6 | 2 | 2.5 | 3 | 3 | 2 | 1.5 | 3 | 2 | 1.5 | 3 | 6 | 3 | 3 | 1.5 | 3 | 3 | 2.5 | 3 | 6 | 2.5 | 1.5 | 2.5 | 4 | 3 | 4 | 5 | 6 | 5 | 3 | 5
301 | 15.5 | 9.5 | 21 | 33 | 48.5 | 62 | 79 | 89.5 | 100.5 | 113.5 | 126.5 | 138.5 | 152.5 | 167.5 | 2.5 | 2 | 2 | 3 | 3 | 3 | 2.5 | 3 | 4 | 2 | 3 | 3 | 2.5 | 5 | 5 | 3 | 2.5 | 6 | 2 | 3 | 6 | 3 | 3 | 5 | 2 | 3 | 1.5 | 4 | 2.5 | 1.5 | 4 | 3 | 5 | 3 | 2 | 3 | 2 | 3 | 5 | 3 | 3 | 3 | 2 | 4 | 6 | 3 | 2 | 3 | 3 | 2 | 6 | 4
302 | 22 | 14 | 28 | 40.5 | 53 | 62.5 | 79 | 94 | 103.5 | 115.5 | 131 | 150 | 162 | 175 | 3 | 6 | 3 | 2 | 5 | 3 | 3 | 3 | 5 | 1.5 | 3 | 3 | 2 | 3 | 5 | 2.5 | 3 | 1.5 | 2 | 3 | 6 | 6 | 2 | 2.5 | 6 | 3 | 2 | 4 | 3 | 3 | 2 | 1.5 | 4 | 4 | 1.5 | 2.5 | 3 | 2.5 | 4 | 6 | 3 | 6 | 6 | 4 | 2.5 | 2 | 2.5 | 5 | 1.5 | 2.5 | 3 | 6
303 | 20.5 | 10.5 | 26 | 42.5 | 54.5 | 71 | 83.5 | 92.5 | 103 | 114.5 | 125.5 | 137.5 | 154.5 | 164 | 4 | 3 | 1.5 | 2 | 5 | 5 | 2.5 | 3 | 6 | 3 | 1.5 | 6 | 5 | 3 | 2.5 | 1.5 | 1.5 | 6 | 3 | 6 | 5 | 2.5 | 3 | 2 | 3 | 1.5 | 3 | 1.5 | 2.5 | 4 | 2 | 2 | 4 | 3 | 1.5 | 3 | 5 | 1.5 | 2 | 2.5 | 5 | 3 | 2.5 | 1.5 | 5 | 6 | 2 | 4 | 1.5 | 3 | 2.5 | 2.5
304 | 27.5 | 20 | 34 | 47 | 55 | 70.5 | 87.5 | 97 | 109 | 119 | 132 | 144 | 164 | 177.5 | 5 | 5 | 5 | 5 | 1.5 | 6 | 4 | 2.5 | 2 | 6 | 2 | 3 | 1.5 | 3 | 2 | 1.5 | 5 | 3 | 1.5 | 6 | 3 | 4 | 5 | 5 | 2.5 | 2.5 | 3 | 1.5 | 3 | 2 | 3 | 4 | 2.5 | 1.5 | 2 | 4 | 2.5 | 5 | 2.5 | 3 | 3 | 4 | 2 | 3 | 6 | 6 | 6 | 2 | 1.5 | 3 | 3 | 6
305 | 14 | 9.5 | 21 | 36 | 54 | 66 | 81.5 | 95 | 107 | 121 | 133.5 | 146 | 164 | 178.5 | 1.5 | 1.5 | 4 | 2.5 | 3 | 1.5 | 3 | 4 | 5 | 5 | 2.5 | 2.5 | 6 | 3 | 6 | 3 | 3 | 3 | 3 | 3 | 6 | 2.5 | 3 | 4 | 3 | 3 | 1.5 | 6 | 1.5 | 5 | 2.5 | 3 | 2 | 3 | 3 | 6 | 4 | 4 | 3 | 1.5 | 3 | 1.5 | 3 | 5 | 5 | 4 | 5 | 4 | 5 | 2.5 | 4 | 3
306 | 28.5 | 20 | 37.5 | 48 | 63 | 76.5 | 86.5 | 95.5 | 113 | 125.5 | 137.5 | 149 | 162 | 179 | 6 | 6 | 3 | 5 | 6 | 2.5 | 3 | 6 | 2.5 | 5 | 1.5 | 1.5 | 2 | 6 | 4 | 3 | 3 | 1.5 | 4 | 5 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 6 | 6 | 2.5 | 2 | 1.5 | 4 | 5 | 5 | 3 | 2 | 2 | 1.5 | 2.5 | 1.5 | 6 | 2 | 5 | 3 | 3 | 6 | 5 | 2 | 4
307 | 19 | 15 | 24 | 34 | 49.5 | 63 | 80 | 93.5 | 103.5 | 112 | 126 | 136.5 | 154 | 165 | 3 | 6 | 4 | 2 | 1.5 | 2.5 | 2 | 3 | 2 | 1.5 | 4 | 2.5 | 2 | 6 | 5 | 2.5 | 6 | 4 | 2 | 1.5 | 4 | 6 | 3 | 4 | 2 | 3 | 6 | 2.5 | 2 | 2 | 3 | 3 | 2 | 2 | 1.5 | 3 | 3 | 2 | 5 | 4 | 3 | 2 | 2.5 | 3 | 6 | 2.5 | 6 | 3 | 4 | 3 | 1.5 | 2.5
308 | 24.5 | 13.5 | 29 | 42 | 52.5 | 63.5 | 76 | 88.5 | 101.5 | 118 | 131 | 149 | 164 | 175 | 3 | 6 | 2.5 | 2 | 6 | 5 | 2.5 | 2 | 3 | 3 | 5 | 2 | 3 | 1.5 | 2 | 4 | 1.5 | 1.5 | 6 | 2 | 2.5 | 1.5 | 2.5 | 6 | 2 | 3 | 5 | 2.5 | 3 | 1.5 | 2.5 | 6 | 1.5 | 4 | 5 | 6 | 2 | 5 | 3 | 3 | 5 | 5 | 3 | 5 | 4 | 3 | 3 | 5 | 2 | 3 | 3 | 3
309 | 19.5 | 15 | 24.5 | 35 | 50 | 66 | 79.5 | 93.5 | 108 | 122 | 134.5 | 145 | 164 | 179.5 | 2 | 2 | 5 | 6 | 3 | 1.5 | 2 | 3 | 4 | 3 | 2 | 1.5 | 6 | 3 | 3 | 3 | 5 | 3 | 5 | 3 | 2 | 5 | 1.5 | 5 | 3 | 3 | 6 | 2 | 1.5 | 4 | 3 | 6 | 4 | 2 | 2 | 6 | 6 | 2 | 2 | 2.5 | 2.5 | 2 | 4 | 2 | 4 | 3 | 6 | 6 | 5 | 5 | 2.5 | 3
310 | 13 | 8.5 | 18.5 | 33.5 | 47 | 58.5 | 72.5 | 88 | 100 | 113 | 129 | 142.5 | 159 | 169 | 2.5 | 3 | 1.5 | 1.5 | 2 | 2.5 | 2.5 | 3 | 4 | 3 | 4 | 4 | 2 | 5 | 1.5 | 5 | 3 | 2.5 | 3 | 3 | 2 | 3 | 4 | 5 | 3 | 1.5 | 6 | 5 | 4 | 2.5 | 4 | 1.5 | 5 | 3 | 2 | 3 | 3 | 4 | 4 | 5 | 3 | 5 | 2.5 | 3 | 5 | 5 | 4 | 2.5 | 1.5 | 3 | 2.5 | 3
311 | 20 | 11 | 25.5 | 38.5 | 51.5 | 66 | 79 | 93 | 109.5 | 123 | 133 | 149 | 163 | 177.5 | 3 | 3 | 2 | 3 | 5 | 4 | 2.5 | 3 | 4 | 2.5 | 5 | 1.5 | 2 | 2 | 3 | 6 | 3 | 2.5 | 6 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 2 | 5 | 2.5 | 6 | 2 | 6 | 6 | 3 | 1.5 | 3 | 3 | 2.5 | 2.5 | 2 | 6 | 1.5 | 6 | 2.5 | 4 | 6 | 1.5 | 2.5 | 5 | 4 | 2.5 | 3
312 | 20.5 | 15.5 | 26 | 38.5 | 51 | 63.5 | 74 | 86.5 | 100.5 | 119.5 | 127 | 138.5 | 155.5 | 171 | 5 | 1.5 | 4 | 5 | 3 | 2 | 2.5 | 3 | 2.5 | 5 | 2 | 3 | 5 | 2 | 1.5 | 4 | 5 | 4 | 2 | 1.5 | 2 | 1.5 | 3 | 4 | 4 | 2.5 | 3 | 3 | 4 | 6 | 2.5 | 1.5 | 2 | 5 | 6 | 6 | 1.5 | 1.5 | 2.5 | 2 | 1.5 | 2 | 5 | 3 | 2 | 6 | 4 | 5 | 6 | 5 | 3 | 1.5
313 | 21 | 13.5 | 25.5 | 39.5 | 55.5 | 63 | 70 | 84 | 96.5 | 108.5 | 129 | 143.5 | 155 | 172 | 2 | 5 | 2.5 | 4 | 6 | 1.5 | 1.5 | 3 | 3 | 4 | 5 | 2 | 6 | 3 | 2 | 5 | 1.5 | 1.5 | 1.5 | 3 | 1.5 | 2.5 | 1.5 | 1.5 | 2 | 5 | 2 | 5 | 1.5 | 4 | 3 | 4 | 5 | 1.5 | 3 | 2.5 | 6 | 6 | 6 | 2.5 | 2.5 | 3 | 4 | 5 | 1.5 | 2 | 4 | 4 | 2.5 | 2.5 | 6 | 6
314 | 21 | 14.5 | 28.5 | 41.5 | 50.5 | 65 | 85 | 98.5 | 111 | 124.5 | 146.5 | 158 | 172 | 189.5 | 1.5 | 3 | 4 | 6 | 2.5 | 4 | 2.5 | 5 | 6 | 2 | 3 | 2 | 2.5 | 2 | 1.5 | 3 | 2.5 | 6 | 4 | 2 | 5 | 4 | 6 | 5 | 5 | 2 | 2.5 | 4 | 3 | 5 | 1.5 | 3 | 6 | 4 | 1.5 | 2 | 6 | 6 | 4 | 6 | 5 | 1.5 | 2.5 | 2.5 | 3 | 3 | 3 | 5 | 2.5 | 5 | 4 | 6
315 | 18.5 | 13.5 | 23.5 | 42.5 | 55 | 63 | 72.5 | 84 | 98.5 | 115.5 | 125 | 141 | 149 | 164 | 4 | 1.5 | 2 | 6 | 2.5 | 2.5 | 2 | 3 | 6 | 2 | 5 | 6 | 3 | 3 | 1.5 | 5 | 2 | 2 | 2.5 | 1.5 | 2 | 3 | 3 | 1.5 | 4 | 2 | 3 | 2.5 | 6 | 2.5 | 3 | 3 | 2 | 6 | 3 | 6 | 3 | 2 | 1.5 | 3 | 3 | 3 | 6 | 4 | 2.5 | 2 | 2 | 1.5 | 5 | 4 | 4 | 2
316 | 14 | 9.5 | 26 | 37 | 53 | 65 | 76.5 | 88.5 | 100.5 | 115 | 131 | 147.5 | 161 | 177 | 1.5 | 2.5 | 3 | 2.5 | 3 | 1.5 | 6 | 6 | 1.5 | 1.5 | 3 | 5 | 6 | 2.5 | 1.5 | 6 | 3 | 2.5 | 1.5 | 5 | 3 | 2.5 | 3 | 3 | 2.5 | 5 | 2.5 | 2 | 2 | 3 | 2 | 5 | 5 | 1.5 | 4 | 4 | 4 | 6 | 4 | 2 | 1.5 | 6 | 6 | 3 | 2.5 | 4 | 2 | 5 | 3 | 5 | 4 | 4
317 | 14.5 | 10 | 19.5 | 36.5 | 47 | 62.5 | 73.5 | 88.5 | 102.5 | 112 | 127.5 | 139 | 155 | 168.5 | 3 | 3 | 2.5 | 1.5 | 2.5 | 2 | 2.5 | 2.5 | 3 | 5 | 6 | 3 | 1.5 | 3 | 3 | 3 | 2.5 | 6 | 3 | 4 | 3 | 2.5 | 3 | 2.5 | 4 | 3 | 3 | 5 | 4 | 3 | 4 | 3 | 1.5 | 3 | 3 | 2 | 3 | 5 | 6 | 1.5 | 3 | 2.5 | 4 | 2 | 5 | 5 | 3 | 3 | 6 | 1.5 | 3 | 3
318 | 26.5 | 16.5 | 33.5 | 49.5 | 60 | 73 | 84 | 97.5 | 108 | 118.5 | 128 | 139 | 150.5 | 170.5 | 6 | 5 | 3 | 2.5 | 4 | 6 | 3 | 4 | 5 | 3 | 2 | 6 | 2.5 | 3 | 2.5 | 2.5 | 2.5 | 1.5 | 6 | 3 | 4 | 2.5 | 1.5 | 3 | 3 | 6 | 3 | 1.5 | 1.5 | 4 | 2 | 3 | 1.5 | 3 | 3 | 3 | 2 | 1.5 | 3 | 3 | 2 | 5 | 1.5 | 2.5 | 3 | 4 | 3 | 1.5 | 6 | 5 | 6 | 3
319 | 25.5 | 16.5 | 33.5 | 42.5 | 54.5 | 67 | 76 | 86.5 | 100.5 | 113.5 | 130.5 | 140 | 156.5 | 169.5 | 2.5 | 2 | 6 | 6 | 6 | 3 | 6 | 2 | 2 | 2.5 | 1.5 | 3 | 2 | 3 | 3 | 4 | 3 | 2.5 | 4 | 3 | 2 | 3 | 1.5 | 2.5 | 2.5 | 1.5 | 5 | 1.5 | 4 | 3 | 3 | 4 | 2.5 | 1.5 | 6 | 3 | 4 | 5 | 2 | 6 | 2 | 1.5 | 2 | 4 | 5 | 2.5 | 6 | 3 | 2 | 2.5 | 2.5 | 6
320 | 23 | 17 | 31 | 45.5 | 63.5 | 75.5 | 93.5 | 104.5 | 120.5 | 135 | 148 | 162 | 170.5 | 185.5 | 4 | 5 | 4 | 4 | 3 | 3 | 6 | 2 | 3 | 3 | 2.5 | 6 | 5 | 3 | 4 | 6 | 4 | 3 | 2.5 | 2.5 | 6 | 5 | 2 | 5 | 5 | 1.5 | 2.5 | 2 | 5 | 3 | 5 | 3 | 5 | 3 | 4 | 2.5 | 4 | 2 | 3 | 4 | 3 | 2 | 5 | 4 | 2 | 1.5 | 3 | 2 | 6 | 3 | 3 | 3
321 | 17.5 | 11.5 | 25 | 39 | 50 | 61 | 76 | 89 | 101 | 112.5 | 127 | 139 | 150.5 | 161.5 | 3 | 1.5 | 5 | 2 | 3 | 3 | 6 | 1.5 | 2 | 3 | 6 | 3 | 4 | 2.5 | 1.5 | 3 | 3 | 1.5 | 1.5 | 5 | 3 | 3 | 4 | 5 | 2 | 2 | 3 | 6 | 4 | 1.5 | 2.5 | 4 | 1.5 | 2 | 4 | 4 | 2.5 | 4 | 3 | 5 | 5 | 2.5 | 1.5 | 3 | 4 | 3 | 2.5 | 2 | 4 | 2.5 | 3 | 1.5
322 | 17.5 | 12 | 21.5 | 35 | 49.5 | 63.5 | 75.5 | 88.5 | 107.5 | 123 | 137.5 | 152.5 | 167 | 184 | 3 | 1.5 | 5 | 2.5 | 3 | 2.5 | 2.5 | 1.5 | 2.5 | 3 | 3 | 5 | 6 | 3 | 3 | 2.5 | 1.5 | 1.5 | 6 | 5 | 1.5 | 3 | 5 | 2.5 | 3 | 3 | 3 | 4 | 5 | 5 | 6 | 3 | 6 | 1.5 | 5 | 3 | 6 | 4 | 3 | 1.5 | 2 | 4 | 6 | 3 | 4 | 3 | 5 | 2.5 | 3 | 6 | 6 | 2
323 | 17.5 | 13.5 | 23.5 | 33.5 | 44 | 65 | 75 | 87 | 98.5 | 107.5 | 119.5 | 137.5 | 152.5 | 164.5 | 6 | 2.5 | 3 | 2 | 2.5 | 1.5 | 3 | 3 | 2.5 | 4 | 2 | 1.5 | 3 | 2.5 | 2 | 3 | 6 | 5 | 6 | 4 | 2.5 | 2.5 | 2 | 3 | 2 | 4 | 2 | 4 | 1.5 | 2.5 | 1.5 | 6 | 2 | 2.5 | 2 | 2.5 | 1.5 | 5 | 3 | 2.5 | 4 | 6 | 5 | 3 | 2 | 5 | 5 | 3 | 3 | 3 | 4 | 2
324 | 20.5 | 12 | 28 | 44 | 56.5 | 66 | 79.5 | 96 | 111 | 127 | 137.5 | 151 | 161.5 | 174 | 2 | 2 | 3 | 5 | 2.5 | 6 | 6 | 1.5 | 4 | 6 | 3 | 3 | 1.5 | 3 | 6 | 2 | 2.5 | 1.5 | 4 | 1.5 | 2 | 5 | 4 | 2.5 | 4 | 6 | 1.5 | 5 | 5 | 6 | 1.5 | 2.5 | 5 | 6 | 2 | 3 | 2 | 2.5 | 3 | 3 | 2.5 | 4 | 2 | 5 | 3 | 1.5 | 2 | 4 | 3 | 5 | 1.5 | 3
325 | 18 | 12 | 23 | 33.5 | 45 | 62.5 | 75 | 95 | 113 | 126.5 | 142.5 | 155.5 | 163.5 | 178.5 | 2 | 2 | 3 | 5 | 3 | 3 | 2.5 | 2.5 | 6 | 1.5 | 1.5 | 1.5 | 1.5 | 4 | 2 | 4 | 5 | 6 | 2.5 | 4 | 6 | 1.5 | 3 | 2 | 6 | 6 | 5 | 3 | 5 | 6 | 5 | 2 | 4 | 5 | 3 | 1.5 | 2 | 6 | 6 | 2 | 2 | 4 | 3 | 4 | 1.5 | 3 | 1.5 | 2 | 4 | 4 | 3 | 4
326 | 17.5 | 12 | 21.5 | 31.5 | 39.5 | 52 | 64.5 | 76 | 86 | 95.5 | 110.5 | 119 | 131 | 148 | 2 | 3 | 4 | 3 | 3 | 2.5 | 2 | 2 | 2.5 | 3 | 3 | 1.5 | 1.5 | 3 | 2 | 1.5 | 2 | 1.5 | 5 | 4 | 5 | 1.5 | 3 | 3 | 1.5 | 6 | 2.5 | 1.5 | 3 | 3 | 2 | 2 | 3 | 2 | 3 | 1.5 | 2 | 5 | 3 | 5 | 3 | 1.5 | 2.5 | 1.5 | 2.5 | 1.5 | 4 | 4 | 5 | 3 | 3 | 6
327 | 19 | 9 | 29 | 40.5 | 54.5 | 70 | 83 | 98.5 | 108 | 126 | 137 | 154 | 168 | 182 | 1.5 | 1.5 | 2 | 4 | 6 | 4 | 5 | 5 | 6 | 1.5 | 2.5 | 1.5 | 4 | 2.5 | 5 | 2.5 | 5 | 1.5 | 4 | 5 | 3 | 3 | 3 | 4 | 5 | 2.5 | 3 | 5 | 2 | 1.5 | 3 | 3 | 3 | 6 | 6 | 3 | 2 | 6 | 1.5 | 1.5 | 5 | 5 | 5 | 2 | 2 | 3 | 4 | 5 | 3 | 6 | 2 | 3
328 | 20 | 16.5 | 28 | 37.5 | 48 | 59 | 73 | 91.5 | 102.5 | 117 | 134 | 147.5 | 159 | 172 | 1.5 | 5 | 4 | 6 | 1.5 | 2 | 2 | 6 | 3 | 2.5 | 2.5 | 1.5 | 3 | 2.5 | 3 | 2 | 3 | 2.5 | 2.5 | 3 | 4 | 2 | 3 | 5 | 6 | 5 | 6 | 1.5 | 1.5 | 1.5 | 3 | 5 | 2 | 6 | 1.5 | 5 | 6 | 5 | 4 | 2 | 2.5 | 6 | 3 | 2 | 1.5 | 4 | 3 | 3 | 2.5 | 6 | 2.5 | 2
329 | 22.5 | 15 | 29 | 44.5 | 58.5 | 70 | 84.5 | 96.5 | 112 | 128.5 | 148.5 | 165 | 178.5 | 188.5 | 2 | 4 | 3 | 6 | 1.5 | 6 | 2.5 | 4 | 4 | 6 | 2.5 | 3 | 3 | 4 | 3 | 4 | 3 | 1.5 | 5 | 2 | 3 | 2.5 | 4 | 5 | 3 | 3 | 3 | 3 | 1.5 | 6 | 4 | 4 | 1.5 | 5 | 4 | 6 | 6 | 4 | 4 | 6 | 5 | 6 | 3 | 2.5 | 2.5 | 3 | 6 | 2 | 4 | 1.5 | 1.5 | 3
330 | 26 | 19 | 31.5 | 42.5 | 53 | 68 | 82.5 | 97.5 | 112.5 | 131 | 142 | 158 | 172 | 190 | 5 | 5 | 5 | 4 | 4 | 3 | 1.5 | 4 | 2 | 3 | 3 | 3 | 2 | 2 | 5 | 1.5 | 3 | 6 | 3 | 3 | 1.5 | 6 | 4 | 3 | 3 | 4 | 5 | 3 | 3 | 3 | 5 | 4 | 6 | 5 | 1.5 | 6 | 2 | 5 | 2.5 | 1.5 | 2 | 6 | 3 | 5 | 5 | 2 | 3 | 4 | 6 | 3 | 6 | 3
331 | 22.5 | 15 | 33.5 | 47.5 | 68.5 | 82 | 95.5 | 104.5 | 123.5 | 135 | 148 | 167 | 183.5 | 195.5 | 2 | 5 | 6 | 2 | 2.5 | 5 | 6 | 5 | 6 | 1.5 | 1.5 | 5 | 5 | 6 | 6 | 4 | 1.5 | 6 | 3 | 3 | 4 | 3 | 1.5 | 5 | 3 | 1.5 | 2.5 | 2 | 4 | 3 | 6 | 6 | 1.5 | 1.5 | 6 | 2.5 | 2.5 | 2.5 | 2 | 6 | 5 | 6 | 6 | 2 | 6 | 6 | 2.5 | 2 | 5 | 1.5 | 2.5 | 3
332 | 21 | 13 | 32 | 47 | 58.5 | 74 | 83.5 | 95 | 104 | 117 | 130 | 142 | 154 | 172 | 2 | 2 | 3 | 6 | 3 | 5 | 6 | 5 | 1.5 | 2.5 | 5 | 6 | 3 | 2 | 2.5 | 4 | 6 | 1.5 | 5 | 3 | 3 | 1.5 | 2 | 3 | 5 | 2.5 | 2.5 | 1.5 | 1.5 | 2 | 2.5 | 3 | 5 | 2 | 3 | 3 | 6 | 2.5 | 2 | 2.5 | 2.5 | 6 | 2 | 1.5 | 3 | 2 | 5 | 2 | 6 | 4 | 6 | 2
333 | 18.5 | 12.5 | 24 | 32 | 41 | 54.5 | 67 | 79.5 | 88 | 104.5 | 116 | 123 | 136 | 151.5 | 3 | 1.5 | 5 | 3 | 3 | 3 | 2.5 | 3 | 2 | 3 | 1.5 | 1.5 | 2 | 3 | 2 | 2 | 6 | 2 | 2.5 | 3 | 5 | 3 | 2.5 | 2 | 1.5 | 4 | 2 | 5 | 1.5 | 2 | 3 | 2 | 2.5 | 6 | 6 | 2 | 2.5 | 3 | 4 | 2 | 1.5 | 1.5 | 2.5 | 1.5 | 3 | 3 | 3 | 4 | 1.5 | 6 | 2 | 6
334 | 22 | 15.5 | 25.5 | 37 | 47 | 64.5 | 79.5 | 88.5 | 105 | 120 | 132.5 | 140 | 157 | 166 | 5 | 6 | 3 | 1.5 | 1.5 | 5 | 2 | 1.5 | 3 | 3 | 1.5 | 4 | 2 | 2.5 | 4 | 1.5 | 2.5 | 6 | 5 | 4 | 6 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 3 | 5 | 1.5 | 4 | 6 | 3 | 2 | 6 | 4 | 3 | 1.5 | 5 | 3 | 1.5 | 3 | 1.5 | 1.5 | 2 | 3 | 6 | 6 | 1.5 | 2 | 3 | 2.5
335 | 17.5 | 12.5 | 23 | 37 | 49.5 | 60.5 | 78.5 | 97.5 | 115 | 128.5 | 143.5 | 156.5 | 171.5 | 182 | 5 | 2.5 | 3 | 2 | 3 | 2 | 4 | 1.5 | 3 | 3 | 5 | 3 | 3 | 2.5 | 3 | 4 | 3 | 1.5 | 4 | 2.5 | 5 | 3 | 5 | 5 | 2 | 6 | 6 | 5 | 6 | 4 | 2.5 | 5 | 2 | 4 | 1.5 | 6 | 3 | 5 | 5 | 2 | 2 | 2 | 4 | 5 | 6 | 3 | 4 | 2 | 2.5 | 2 | 3 | 3
336 | 19 | 11.5 | 27 | 40 | 52 | 68 | 87 | 98.5 | 112 | 122 | 139.5 | 151 | 163 | 175 | 2 | 4 | 4 | 1.5 | 5 | 2.5 | 4 | 4 | 1.5 | 4 | 6 | 1.5 | 2.5 | 1.5 | 2 | 6 | 5 | 4 | 4 | 3 | 3 | 5 | 6 | 5 | 4 | 2 | 3 | 2.5 | 5 | 2 | 2.5 | 4 | 2 | 1.5 | 4 | 2.5 | 1.5 | 4 | 6 | 6 | 3 | 1.5 | 5 | 2 | 2 | 3 | 5 | 2 | 6 | 2 | 2 | 2
337 | 13 | 7.5 | 21 | 34.5 | 50.5 | 60 | 74.5 | 87 | 100 | 110 | 124 | 134 | 154 | 173 | 2 | 2.5 | 1.5 | 1.5 | 3 | 2.5 | 3 | 5 | 3 | 3 | 1.5 | 6 | 6 | 1.5 | 2.5 | 6 | 2.5 | 2 | 2 | 3 | 2.5 | 4 | 6 | 2 | 4 | 1.5 | 5 | 2 | 2 | 6 | 3 | 2 | 2.5 | 2.5 | 2 | 3 | 2.5 | 2.5 | 3 | 6 | 2.5 | 1.5 | 3 | 3 | 5 | 6 | 6 | 3 | 6 | 3 | 5 | 5
338 | 21 | 11 | 29 | 39.5 | 55.5 | 68.5 | 79.5 | 91.5 | 106 | 119.5 | 132 | 141 | 153.5 | 166 | 3 | 2.5 | 2.5 | 3 | 5 | 5 | 3 | 5 | 2.5 | 4 | 1.5 | 2.5 | 6 | 3 | 4 | 3 | 1.5 | 1.5 | 5 | 5 | 2.5 | 2 | 2.5 | 4 | 3 | 3 | 3 | 3 | 4 | 5 | 3 | 2.5 | 1.5 | 6 | 3 | 3 | 3 | 2 | 6 | 1.5 | 1.5 | 3 | 2 | 2.5 | 3 | 2.5 | 3 | 4 | 6 | 3 | 2 | 1.5
339 | 18 | 11 | 26 | 36 | 53.5 | 69 | 82 | 92 | 101.5 | 110 | 129 | 138 | 152.5 | 171.5 | 3 | 2 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 4 | 1.5 | 1.5 | 2.5 | 3 | 6 | 6 | 2.5 | 5 | 2 | 6 | 1.5 | 6 | 4 | 1.5 | 1.5 | 4 | 1.5 | 3 | 2 | 2 | 2.5 | 3 | 2.5 | 1.5 | 1.5 | 3 | 4 | 5 | 4 | 6 | 2 | 2.5 | 1.5 | 3 | 2.5 | 2 | 6 | 4 | 4 | 6 | 5 | 4
340 | 15.5 | 10.5 | 23.5 | 39.5 | 50.5 | 65.5 | 76.5 | 87 | 97.5 | 109 | 123 | 137 | 151.5 | 163.5 | 2 | 1.5 | 4 | 3 | 2 | 3 | 2 | 6 | 4 | 4 | 3 | 5 | 1.5 | 2.5 | 3 | 4 | 6 | 3 | 4 | 2 | 3 | 2.5 | 3 | 2.5 | 2 | 1.5 | 2 | 5 | 2.5 | 3 | 3 | 2 | 3 | 3 | 3 | 2.5 | 6 | 3 | 3 | 2 | 6 | 2.5 | 2.5 | 3 | 4 | 3 | 6 | 1.5 | 3 | 2.5 | 1.5 | 5
341 | 19.5 | 14.5 | 24 | 37.5 | 48.5 | 57 | 77 | 91.5 | 104.5 | 118.5 | 130 | 147.5 | 160.5 | 178 | 4 | 2.5 | 4 | 4 | 2 | 3 | 2 | 2.5 | 2 | 3 | 2.5 | 6 | 5 | 3 | 1.5 | 1.5 | 3 | 1.5 | 1.5 | 2.5 | 6 | 3 | 5 | 6 | 6 | 2.5 | 3 | 3 | 1.5 | 6 | 1.5 | 4 | 5 | 3 | 3 | 3 | 3 | 3 | 4 | 1.5 | 2.5 | 6 | 4 | 5 | 6 | 2 | 3 | 2 | 6 | 6 | 3 | 2.5
342 | 15.5 | 8.5 | 21 | 36.5 | 48 | 61 | 73 | 82.5 | 97 | 112.5 | 130.5 | 151.5 | 167.5 | 179.5 | 3 | 2 | 2 | 1.5 | 3 | 4 | 3 | 2.5 | 5 | 3 | 2.5 | 5 | 2.5 | 3 | 3 | 3 | 3 | 2 | 4 | 4 | 1.5 | 4 | 5 | 1.5 | 3 | 1.5 | 3 | 2 | 6 | 1.5 | 5 | 2 | 2.5 | 4 | 3 | 6 | 3 | 6 | 6 | 3 | 6 | 6 | 6 | 3 | 3 | 4 | 3 | 6 | 5 | 2.5 | 1.5 | 3
343 | 16 | 11.5 | 26 | 38.5 | 50 | 59 | 65.5 | 78.5 | 94.5 | 108.5 | 123 | 135 | 144.5 | 159.5 | 1.5 | 2 | 4 | 4 | 1.5 | 3 | 6 | 4 | 1.5 | 3 | 3 | 5 | 3 | 4 | 2 | 2.5 | 3 | 2.5 | 1.5 | 2 | 2 | 1.5 | 1.5 | 1.5 | 4 | 1.5 | 1.5 | 6 | 3 | 4 | 3 | 6 | 5 | 6 | 1.5 | 1.5 | 3 | 6 | 3 | 2.5 | 1.5 | 1.5 | 3 | 6 | 3 | 2 | 2.5 | 2 | 3 | 2 | 5 | 5
344 | 20 | 12 | 29 | 42.5 | 61.5 | 72 | 82.5 | 94.5 | 108.5 | 117.5 | 129.5 | 147.5 | 160 | 177.5 | 2.5 | 4 | 2.5 | 3 | 3 | 5 | 3 | 6 | 1.5 | 4 | 6 | 2 | 5 | 5 | 3 | 6 | 4 | 3 | 2 | 1.5 | 2 | 2.5 | 3 | 3 | 1.5 | 4 | 4 | 2.5 | 5 | 5 | 1.5 | 2.5 | 1.5 | 1.5 | 3 | 3 | 2.5 | 4 | 3 | 2.5 | 6 | 2 | 6 | 4 | 2 | 3 | 2.5 | 5 | 2.5 | 6 | 6 | 3
345 | 15 | 11 | 20.5 | 31.5 | 43.5 | 57.5 | 72.5 | 89 | 101 | 114.5 | 133 | 146 | 160 | 178 | 2.5 | 3 | 4 | 1.5 | 2 | 2 | 1.5 | 4 | 3 | 1.5 | 4 | 2.5 | 2.5 | 1.5 | 5 | 3 | 2 | 3 | 5 | 4 | 5 | 5 | 3 | 2 | 4 | 1.5 | 6 | 5 | 3 | 5 | 2 | 2 | 2.5 | 2 | 6 | 3 | 6 | 6 | 2.5 | 4 | 5 | 3 | 3 | 2 | 3 | 6 | 2.5 | 2.5 | 3 | 5 | 5 | 5
346 | 18.5 | 11.5 | 25 | 37 | 53.5 | 68.5 | 87.5 | 96 | 113.5 | 127 | 140.5 | 152 | 163 | 179 | 5 | 1.5 | 2.5 | 2.5 | 5 | 2 | 1.5 | 5 | 2.5 | 1.5 | 2 | 6 | 2.5 | 5 | 5 | 4 | 6 | 5 | 1.5 | 2.5 | 6 | 3 | 5 | 5 | 2.5 | 2.5 | 2 | 1.5 | 6 | 1.5 | 4 | 6 | 2.5 | 3 | 6 | 2 | 2.5 | 6 | 2.5 | 2.5 | 1.5 | 5 | 3 | 2 | 1.5 | 2 | 6 | 1.5 | 3 | 5 | 4 | 4
347 | 15.5 | 7.5 | 21 | 36.5 | 51 | 65 | 81 | 97 | 106 | 117.5 | 128.5 | 145.5 | 156 | 165.5 | 1.5 | 1.5 | 1.5 | 3 | 5 | 3 | 3 | 2.5 | 3 | 6 | 2.5 | 4 | 1.5 | 5 | 5 | 3 | 6 | 2 | 3 | 3 | 4 | 2 | 5 | 5 | 3 | 3 | 6 | 4 | 1.5 | 2 | 1.5 | 4 | 1.5 | 3 | 5 | 2 | 2 | 3 | 4 | 2 | 3 | 4 | 6 | 4 | 3 | 2 | 1.5 | 4 | 1.5 | 2.5 | 4 | 1.5
348 | 19 | 11 | 24.5 | 35.5 | 47.5 | 62.5 | 72.5 | 91 | 100 | 109.5 | 117.5 | 127.5 | 142.5 | 152.5 | 3 | 1.5 | 1.5 | 5 | 6 | 2 | 3 | 2.5 | 1.5 | 5 | 2.5 | 2 | 2 | 6 | 1.5 | 2.5 | 2 | 5 | 5 | 3 | 3 | 2 | 3 | 2 | 2.5 | 5 | 5 | 6 | 3 | 1.5 | 1.5 | 3 | 2 | 3 | 2 | 2.5 | 2 | 2 | 2.5 | 1.5 | 3 | 1.5 | 3 | 2.5 | 2 | 3 | 4 | 6 | 2.5 | 3 | 3 | 1.5
349 | 21 | 13 | 25.5 | 37.5 | 50.5 | 65.5 | 83.5 | 96 | 112 | 122 | 132.5 | 151 | 163 | 176 | 6 | 2.5 | 1.5 | 3 | 4 | 4 | 1.5 | 3 | 6 | 3 | 1.5 | 1.5 | 3 | 6 | 2 | 2 | 4 | 3 | 5 | 3 | 5 | 3 | 6 | 4 | 2 | 2.5 | 4 | 4 | 5 | 2 | 6 | 3 | 3 | 2.5 | 1.5 | 3 | 3 | 3 | 2 | 2.5 | 5 | 6 | 1.5 | 6 | 5 | 2 | 2 | 3 | 3 | 6 | 2 | 2
350 | 20.5 | 11.5 | 28.5 | 40.5 | 51.5 | 69 | 78.5 | 90.5 | 103 | 115 | 130 | 143 | 154 | 171 | 2 | 2.5 | 3 | 4 | 6 | 3 | 3 | 5 | 2.5 | 2.5 | 4 | 3 | 5 | 2.5 | 1.5 | 2 | 2.5 | 6 | 5 | 4 | 2.5 | 3 | 2.5 | 1.5 | 5 | 2.5 | 3 | 1.5 | 2 | 5 | 3 | 2.5 | 4 | 3 | 2 | 3 | 3 | 3 | 6 | 3 | 3 | 4 | 3 | 3 | 6 | 1.5 | 2 | 1.5 | 6 | 4 | 4 | 3
351 | 23.5 | 17 | 27.5 | 41.5 | 53.5 | 71 | 88.5 | 104.5 | 118 | 132.5 | 144 | 157.5 | 171.5 | 182.5 | 5 | 6 | 3 | 3 | 1.5 | 5 | 2.5 | 1.5 | 3 | 3 | 6 | 2 | 2.5 | 5 | 3 | 1.5 | 1.5 | 5 | 5 | 6 | 2.5 | 3 | 6 | 6 | 5 | 3 | 5 | 3 | 4 | 2.5 | 2 | 5 | 1.5 | 4 | 6 | 3 | 1.5 | 2 | 6 | 2 | 5 | 2 | 1.5 | 5 | 3 | 6 | 3 | 2 | 3 | 1.5 | 4 | 2.5
352 | 17 | 11.5 | 24 | 37.5 | 49 | 67 | 77.5 | 86 | 101 | 108.5 | 119.5 | 133 | 144 | 159.5 | 1.5 | 4 | 3 | 3 | 2.5 | 3 | 4 | 3 | 3 | 5 | 3 | 2.5 | 3 | 3 | 4 | 1.5 | 4 | 5 | 4 | 5 | 2.5 | 2 | 4 | 2 | 2.5 | 2 | 2.5 | 1.5 | 6 | 1.5 | 5 | 2.5 | 2 | 2 | 1.5 | 2 | 3 | 4 | 1.5 | 2.5 | 4 | 3 | 4 | 2.5 | 1.5 | 4 | 3 | 2.5 | 4 | 2.5 | 4 | 5
353 | 18 | 9 | 23.5 | 32.5 | 50.5 | 63.5 | 81 | 96 | 109 | 122.5 | 141.5 | 156 | 170.5 | 182.5 | 3 | 1.5 | 3 | 1.5 | 4 | 5 | 1.5 | 4 | 2.5 | 1.5 | 2.5 | 2.5 | 3 | 6 | 3 | 6 | 2.5 | 1.5 | 3 | 6 | 5 | 1.5 | 6 | 5 | 4 | 3 | 5 | 3 | 3 | 2 | 2 | 6 | 3 | 3 | 5 | 2.5 | 3 | 6 | 4 | 6 | 2 | 4 | 2.5 | 6 | 3 | 2.5 | 5 | 4 | 1.5 | 5 | 1.5 | 4
354 | 17.5 | 12.5 | 25.5 | 38 | 47.5 | 61 | 74 | 90.5 | 103.5 | 122.5 | 137.5 | 147.5 | 160.5 | 174 | 1.5 | 6 | 2 | 3 | 2 | 3 | 5 | 3 | 3 | 4 | 2.5 | 3 | 5 | 1.5 | 1.5 | 1.5 | 2.5 | 6 | 3 | 2 | 2.5 | 1.5 | 3 | 6 | 5 | 6 | 3 | 2.5 | 2.5 | 1.5 | 3 | 6 | 6 | 5 | 6 | 2 | 5 | 3 | 4 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 6 | 3 | 5 | 1.5 | 4
355 | 21 | 15.5 | 25.5 | 33.5 | 40 | 53 | 61.5 | 69.5 | 82.5 | 99.5 | 114 | 126 | 138 | 150.5 | 5 | 5 | 3 | 2.5 | 4 | 1.5 | 3 | 1.5 | 2 | 1.5 | 2 | 2.5 | 1.5 | 1.5 | 1.5 | 2 | 3 | 4 | 3 | 3 | 2.5 | 2 | 1.5 | 2.5 | 2 | 2.5 | 1.5 | 2 | 4 | 3 | 4 | 2 | 3 | 6 | 2 | 6 | 4 | 6 | 1.5 | 3 | 2 | 4 | 3 | 3 | 2 | 1.5 | 2.5 | 6 | 3 | 3 | 4 | 2.5
356 | 24.5 | 15.5 | 32.5 | 45.5 | 60 | 71 | 80.5 | 88 | 105.5 | 122.5 | 137 | 146.5 | 159.5 | 174.5 | 1.5 | 6 | 5 | 3 | 4 | 5 | 5 | 3 | 6 | 4 | 1.5 | 1.5 | 5 | 2.5 | 3 | 4 | 3 | 3 | 2.5 | 2.5 | 3 | 2 | 2.5 | 2 | 2.5 | 2 | 1.5 | 1.5 | 5 | 4 | 6 | 2.5 | 2.5 | 2.5 | 6 | 6 | 3 | 6 | 3 | 2.5 | 3 | 3 | 2 | 1.5 | 4 | 4 | 3 | 2 | 4 | 3 | 6 | 2
357 | 24.5 | 17.5 | 28.5 | 39.5 | 50 | 62.5 | 80.5 | 93.5 | 105.5 | 114.5 | 130.5 | 146 | 162 | 172 | 3 | 2.5 | 6 | 6 | 3 | 4 | 2 | 2 | 1.5 | 2.5 | 3 | 4 | 3 | 2.5 | 2 | 3 | 5 | 3 | 1.5 | 3 | 4 | 5 | 6 | 3 | 2.5 | 5 | 2.5 | 3 | 3 | 5 | 1.5 | 2.5 | 3 | 2 | 2 | 2 | 4 | 6 | 2 | 4 | 6 | 3 | 2.5 | 4 | 3 | 5 | 3 | 5 | 3 | 2 | 2.5 | 2.5
358 | 18.5 | 11.5 | 24 | 37 | 51.5 | 60.5 | 70 | 80.5 | 99.5 | 112.5 | 126 | 138 | 146.5 | 158.5 | 2.5 | 2.5 | 5 | 1.5 | 3 | 4 | 2.5 | 3 | 1.5 | 1.5 | 4 | 6 | 4 | 4 | 5 | 1.5 | 3 | 2 | 2 | 2 | 2 | 2.5 | 3 | 2 | 4 | 2 | 1.5 | 3 | 5 | 6 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2.5 | 2 | 6 | 3 | 3 | 3 | 3 | 1.5 | 3 | 2.5 | 1.5 | 4 | 4 | 2.5 | 1.5
359 | 14.5 | 6.5 | 24.5 | 38.5 | 52.5 | 65 | 76 | 94 | 107.5 | 118 | 130 | 143.5 | 160 | 171 | 1.5 | 2 | 1.5 | 1.5 | 3 | 5 | 5 | 5 | 4 | 2.5 | 5 | 2.5 | 5 | 5 | 2.5 | 1.5 | 1.5 | 2.5 | 6 | 2.5 | 5 | 1.5 | 3 | 1.5 | 4 | 6 | 6 | 2 | 5 | 4 | 3 | 1.5 | 2 | 2 | 4 | 2.5 | 2.5 | 2.5 | 4 | 3 | 5 | 5 | 2 | 1.5 | 6 | 5 | 2.5 | 3 | 1.5 | 1.5 | 3 | 5
360 | 20.5 | 14.5 | 27 | 34.5 | 49.5 | 59 | 70.5 | 79.5 | 90 | 98.5 | 107.5 | 121 | 135.5 | 152 | 2.5 | 4 | 5 | 3 | 3 | 3 | 2.5 | 4 | 2 | 1.5 | 2 | 2 | 5 | 2.5 | 2.5 | 5 | 2.5 | 1.5 | 4 | 1.5 | 5 | 2 | 1.5 | 3 | 2 | 2.5 | 2.5 | 2 | 1.5 | 4 | 2.5 | 2.5 | 2.5 | 1.5 | 3 | 1.5 | 3 | 2 | 1.5 | 2.5 | 3 | 6 | 3 | 1.5 | 5 | 2 | 6 | 1.5 | 5 | 4 | 2.5 | 5
361 | 16.5 | 11.5 | 20.5 | 35.5 | 48 | 65 | 77 | 94 | 104.5 | 121.5 | 135 | 149.5 | 167.5 | 187.5 | 2.5 | 3 | 4 | 2 | 2 | 3 | 2.5 | 1.5 | 2.5 | 5 | 5 | 2.5 | 3 | 5 | 1.5 | 3 | 2.5 | 6 | 2.5 | 6 | 3 | 5 | 2 | 2 | 3 | 6 | 3 | 5 | 1.5 | 3 | 3 | 3 | 5 | 4 | 5 | 3 | 5 | 2.5 | 2 | 4 | 4 | 6 | 2.5 | 2 | 5 | 4 | 3 | 6 | 5 | 4 | 5 | 6
362 | 18 | 9.5 | 29 | 37.5 | 51 | 72 | 86.5 | 96.5 | 106 | 117 | 131.5 | 144.5 | 157 | 174.5 | 1.5 | 1.5 | 1.5 | 5 | 6 | 2.5 | 6 | 5 | 1.5 | 1.5 | 3 | 2.5 | 5 | 3 | 2.5 | 3 | 6 | 4 | 5 | 6 | 2 | 6 | 4 | 2.5 | 4 | 1.5 | 2 | 2.5 | 3 | 2.5 | 1.5 | 2.5 | 1.5 | 1.5 | 4 | 4 | 6 | 2.5 | 3 | 3 | 4 | 3 | 2 | 4 | 4 | 2 | 1.5 | 5 | 3 | 6 | 2.5 | 6
363 | 16.5 | 11 | 21.5 | 34.5 | 43.5 | 55 | 69 | 79 | 90.5 | 100.5 | 112.5 | 123 | 135.5 | 145.5 | 3 | 3 | 2 | 3 | 1.5 | 4 | 3 | 2 | 2 | 5 | 4 | 2 | 4 | 1.5 | 2 | 1.5 | 2.5 | 4 | 3 | 2 | 1.5 | 1.5 | 5 | 6 | 2 | 5 | 1.5 | 1.5 | 3 | 2 | 5 | 1.5 | 4 | 1.5 | 3 | 1.5 | 2 | 3 | 3 | 4 | 2 | 4 | 3 | 1.5 | 3 | 2.5 | 2 | 5 | 2.5 | 1.5 | 3 | 3
364 | 18 | 10 | 22.5 | 31.5 | 43.5 | 59 | 74.5 | 85.5 | 99 | 117 | 132.5 | 152 | 163 | 174 | 2 | 4 | 1.5 | 2.5 | 3 | 5 | 3 | 1.5 | 3 | 2.5 | 1.5 | 2 | 1.5 | 4 | 2.5 | 4 | 4 | 1.5 | 4 | 6 | 5 | 6 | 3 | 1.5 | 1.5 | 2.5 | 3 | 4 | 3 | 1.5 | 6 | 3 | 6 | 5 | 3 | 4 | 5 | 3 | 6 | 1.5 | 1.5 | 6 | 6 | 6 | 2.5 | 3 | 3 | 2.5 | 2 | 3 | 3 | 3
365 | 18.5 | 11 | 27.5 | 41.5 | 59.5 | 70.5 | 82 | 95 | 110 | 127 | 136 | 155 | 165.5 | 176 | 4 | 2 | 3 | 2 | 1.5 | 6 | 3 | 6 | 2.5 | 5 | 5 | 1.5 | 5 | 5 | 6 | 2 | 1.5 | 3 | 5 | 1.5 | 2 | 5 | 3 | 1.5 | 2 | 6 | 3 | 2 | 6 | 4 | 2.5 | 2.5 | 3 | 3 | 6 | 5 | 3 | 1.5 | 3 | 1.5 | 4 | 3 | 6 | 6 | 4 | 3 | 2 | 1.5 | 4 | 2 | 1.5 | 3
366 | 21 | 12 | 29 | 45 | 56.5 | 67.5 | 79 | 93.5 | 109.5 | 123.5 | 139.5 | 152 | 166 | 181 | 4 | 1.5 | 4 | 2.5 | 6 | 3 | 3 | 5 | 4 | 3 | 6 | 3 | 4 | 4 | 1.5 | 2 | 1.5 | 2 | 1.5 | 6 | 3 | 4 | 1.5 | 3 | 3 | 6 | 3 | 2.5 | 6 | 2.5 | 1.5 | 6 | 4 | 1.5 | 2.5 | 6 | 3 | 3 | 5 | 5 | 1.5 | 6 | 3 | 2 | 6 | 3 | 3 | 2 | 5 | 4 | 2 | 4
367 | 19 | 12.5 | 23.5 | 35.5 | 50.5 | 71 | 86.5 | 100 | 114 | 128.5 | 146.5 | 157.5 | 169 | 183.5 | 1.5 | 6 | 3 | 2 | 1.5 | 5 | 2 | 2.5 | 5 | 1.5 | 3 | 2.5 | 4 | 4 | 2 | 5 | 2.5 | 6 | 6 | 6 | 2 | 6 | 2.5 | 5 | 6 | 3 | 3 | 1.5 | 4 | 2.5 | 6 | 1.5 | 3 | 1.5 | 5 | 5 | 6 | 6 | 3 | 3 | 3 | 2 | 2 | 4 | 4 | 1.5 | 3 | 3 | 6 | 4 | 2 | 2.5
368 | 20.5 | 13.5 | 27.5 | 42.5 | 55 | 73 | 84 | 97.5 | 111 | 123 | 135.5 | 150 | 163.5 | 173 | 2.5 | 3 | 4 | 4 | 4 | 3 | 2 | 5 | 5 | 6 | 1.5 | 2.5 | 1.5 | 4 | 4 | 3 | 2 | 6 | 6 | 4 | 3 | 3 | 2 | 3 | 3 | 1.5 | 3 | 6 | 3 | 2.5 | 5 | 3 | 3 | 3 | 4 | 2 | 2 | 5 | 3 | 2.5 | 3 | 6 | 4 | 1.5 | 1.5 | 6 | 3 | 3 | 3 | 3 | 1.5 | 2
369 | 18 | 9.5 | 22.5 | 37 | 51 | 66.5 | 77 | 86.5 | 99.5 | 112.5 | 124.5 | 134.5 | 152 | 160 | 2.5 | 2.5 | 1.5 | 3 | 6 | 2.5 | 2 | 2.5 | 2 | 5 | 5 | 2.5 | 3 | 2 | 6 | 3 | 4 | 4 | 5 | 2.5 | 1.5 | 4 | 2 | 3 | 2.5 | 2 | 2.5 | 2.5 | 2.5 | 1.5 | 6 | 3 | 4 | 2 | 3 | 4 | 3 | 2.5 | 2.5 | 4 | 2 | 2.5 | 3 | 2.5 | 1.5 | 6 | 6 | 4 | 2 | 2 | 1.5 | 2.5
370 | 22.5 | 18 | 31 | 43.5 | 57 | 69 | 83.5 | 95.5 | 105 | 117.5 | 129 | 146.5 | 161.5 | 174 | 5 | 3 | 6 | 4 | 2.5 | 2 | 6 | 2.5 | 2 | 1.5 | 3 | 6 | 3 | 2.5 | 3 | 5 | 2.5 | 5 | 1.5 | 3 | 3 | 6 | 3 | 2.5 | 6 | 2 | 2.5 | 1.5 | 4 | 1.5 | 1.5 | 2.5 | 4 | 3 | 3 | 2.5 | 2.5 | 4 | 2 | 3 | 6 | 1.5 | 4 | 6 | 2 | 6 | 2 | 5 | 3 | 2 | 2.5 | 5
371 | 14.5 | 9 | 20 | 33.5 | 44.5 | 55.5 | 64 | 72.5 | 88 | 98 | 111.5 | 124 | 140.5 | 153 | 2 | 1.5 | 4 | 1.5 | 2.5 | 3 | 3 | 2.5 | 2.5 | 2 | 3 | 6 | 4 | 3 | 1.5 | 2.5 | 3 | 4 | 2 | 2 | 1.5 | 2 | 3 | 2 | 1.5 | 1.5 | 1.5 | 4 | 5 | 5 | 3 | 2.5 | 2.5 | 2 | 3 | 2.5 | 2.5 | 2 | 4 | 5 | 6 | 2.5 | 2 | 2 | 4 | 6 | 4 | 2.5 | 1.5 | 4 | 5 | 2
372 | 18.5 | 11.5 | 26 | 37 | 53.5 | 68.5 | 76.5 | 91.5 | 104 | 119.5 | 129.5 | 146 | 156 | 170 | 2 | 2.5 | 4 | 3 | 2 | 5 | 6 | 1.5 | 1.5 | 2.5 | 4 | 3 | 4 | 6 | 2.5 | 4 | 1.5 | 5 | 2.5 | 6 | 1.5 | 2.5 | 2.5 | 1.5 | 3 | 6 | 4 | 2 | 1.5 | 4 | 4 | 3 | 6 | 4 | 3 | 2.5 | 1.5 | 4 | 3 | 1.5 | 6 | 2.5 | 3 | 5 | 2.5 | 1.5 | 4 | 2 | 3 | 6 | 3 | 2
373 | 15 | 11 | 19 | 34.5 | 51.5 | 68 | 79 | 94.5 | 101.5 | 114 | 129.5 | 147.5 | 160.5 | 179.5 | 4 | 2 | 3 | 2 | 2.5 | 1.5 | 1.5 | 2.5 | 5 | 6 | 1.5 | 3 | 3 | 3 | 5 | 6 | 6 | 1.5 | 6 | 3 | 1.5 | 6 | 2 | 1.5 | 2.5 | 5 | 6 | 2 | 1.5 | 1.5 | 2.5 | 1.5 | 4 | 3 | 4 | 1.5 | 3 | 6 | 1.5 | 5 | 4 | 5 | 3 | 6 | 3 | 2 | 6 | 2 | 6 | 2 | 6 | 5
374 | 17 | 11.5 | 22 | 36.5 | 49 | 65 | 75.5 | 86 | 103 | 117.5 | 128 | 141 | 148.5 | 163 | 2 | 4 | 2.5 | 3 | 3 | 2.5 | 2 | 3 | 1.5 | 5 | 3 | 5 | 3 | 5 | 3 | 1.5 | 3 | 5 | 2 | 6 | 2 | 5 | 1.5 | 2 | 2 | 1.5 | 4 | 3 | 3 | 4 | 5 | 5 | 2.5 | 4 | 6 | 2 | 3 | 1.5 | 4 | 2 | 2.5 | 3 | 1.5 | 6 | 1.5 | 2 | 2.5 | 1.5 | 3 | 4 | 5 | 2.5
375 | 22.5 | 16.5 | 29.5 | 41.5 | 59.5 | 70 | 80.5 | 93 | 104.5 | 118.5 | 128 | 140 | 158 | 173 | 4 | 5 | 2.5 | 5 | 3 | 3 | 3 | 4 | 1.5 | 6 | 1.5 | 3 | 4 | 6 | 6 | 2 | 4 | 1.5 | 2 | 3 | 1.5 | 4 | 2 | 3 | 3 | 3 | 2.5 | 4 | 2 | 2.5 | 3 | 4 | 6 | 3 | 3 | 2 | 3 | 1.5 | 2 | 3 | 2 | 5 | 3 | 2 | 4 | 6 | 4 | 4 | 3 | 6 | 3 | 3
376 | 17 | 12 | 24 | 37 | 51.5 | 65.5 | 82 | 93.5 | 105.5 | 117.5 | 127 | 143.5 | 160 | 171 | 3 | 2 | 2 | 5 | 2.5 | 2.5 | 3 | 4 | 3 | 1.5 | 6 | 2.5 | 4 | 2.5 | 5 | 3 | 1.5 | 6 | 5 | 1.5 | 3 | 1.5 | 6 | 6 | 4 | 3 | 1.5 | 3 | 2.5 | 4 | 2.5 | 3 | 4 | 2 | 3 | 3 | 1.5 | 4 | 2 | 2 | 5 | 3 | 2.5 | 6 | 6 | 3 | 2.5 | 5 | 2 | 3 | 3 | 3
377 | 22.5 | 14.5 | 28 | 40.5 | 52 | 65 | 78.5 | 90.5 | 101.5 | 118.5 | 132 | 148.5 | 156.5 | 166 | 6 | 1.5 | 4 | 3 | 3 | 5 | 1.5 | 4 | 5 | 4 | 2 | 1.5 | 2 | 1.5 | 4 | 4 | 4 | 3 | 4 | 2 | 2 | 1.5 | 4 | 6 | 4 | 2.5 | 4 | 1.5 | 3 | 2.5 | 2.5 | 3 | 4 | 3 | 6 | 4 | 1.5 | 3 | 3 | 6 | 3 | 6 | 5 | 2.5 | 1.5 | 2 | 2.5 | 2 | 2.5 | 2 | 2.5 | 2.5
378 | 22.5 | 14.5 | 29.5 | 48.5 | 60.5 | 78 | 97 | 110 | 122 | 137.5 | 150.5 | 162 | 176.5 | 196.5 | 1.5 | 5 | 5 | 3 | 4 | 4 | 4 | 3 | 5 | 5 | 4 | 5 | 2.5 | 2.5 | 4 | 3 | 2.5 | 4 | 6 | 5 | 5 | 6 | 5 | 3 | 5 | 3 | 2 | 3 | 1.5 | 2.5 | 2 | 6 | 2.5 | 4 | 6 | 3 | 4 | 4 | 2 | 3 | 4 | 2.5 | 2.5 | 2.5 | 1.5 | 5 | 6 | 2 | 5 | 6 | 3 | 6
379 | 16.5 | 12 | 23.5 | 38 | 50.5 | 67.5 | 82 | 99 | 115.5 | 133.5 | 147 | 164 | 179 | 194.5 | 3 | 3 | 2 | 4 | 3 | 1.5 | 4 | 3 | 1.5 | 3 | 4 | 6 | 3 | 4 | 1.5 | 4 | 4 | 3 | 6 | 4 | 5 | 4 | 3 | 2.5 | 3 | 5 | 3 | 6 | 6 | 5 | 2.5 | 3 | 4 | 4 | 5 | 5 | 3 | 3 | 2.5 | 5 | 6 | 2.5 | 2.5 | 6 | 3 | 2 | 5 | 5 | 4 | 1.5 | 5 | 5
380 | 26.5 | 17.5 | 33 | 46 | 63 | 77.5 | 96.5 | 107.5 | 118 | 129.5 | 144.5 | 165.5 | 178.5 | 193 | 4 | 2.5 | 6 | 5 | 6 | 3 | 2.5 | 4 | 3 | 5 | 2.5 | 2.5 | 3 | 6 | 3 | 5 | 2 | 6 | 1.5 | 5 | 4 | 3 | 6 | 6 | 1.5 | 4 | 2.5 | 3 | 4 | 3 | 2 | 1.5 | 1.5 | 2 | 5 | 3 | 4 | 2 | 3 | 6 | 5 | 4 | 6 | 6 | 2.5 | 5 | 4 | 1.5 | 3 | 2.5 | 3 | 6
381 | 17.5 | 14 | 23.5 | 34.5 | 47.5 | 57 | 68 | 81 | 94.5 | 105 | 123.5 | 135 | 149 | 159 | 6 | 1.5 | 2.5 | 4 | 1.5 | 2 | 4 | 2 | 2 | 3 | 4 | 2 | 5 | 3 | 2 | 3 | 2 | 1.5 | 3 | 3 | 2.5 | 2.5 | 3 | 3 | 2 | 6 | 3 | 2 | 4 | 1.5 | 5 | 3 | 2.5 | 2.5 | 2.5 | 3 | 2.5 | 6 | 6 | 4 | 3 | 3 | 4 | 1.5 | 3 | 3 | 3 | 5 | 3 | 2.5 | 3 | 1.5
382 | 26 | 16 | 33.5 | 50 | 60.5 | 72.5 | 88 | 101.5 | 114 | 126 | 143 | 153.5 | 167 | 177 | 3 | 6 | 5 | 2 | 6 | 4 | 5 | 2.5 | 1.5 | 6 | 4 | 5 | 3 | 1.5 | 3 | 3 | 5 | 3 | 1.5 | 2.5 | 5 | 2.5 | 3 | 5 | 3 | 1.5 | 3 | 6 | 3 | 1.5 | 5 | 3 | 4 | 3 | 2.5 | 2.5 | 5 | 6 | 2 | 4 | 3 | 1.5 | 3 | 3 | 5 | 1.5 | 4 | 3 | 2.5 | 3 | 1.5 | 3
383 | 19.5 | 10.5 | 27.5 | 40 | 51.5 | 65.5 | 77.5 | 87 | 106 | 119.5 | 133 | 147.5 | 162.5 | 178 | 3 | 2 | 2.5 | 3 | 3 | 6 | 5 | 3 | 1.5 | 2.5 | 6 | 2.5 | 2.5 | 3 | 3 | 3 | 6 | 2.5 | 2.5 | 3 | 1.5 | 6 | 1.5 | 3 | 5 | 1.5 | 1.5 | 1.5 | 5 | 3 | 5 | 6 | 5 | 3 | 2.5 | 3 | 4 | 2.5 | 3 | 4 | 4 | 2.5 | 3 | 5 | 4 | 4 | 3 | 4 | 6 | 3 | 5 | 1.5
384 | 24.5 | 14.5 | 30.5 | 44.5 | 57 | 68 | 79 | 90.5 | 102 | 111 | 126 | 141 | 152.5 | 162.5 | 2 | 5 | 2.5 | 5 | 6 | 4 | 3 | 3 | 4 | 5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.5 | 6 | 2 | 4 | 2.5 | 2.5 | 2.5 | 3 | 1.5 | 4 | 1.5 | 3 | 3 | 4 | 4 | 3 | 1.5 | 3 | 1.5 | 1.5 | 3 | 3 | 2.5 | 5 | 1.5 | 6 | 2 | 4 | 6 | 3 | 6 | 1.5 | 1.5 | 2.5 | 1.5 | 2.5 | 3 | 3
385 | 18.5 | 14 | 23 | 42 | 56 | 70 | 79 | 92 | 104.5 | 125.5 | 138 | 156 | 171 | 181.5 | 4 | 1.5 | 6 | 2.5 | 1.5 | 3 | 1.5 | 3 | 4 | 6 | 6 | 3 | 2.5 | 6 | 3 | 2.5 | 6 | 3 | 2 | 3 | 2 | 2.5 | 2.5 | 2 | 1.5 | 2.5 | 6 | 3 | 3 | 1.5 | 4 | 4 | 6 | 6 | 3 | 6 | 1.5 | 2 | 6 | 3 | 3 | 4 | 5 | 6 | 4 | 6 | 2.5 | 2.5 | 3 | 3 | 2 | 2.5
386 | 19 | 14 | 25 | 42 | 56.5 | 71 | 81 | 99.5 | 108.5 | 121 | 131.5 | 144 | 157 | 169.5 | 5 | 2 | 3 | 4 | 2 | 3 | 4 | 2 | 6 | 6 | 2 | 3 | 1.5 | 5 | 5 | 3 | 2 | 4 | 2.5 | 6 | 3 | 3 | 1.5 | 2.5 | 5 | 6 | 5 | 2.5 | 3 | 2 | 2 | 2 | 2 | 2 | 2.5 | 6 | 1.5 | 2.5 | 1.5 | 5 | 6 | 2 | 2.5 | 2 | 3 | 4 | 3 | 3 | 6 | 2.5 | 2 | 2
387 | 16 | 7 | 21 | 30 | 39.5 | 56 | 71.5 | 92.5 | 111.5 | 120 | 128.5 | 142.5 | 154.5 | 171.5 | 1.5 | 1.5 | 1.5 | 2.5 | 3 | 6 | 3 | 2 | 3 | 2 | 2 | 2 | 3 | 2 | 2 | 2.5 | 2.5 | 5 | 6 | 3 | 3 | 5 | 1.5 | 6 | 6 | 6 | 4 | 5 | 6 | 6 | 4 | 3 | 3 | 2 | 2 | 1.5 | 2.5 | 1.5 | 3 | 1.5 | 4 | 4 | 2 | 4 | 3 | 4 | 2 | 3 | 5 | 3 | 3 | 6
388 | 19 | 12.5 | 26.5 | 39.5 | 57 | 68.5 | 79.5 | 94 | 103.5 | 116.5 | 126.5 | 139 | 159 | 173.5 | 2 | 4 | 4 | 2.5 | 2.5 | 4 | 2.5 | 5 | 2.5 | 6 | 3 | 1.5 | 6 | 1.5 | 6 | 4 | 6 | 1.5 | 1.5 | 2.5 | 3 | 5 | 1.5 | 1.5 | 3 | 4 | 2.5 | 5 | 2.5 | 2.5 | 2.5 | 2 | 6 | 2.5 | 1.5 | 3 | 2 | 4 | 2.5 | 1.5 | 1.5 | 6 | 3 | 2 | 6 | 6 | 3 | 5 | 3 | 3 | 2.5 | 6
389 | 20 | 10 | 29 | 38.5 | 54 | 67 | 80 | 92.5 | 109.5 | 126.5 | 139 | 152.5 | 167 | 175 | 1.5 | 3 | 1.5 | 4 | 4 | 6 | 5 | 4 | 2 | 1.5 | 3 | 3 | 6 | 3 | 1.5 | 5 | 5 | 4 | 2 | 2 | 1.5 | 4 | 6 | 1.5 | 3 | 3 | 4 | 2.5 | 5 | 4 | 5 | 3 | 6 | 5 | 3 | 3 | 6 | 1.5 | 2.5 | 2.5 | 3 | 3 | 1.5 | 6 | 3 | 4 | 1.5 | 6 | 1.5 | 1.5 | 2.5 | 2.5
390 | 33 | 21 | 42 | 57 | 71 | 87.5 | 102.5 | 113 | 122.5 | 138 | 155 | 167.5 | 178.5 | 193 | 6 | 6 | 5 | 4 | 6 | 6 | 4 | 5 | 4 | 2 | 5 | 4 | 3 | 6 | 3 | 2 | 6 | 2.5 | 3 | 5 | 5 | 2.5 | 1.5 | 6 | 2.5 | 1.5 | 5 | 1.5 | 2 | 2 | 3 | 2.5 | 6 | 6 | 1.5 | 2 | 6 | 4 | 3 | 4 | 3 | 5 | 2.5 | 2 | 4 | 1.5 | 2.5 | 3 | 6 | 3 | 3 | 2.5
391 | 19 | 10 | 23 | 39 | 57 | 74 | 82.5 | 95 | 106.5 | 117.5 | 128.5 | 137 | 144 | 155.5 | 2.5 | 2 | 3 | 2.5 | 3 | 6 | 2 | 2 | 6 | 5 | 2 | 3 | 6 | 6 | 3 | 3 | 3 | 4 | 6 | 4 | 2.5 | 1.5 | 2.5 | 2 | 3 | 6 | 2 | 1.5 | 4 | 2.5 | 3 | 2 | 1.5 | 5 | 2.5 | 2 | 2.5 | 5 | 2 | 1.5 | 3 | 2 | 2 | 1.5 | 1.5 | 2 | 1.5 | 2 | 3 | 4 | 2 | 2.5
392 | 28 | 22 | 39 | 54.5 | 71.5 | 84 | 96.5 | 116.5 | 124 | 133.5 | 149 | 164 | 178.5 | 191.5 | 5 | 6 | 6 | 5 | 3 | 3 | 5 | 6 | 2.5 | 5 | 5 | 3 | 2 | 4 | 6 | 5 | 3 | 4 | 1.5 | 4 | 2.5 | 2 | 6 | 2 | 6 | 6 | 3 | 5 | 2 | 2.5 | 1.5 | 1.5 | 3 | 2 | 2 | 2.5 | 4 | 5 | 1.5 | 5 | 5 | 2 | 6 | 2 | 2 | 6 | 4 | 2.5 | 3 | 2.5 | 6 | 1.5
393 | 21 | 13 | 25.5 | 39 | 52 | 74 | 85.5 | 97.5 | 115 | 130.5 | 149 | 157.5 | 168.5 | 178.5 | 3 | 2 | 2 | 6 | 6 | 2 | 3 | 1.5 | 2.5 | 2 | 3 | 6 | 5 | 5 | 1.5 | 1.5 | 6 | 6 | 6 | 4 | 3 | 3 | 3 | 2.5 | 2.5 | 1.5 | 5 | 3 | 4 | 2.5 | 6 | 5 | 2.5 | 6 | 4 | 3 | 2.5 | 4 | 6 | 6 | 2 | 1.5 | 3 | 2 | 2.5 | 4 | 3 | 1.5 | 2.5 | 3 | 1.5 | 3
394 | 20.5 | 12.5 | 26.5 | 41 | 54 | 72 | 87 | 97 | 105.5 | 127.5 | 136.5 | 147 | 164 | 173.5 | 2.5 | 3 | 4 | 3 | 3 | 5 | 3 | 3 | 4 | 3 | 6 | 1.5 | 5 | 2 | 3 | 3 | 3 | 5 | 6 | 4 | 3 | 3 | 6 | 3 | 2 | 3 | 2 | 3 | 3 | 1.5 | 2.5 | 1.5 | 5 | 6 | 6 | 5 | 1.5 | 4 | 1.5 | 2 | 3 | 2.5 | 3 | 2 | 6 | 3 | 6 | 2 | 3 | 2.5 | 1.5 | 2.5
395 | 18.5 | 14 | 23 | 35 | 52 | 64.5 | 78.5 | 97.5 | 112.5 | 126.5 | 137.5 | 147.5 | 157.5 | 171.5 | 2.5 | 6 | 2.5 | 3 | 2.5 | 2 | 3 | 1.5 | 2 | 2.5 | 2.5 | 5 | 4 | 3 | 6 | 4 | 1.5 | 3 | 6 | 2 | 6 | 2.5 | 3 | 2.5 | 6 | 4 | 3 | 6 | 6 | 3 | 3 | 3 | 2 | 3 | 3 | 6 | 3 | 1.5 | 4 | 2.5 | 2.5 | 3 | 3 | 1.5 | 1.5 | 2 | 1.5 | 5 | 2 | 3 | 5 | 4
396 | 21.5 | 13 | 30.5 | 43 | 56 | 71 | 87 | 106 | 124 | 136.5 | 148.5 | 167.5 | 181.5 | 199.5 | 2 | 3 | 3 | 5 | 6 | 2.5 | 3 | 6 | 4 | 3 | 3 | 2.5 | 3 | 4 | 3 | 3 | 6 | 4 | 3 | 2 | 4 | 5 | 5 | 2 | 6 | 6 | 3 | 4 | 4 | 4 | 5 | 5 | 4 | 3 | 2.5 | 3 | 2 | 3 | 3 | 4 | 6 | 5 | 6 | 2 | 2.5 | 2.5 | 6 | 3 | 5 | 3 | 6 | 4
397 | 22.5 | 17 | 28 | 36 | 43 | 52 | 69.5 | 83 | 102 | 119 | 136 | 144.5 | 157 | 171.5 | 6 | 5 | 4 | 2 | 1.5 | 4 | 3 | 2.5 | 1.5 | 3 | 1.5 | 2 | 2.5 | 1.5 | 1.5 | 1.5 | 2.5 | 3 | 1.5 | 2 | 5 | 2.5 | 6 | 4 | 1.5 | 4 | 3 | 5 | 5 | 4 | 4 | 6 | 6 | 4 | 4 | 3 | 6 | 3 | 3 | 5 | 3 | 2.5 | 1.5 | 1.5 | 2.5 | 2 | 4 | 4 | 4 | 3 | 6 | 1.5
398 | 23 | 17 | 29 | 41 | 52.5 | 64.5 | 78 | 95 | 107.5 | 120.5 | 134.5 | 145 | 161.5 | 172.5 | 5 | 4 | 4 | 4 | 4 | 2 | 2 | 4 | 3 | 2.5 | 1.5 | 5 | 3 | 4 | 1.5 | 3 | 1.5 | 1.5 | 3 | 6 | 3 | 1.5 | 5 | 4 | 5 | 3 | 3 | 6 | 3 | 3 | 4 | 2.5 | 3 | 3 | 4 | 3 | 3 | 6 | 2 | 3 | 3 | 2 | 2.5 | 3 | 6 | 4 | 4 | 2.5 | 2.5 | 4 | 1.5 | 3
399 | 21.5 | 14.5 | 28 | 43 | 53 | 63.5 | 81.5 | 90.5 | 107 | 120.5 | 132.5 | 151.5 | 164 | 179 | 6 | 2 | 4 | 2.5 | 3 | 4 | 2.5 | 4 | 3 | 3 | 3 | 6 | 3 | 3 | 2.5 | 1.5 | 2 | 4 | 3 | 1.5 | 5 | 4 | 6 | 3 | 2.5 | 1.5 | 2.5 | 2.5 | 6 | 5 | 3 | 2.5 | 3 | 2 | 6 | 2.5 | 4 | 3 | 2.5 | 2.5 | 4 | 5 | 6 | 4 | 6 | 2 | 1.5 | 3 | 4 | 3 | 5 | 3
400 | 15 | 12 | 21 | 37 | 51.5 | 65 | 75.5 | 87.5 | 101.5 | 111.5 | 125 | 133.5 | 146 | 157.5 | 4 | 5 | 1.5 | 1.5 | 1.5 | 1.5 | 3 | 3 | 2.5 | 5 | 2.5 | 6 | 5 | 6 | 2 | 1.5 | 1.5 | 3 | 6 | 3 | 3 | 2 | 2.5 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 5 | 2 | 1.5 | 2 | 4 | 2.5 | 3 | 6 | 1.5 | 3 | 1.5 | 2 | 2 | 3 | 1.5 | 3 | 3 | 5 | 3 | 2 | 1.5 | 5
401 | 19.5 | 12 | 26.5 | 39 | 52 | 64.5 | 83 | 93 | 103.5 | 111.5 | 128 | 136 | 151.5 | 168.5 | 2 | 3 | 4 | 3 | 2.5 | 5 | 2 | 5 | 1.5 | 3 | 5 | 3 | 2.5 | 1.5 | 3 | 6 | 1.5 | 3 | 4 | 4 | 5 | 6 | 6 | 1.5 | 2.5 | 3 | 1.5 | 3 | 1.5 | 3 | 3 | 3 | 1.5 | 2.5 | 2 | 2 | 3 | 6 | 6 | 1.5 | 2 | 2.5 | 1.5 | 2 | 4 | 4 | 6 | 1.5 | 3 | 3 | 6 | 5
402 | 24 | 20 | 34 | 41 | 58 | 67 | 77.5 | 91 | 105 | 126 | 136.5 | 151 | 162.5 | 176 | 3 | 5 | 6 | 6 | 2.5 | 1.5 | 5 | 5 | 1.5 | 1.5 | 2 | 2 | 2.5 | 2.5 | 6 | 6 | 3 | 1.5 | 2 | 2.5 | 3 | 3 | 1.5 | 3 | 2.5 | 3 | 6 | 2 | 6 | 2 | 2 | 4 | 6 | 6 | 3 | 6 | 3 | 2.5 | 3 | 2 | 5 | 5 | 1.5 | 3 | 1.5 | 4 | 2 | 4 | 2.5 | 3 | 3 | 5
403 | 29.5 | 19.5 | 36 | 54 | 68 | 78.5 | 89 | 101.5 | 111 | 123 | 137 | 151.5 | 167.5 | 183.5 | 5 | 6 | 6 | 2.5 | 6 | 4 | 2.5 | 4 | 6 | 4 | 5 | 3 | 2.5 | 1.5 | 4 | 6 | 2.5 | 2.5 | 3 | 2.5 | 2.5 | 2.5 | 4 | 1.5 | 2.5 | 4 | 2 | 4 | 3 | 2.5 | 1.5 | 2.5 | 3 | 3 | 3 | 3 | 3 | 6 | 3 | 2 | 6 | 3 | 3 | 2.5 | 5 | 2 | 4 | 5 | 6 | 5 | 3 | 2
404 | 24 | 14 | 29.5 | 43.5 | 57.5 | 67 | 80 | 92 | 105 | 119 | 129 | 142 | 158.5 | 170.5 | 3 | 4 | 4 | 3 | 5 | 5 | 2.5 | 3 | 5 | 3 | 3 | 3 | 3 | 3 | 6 | 2 | 2 | 4 | 1.5 | 2 | 6 | 1.5 | 4 | 1.5 | 6 | 1.5 | 1.5 | 3 | 3 | 5 | 2 | 3 | 6 | 2 | 4 | 2 | 2.5 | 2.5 | 3 | 2 | 4 | 1.5 | 5 | 2.5 | 2 | 6 | 6 | 2.5 | 3 | 3 | 3 | 3
405 | 22.5 | 17 | 28 | 38.5 | 53 | 68 | 81 | 97 | 115.5 | 127 | 140 | 154.5 | 167.5 | 182.5 | 2.5 | 6 | 6 | 2.5 | 3 | 2.5 | 2.5 | 3 | 3 | 2.5 | 2.5 | 2.5 | 2 | 5 | 5 | 2.5 | 6 | 2.5 | 5 | 1.5 | 3 | 3 | 4 | 3 | 4 | 6 | 3 | 3 | 6 | 6 | 5 | 1.5 | 3 | 3 | 2.5 | 3 | 3 | 3 | 4 | 3 | 3 | 6 | 3 | 2.5 | 3 | 2 | 2 | 6 | 6 | 1.5 | 1.5 | 6
406 | 20.5 | 12 | 24 | 38.5 | 54 | 71 | 85.5 | 100 | 114.5 | 125.5 | 136 | 150 | 166 | 177 | 3 | 2.5 | 1.5 | 5 | 2.5 | 6 | 1.5 | 2 | 2 | 5 | 6 | 1.5 | 2.5 | 6 | 5 | 2 | 5 | 3 | 6 | 3 | 1.5 | 4 | 4 | 5 | 5 | 4 | 1.5 | 4 | 4 | 6 | 1.5 | 3 | 2.5 | 3 | 2.5 | 3 | 4 | 2.5 | 1.5 | 2.5 | 2 | 4 | 3 | 5 | 2 | 6 | 6 | 2 | 1.5 | 5 | 1.5 | 3
407 | 19.5 | 12 | 25.5 | 37.5 | 48 | 65.5 | 79.5 | 93 | 105 | 119.5 | 135.5 | 147 | 162 | 179 | 1.5 | 1.5 | 6 | 3 | 1.5 | 6 | 4 | 2 | 2.5 | 2.5 | 3 | 4 | 3 | 3 | 1.5 | 3 | 6 | 5 | 4 | 2.5 | 3 | 5 | 2 | 4 | 4 | 3 | 1.5 | 5 | 2 | 2 | 2 | 6 | 5 | 4 | 3 | 2.5 | 3 | 2 | 5 | 6 | 2 | 4 | 1.5 | 4 | 2.5 | 2.5 | 5 | 5 | 3 | 5 | 3 | 6
408 | 18.5 | 12 | 24.5 | 40 | 52 | 68.5 | 84 | 97 | 110 | 121 | 135 | 149 | 156.5 | 167 | 2.5 | 2 | 2.5 | 5 | 4 | 2.5 | 3 | 3 | 5 | 5 | 2.5 | 3 | 2.5 | 3 | 1.5 | 5 | 4 | 4 | 2.5 | 6 | 6 | 2.5 | 5 | 2 | 4 | 3 | 3 | 3 | 2.5 | 1.5 | 3 | 6 | 2.5 | 4 | 1.5 | 3 | 3 | 3 | 3 | 5 | 4 | 3 | 3 | 4 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 6
409 | 22.5 | 16.5 | 28.5 | 37.5 | 48 | 64 | 77.5 | 87 | 96 | 112.5 | 130.5 | 146.5 | 159 | 167 | 6 | 1.5 | 3 | 6 | 3 | 3 | 2 | 4 | 1.5 | 2.5 | 2 | 3 | 3 | 2.5 | 2 | 3 | 5 | 3 | 5 | 3 | 4 | 1.5 | 5 | 3 | 3 | 3 | 2 | 1.5 | 1.5 | 1.5 | 3 | 3 | 4 | 6 | 4 | 2.5 | 2 | 5 | 6 | 5 | 4 | 3 | 5 | 4 | 5 | 2.5 | 2.5 | 2.5 | 1.5 | 2 | 1.5 | 3
410 | 17 | 12 | 22.5 | 32 | 47 | 58 | 72.5 | 84 | 97 | 110.5 | 121.5 | 134 | 145.5 | 157.5 | 3 | 5 | 2 | 2 | 3 | 2 | 1.5 | 4 | 4 | 1.5 | 2.5 | 1.5 | 2 | 4 | 6 | 3 | 3 | 1.5 | 2.5 | 4 | 2 | 1.5 | 5 | 6 | 3 | 3 | 2.5 | 3 | 3 | 5 | 2.5 | 2.5 | 2.5 | 5 | 3 | 3 | 1.5 | 6 | 2 | 1.5 | 3 | 2 | 6 | 1.5 | 4 | 2.5 | 2 | 3 | 5 | 2 | 2 | 3
411 | 13 | 8 | 20 | 35.5 | 49.5 | 64 | 79 | 91.5 | 107 | 119 | 131.5 | 149.5 | 164 | 180.5 | 3 | 1.5 | 1.5 | 2 | 2.5 | 2.5 | 5 | 2 | 5 | 1.5 | 6 | 3 | 2 | 3 | 6 | 3 | 2.5 | 3 | 5 | 4 | 6 | 2.5 | 4 | 2.5 | 1.5 | 3 | 3 | 5 | 6 | 3 | 5 | 1.5 | 5 | 3 | 2.5 | 1.5 | 1.5 | 5 | 3 | 3 | 4 | 3 | 5 | 6 | 2.5 | 3 | 5 | 4 | 6 | 6 | 2 | 2.5
412 | 19 | 12 | 28 | 40 | 50.5 | 63.5 | 76.5 | 88.5 | 100 | 118 | 126.5 | 139 | 148.5 | 165.5 | 4 | 3 | 3 | 2 | 4 | 3 | 3 | 6 | 2.5 | 2.5 | 3 | 4 | 1.5 | 3 | 3 | 3 | 4 | 3 | 2 | 4 | 2.5 | 5 | 2.5 | 3 | 1.5 | 3 | 2.5 | 5 | 2 | 1.5 | 3 | 5 | 3 | 6 | 6 | 3 | 1.5 | 1.5 | 4 | 1.5 | 4 | 3 | 1.5 | 4 | 1.5 | 4 | 1.5 | 2.5 | 6 | 5 | 3 | 3
413 | 22 | 15 | 25.5 | 36 | 50.5 | 60.5 | 74.5 | 87.5 | 104 | 119 | 133 | 145 | 158.5 | 170 | 5 | 5 | 2 | 3 | 5 | 2 | 2 | 1.5 | 4 | 2 | 3 | 1.5 | 6 | 2 | 5 | 1.5 | 2 | 2.5 | 1.5 | 4 | 1.5 | 6 | 1.5 | 5 | 4 | 4 | 2 | 3 | 3 | 5 | 6 | 2.5 | 3 | 3 | 6 | 3 | 2 | 5 | 2 | 5 | 3 | 6 | 1.5 | 1.5 | 2.5 | 4 | 4 | 3 | 3 | 1.5 | 2 | 5
414 | 19.5 | 12.5 | 27.5 | 43.5 | 59 | 71.5 | 87.5 | 100 | 115.5 | 133.5 | 141.5 | 158.5 | 175.5 | 189.5 | 2 | 1.5 | 6 | 3 | 2 | 5 | 2 | 6 | 3 | 4 | 5 | 4 | 2.5 | 3 | 4 | 6 | 2 | 6 | 3 | 1.5 | 4 | 3 | 3 | 6 | 3 | 1.5 | 3 | 5 | 3 | 6 | 2.5 | 4 | 6 | 3 | 3 | 6 | 2 | 2 | 1.5 | 2.5 | 4 | 4 | 5 | 4 | 4 | 5 | 3 | 5 | 5 | 5 | 1.5 | 2.5
415 | 26.5 | 20 | 32.5 | 46 | 59 | 74 | 84.5 | 96.5 | 107.5 | 121.5 | 136.5 | 149 | 161.5 | 175.5 | 5 | 6 | 5 | 4 | 1.5 | 5 | 3 | 3 | 4 | 5 | 3 | 1.5 | 5 | 3 | 3 | 2 | 5 | 5 | 3 | 2 | 1.5 | 2.5 | 1.5 | 5 | 1.5 | 5 | 3 | 2.5 | 3 | 3 | 3 | 2 | 5 | 2 | 2 | 5 | 5 | 3 | 4 | 3 | 5 | 3 | 2.5 | 2 | 1.5 | 5 | 3 | 3 | 2 | 6 | 3 | 3
416 | 21 | 16.5 | 26.5 | 42 | 58.5 | 73.5 | 84 | 104 | 119 | 129.5 | 143.5 | 156.5 | 168 | 177 | 1.5 | 6 | 4 | 5 | 3 | 1.5 | 3 | 2.5 | 6 | 2.5 | 5 | 2 | 6 | 3 | 5 | 2.5 | 3 | 4 | 2 | 6 | 1.5 | 4 | 2.5 | 2.5 | 6 | 6 | 5 | 3 | 6 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 5 | 5 | 2.5 | 4 | 3 | 3 | 3 | 3 | 2 | 1.5 | 5 | 1.5 | 2 | 4 | 1.5
417 | 16.5 | 11.5 | 26.5 | 41 | 50.5 | 62.5 | 72.5 | 87 | 101.5 | 114.5 | 125.5 | 136 | 151.5 | 158 | 1.5 | 3 | 3 | 4 | 2 | 3 | 5 | 5 | 2.5 | 3 | 6 | 3 | 1.5 | 1.5 | 2.5 | 4 | 5 | 4 | 1.5 | 1.5 | 1.5 | 4 | 2.5 | 2 | 1.5 | 5 | 6 | 2 | 3 | 3 | 6 | 2.5 | 3 | 3 | 2 | 5 | 3 | 2 | 3 | 3 | 2 | 1.5 | 4 | 3 | 2.5 | 4 | 5 | 4 | 1.5 | 2 | 1.5 | 1.5
418 | 16.5 | 13 | 22.5 | 30.5 | 43 | 53.5 | 65.5 | 77.5 | 92.5 | 108.5 | 121.5 | 136 | 150.5 | 164 | 2 | 3 | 6 | 2 | 1.5 | 2 | 3 | 3 | 1.5 | 2 | 2 | 2.5 | 4 | 4 | 3 | 1.5 | 4 | 3 | 1.5 | 2 | 3 | 4 | 3 | 2 | 2 | 4 | 4 | 2 | 5 | 4 | 3 | 3 | 6 | 2 | 3 | 5 | 3 | 4 | 2 | 4 | 4 | 3 | 1.5 | 6 | 6 | 4 | 2.5 | 2 | 3 | 2.5 | 3 | 5
419 | 16.5 | 10.5 | 23.5 | 35.5 | 49.5 | 62 | 70.5 | 83.5 | 96 | 111 | 126 | 138 | 151 | 161 | 2.5 | 3 | 3 | 2 | 3 | 3 | 4 | 3 | 2.5 | 3 | 4 | 2.5 | 2 | 5 | 4 | 3 | 2.5 | 2 | 5 | 3 | 3 | 1.5 | 2 | 2 | 4 | 3 | 3 | 3 | 3 | 1.5 | 3 | 5 | 3 | 2 | 5 | 5 | 5 | 3 | 4 | 3 | 2 | 2 | 3 | 5 | 1.5 | 1.5 | 4 | 6 | 4 | 3 | 1.5 | 1.5
420 | 19 | 11.5 | 25 | 37.5 | 50 | 61.5 | 79.5 | 95 | 104.5 | 122 | 132 | 145.5 | 158.5 | 175 | 1.5 | 5 | 3 | 2 | 1.5 | 6 | 3 | 3 | 4 | 2.5 | 3 | 3 | 3 | 4 | 2.5 | 3 | 2 | 5 | 3 | 1.5 | 5 | 5 | 5 | 3 | 6 | 5 | 1.5 | 3 | 2.5 | 2.5 | 2 | 2.5 | 3 | 6 | 6 | 2.5 | 2 | 1.5 | 5 | 1.5 | 1.5 | 4 | 6 | 2 | 2.5 | 1.5 | 3 | 6 | 1.5 | 5 | 4 | 6
421 | 26 | 19 | 35 | 46.5 | 59.5 | 78.5 | 91 | 104 | 113 | 126.5 | 139 | 158 | 172 | 184 | 6 | 2 | 5 | 6 | 4 | 3 | 3 | 6 | 3 | 2.5 | 4 | 2 | 2.5 | 2 | 6 | 2.5 | 6 | 3 | 4 | 6 | 2 | 2.5 | 2 | 6 | 5 | 3 | 2 | 3 | 1.5 | 2 | 2.5 | 3 | 4 | 2 | 2.5 | 5 | 5 | 3 | 1.5 | 3 | 6 | 5 | 6 | 2 | 3 | 5 | 3 | 3 | 2 | 3 | 4 | 3
422 | 16 | 10 | 25 | 36.5 | 49 | 65 | 76.5 | 86 | 100.5 | 118.5 | 128.5 | 142 | 158 | 172.5 | 3 | 2.5 | 2.5 | 2 | 3 | 3 | 4 | 5 | 3 | 2.5 | 3 | 3 | 3 | 3 | 1.5 | 5 | 3 | 5 | 5 | 3 | 3 | 2.5 | 3 | 3 | 1.5 | 2.5 | 3 | 2.5 | 5 | 6 | 2 | 1.5 | 4 | 6 | 3 | 5 | 1.5 | 2.5 | 3 | 3 | 2.5 | 6 | 3 | 2 | 2.5 | 1.5 | 6 | 6 | 2.5 | 3 | 5 | 4
423 | 16.5 | 13.5 | 21 | 33.5 | 52.5 | 70.5 | 82.5 | 92 | 105 | 120.5 | 129.5 | 142.5 | 155 | 164 | 2.5 | 3 | 3 | 5 | 1.5 | 1.5 | 3 | 1.5 | 1.5 | 2 | 4 | 5 | 5 | 6 | 4 | 4 | 6 | 4 | 5 | 3 | 2 | 3 | 4 | 3 | 2.5 | 2.5 | 3 | 1.5 | 2.5 | 3 | 2.5 | 5 | 2 | 5 | 2.5 | 6 | 4 | 2 | 1.5 | 1.5 | 3 | 2.5 | 1.5 | 6 | 3 | 6 | 2 | 1.5 | 2.5 | 3 | 2 | 1.5
424 | 20.5 | 14 | 24.5 | 35.5 | 50.5 | 65 | 81.5 | 96 | 113 | 127 | 142.5 | 153 | 165 | 174.5 | 4 | 5 | 2.5 | 2.5 | 1.5 | 5 | 2.5 | 1.5 | 2 | 2.5 | 4 | 2.5 | 1.5 | 2.5 | 6 | 5 | 5 | 5 | 3 | 1.5 | 4 | 4 | 2.5 | 6 | 5 | 4 | 2.5 | 3 | 2 | 3 | 6 | 6 | 3 | 3 | 3 | 5 | 1.5 | 5 | 6 | 3 | 1.5 | 3 | 3 | 3 | 1.5 | 3 | 5 | 2.5 | 4 | 2 | 2 | 1.5
425 | 24 | 19.5 | 32 | 46 | 66 | 78.5 | 89 | 101.5 | 117 | 133 | 150 | 162.5 | 177 | 193.5 | 6 | 6 | 5 | 2.5 | 3 | 1.5 | 3 | 5 | 4 | 1.5 | 2.5 | 6 | 5 | 3 | 6 | 6 | 5 | 1.5 | 2 | 4 | 2.5 | 2.5 | 2.5 | 3 | 4 | 3 | 2.5 | 3 | 3 | 6 | 2.5 | 4 | 2 | 5 | 6 | 3 | 5 | 2 | 5 | 5 | 6 | 3 | 1.5 | 2 | 3 | 6 | 1.5 | 4 | 3 | 5 | 6 | 2.5
426 | 26.5 | 15.5 | 34 | 45.5 | 56 | 69.5 | 86.5 | 95.5 | 105.5 | 120.5 | 133 | 147 | 164 | 178 | 2.5 | 5 | 3 | 5 | 5 | 6 | 2.5 | 5 | 3 | 2 | 1.5 | 5 | 2.5 | 3 | 3 | 2 | 2.5 | 2.5 | 2.5 | 6 | 6 | 2.5 | 2.5 | 6 | 2.5 | 1.5 | 2.5 | 2.5 | 3 | 2 | 2 | 3 | 3 | 6 | 3 | 3 | 2.5 | 2.5 | 5 | 2.5 | 6 | 3 | 2 | 3 | 6 | 2 | 4 | 5 | 4 | 5 | 3 | 2
427 | 21.5 | 12.5 | 28.5 | 42.5 | 51.5 | 68 | 84 | 95 | 109 | 127 | 141.5 | 153 | 169 | 182.5 | 2.5 | 2 | 6 | 2 | 6 | 3 | 4 | 3 | 1.5 | 5 | 1.5 | 6 | 1.5 | 3 | 2.5 | 2 | 5 | 3 | 6 | 2.5 | 5 | 2 | 5 | 4 | 3 | 1.5 | 5 | 1.5 | 4 | 3 | 2 | 5 | 4 | 6 | 2 | 6 | 1.5 | 5 | 4 | 4 | 2 | 5 | 1.5 | 3 | 5 | 3 | 5 | 3 | 2 | 1.5 | 4 | 6
428 | 19.5 | 15 | 24.5 | 41 | 56.5 | 65 | 81.5 | 94.5 | 104.5 | 120.5 | 132.5 | 139.5 | 151 | 165.5 | 5 | 3 | 3 | 4 | 2.5 | 2 | 2.5 | 2.5 | 5 | 5 | 4 | 2.5 | 5 | 3 | 6 | 1.5 | 1.5 | 3 | 2 | 2 | 6 | 2.5 | 4 | 4 | 5 | 2 | 2 | 4 | 2 | 2 | 2 | 4 | 6 | 6 | 2 | 2 | 3 | 5 | 1.5 | 2.5 | 1.5 | 2.5 | 1.5 | 1.5 | 2 | 5 | 3 | 1.5 | 6 | 5 | 1.5 | 2
429 | 20.5 | 15.5 | 28 | 41 | 57 | 69 | 81 | 92.5 | 110.5 | 124.5 | 137 | 149 | 161.5 | 174.5 | 3 | 1.5 | 6 | 5 | 2.5 | 2.5 | 5 | 2.5 | 6 | 3 | 2.5 | 1.5 | 2.5 | 5 | 2.5 | 6 | 3 | 2 | 4 | 3 | 2 | 3 | 2 | 5 | 4 | 2 | 3 | 2.5 | 6 | 3 | 3 | 6 | 6 | 3 | 2.5 | 2.5 | 3 | 4 | 3 | 2.5 | 1.5 | 6 | 1.5 | 3 | 2.5 | 2 | 6 | 2 | 2.5 | 1.5 | 3 | 6
430 | 17 | 12 | 23 | 37 | 48 | 58.5 | 71.5 | 86 | 95.5 | 107.5 | 119 | 133 | 146 | 159 | 5 | 2 | 2 | 3 | 2 | 3 | 3 | 3 | 1.5 | 4 | 6 | 2.5 | 3 | 3 | 2 | 3 | 2 | 1.5 | 2 | 5 | 4 | 2.5 | 1.5 | 5 | 3 | 5 | 2.5 | 4 | 3 | 1.5 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 4 | 3 | 3 | 6 | 2 | 3 | 5 | 3 | 2 | 3 | 2.5 | 3 | 2.5 | 5
431 | 26.5 | 17.5 | 33.5 | 55.5 | 70.5 | 84.5 | 97 | 111.5 | 129.5 | 142 | 156 | 169 | 188 | 203 | 6 | 1.5 | 4 | 6 | 3 | 6 | 4 | 3 | 5 | 5 | 6 | 6 | 6 | 2 | 4 | 3 | 4 | 4 | 2 | 4 | 3 | 4 | 3 | 2.5 | 3 | 6 | 2.5 | 3 | 4 | 6 | 4 | 4 | 1.5 | 5 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 2 | 4 | 3 | 5 | 3 | 6 | 5 | 3 | 3 | 3 | 6
432 | 19 | 13 | 23.5 | 36 | 46 | 54.5 | 70.5 | 89.5 | 104 | 115.5 | 126 | 134 | 147.5 | 162 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2.5 | 5 | 2.5 | 3 | 2 | 1.5 | 2.5 | 3 | 3 | 1.5 | 2.5 | 2 | 2.5 | 6 | 6 | 2.5 | 1.5 | 2 | 6 | 6 | 5 | 5 | 1.5 | 2 | 6 | 3 | 2.5 | 3 | 3 | 3 | 1.5 | 3 | 3 | 1.5 | 2.5 | 2.5 | 1.5 | 1.5 | 6 | 3 | 3 | 6 | 2 | 5 | 1.5
433 | 23.5 | 16.5 | 31.5 | 44.5 | 57 | 66.5 | 77 | 87 | 101 | 112.5 | 122 | 131 | 146 | 165.5 | 5 | 5 | 4 | 2.5 | 3 | 4 | 3 | 5 | 4 | 3 | 3 | 3 | 5 | 1.5 | 3 | 3 | 3 | 2 | 3 | 1.5 | 2.5 | 2 | 2 | 4 | 2 | 2 | 3 | 3 | 5 | 2 | 4 | 3 | 2 | 4 | 2.5 | 3 | 3 | 1.5 | 3 | 2 | 2 | 2.5 | 2 | 2.5 | 5 | 2.5 | 6 | 1.5 | 6 | 6 | 2.5 | 5
434 | 23 | 15.5 | 28 | 42 | 55 | 67.5 | 78.5 | 89 | 107 | 121.5 | 132 | 141 | 155 | 174 | 6 | 2.5 | 3 | 4 | 1.5 | 6 | 2.5 | 2.5 | 2 | 5 | 2 | 5 | 3 | 5 | 3 | 2 | 2.5 | 4 | 3 | 3 | 2 | 3 | 2 | 4 | 2.5 | 2 | 2 | 4 | 2 | 6 | 4 | 6 | 5 | 4 | 3 | 2.5 | 3 | 2 | 1.5 | 4 | 3 | 1.5 | 2 | 2.5 | 4 | 3 | 3 | 4 | 6 | 5 | 5 | 3
435 | 20 | 15.5 | 27.5 | 42 | 57.5 | 72 | 82.5 | 92 | 112 | 123 | 135 | 149 | 159.5 | 171.5 | 5 | 5 | 4 | 1.5 | 2 | 2.5 | 2.5 | 5 | 3 | 1.5 | 4 | 6 | 1.5 | 6 | 3 | 5 | 1.5 | 3 | 6 | 4 | 1.5 | 3 | 3 | 3 | 3 | 3 | 1.5 | 2 | 6 | 3 | 5 | 6 | 4 | 3 | 2.5 | 1.5 | 4 | 2 | 3 | 3 | 3 | 2 | 6 | 3 | 5 | 2 | 1.5 | 2 | 4 | 3 | 3 | 2
436 | 22 | 16 | 29.5 | 41 | 50 | 65 | 79 | 93.5 | 107.5 | 119.5 | 133 | 147 | 158.5 | 169 | 3 | 3 | 5 | 5 | 3 | 3 | 2.5 | 5 | 1.5 | 4 | 2 | 4 | 3 | 1.5 | 3 | 1.5 | 6 | 4 | 2 | 3 | 3 | 4 | 3 | 4 | 5 | 4 | 2.5 | 3 | 2 | 5 | 5 | 2 | 3 | 2 | 4 | 3 | 1.5 | 5 | 4 | 3 | 2 | 5 | 5 | 2 | 3 | 5 | 1.5 | 2 | 1.5 | 4 | 2.5 | 2.5
437 | 26.5 | 17.5 | 33.5 | 48.5 | 62.5 | 78 | 87.5 | 103.5 | 123 | 141 | 158 | 176 | 191.5 | 203 | 6 | 2.5 | 4 | 5 | 3 | 6 | 3 | 4 | 4 | 5 | 3 | 3 | 3 | 5 | 3 | 3 | 5 | 1.5 | 6 | 3 | 1.5 | 1.5 | 4 | 2.5 | 2 | 5 | 6 | 3 | 2.5 | 6 | 5 | 6 | 6 | 2 | 4 | 6 | 3 | 6 | 4 | 4 | 4 | 4 | 6 | 4 | 6 | 1.5 | 5 | 3 | 3 | 3 | 2.5 | 3
438 | 17 | 10 | 23 | 38 | 50.5 | 61.5 | 70.5 | 81 | 96.5 | 114.5 | 131 | 144 | 155 | 169.5 | 4 | 1.5 | 2 | 2.5 | 5 | 2 | 3 | 3 | 1.5 | 6 | 1.5 | 6 | 3 | 3 | 4 | 2.5 | 2.5 | 2.5 | 4 | 2 | 2 | 2.5 | 1.5 | 3 | 3 | 2 | 2.5 | 3 | 4 | 3 | 2.5 | 6 | 4 | 5 | 3 | 6 | 5 | 6 | 2.5 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | 3 | 2 | 1.5 | 5 | 6
439 | 22.5 | 15.5 | 27 | 38 | 48.5 | 58.5 | 73 | 87 | 107 | 118.5 | 129 | 141 | 158.5 | 167.5 | 3 | 5 | 1.5 | 6 | 3 | 4 | 2 | 2.5 | 2.5 | 3 | 2.5 | 3 | 3 | 2 | 1.5 | 4 | 1.5 | 4 | 3 | 1.5 | 4 | 5 | 3 | 2.5 | 3 | 3 | 5 | 3 | 4 | 6 | 5 | 5 | 2.5 | 2 | 4 | 3 | 3 | 3 | 2 | 2.5 | 4 | 2 | 3 | 3 | 1.5 | 6 | 6 | 4 | 2.5 | 2 | 1.5 | 3
440 | 15 | 7.5 | 20.5 | 32 | 44 | 58.5 | 68 | 83.5 | 101.5 | 116.5 | 133.5 | 146 | 161 | 169.5 | 2.5 | 1.5 | 1.5 | 2 | 6 | 1.5 | 3 | 2.5 | 2.5 | 2 | 3 | 4 | 1.5 | 2.5 | 3 | 5 | 3 | 5 | 1.5 | 5 | 3 | 1.5 | 2 | 3 | 3 | 2.5 | 5 | 5 | 6 | 6 | 3 | 3 | 6 | 3 | 3 | 3 | 4 | 3 | 4 | 6 | 3 | 5 | 1.5 | 3 | 2.5 | 2.5 | 6 | 4 | 1.5 | 1.5 | 2.5 | 3
441 | 16 | 11 | 21.5 | 34 | 47 | 58.5 | 69 | 89 | 101.5 | 115.5 | 132 | 144.5 | 162.5 | 179.5 | 6 | 2 | 1.5 | 1.5 | 3 | 2 | 4 | 1.5 | 5 | 3 | 1.5 | 3 | 2.5 | 5 | 2.5 | 3 | 2.5 | 6 | 1.5 | 1.5 | 3 | 2.5 | 3 | 2 | 6 | 5 | 3 | 6 | 1.5 | 2 | 5 | 4 | 5 | 3 | 2 | 4 | 6 | 2.5 | 4 | 4 | 1.5 | 5 | 3 | 3 | 6 | 3 | 3 | 6 | 5 | 6 | 2 | 4
442 | 18 | 10 | 22.5 | 36 | 52.5 | 65.5 | 78.5 | 90 | 102.5 | 114.5 | 126 | 143 | 155.5 | 168 | 2.5 | 3 | 1.5 | 3 | 5 | 3 | 3 | 1.5 | 2.5 | 3 | 3 | 5 | 6 | 5 | 2.5 | 3 | 2 | 3 | 6 | 2 | 3 | 5 | 3 | 2 | 3 | 3 | 1.5 | 4 | 2.5 | 2.5 | 1.5 | 6 | 3 | 3 | 2 | 4 | 3 | 2.5 | 3 | 3 | 6 | 3 | 4 | 4 | 2 | 4 | 1.5 | 5 | 4 | 2 | 1.5 | 5
443 | 16 | 10 | 24 | 34 | 41.5 | 61 | 75.5 | 92.5 | 105.5 | 119.5 | 134 | 148 | 159.5 | 171.5 | 3 | 3 | 1.5 | 2.5 | 3 | 3 | 4 | 4 | 2 | 3 | 3 | 2 | 1.5 | 3 | 1.5 | 1.5 | 6 | 2.5 | 5 | 6 | 2 | 2.5 | 4 | 6 | 3 | 6 | 4 | 4 | 5 | 1.5 | 4 | 2.5 | 4 | 2.5 | 6 | 1.5 | 3 | 4 | 1.5 | 6 | 4 | 2.5 | 2.5 | 5 | 2.5 | 1.5 | 5 | 2.5 | 2 | 2.5 | 6 | 1.5
444 | 17.5 | 11 | 21 | 37.5 | 52.5 | 67 | 77 | 95 | 109.5 | 125.5 | 141 | 156 | 165 | 176 | 3 | 4 | 2 | 2 | 1.5 | 5 | 2 | 1.5 | 1.5 | 3 | 6 | 6 | 2 | 6 | 5 | 2 | 3 | 1.5 | 6 | 4 | 2 | 3 | 2 | 3 | 5 | 5 | 2 | 6 | 6 | 2 | 4 | 2.5 | 5 | 6 | 2 | 3 | 1.5 | 5 | 6 | 3 | 1.5 | 6 | 6 | 1.5 | 2.5 | 2 | 3 | 1.5 | 1.5 | 2.5 | 4 | 3
445 | 18 | 12.5 | 23.5 | 34 | 47.5 | 58 | 70 | 84.5 | 102.5 | 116 | 129 | 146 | 160 | 170 | 2.5 | 3 | 2 | 5 | 2.5 | 3 | 1.5 | 4 | 1.5 | 4 | 2 | 3 | 3 | 6 | 3 | 1.5 | 1.5 | 3 | 3 | 3 | 5 | 2 | 3 | 2 | 1.5 | 3 | 5 | 5 | 3 | 5 | 5 | 5 | 6 | 3 | 3 | 1.5 | 2 | 3 | 5 | 3 | 3 | 6 | 6 | 2 | 3 | 5 | 2 | 4 | 4 | 2 | 1.5 | 2.5
446 | 25.5 | 18 | 30 | 47.5 | 63.5 | 82.5 | 91 | 104 | 117.5 | 129.5 | 140.5 | 153.5 | 170.5 | 185 | 6 | 6 | 2 | 4 | 5 | 2.5 | 3 | 1.5 | 5 | 1.5 | 5 | 6 | 5 | 2 | 5 | 4 | 2 | 6 | 6 | 5 | 1.5 | 1.5 | 1.5 | 4 | 3 | 2.5 | 1.5 | 6 | 3 | 1.5 | 6 | 3 | 3 | 5 | 2.5 | 1.5 | 4 | 3 | 2 | 2 | 2.5 | 5 | 3 | 2.5 | 3 | 4 | 5 | 5 | 3 | 6 | 3 | 2.5
447 | 25 | 20 | 34 | 50.5 | 65 | 74.5 | 87.5 | 101.5 | 117 | 128 | 144.5 | 156 | 166 | 180.5 | 6 | 5 | 6 | 3 | 2 | 3 | 6 | 3 | 6 | 2 | 2.5 | 6 | 3 | 1.5 | 6 | 4 | 3 | 3 | 2 | 1.5 | 2 | 5 | 3 | 3 | 5 | 4 | 3 | 2 | 5 | 1.5 | 4 | 5 | 4 | 3 | 1.5 | 2.5 | 2.5 | 5 | 6 | 3 | 2 | 2 | 6 | 1.5 | 3 | 1.5 | 3 | 2.5 | 1.5 | 4 | 6 | 3
448 | 18.5 | 14.5 | 28.5 | 43.5 | 55 | 65.5 | 77.5 | 90 | 103 | 113.5 | 127.5 | 143 | 159 | 168 | 2.5 | 4 | 4 | 4 | 2.5 | 1.5 | 6 | 4 | 6 | 1.5 | 2.5 | 5 | 3 | 3 | 3 | 2.5 | 3 | 3 | 3 | 1.5 | 2.5 | 3 | 2.5 | 4 | 5 | 2.5 | 3 | 2 | 3 | 2 | 2 | 6 | 2.5 | 3 | 3 | 2 | 3 | 2.5 | 2.5 | 6 | 3 | 4 | 6 | 2.5 | 5 | 3 | 3 | 5 | 1.5 | 3 | 1.5 | 3
449 | 22 | 16.5 | 28 | 40.5 | 55.5 | 65 | 79 | 89.5 | 99 | 110 | 122 | 133.5 | 144.5 | 156 | 6 | 2.5 | 5 | 3 | 3 | 2.5 | 3 | 3 | 5 | 4 | 1.5 | 2 | 6 | 2.5 | 5 | 1.5 | 1.5 | 2 | 2 | 4 | 2.5 | 5 | 5 | 1.5 | 1.5 | 2 | 4 | 3 | 3 | 2.5 | 1.5 | 2.5 | 2 | 1.5 | 6 | 1.5 | 2.5 | 2.5 | 4 | 3 | 3 | 3 | 4 | 1.5 | 3 | 1.5 | 1.5 | 5 | 3 | 5 | 2 | 1.5
450 | 25 | 19 | 32.5 | 48.5 | 58.5 | 68.5 | 82 | 99 | 118 | 129 | 145 | 160.5 | 175 | 183.5 | 5 | 5 | 6 | 3 | 3 | 3 | 6 | 1.5 | 5 | 3 | 3 | 5 | 3 | 1.5 | 4 | 1.5 | 1.5 | 2 | 5 | 1.5 | 2.5 | 4 | 2 | 5 | 4 | 6 | 5 | 2 | 5 | 4 | 5 | 5 | 2 | 3 | 4 | 2 | 3 | 4 | 5 | 4 | 5 | 1.5 | 4 | 5 | 6 | 3 | 2.5 | 3 | 2.5 | 2.5 | 1.5 | 2
451 | 16 | 11 | 20 | 32.5 | 49.5 | 65.5 | 77.5 | 94.5 | 103.5 | 117 | 133 | 148.5 | 160.5 | 174.5 | 1.5 | 3 | 5 | 1.5 | 3 | 2 | 1.5 | 2.5 | 5 | 3 | 3 | 1.5 | 6 | 3 | 5 | 3 | 3 | 5 | 5 | 3 | 2.5 | 5 | 2.5 | 2 | 5 | 5 | 3 | 4 | 2 | 3 | 2.5 | 1.5 | 1.5 | 2 | 4 | 6 | 4 | 6 | 3 | 3 | 2.5 | 6 | 5 | 2 | 3 | 2.5 | 2.5 | 4 | 3 | 6 | 3 | 2
452 | 20 | 12 | 27.5 | 44.5 | 57 | 72.5 | 84.5 | 94.5 | 109.5 | 126.5 | 136.5 | 151 | 166.5 | 179 | 2.5 | 3 | 2.5 | 4 | 3 | 5 | 1.5 | 6 | 3 | 5 | 6 | 3 | 1.5 | 2 | 3 | 6 | 5 | 4 | 5 | 1.5 | 5 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 5 | 5 | 3 | 5 | 6 | 3 | 3 | 3 | 3 | 1.5 | 2.5 | 3 | 5 | 5 | 1.5 | 5 | 1.5 | 3 | 6 | 1.5 | 3 | 5 | 3
453 | 21 | 12 | 26.5 | 43 | 56 | 70 | 82 | 98 | 111.5 | 123.5 | 140.5 | 154.5 | 168.5 | 181 | 2.5 | 3 | 4 | 2.5 | 6 | 3 | 2.5 | 3 | 5 | 4 | 1.5 | 6 | 2 | 2 | 3 | 6 | 5 | 3 | 4 | 2 | 4 | 4 | 2 | 2 | 5 | 3 | 3 | 5 | 2.5 | 3 | 5 | 3 | 2 | 3 | 4 | 3 | 6 | 6 | 2 | 3 | 3 | 3 | 4 | 4 | 6 | 2.5 | 3 | 2.5 | 5 | 2 | 4 | 1.5
454 | 24 | 16.5 | 33 | 50 | 68 | 82 | 96.5 | 109.5 | 122.5 | 139 | 151 | 168 | 184 | 205 | 6 | 6 | 2 | 2.5 | 6 | 1.5 | 6 | 3 | 5 | 4 | 3 | 5 | 4 | 6 | 3 | 5 | 5 | 6 | 1.5 | 1.5 | 4 | 3 | 5 | 2.5 | 6 | 4 | 1.5 | 1.5 | 3 | 4 | 4 | 2 | 1.5 | 6 | 6 | 3 | 3 | 4 | 2 | 3 | 6 | 5 | 3 | 3 | 6 | 4 | 4 | 2 | 6 | 5 | 6 | 4
455 | 21.5 | 16 | 31.5 | 45.5 | 56.5 | 67.5 | 81.5 | 94 | 107.5 | 121.5 | 132 | 150 | 166 | 183 | 2 | 3 | 6 | 5 | 4 | 1.5 | 6 | 4 | 6 | 3 | 2 | 3 | 2 | 2 | 4 | 3 | 4 | 3 | 1.5 | 2.5 | 3 | 4 | 3 | 4 | 3 | 3 | 2.5 | 4 | 4 | 3 | 1.5 | 5 | 5 | 2 | 5 | 2 | 3 | 2 | 2.5 | 3 | 6 | 3 | 6 | 3 | 2 | 6 | 3 | 5 | 3 | 4 | 6 | 4
456 | 21 | 17 | 27.5 | 37.5 | 50 | 65.5 | 75 | 86 | 108 | 122.5 | 138 | 157.5 | 172.5 | 184 | 6 | 6 | 3 | 2 | 2.5 | 1.5 | 1.5 | 5 | 3 | 1.5 | 2.5 | 3 | 2.5 | 1.5 | 6 | 2.5 | 1.5 | 4 | 5 | 5 | 4 | 2.5 | 1.5 | 1.5 | 3 | 3 | 2 | 3 | 6 | 5 | 5 | 6 | 3 | 2.5 | 4 | 5 | 2 | 5 | 2.5 | 6 | 2.5 | 6 | 5 | 6 | 3 | 2 | 5 | 5 | 2 | 5 | 2.5 | 2
457 | 23.5 | 14.5 | 27.5 | 44.5 | 60 | 70.5 | 88.5 | 100 | 115 | 126.5 | 143.5 | 153.5 | 163.5 | 175.5 | 1.5 | 5 | 4 | 4 | 6 | 3 | 2.5 | 1.5 | 3 | 4 | 5 | 5 | 5 | 5 | 3 | 2.5 | 2.5 | 3 | 2 | 3 | 3 | 6 | 6 | 3 | 6 | 2 | 2 | 1.5 | 3 | 4 | 2 | 6 | 2 | 2.5 | 4 | 3 | 3 | 4 | 5 | 5 | 2 | 3 | 3 | 2 | 4 | 3 | 1.5 | 1.5 | 6 | 1.5 | 1.5 | 3
458 | 24 | 12 | 30 | 44 | 56 | 71.5 | 86.5 | 94.5 | 107.5 | 118 | 130.5 | 145 | 154 | 162.5 | 2 | 5 | 3 | 2 | 6 | 6 | 3 | 3 | 2 | 4 | 5 | 3 | 4 | 2.5 | 2.5 | 3 | 3 | 6 | 4 | 2.5 | 4 | 6 | 3 | 2 | 2.5 | 2 | 2 | 1.5 | 3 | 3 | 2 | 5 | 4 | 3 | 2 | 1.5 | 2.5 | 3 | 3 | 4 | 3 | 6 | 1.5 | 4 | 1.5 | 2 | 1.5 | 4 | 1.5 | 3 | 2.5 | 1.5
459 | 25 | 14 | 29 | 44 | 59 | 68.5 | 76.5 | 90.5 | 103.5 | 118 | 130 | 144 | 153.5 | 168 | 2.5 | 4 | 5 | 2.5 | 5 | 6 | 2 | 2 | 6 | 3 | 3 | 3 | 3 | 4 | 5 | 3 | 3 | 2 | 3 | 1.5 | 2 | 2.5 | 1.5 | 2 | 5 | 3 | 3 | 3 | 2.5 | 6 | 1.5 | 3 | 2.5 | 3 | 3 | 6 | 1.5 | 3 | 5 | 2.5 | 3 | 3 | 3 | 5 | 2 | 1.5 | 3 | 3 | 5 | 4 | 2.5 | 3
460 | 23 | 15.5 | 33 | 49 | 62 | 76 | 92 | 104.5 | 117 | 134.5 | 153.5 | 164 | 179 | 195 | 1.5 | 3 | 6 | 5 | 5 | 2.5 | 5 | 5 | 3 | 5 | 2 | 6 | 5 | 1.5 | 4 | 2.5 | 3 | 6 | 2.5 | 2.5 | 3 | 6 | 2 | 5 | 3 | 1.5 | 3 | 5 | 3 | 2 | 2.5 | 5 | 6 | 6 | 3 | 2.5 | 6 | 3 | 4 | 6 | 5 | 1.5 | 2.5 | 1.5 | 3 | 3 | 5 | 4 | 4 | 4 | 4 | 4
461 | 14 | 8.5 | 21 | 33.5 | 47.5 | 59.5 | 78.5 | 87.5 | 105 | 122.5 | 134 | 150.5 | 164.5 | 179 | 2.5 | 1.5 | 3 | 1.5 | 2.5 | 3 | 2 | 5 | 3 | 5 | 2 | 2.5 | 6 | 3 | 2 | 3 | 6 | 3 | 1.5 | 1.5 | 5 | 3 | 5 | 6 | 2 | 3 | 1.5 | 2.5 | 6 | 6 | 2.5 | 3 | 5 | 5 | 1.5 | 6 | 3 | 3 | 2.5 | 3 | 2.5 | 6 | 2 | 6 | 3 | 3 | 5 | 3 | 3 | 3 | 2.5 | 6
462 | 28 | 19 | 35.5 | 49 | 63 | 75 | 93.5 | 113.5 | 124.5 | 140 | 154.5 | 175.5 | 191 | 205.5 | 3 | 5 | 5 | 6 | 6 | 3 | 5 | 2.5 | 3 | 4 | 2.5 | 4 | 4 | 2 | 6 | 2 | 5 | 3 | 2.5 | 1.5 | 1.5 | 6 | 5 | 6 | 6 | 6 | 5 | 3 | 3 | 2.5 | 1.5 | 4 | 5 | 3 | 2.5 | 5 | 6 | 1.5 | 4 | 3 | 5 | 4 | 6 | 6 | 3 | 6 | 1.5 | 5 | 2 | 5 | 1.5 | 6
463 | 25.5 | 18 | 33 | 47 | 61 | 72.5 | 83 | 100.5 | 112 | 127 | 141 | 153 | 165.5 | 175.5 | 6 | 5 | 4 | 3 | 5 | 2.5 | 2.5 | 5 | 6 | 4 | 2.5 | 1.5 | 3 | 5 | 3 | 3 | 2.5 | 3 | 3 | 3 | 2 | 2 | 4 | 2.5 | 6 | 6 | 3 | 2.5 | 1.5 | 4 | 4 | 2 | 4 | 2.5 | 2.5 | 6 | 4 | 4 | 3 | 3 | 1.5 | 2.5 | 3 | 5 | 5 | 2 | 2.5 | 3 | 2.5 | 2 | 1.5 | 4
464 | 25.5 | 15.5 | 31.5 | 50 | 62.5 | 74 | 86.5 | 98 | 111.5 | 120.5 | 140.5 | 158.5 | 169.5 | 182 | 5 | 1.5 | 4 | 5 | 6 | 4 | 4 | 2 | 4 | 6 | 6 | 2.5 | 3 | 2.5 | 2 | 5 | 4 | 2.5 | 2.5 | 2.5 | 2 | 5 | 4 | 1.5 | 4 | 3 | 2 | 2.5 | 5 | 4 | 1.5 | 3 | 1.5 | 3 | 2 | 2.5 | 5 | 6 | 6 | 3 | 4 | 5 | 5 | 4 | 2 | 3 | 3 | 3 | 2 | 4 | 5 | 1.5
465 | 13.5 | 8 | 24.5 | 39 | 50.5 | 64 | 78.5 | 92.5 | 110.5 | 119 | 130.5 | 146.5 | 164.5 | 176 | 2.5 | 1.5 | 1.5 | 2.5 | 3 | 2.5 | 5 | 6 | 5 | 1.5 | 3 | 5 | 2 | 2 | 1.5 | 6 | 3 | 1.5 | 6 | 3 | 6 | 3 | 2.5 | 3 | 3 | 3 | 4 | 4 | 3 | 6 | 6 | 3 | 2 | 2 | 1.5 | 3 | 2 | 3 | 5 | 1.5 | 6 | 3 | 5 | 2 | 5 | 6 | 4 | 3 | 3 | 2 | 4 | 2.5
466 | 16.5 | 9.5 | 21 | 34 | 51 | 61 | 72.5 | 84.5 | 94.5 | 109.5 | 123 | 140 | 153.5 | 168 | 4 | 1.5 | 2.5 | 1.5 | 4 | 3 | 3 | 1.5 | 2.5 | 6 | 2.5 | 2 | 6 | 6 | 2 | 3 | 1.5 | 3 | 2.5 | 3 | 2 | 4 | 2.5 | 3 | 2 | 6 | 1.5 | 2.5 | 1.5 | 3 | 1.5 | 4 | 5 | 3 | 2 | 5 | 3 | 1.5 | 6 | 3 | 6 | 4 | 2 | 5 | 3 | 5 | 2.5 | 3 | 6 | 1.5 | 2 | 5
467 | 19.5 | 12.5 | 25.5 | 38.5 | 49 | 61 | 77 | 89 | 108 | 121 | 135 | 141.5 | 154.5 | 168 | 3 | 2 | 2.5 | 5 | 4 | 3 | 3 | 3 | 4 | 3 | 3 | 3 | 2 | 2.5 | 3 | 3 | 3 | 4 | 2 | 3 | 4 | 3 | 6 | 3 | 3 | 3 | 3 | 3 | 5 | 4 | 6 | 4 | 2.5 | 2.5 | 4 | 4 | 3 | 2.5 | 2.5 | 6 | 1.5 | 1.5 | 1.5 | 2 | 6 | 1.5 | 1.5 | 4 | 5 | 1.5 | 5 | 2
468 | 18 | 14.5 | 23 | 34 | 45.5 | 59 | 75 | 89.5 | 103.5 | 113 | 127.5 | 142 | 155.5 | 173.5 | 6 | 3 | 3 | 2.5 | 2 | 1.5 | 2 | 3 | 3 | 1.5 | 1.5 | 5 | 5 | 3 | 2 | 1.5 | 3 | 4 | 4 | 2.5 | 2 | 6 | 6 | 2 | 3 | 3 | 2.5 | 6 | 4 | 2 | 6 | 2 | 1.5 | 2 | 3 | 3 | 2.5 | 4 | 4 | 4 | 1.5 | 4 | 6 | 3 | 5 | 2.5 | 3 | 3 | 5 | 6 | 2 | 5
469 | 17.5 | 13.5 | 24 | 35.5 | 45 | 61.5 | 81.5 | 95 | 109.5 | 125.5 | 141.5 | 158 | 174 | 186 | 2 | 6 | 1.5 | 4 | 2 | 2 | 5 | 1.5 | 5 | 1.5 | 2.5 | 2.5 | 1.5 | 3 | 2 | 3 | 2.5 | 5 | 6 | 3 | 5 | 3 | 6 | 6 | 2 | 2.5 | 3 | 6 | 5 | 1.5 | 5 | 3 | 4 | 4 | 3 | 5 | 2 | 6 | 5 | 3 | 1.5 | 5 | 6 | 4 | 6 | 2 | 3 | 5 | 3 | 3 | 3 | 3
470 | 24.5 | 16 | 30 | 42.5 | 53.5 | 62.5 | 77 | 96 | 108.5 | 122.5 | 134.5 | 152.5 | 164.5 | 175.5 | 3 | 5 | 2 | 6 | 6 | 2.5 | 1.5 | 4 | 2.5 | 2.5 | 2.5 | 5 | 2 | 3 | 3 | 3 | 1.5 | 2.5 | 3 | 2 | 6 | 3 | 2.5 | 3 | 2 | 6 | 5 | 6 | 3 | 3 | 1.5 | 5 | 6 | 3 | 2 | 3 | 1.5 | 5 | 3 | 2.5 | 3 | 6 | 4 | 5 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3
471 | 19.5 | 15 | 26.5 | 37.5 | 44.5 | 60.5 | 75.5 | 86.5 | 95 | 106.5 | 126.5 | 141.5 | 159 | 172.5 | 6 | 3 | 3 | 3 | 2 | 2.5 | 4 | 3 | 4 | 2.5 | 1.5 | 3 | 2 | 1.5 | 1.5 | 2 | 3 | 4 | 3 | 6 | 2 | 4 | 5 | 4 | 3 | 2 | 3 | 3 | 2.5 | 1.5 | 1.5 | 3 | 2 | 3 | 4 | 2.5 | 3 | 6 | 6 | 5 | 3 | 6 | 2 | 4 | 2.5 | 6 | 5 | 4 | 3 | 5 | 2.5 | 3
472 | 26.5 | 18.5 | 29.5 | 43.5 | 56 | 71 | 84 | 94 | 112 | 124.5 | 139 | 154.5 | 172.5 | 191 | 6 | 2.5 | 6 | 4 | 5 | 3 | 1.5 | 1.5 | 2 | 6 | 2 | 4 | 1.5 | 2.5 | 2.5 | 6 | 4 | 3 | 2 | 6 | 2.5 | 3 | 6 | 1.5 | 1.5 | 1.5 | 3 | 4 | 6 | 4 | 6 | 2 | 4 | 3 | 4 | 1.5 | 6 | 3 | 2.5 | 3 | 2.5 | 4 | 3 | 6 | 6 | 5 | 3 | 4 | 2.5 | 6 | 5 | 5
473 | 18.5 | 10.5 | 24.5 | 40.5 | 54.5 | 66.5 | 80 | 96 | 105.5 | 118 | 130 | 142 | 150.5 | 167.5 | 2.5 | 4 | 2 | 2 | 3 | 5 | 2 | 4 | 4 | 5 | 4 | 3 | 6 | 2.5 | 3 | 2.5 | 6 | 1.5 | 1.5 | 3 | 3 | 2 | 2.5 | 6 | 4 | 6 | 3 | 3 | 2.5 | 1.5 | 3 | 2.5 | 2.5 | 2 | 5 | 3 | 2 | 4 | 4 | 2 | 1.5 | 3 | 2.5 | 5 | 2.5 | 2 | 2 | 2 | 5 | 4 | 2 | 6
474 | 13.5 | 10.5 | 19.5 | 31 | 51 | 61 | 72 | 83 | 96 | 115 | 125 | 139 | 152 | 161 | 1.5 | 2 | 3 | 4 | 1.5 | 1.5 | 2 | 4 | 2.5 | 2 | 3 | 4 | 5 | 5 | 4 | 6 | 2 | 2.5 | 4 | 1.5 | 2.5 | 2 | 5 | 1.5 | 4 | 3 | 2.5 | 1.5 | 4 | 3 | 2 | 4 | 6 | 3 | 4 | 6 | 2 | 4 | 2.5 | 1.5 | 4 | 3 | 5 | 2 | 5 | 3 | 3 | 2 | 3 | 1.5 | 2 | 2.5
475 | 15.5 | 12 | 24.5 | 39.5 | 51 | 63.5 | 74.5 | 82.5 | 99.5 | 118 | 128.5 | 137.5 | 154 | 172 | 2 | 3 | 3 | 4 | 1.5 | 2 | 3 | 6 | 5 | 3 | 3 | 4 | 2.5 | 1.5 | 1.5 | 6 | 2.5 | 6 | 2.5 | 1.5 | 4 | 3 | 2.5 | 1.5 | 2.5 | 2.5 | 1.5 | 1.5 | 6 | 3 | 2 | 6 | 2.5 | 6 | 4 | 6 | 3 | 3 | 2 | 2.5 | 1.5 | 3 | 3 | 1.5 | 3 | 6 | 2.5 | 5 | 6 | 6 | 2 | 4
476 | 22.5 | 15 | 30 | 38.5 | 53.5 | 62 | 77.5 | 93 | 106.5 | 121 | 133.5 | 147 | 157.5 | 173 | 3 | 6 | 3 | 3 | 2.5 | 5 | 2.5 | 5 | 1.5 | 2.5 | 1.5 | 3 | 3 | 3 | 3 | 6 | 1.5 | 3 | 2.5 | 1.5 | 3 | 4 | 2.5 | 6 | 5 | 4 | 1.5 | 5 | 6 | 2 | 4 | 1.5 | 5 | 1.5 | 3 | 5 | 5 | 2.5 | 3 | 2 | 2.5 | 5 | 3 | 3 | 3 | 2 | 3 | 2.5 | 1.5 | 6 | 5 | 3
477 | 19.5 | 12.5 | 25.5 | 38 | 56 | 69 | 82 | 91.5 | 103.5 | 119.5 | 131.5 | 147 | 162 | 178.5 | 2.5 | 2 | 5 | 3 | 3 | 4 | 3 | 3 | 2.5 | 2 | 3 | 5 | 3 | 3 | 6 | 6 | 1.5 | 2.5 | 5 | 4 | 4 | 2.5 | 5 | 1.5 | 3 | 2 | 1.5 | 3 | 2.5 | 3 | 4 | 2.5 | 3 | 2 | 6 | 5 | 5 | 2.5 | 3 | 1.5 | 2.5 | 4 | 6 | 3 | 3 | 3 | 6 | 3 | 6 | 1.5 | 6 | 3
478 | 22 | 16 | 27.5 | 42.5 | 58.5 | 72.5 | 83 | 96 | 108 | 120.5 | 133 | 146 | 161.5 | 174 | 6 | 3 | 3 | 4 | 2 | 4 | 3 | 2.5 | 3 | 3 | 5 | 4 | 5 | 4 | 5 | 2 | 1.5 | 5 | 5 | 2.5 | 1.5 | 2 | 3 | 4 | 2.5 | 1.5 | 3 | 6 | 2 | 3 | 3 | 4 | 5 | 3 | 1.5 | 3 | 5 | 3 | 2.5 | 2 | 3 | 1.5 | 2.5 | 6 | 2.5 | 3 | 5 | 5 | 2.5 | 2 | 4 | 4
479 | 22.5 | 16.5 | 28 | 38 | 48.5 | 65 | 76.5 | 91 | 102 | 118 | 130.5 | 142.5 | 152 | 165.5 | 6 | 2.5 | 4 | 4 | 3 | 3 | 2.5 | 3 | 3 | 3 | 2.5 | 1.5 | 2 | 1.5 | 2 | 5 | 2.5 | 6 | 5 | 3 | 4 | 1.5 | 3 | 3 | 3 | 6 | 4 | 1.5 | 2.5 | 2.5 | 3 | 3 | 6 | 2.5 | 1.5 | 6 | 3 | 4 | 4 | 1.5 | 3 | 3 | 3 | 3 | 1.5 | 3 | 2 | 3 | 6 | 1.5 | 3 | 3
480 | 22 | 16.5 | 25.5 | 42.5 | 53.5 | 65.5 | 78 | 89.5 | 103 | 118 | 130 | 143 | 153 | 166.5 | 4 | 6 | 2.5 | 4 | 4 | 1.5 | 1.5 | 2 | 4 | 4 | 6 | 3 | 6 | 1.5 | 2 | 1.5 | 1.5 | 1.5 | 6 | 3 | 4 | 2.5 | 3 | 3 | 3 | 1.5 | 2 | 5 | 3 | 5 | 3 | 2.5 | 3 | 6 | 3 | 3 | 5 | 3 | 1.5 | 2.5 | 4 | 3 | 3 | 3 | 1.5 | 2.5 | 3 | 3 | 4 | 2.5 | 3 | 4
481 | 21.5 | 14.5 | 25 | 40 | 50.5 | 63.5 | 77.5 | 87.5 | 102.5 | 111.5 | 118.5 | 134.5 | 145.5 | 157.5 | 2.5 | 5 | 5 | 2 | 4 | 3 | 1.5 | 2 | 6 | 2 | 5 | 2 | 2 | 2 | 4 | 2.5 | 3 | 4 | 3 | 3 | 4 | 3 | 2 | 5 | 1.5 | 3 | 2.5 | 3 | 4 | 2 | 4 | 5 | 3 | 1.5 | 3 | 1.5 | 1.5 | 1.5 | 1.5 | 2.5 | 6 | 4 | 2 | 4 | 1.5 | 2 | 5 | 2.5 | 1.5 | 2.5 | 3 | 5
482 | 15.5 | 11 | 23.5 | 33 | 40.5 | 53 | 64 | 75 | 86.5 | 101.5 | 116 | 129.5 | 149 | 164 | 2 | 1.5 | 6 | 1.5 | 1.5 | 3 | 3 | 5 | 4 | 2 | 1.5 | 2 | 1.5 | 1.5 | 1.5 | 3 | 6 | 2 | 2 | 2.5 | 3 | 2.5 | 3 | 2.5 | 2.5 | 3 | 1.5 | 4 | 2 | 5 | 2.5 | 2 | 3 | 3 | 3 | 6 | 1.5 | 3 | 6 | 4 | 3 | 4 | 5 | 1.5 | 6 | 2.5 | 5 | 6 | 5 | 6 | 2 | 2
483 | 19 | 13.5 | 26 | 39.5 | 52 | 64.5 | 77 | 90 | 101.5 | 109.5 | 122.5 | 135 | 155 | 164 | 2 | 6 | 1.5 | 4 | 3 | 2.5 | 5 | 2 | 1.5 | 4 | 4 | 4 | 3 | 2.5 | 4 | 3 | 2.5 | 2.5 | 2.5 | 5 | 3 | 6 | 2 | 1.5 | 4 | 4 | 2 | 3 | 3 | 4 | 2 | 2.5 | 1.5 | 2 | 1.5 | 3 | 3 | 3 | 3 | 4 | 4 | 3 | 2.5 | 3 | 6 | 6 | 4 | 4 | 1.5 | 2.5 | 2 | 3
484 | 18.5 | 11 | 27.5 | 44.5 | 55 | 71 | 80.5 | 94 | 105.5 | 118 | 129.5 | 140.5 | 149 | 159.5 | 2 | 5 | 2.5 | 1.5 | 5 | 2.5 | 6 | 3 | 3 | 6 | 6 | 2 | 2 | 2.5 | 4 | 2 | 5 | 4 | 3 | 4 | 1.5 | 4 | 2.5 | 1.5 | 3 | 1.5 | 3 | 6 | 3 | 3 | 3 | 2.5 | 6 | 3 | 2 | 1.5 | 4 | 1.5 | 3 | 3 | 5 | 2 | 2.5 | 1.5 | 2 | 2 | 2.5 | 2 | 2 | 4 | 3 | 1.5
485 | 16 | 11.5 | 21 | 30 | 44.5 | 55.5 | 65.5 | 79 | 93.5 | 106.5 | 117.5 | 130.5 | 144.5 | 160.5 | 5 | 2.5 | 2.5 | 1.5 | 1.5 | 3 | 3 | 2 | 1.5 | 2 | 3 | 2.5 | 3 | 4 | 2.5 | 5 | 4 | 2 | 2.5 | 2.5 | 1.5 | 1.5 | 4 | 3 | 2.5 | 6 | 2.5 | 2.5 | 3 | 5 | 2.5 | 4 | 2 | 4 | 4 | 3 | 4 | 2.5 | 3 | 1.5 | 2.5 | 5 | 4 | 1.5 | 3 | 2 | 6 | 3 | 2 | 2 | 6 | 6
486 | 19 | 15 | 25.5 | 39.5 | 51 | 63 | 74 | 89.5 | 100 | 114.5 | 125.5 | 139.5 | 148.5 | 159.5 | 2 | 4 | 3 | 6 | 2 | 2 | 2.5 | 4 | 3 | 5 | 3 | 3 | 2.5 | 2.5 | 5 | 1.5 | 3 | 2.5 | 2.5 | 4 | 2 | 3 | 4 | 2 | 2.5 | 2 | 5 | 6 | 2.5 | 3 | 2 | 3 | 2.5 | 2 | 5 | 5 | 4 | 2 | 3 | 2 | 2 | 5 | 4 | 3 | 3 | 2 | 1.5 | 2.5 | 2.5 | 4 | 3 | 1.5
487 | 24.5 | 15.5 | 28 | 40 | 51.5 | 60 | 72 | 86 | 101.5 | 116 | 127.5 | 139.5 | 149.5 | 167 | 3 | 4 | 6 | 2.5 | 3 | 6 | 1.5 | 2 | 1.5 | 1.5 | 5 | 4 | 2.5 | 3 | 3 | 3 | 3 | 2 | 2 | 1.5 | 3 | 1.5 | 1.5 | 6 | 5 | 5 | 1.5 | 2.5 | 6 | 1.5 | 3 | 5 | 5 | 2.5 | 3 | 4 | 2 | 2.5 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 1.5 | 3 | 1.5 | 6 | 5 | 4 | 2.5
488 | 15 | 9.5 | 22.5 | 33 | 42 | 57.5 | 72.5 | 82.5 | 96.5 | 112.5 | 126 | 140.5 | 151.5 | 163 | 2 | 1.5 | 3 | 3 | 2.5 | 3 | 6 | 1.5 | 4 | 1.5 | 2.5 | 2.5 | 3 | 2 | 1.5 | 2.5 | 4 | 6 | 2.5 | 3 | 5 | 5 | 3 | 2 | 2 | 2 | 2 | 4 | 3 | 2 | 3 | 6 | 2.5 | 5 | 6 | 2.5 | 6 | 3 | 2 | 2.5 | 3 | 6 | 1.5 | 4 | 5 | 1.5 | 1.5 | 3 | 1.5 | 2 | 3 | 5
489 | 22 | 14.5 | 27.5 | 45.5 | 63 | 75.5 | 86.5 | 98 | 107.5 | 121.5 | 136.5 | 148 | 164 | 174 | 5 | 5 | 3 | 1.5 | 1.5 | 6 | 2.5 | 3 | 3 | 4 | 6 | 5 | 5 | 1.5 | 5 | 6 | 4 | 2.5 | 2 | 4 | 4 | 2 | 2 | 3 | 3 | 1.5 | 5 | 2 | 1.5 | 3 | 2.5 | 2.5 | 2.5 | 6 | 4 | 1.5 | 2.5 | 5 | 6 | 1.5 | 3 | 5 | 1.5 | 2 | 6 | 5 | 3 | 2 | 2.5 | 4 | 1.5 | 2
490 | 24 | 17 | 29 | 45 | 57.5 | 67 | 84.5 | 99.5 | 117 | 131 | 148 | 161.5 | 178.5 | 190 | 6 | 6 | 3 | 2 | 3 | 4 | 3 | 2 | 6 | 2.5 | 1.5 | 6 | 4 | 3 | 3 | 2.5 | 3 | 2 | 2.5 | 2 | 1.5 | 5 | 5 | 6 | 5 | 5 | 2 | 3 | 5 | 4 | 2.5 | 6 | 2.5 | 1.5 | 6 | 4 | 5 | 6 | 3 | 3 | 4 | 1.5 | 5 | 3 | 2.5 | 6 | 2.5 | 6 | 3 | 5 | 2 | 1.5
491 | 25.5 | 15.5 | 34.5 | 54.5 | 67.5 | 85.5 | 97 | 109 | 121.5 | 139.5 | 152 | 162 | 174.5 | 183.5 | 4 | 2.5 | 5 | 4 | 6 | 4 | 3 | 6 | 5 | 6 | 6 | 3 | 2 | 3 | 3 | 5 | 3 | 6 | 3 | 6 | 3 | 2.5 | 3 | 3 | 3 | 5 | 2 | 2 | 2.5 | 2 | 4 | 4 | 5 | 4 | 6 | 3 | 2.5 | 5 | 2 | 3 | 3 | 1.5 | 2.5 | 3 | 2 | 3 | 6 | 1.5 | 2.5 | 2 | 2.5 | 2
492 | 19 | 12 | 27 | 42 | 57 | 70 | 82 | 97 | 104.5 | 120.5 | 140.5 | 154.5 | 172 | 188.5 | 4 | 2 | 3 | 3 | 2 | 5 | 3 | 5 | 3 | 3 | 3 | 6 | 4 | 2 | 4 | 5 | 3 | 3 | 3 | 4 | 1.5 | 4 | 2.5 | 4 | 2.5 | 6 | 2.5 | 4 | 1.5 | 3 | 1.5 | 1.5 | 4 | 6 | 4 | 2 | 6 | 3 | 6 | 5 | 3 | 6 | 2 | 3 | 6 | 2.5 | 6 | 3 | 5 | 2.5 | 6 | 3
493 | 26.5 | 16.5 | 32 | 42 | 53.5 | 63.5 | 76 | 91.5 | 102.5 | 113.5 | 132.5 | 152.5 | 164.5 | 182.5 | 5 | 6 | 3 | 2.5 | 6 | 4 | 1.5 | 4 | 3 | 2 | 3 | 2 | 4 | 2 | 3 | 2.5 | 3 | 3 | 2 | 2 | 1.5 | 2 | 5 | 4 | 5 | 2.5 | 3 | 5 | 3 | 2 | 3 | 3 | 2.5 | 3 | 4 | 1.5 | 6 | 3 | 6 | 4 | 4 | 6 | 4 | 6 | 3 | 1.5 | 5 | 2.5 | 3 | 6 | 3 | 6
494 | 19.5 | 12 | 25 | 41.5 | 55 | 64 | 82 | 91.5 | 104.5 | 116.5 | 132.5 | 149 | 158.5 | 171.5 | 2 | 5 | 2.5 | 2.5 | 1.5 | 6 | 1.5 | 4 | 2.5 | 4 | 6 | 4 | 5 | 2.5 | 3 | 3 | 3 | 2 | 2 | 2 | 6 | 3 | 6 | 3 | 2 | 2.5 | 2 | 3 | 6 | 2.5 | 2.5 | 2 | 4 | 1.5 | 4 | 2.5 | 5 | 3 | 3 | 5 | 5 | 6 | 3 | 2.5 | 2 | 3 | 3 | 1.5 | 3 | 4 | 3 | 3
495 | 22.5 | 14 | 30 | 40 | 55.5 | 69 | 82 | 93.5 | 108 | 123 | 141 | 154 | 166 | 177.5 | 4 | 4 | 3 | 3 | 2.5 | 6 | 6 | 1.5 | 4 | 1.5 | 1.5 | 3 | 6 | 2.5 | 4 | 3 | 2 | 4 | 2.5 | 5 | 2.5 | 2.5 | 5 | 3 | 3 | 2 | 2.5 | 4 | 2.5 | 2 | 6 | 4 | 5 | 5 | 2 | 3 | 5 | 2 | 6 | 5 | 3 | 1.5 | 6 | 2.5 | 2 | 2.5 | 5 | 2.5 | 4 | 1.5 | 3 | 3
496 | 26 | 21 | 37 | 55.5 | 67.5 | 85 | 99 | 110.5 | 121.5 | 138 | 151.5 | 169 | 180 | 195.5 | 6 | 3 | 6 | 6 | 3 | 2 | 5 | 6 | 5 | 6 | 1.5 | 6 | 2.5 | 2.5 | 4 | 3 | 2.5 | 6 | 4 | 5 | 3 | 2 | 3 | 6 | 2 | 5 | 2.5 | 2 | 2.5 | 3 | 2.5 | 3 | 6 | 5 | 3 | 2.5 | 3 | 1.5 | 3 | 6 | 5 | 5 | 1.5 | 6 | 3 | 1.5 | 4 | 2.5 | 1.5 | 4 | 6 | 4
497 | 16 | 9 | 22 | 35.5 | 49 | 66 | 75 | 91.5 | 108 | 117 | 127 | 139.5 | 154.5 | 172 | 2 | 2 | 2.5 | 2.5 | 3 | 4 | 4 | 2 | 1.5 | 5 | 2 | 5 | 3 | 2.5 | 4 | 4 | 5 | 3 | 6 | 3 | 3 | 2 | 1.5 | 2.5 | 3 | 6 | 6 | 1.5 | 2.5 | 3 | 5 | 6 | 2 | 4 | 1.5 | 1.5 | 3 | 1.5 | 3 | 2.5 | 5 | 2.5 | 2.5 | 2.5 | 5 | 2 | 4 | 4 | 4 | 5 | 2.5 | 6
498 | 19.5 | 13.5 | 25.5 | 36.5 | 47 | 68 | 79 | 95.5 | 111.5 | 126.5 | 140 | 151 | 164 | 176.5 | 5 | 4 | 2.5 | 2 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5 | 5 | 3 | 3 | 1.5 | 3 | 5 | 5 | 6 | 5 | 2.5 | 5 | 1.5 | 2 | 6 | 5 | 2.5 | 3 | 3 | 5 | 3 | 5 | 3 | 3 | 4 | 5 | 5 | 2.5 | 4 | 2 | 3 | 3 | 2.5 | 2.5 | 2 | 3 | 6 | 2 | 3 | 4 | 2.5 | 3
499 | 20.5 | 15.5 | 31.5 | 45.5 | 58.5 | 69.5 | 81.5 | 95.5 | 106 | 119 | 130 | 140.5 | 158.5 | 171 | 1.5 | 5 | 5 | 4 | 3 | 2 | 6 | 5 | 5 | 6 | 1.5 | 1.5 | 3 | 3 | 4 | 3 | 1.5 | 3 | 4 | 2.5 | 4 | 2.5 | 3 | 2.5 | 6 | 4 | 2.5 | 1.5 | 2 | 4 | 3 | 1.5 | 1.5 | 6 | 1.5 | 4 | 2 | 3 | 3 | 3 | 3 | 1.5 | 3 | 3 | 5 | 4 | 3 | 6 | 2.5 | 3 | 3 | 4
500 | 15 | 10 | 19.5 | 34 | 49 | 64.5 | 80.5 | 99.5 | 115 | 126 | 138 | 151 | 163.5 | 181 | 1.5 | 3 | 2.5 | 3 | 2 | 3 | 3 | 1.5 | 4 | 3 | 6 | 1.5 | 3 | 3 | 6 | 3 | 6 | 3 | 5 | 1.5 | 2 | 3 | 5 | 6 | 6 | 6 | 3 | 4 | 4 | 1.5 | 5 | 5 | 1.5 | 6 | 1.5 | 2 | 6 | 1.5 | 3 | 1.5 | 3 | 4 | 3 | 3 | 2 | 1.5 | 5 | 4 | 1.5 | 5 | 6 | 5
| 6 | Sum4: 4; Sum8: 8; Sum12: 12; Sum16: 16; Sum20: 20; Sum24: 24; Sum28: 28; Sum32: 32; Sum36: 36; Sum40: 40; Sum44: 44; Sum48: 48; Sum52: 52
1% | 13 | Sum4: 7.5; Sum8: 18.995; Sum12: 30; Sum16: 40.495; Sum20: 52; Sum24: 62.995; Sum28: 74.495; Sum32: 86.495; Sum36: 97.985; Sum40: 108.99; Sum44: 121; Sum48: 134.495; Sum52: 148.495
2% | 13.5 | Sum4: 8; Sum8: 19.5; Sum12: 31.5; Sum16: 41.5; Sum20: 53; Sum24: 64.5; Sum28: 77.49; Sum32: 88.49; Sum36: 101.48; Sum40: 114.49; Sum44: 124.98; Sum48: 139.47; Sum52: 151.5
3% | 14 | Sum4: 8; Sum8: 20; Sum12: 32; Sum16: 42.5; Sum20: 54.5; Sum24: 65.5; Sum28: 79; Sum32: 91; Sum36: 104.47; Sum40: 115.97; Sum44: 127.485; Sum48: 142.485; Sum52: 153.485
4% | 14.5 | Sum4: 8.5; Sum8: 20.5; Sum12: 32; Sum16: 43.5; Sum20: 55.5; Sum24: 66.98; Sum28: 79.5; Sum32: 92.98; Sum36: 105.98; Sum40: 117.5; Sum44: 130; Sum48: 143.5; Sum52: 155.5
5% | 14.5 | Sum4: 9; Sum8: 20.975; Sum12: 32.5; Sum16: 44; Sum20: 56.475; Sum24: 68; Sum28: 80; Sum32: 94; Sum36: 106.5; Sum40: 119.5; Sum44: 131; Sum48: 144; Sum52: 156.475
6% | 15 | Sum4: 9; Sum8: 21; Sum12: 33; Sum16: 44.5; Sum20: 57; Sum24: 68.97; Sum28: 81; Sum32: 94.5; Sum36: 107.5; Sum40: 119.97; Sum44: 132.47; Sum48: 144.5; Sum52: 157.5
7% | 15 | Sum4: 9.5; Sum8: 21; Sum12: 33; Sum16: 45; Sum20: 57; Sum24: 69.465; Sum28: 81.5; Sum32: 95.5; Sum36: 108.5; Sum40: 121.465; Sum44: 133; Sum48: 145.5; Sum52: 158.5
8% | 15 | Sum4: 9.5; Sum8: 21; Sum12: 33.5; Sum16: 45.5; Sum20: 57.5; Sum24: 70; Sum28: 82.5; Sum32: 96; Sum36: 108.96; Sum40: 122; Sum44: 133.5; Sum48: 146; Sum52: 159.5
9% | 15.5 | Sum4: 9.5; Sum8: 21.455; Sum12: 33.5; Sum16: 46; Sum20: 58; Sum24: 70.5; Sum28: 83; Sum32: 96.5; Sum36: 109.455; Sum40: 122.5; Sum44: 134; Sum48: 147.5; Sum52: 160
10% | 15.5 | Sum4: 9.5; Sum8: 21.5; Sum12: 34; Sum16: 46; Sum20: 58; Sum24: 71; Sum28: 83.95; Sum32: 97; Sum36: 110; Sum40: 122.95; Sum44: 134.95; Sum48: 148.5; Sum52: 160.95
11% | 16 | Sum4: 10; Sum8: 21.5; Sum12: 34; Sum16: 46.5; Sum20: 58.5; Sum24: 71.5; Sum28: 84; Sum32: 97.5; Sum36: 110.445; Sum40: 123.5; Sum44: 135.945; Sum48: 149.445; Sum52: 161.5
12% | 16 | Sum4: 10; Sum8: 22; Sum12: 34; Sum16: 47; Sum20: 58.5; Sum24: 71.94; Sum28: 84.5; Sum32: 98.5; Sum36: 111; Sum40: 124; Sum44: 136.44; Sum48: 150; Sum52: 162.5
13% | 16 | Sum4: 10; Sum8: 22; Sum12: 34.5; Sum16: 47; Sum20: 59; Sum24: 72; Sum28: 85; Sum32: 98.5; Sum36: 111.5; Sum40: 124; Sum44: 137; Sum48: 150.5; Sum52: 163
14% | 16.5 | Sum4: 10; Sum8: 22; Sum12: 34.5; Sum16: 47.43; Sum20: 59.43; Sum24: 72.43; Sum28: 85; Sum32: 99; Sum36: 111.5; Sum40: 124.5; Sum44: 137.5; Sum48: 150.93; Sum52: 164
15% | 16.5 | Sum4: 10.425; Sum8: 22.5; Sum12: 34.925; Sum16: 47.5; Sum20: 59.5; Sum24: 72.5; Sum28: 85.5; Sum32: 99.5; Sum36: 112; Sum40: 125; Sum44: 138; Sum48: 151.5; Sum52: 164
16% | 16.5 | Sum4: 10.5; Sum8: 22.5; Sum12: 35; Sum16: 47.5; Sum20: 60; Sum24: 72.5; Sum28: 86; Sum32: 99.5; Sum36: 112.42; Sum40: 125.5; Sum44: 138.5; Sum48: 151.5; Sum52: 165
17% | 16.5 | Sum4: 10.5; Sum8: 22.915; Sum12: 35.5; Sum16: 48; Sum20: 60.5; Sum24: 72.915; Sum28: 86.415; Sum32: 100; Sum36: 112.5; Sum40: 125.915; Sum44: 139; Sum48: 152; Sum52: 165.5
18% | 16.5 | Sum4: 11; Sum8: 23; Sum12: 35.5; Sum16: 48; Sum20: 60.5; Sum24: 73; Sum28: 86.5; Sum32: 100; Sum36: 112.91; Sum40: 126; Sum44: 139; Sum48: 152.41; Sum52: 166
19% | 17 | Sum4: 11; Sum8: 23; Sum12: 35.5; Sum16: 48.5; Sum20: 61; Sum24: 73.5; Sum28: 86.905; Sum32: 100.5; Sum36: 113; Sum40: 126.5; Sum44: 139.5; Sum48: 152.5; Sum52: 166.5
20% | 17 | Sum4: 11; Sum8: 23; Sum12: 35.5; Sum16: 48.5; Sum20: 61; Sum24: 73.9; Sum28: 87; Sum32: 100.5; Sum36: 113.5; Sum40: 127; Sum44: 140; Sum48: 153; Sum52: 166.9
21% | 17 | Sum4: 11; Sum8: 23.5; Sum12: 35.895; Sum16: 48.895; Sum20: 61.5; Sum24: 74; Sum28: 87; Sum32: 101; Sum36: 113.5; Sum40: 127.5; Sum44: 140; Sum48: 153.5; Sum52: 167
22% | 17.5 | Sum4: 11; Sum8: 23.5; Sum12: 36; Sum16: 49; Sum20: 61.5; Sum24: 74.5; Sum28: 87.5; Sum32: 101; Sum36: 114.5; Sum40: 128; Sum44: 140.5; Sum48: 153.89; Sum52: 167.5
23% | 17.5 | Sum4: 11.385; Sum8: 23.5; Sum12: 36; Sum16: 49; Sum20: 62; Sum24: 75; Sum28: 87.5; Sum32: 101; Sum36: 114.5; Sum40: 128; Sum44: 141; Sum48: 154; Sum52: 167.885
24% | 17.5 | Sum4: 11.5; Sum8: 23.5; Sum12: 36; Sum16: 49; Sum20: 62.38; Sum24: 75; Sum28: 88; Sum32: 101.5; Sum36: 115; Sum40: 128.38; Sum44: 141; Sum48: 154.5; Sum52: 168
25% | 17.5 | Sum4: 11.5; Sum8: 23.5; Sum12: 36; Sum16: 49.5; Sum20: 62.5; Sum24: 75.5; Sum28: 88; Sum32: 101.5; Sum36: 115; Sum40: 128.5; Sum44: 141; Sum48: 154.5; Sum52: 168.375
26% | 17.5 | Sum4: 11.5; Sum8: 24; Sum12: 36.5; Sum16: 49.5; Sum20: 62.5; Sum24: 75.5; Sum28: 88.5; Sum32: 101.87; Sum36: 115.5; Sum40: 129; Sum44: 141.5; Sum48: 155; Sum52: 168.5
27% | 18 | Sum4: 11.5; Sum8: 24; Sum12: 36.5; Sum16: 49.5; Sum20: 62.865; Sum24: 76; Sum28: 88.5; Sum32: 102.5; Sum36: 115.865; Sum40: 129; Sum44: 141.865; Sum48: 155.365; Sum52: 169
28% | 18 | Sum4: 11.5; Sum8: 24; Sum12: 36.5; Sum16: 50; Sum20: 63; Sum24: 76; Sum28: 89; Sum32: 102.5; Sum36: 116.5; Sum40: 129; Sum44: 142; Sum48: 155.5; Sum52: 169
29% | 18 | Sum4: 11.5; Sum8: 24; Sum12: 36.5; Sum16: 50; Sum20: 63.5; Sum24: 76.355; Sum28: 89; Sum32: 102.5; Sum36: 116.5; Sum40: 129.5; Sum44: 142.5; Sum48: 156; Sum52: 169.5
30% | 18 | Sum4: 12; Sum8: 24; Sum12: 37; Sum16: 50; Sum20: 63.5; Sum24: 76.5; Sum28: 89.5; Sum32: 103; Sum36: 117; Sum40: 130; Sum44: 142.5; Sum48: 156.5; Sum52: 169.5
31% | 18.345 | Sum4: 12; Sum8: 24.5; Sum12: 37; Sum16: 50.5; Sum20: 63.5; Sum24: 76.5; Sum28: 89.5; Sum32: 103; Sum36: 117; Sum40: 130; Sum44: 143; Sum48: 156.5; Sum52: 170
32% | 18.5 | Sum4: 12; Sum8: 24.5; Sum12: 37; Sum16: 50.5; Sum20: 63.5; Sum24: 77; Sum28: 90; Sum32: 103.5; Sum36: 117.34; Sum40: 130; Sum44: 143; Sum48: 156.84; Sum52: 170.5
33% | 18.5 | Sum4: 12; Sum8: 24.5; Sum12: 37.335; Sum16: 50.5; Sum20: 64; Sum24: 77; Sum28: 90.335; Sum32: 103.5; Sum36: 117.5; Sum40: 130.335; Sum44: 143.5; Sum48: 157; Sum52: 171
34% | 18.5 | Sum4: 12; Sum8: 25; Sum12: 37.5; Sum16: 50.5; Sum20: 64; Sum24: 77; Sum28: 90.5; Sum32: 103.5; Sum36: 117.5; Sum40: 130.5; Sum44: 143.83; Sum48: 157; Sum52: 171
35% | 18.5 | Sum4: 12; Sum8: 25; Sum12: 37.5; Sum16: 50.5; Sum20: 64.5; Sum24: 77.5; Sum28: 90.5; Sum32: 104; Sum36: 118; Sum40: 130.5; Sum44: 144; Sum48: 157.5; Sum52: 171
36% | 18.82 | Sum4: 12; Sum8: 25; Sum12: 37.5; Sum16: 51; Sum20: 64.5; Sum24: 77.5; Sum28: 91; Sum32: 104; Sum36: 118; Sum40: 130.82; Sum44: 144.5; Sum48: 158; Sum52: 171.5
37% | 19 | Sum4: 12; Sum8: 25; Sum12: 38; Sum16: 51; Sum20: 64.5; Sum24: 77.815; Sum28: 91.5; Sum32: 104.5; Sum36: 118; Sum40: 131; Sum44: 144.5; Sum48: 158.315; Sum52: 171.5
38% | 19 | Sum4: 12; Sum8: 25.5; Sum12: 38; Sum16: 51; Sum20: 64.5; Sum24: 78; Sum28: 91.5; Sum32: 104.5; Sum36: 118.5; Sum40: 131.5; Sum44: 145; Sum48: 158.5; Sum52: 172
39% | 19 | Sum4: 12.305; Sum8: 25.5; Sum12: 38; Sum16: 51.5; Sum20: 65; Sum24: 78; Sum28: 91.5; Sum32: 104.5; Sum36: 118.5; Sum40: 131.5; Sum44: 145; Sum48: 158.5; Sum52: 172
40% | 19 | Sum4: 12.5; Sum8: 25.5; Sum12: 38.5; Sum16: 51.5; Sum20: 65; Sum24: 78.5; Sum28: 91.8; Sum32: 105; Sum36: 118.5; Sum40: 132; Sum44: 145.3; Sum48: 159; Sum52: 172.5
41% | 19 | Sum4: 12.5; Sum8: 25.5; Sum12: 38.5; Sum16: 51.5; Sum20: 65; Sum24: 78.5; Sum28: 92; Sum32: 105; Sum36: 119; Sum40: 132; Sum44: 145.5; Sum48: 159; Sum52: 172.5
42% | 19 | Sum4: 12.5; Sum8: 25.5; Sum12: 38.5; Sum16: 51.79; Sum20: 65; Sum24: 78.5; Sum28: 92; Sum32: 105; Sum36: 119; Sum40: 132; Sum44: 145.79; Sum48: 159.5; Sum52: 173
43% | 19 | Sum4: 12.5; Sum8: 25.5; Sum12: 38.785; Sum16: 52; Sum20: 65.5; Sum24: 79; Sum28: 92.5; Sum32: 105.5; Sum36: 119.5; Sum40: 132; Sum44: 146; Sum48: 159.5; Sum52: 173.5
44% | 19.5 | Sum4: 12.5; Sum8: 25.78; Sum12: 39; Sum16: 52; Sum20: 65.5; Sum24: 79; Sum28: 92.5; Sum32: 105.5; Sum36: 119.5; Sum40: 132.5; Sum44: 146; Sum48: 160; Sum52: 173.5
45% | 19.5 | Sum4: 12.5; Sum8: 26; Sum12: 39; Sum16: 52.5; Sum20: 65.5; Sum24: 79; Sum28: 93; Sum32: 106; Sum36: 119.5; Sum40: 132.5; Sum44: 146.5; Sum48: 160; Sum52: 174
46% | 19.5 | Sum4: 12.77; Sum8: 26; Sum12: 39.5; Sum16: 52.5; Sum20: 66; Sum24: 79; Sum28: 93; Sum32: 106; Sum36: 120; Sum40: 133; Sum44: 147; Sum48: 160.5; Sum52: 174
47% | 19.5 | Sum4: 13; Sum8: 26.5; Sum12: 39.5; Sum16: 52.5; Sum20: 66; Sum24: 79.5; Sum28: 93; Sum32: 106.5; Sum36: 120.5; Sum40: 133; Sum44: 147; Sum48: 160.5; Sum52: 174.5
48% | 19.5 | Sum4: 13; Sum8: 26.5; Sum12: 39.5; Sum16: 53; Sum20: 66; Sum24: 79.5; Sum28: 93; Sum32: 106.5; Sum36: 120.5; Sum40: 133; Sum44: 147; Sum48: 161; Sum52: 174.5
49% | 19.755 | Sum4: 13; Sum8: 26.5; Sum12: 39.755; Sum16: 53; Sum20: 66.5; Sum24: 79.5; Sum28: 93.5; Sum32: 107; Sum36: 120.5; Sum40: 133.5; Sum44: 147.5; Sum48: 161.5; Sum52: 175
50% | 20 | Sum4: 13; Sum8: 26.5; Sum12: 40; Sum16: 53; Sum20: 66.75; Sum24: 80; Sum28: 93.5; Sum32: 107; Sum36: 120.5; Sum40: 133.5; Sum44: 147.5; Sum48: 161.5; Sum52: 175
51% | 20 | Sum4: 13; Sum8: 27; Sum12: 40; Sum16: 53.5; Sum20: 67; Sum24: 80; Sum28: 93.5; Sum32: 107; Sum36: 121; Sum40: 134; Sum44: 148; Sum48: 161.745; Sum52: 175
52% | 20 | Sum4: 13; Sum8: 27; Sum12: 40; Sum16: 53.5; Sum20: 67; Sum24: 80.5; Sum28: 93.74; Sum32: 107.5; Sum36: 121; Sum40: 134; Sum44: 148; Sum48: 162; Sum52: 175.5
53% | 20 | Sum4: 13.5; Sum8: 27; Sum12: 40; Sum16: 53.5; Sum20: 67; Sum24: 80.5; Sum28: 94; Sum32: 107.5; Sum36: 121; Sum40: 134.5; Sum44: 148.5; Sum48: 162.235; Sum52: 175.5
54% | 20.5 | Sum4: 13.5; Sum8: 27.5; Sum12: 40.5; Sum16: 53.5; Sum20: 67.5; Sum24: 80.5; Sum28: 94; Sum32: 107.5; Sum36: 121.23; Sum40: 134.5; Sum44: 148.5; Sum48: 162.5; Sum52: 176
55% | 20.5 | Sum4: 13.5; Sum8: 27.5; Sum12: 40.5; Sum16: 53.725; Sum20: 67.5; Sum24: 80.5; Sum28: 94.5; Sum32: 108; Sum36: 121.5; Sum40: 135; Sum44: 149; Sum48: 162.5; Sum52: 176
56% | 20.5 | Sum4: 13.5; Sum8: 27.5; Sum12: 40.5; Sum16: 54; Sum20: 67.5; Sum24: 81; Sum28: 94.5; Sum32: 108; Sum36: 121.5; Sum40: 135; Sum44: 149; Sum48: 163; Sum52: 176.5
57% | 20.5 | Sum4: 13.5; Sum8: 27.5; Sum12: 40.5; Sum16: 54; Sum20: 68; Sum24: 81; Sum28: 95; Sum32: 108; Sum36: 121.715; Sum40: 135.5; Sum44: 149; Sum48: 163; Sum52: 176.5
58% | 20.5 | Sum4: 13.71; Sum8: 27.5; Sum12: 41; Sum16: 54.5; Sum20: 68; Sum24: 81.5; Sum28: 95; Sum32: 108.21; Sum36: 122; Sum40: 136; Sum44: 149.5; Sum48: 163.5; Sum52: 176.71
59% | 20.5 | Sum4: 14; Sum8: 27.5; Sum12: 41; Sum16: 54.5; Sum20: 68; Sum24: 81.5; Sum28: 95; Sum32: 108.5; Sum36: 122; Sum40: 136.205; Sum44: 149.705; Sum48: 163.5; Sum52: 177
60% | 21 | Sum4: 14; Sum8: 27.7; Sum12: 41; Sum16: 54.5; Sum20: 68.5; Sum24: 81.5; Sum28: 95; Sum32: 108.5; Sum36: 122.5; Sum40: 136.5; Sum44: 150; Sum48: 163.5; Sum52: 177.5
61% | 21 | Sum4: 14; Sum8: 28; Sum12: 41; Sum16: 55; Sum20: 68.5; Sum24: 81.5; Sum28: 95.5; Sum32: 109; Sum36: 122.5; Sum40: 136.5; Sum44: 150.195; Sum48: 164; Sum52: 177.5
62% | 21 | Sum4: 14; Sum8: 28; Sum12: 41.19; Sum16: 55; Sum20: 68.5; Sum24: 82; Sum28: 95.5; Sum32: 109; Sum36: 122.5; Sum40: 137; Sum44: 150.5; Sum48: 164; Sum52: 178
63% | 21 | Sum4: 14; Sum8: 28; Sum12: 41.5; Sum16: 55; Sum20: 68.5; Sum24: 82; Sum28: 95.5; Sum32: 109.5; Sum36: 123; Sum40: 137; Sum44: 151; Sum48: 164; Sum52: 178
64% | 21.18 | Sum4: 14.18; Sum8: 28; Sum12: 41.5; Sum16: 55; Sum20: 68.68; Sum24: 82; Sum28: 95.5; Sum32: 109.5; Sum36: 123; Sum40: 137; Sum44: 151; Sum48: 164.5; Sum52: 178
65% | 21.5 | Sum4: 14.5; Sum8: 28; Sum12: 41.5; Sum16: 55; Sum20: 69; Sum24: 82.5; Sum28: 96; Sum32: 109.5; Sum36: 123; Sum40: 137.5; Sum44: 151; Sum48: 164.5; Sum52: 178.5
66% | 21.5 | Sum4: 14.5; Sum8: 28; Sum12: 42; Sum16: 55.5; Sum20: 69; Sum24: 82.5; Sum28: 96; Sum32: 110; Sum36: 123.5; Sum40: 137.5; Sum44: 151.5; Sum48: 165; Sum52: 178.67
67% | 21.5 | Sum4: 14.5; Sum8: 28.5; Sum12: 42; Sum16: 55.5; Sum20: 69.165; Sum24: 82.5; Sum28: 96; Sum32: 110.5; Sum36: 124; Sum40: 137.5; Sum44: 152; Sum48: 165.5; Sum52: 179
68% | 21.66 | Sum4: 14.5; Sum8: 28.5; Sum12: 42; Sum16: 56; Sum20: 69.5; Sum24: 83; Sum28: 96; Sum32: 110.5; Sum36: 124.5; Sum40: 138; Sum44: 152; Sum48: 165.5; Sum52: 179.16
69% | 22 | Sum4: 14.5; Sum8: 28.5; Sum12: 42.155; Sum16: 56; Sum20: 69.5; Sum24: 83; Sum28: 96.5; Sum32: 111; Sum36: 124.5; Sum40: 138; Sum44: 152.5; Sum48: 166; Sum52: 179.5
70% | 22 | Sum4: 14.5; Sum8: 28.5; Sum12: 42.5; Sum16: 56; Sum20: 70; Sum24: 83; Sum28: 96.5; Sum32: 111; Sum36: 125; Sum40: 138.65; Sum44: 152.65; Sum48: 166; Sum52: 179.5
71% | 22 | Sum4: 14.5; Sum8: 29; Sum12: 42.5; Sum16: 56.145; Sum20: 70; Sum24: 83.5; Sum28: 97; Sum32: 111.5; Sum36: 125.5; Sum40: 139; Sum44: 153; Sum48: 166.5; Sum52: 180
72% | 22 | Sum4: 15; Sum8: 29; Sum12: 42.5; Sum16: 56.5; Sum20: 70.5; Sum24: 83.5; Sum28: 97; Sum32: 111.5; Sum36: 125.5; Sum40: 139; Sum44: 153; Sum48: 167; Sum52: 180.5
73% | 22 | Sum4: 15; Sum8: 29; Sum12: 42.5; Sum16: 56.5; Sum20: 70.5; Sum24: 83.5; Sum28: 97.5; Sum32: 111.635; Sum36: 126; Sum40: 139.5; Sum44: 153.5; Sum48: 167.135; Sum52: 180.5
74% | 22.13 | Sum4: 15; Sum8: 29; Sum12: 43; Sum16: 56.5; Sum20: 70.63; Sum24: 84; Sum28: 97.5; Sum32: 112; Sum36: 126; Sum40: 139.5; Sum44: 154; Sum48: 167.5; Sum52: 180.63
75% | 22.5 | Sum4: 15; Sum8: 29; Sum12: 43; Sum16: 56.625; Sum20: 71; Sum24: 84; Sum28: 97.625; Sum32: 112; Sum36: 126.5; Sum40: 140; Sum44: 154; Sum48: 167.625; Sum52: 181
76% | 22.5 | Sum4: 15.5; Sum8: 29.5; Sum12: 43.5; Sum16: 57; Sum20: 71; Sum24: 84.5; Sum28: 98; Sum32: 112.5; Sum36: 126.5; Sum40: 140; Sum44: 154.5; Sum48: 168; Sum52: 181.62
77% | 22.5 | Sum4: 15.5; Sum8: 29.5; Sum12: 43.5; Sum16: 57; Sum20: 71; Sum24: 84.5; Sum28: 98; Sum32: 112.5; Sum36: 126.5; Sum40: 140.115; Sum44: 154.5; Sum48: 168.5; Sum52: 182.115
78% | 22.5 | Sum4: 15.5; Sum8: 29.5; Sum12: 43.5; Sum16: 57; Sum20: 71.11; Sum24: 84.61; Sum28: 98.5; Sum32: 112.61; Sum36: 126.61; Sum40: 140.5; Sum44: 155; Sum48: 169; Sum52: 182.5
79% | 22.5 | Sum4: 15.5; Sum8: 30; Sum12: 44; Sum16: 57.5; Sum20: 71.5; Sum24: 85.105; Sum28: 98.5; Sum32: 113; Sum36: 127; Sum40: 141; Sum44: 155.5; Sum48: 169; Sum52: 183
80% | 23 | Sum4: 15.6; Sum8: 30; Sum12: 44; Sum16: 57.5; Sum20: 72; Sum24: 85.5; Sum28: 99; Sum32: 113; Sum36: 127; Sum40: 141.1; Sum44: 155.5; Sum48: 169.5; Sum52: 183
81% | 23 | Sum4: 16; Sum8: 30; Sum12: 44.5; Sum16: 58; Sum20: 72; Sum24: 86; Sum28: 99; Sum32: 113.5; Sum36: 127.5; Sum40: 141.5; Sum44: 156; Sum48: 169.595; Sum52: 183.5
82% | 23 | Sum4: 16; Sum8: 30.5; Sum12: 44.5; Sum16: 58.5; Sum20: 72; Sum24: 86.5; Sum28: 99.59; Sum32: 114; Sum36: 127.5; Sum40: 142; Sum44: 156; Sum48: 170.5; Sum52: 183.5
83% | 23.5 | Sum4: 16.085; Sum8: 30.5; Sum12: 45; Sum16: 58.5; Sum20: 72.5; Sum24: 86.5; Sum28: 100; Sum32: 114; Sum36: 128; Sum40: 142.5; Sum44: 156.5; Sum48: 171; Sum52: 184
84% | 23.5 | Sum4: 16.5; Sum8: 31; Sum12: 45; Sum16: 58.58; Sum20: 72.5; Sum24: 86.5; Sum28: 100.5; Sum32: 115; Sum36: 128.5; Sum40: 143; Sum44: 157; Sum48: 171; Sum52: 184.5
85% | 24 | Sum4: 16.5; Sum8: 31.5; Sum12: 45.5; Sum16: 59; Sum20: 72.575; Sum24: 87; Sum28: 101; Sum32: 115; Sum36: 128.5; Sum40: 143.5; Sum44: 157.5; Sum48: 171.5; Sum52: 185.075
86% | 24 | Sum4: 16.5; Sum8: 31.5; Sum12: 45.5; Sum16: 59.07; Sum20: 73; Sum24: 87.07; Sum28: 101.5; Sum32: 115.5; Sum36: 129; Sum40: 143.5; Sum44: 157.5; Sum48: 172; Sum52: 185.57
87% | 24 | Sum4: 17; Sum8: 31.5; Sum12: 46; Sum16: 59.5; Sum20: 73.5; Sum24: 87.5; Sum28: 101.5; Sum32: 115.5; Sum36: 129.5; Sum40: 144.5; Sum44: 158; Sum48: 172; Sum52: 186.065
88% | 24.5 | Sum4: 17; Sum8: 32; Sum12: 46; Sum16: 60; Sum20: 74; Sum24: 87.5; Sum28: 102; Sum32: 116.5; Sum36: 130.06; Sum40: 144.5; Sum44: 158; Sum48: 172.56; Sum52: 187.06
89% | 24.5 | Sum4: 17; Sum8: 32; Sum12: 46; Sum16: 60; Sum20: 74; Sum24: 88.055; Sum28: 102.5; Sum32: 117; Sum36: 130.555; Sum40: 145.055; Sum44: 158.555; Sum48: 173.555; Sum52: 187.5
90% | 24.5 | Sum4: 17; Sum8: 32.5; Sum12: 46.5; Sum16: 60.5; Sum20: 74.5; Sum24: 88.5; Sum28: 103; Sum32: 117; Sum36: 131; Sum40: 146.05; Sum44: 159; Sum48: 174.5; Sum52: 188.5
91% | 25 | Sum4: 17.5; Sum8: 32.5; Sum12: 47; Sum16: 61; Sum20: 75; Sum24: 89; Sum28: 103.5; Sum32: 117.545; Sum36: 132; Sum40: 147; Sum44: 160.5; Sum48: 175; Sum52: 189.5
92% | 25.5 | Sum4: 17.5; Sum8: 33; Sum12: 47; Sum16: 61.5; Sum20: 75.5; Sum24: 89.04; Sum28: 104; Sum32: 118.04; Sum36: 133; Sum40: 147.54; Sum44: 161.5; Sum48: 176; Sum52: 190
93% | 25.535 | Sum4: 18; Sum8: 33; Sum12: 47.5; Sum16: 62; Sum20: 76.035; Sum24: 90.5; Sum28: 104.5; Sum32: 119.035; Sum36: 133.5; Sum40: 148; Sum44: 161.535; Sum48: 176.535; Sum52: 190.035
94% | 26 | Sum4: 18; Sum8: 33.5; Sum12: 47.5; Sum16: 62.5; Sum20: 77; Sum24: 91; Sum28: 105.53; Sum32: 120.03; Sum36: 135; Sum40: 148.53; Sum44: 162.5; Sum48: 177.5; Sum52: 191.5
95% | 26.025 | Sum4: 18.525; Sum8: 33.525; Sum12: 48; Sum16: 63; Sum20: 77.5; Sum24: 92; Sum28: 107.025; Sum32: 121.5; Sum36: 135.5; Sum40: 149.525; Sum44: 163.525; Sum48: 178.5; Sum52: 192.05
96% | 26.5 | Sum4: 19; Sum8: 34; Sum12: 48.52; Sum16: 63.5; Sum20: 78; Sum24: 92.54; Sum28: 107.52; Sum32: 122.5; Sum36: 136.54; Sum40: 151; Sum44: 165; Sum48: 179; Sum52: 193.02
97% | 26.515 | Sum4: 19; Sum8: 34.5; Sum12: 49.515; Sum16: 64.5; Sum20: 78.5; Sum24: 94.5; Sum28: 108.515; Sum32: 123; Sum36: 138.03; Sum40: 152.5; Sum44: 166.5; Sum48: 179.515; Sum52: 195.5
98% | 27.5 | Sum4: 20; Sum8: 36; Sum12: 50; Sum16: 65.51; Sum20: 80.53; Sum24: 96.5; Sum28: 110.5; Sum32: 124; Sum36: 140; Sum40: 154.01; Sum44: 167.5; Sum48: 181.01; Sum52: 196.5
99% | 28.005 | Sum4: 20; Sum8: 37; Sum12: 54.005; Sum16: 68; Sum20: 84.005; Sum24: 97.005; Sum28: 112.505; Sum32: 124.515; Sum36: 140.505; Sum40: 156.005; Sum44: 169; Sum48: 184.015; Sum52: 200.03
100% | 33 | Sum4: 22; Sum8: 42; Sum12: 57; Sum16: 71.5; Sum20: 87.5; Sum24: 102.5; Sum28: 116.5; Sum32: 130.5; Sum36: 147.5; Sum40: 159.5; Sum44: 176; Sum48: 191.5; Sum52: 205.5