## Cost of Delay
Cost of Delay Proritization Calculator
What is this: This spreadsheet helps to find preferred work start order by balancing value and duration. This is based on work published by Donald G. Reinertsen in his book The Principles of Product Development Flow - Second generation Lean Product Development (Location 56% on Kindle version, weird, are we meant to use Kindle positions in references? No page numbers!)
How does it work? This method of scheduling work will optimize cashflow based on cost of delay and duration of any particular feature or product going to market. If you scheduled just the biggest revenue features first you may delay revenue for a period and harm cashflow. Similarly, if you take the fastest feature first, you may release a string of product that doesn't grow or protect revenue, or reduce or avoid cost. This "weight score" balances both.
What about refactoring and low "value" but enabling work? Some work that has little to no customer value of its own ENABLES higher value work to be considered. To reflect that relationship, add a pre-requisite id number to all features a refactoring feature enables. This will be reflected in a increased prioritization for features that enable and unlock the most value. In essence, the refactoring feature is given the sum of all value it enables. Please give us feeback if this causes refactoring work to look "too good to be true".
What about work dependencies? Ideally, unless there are staff constraints, features should be started in the calculated preferred WSJF order. For simple portfolios you may be able to ignore pre-requisites features that have little monetary value, but often you need to consider these. WSJF Pre-Reqs adds the ability to specify dependencies between features and accumate the total COD of a feature and its subordinates.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.

## WSJF Prioritization (simple)
Feature Name | Forecast Days Remaining | Value | Weighted Priority Order (do highest first) | WSJF Preferred Order
Feature 1 | 20 | 3 - Medium/High | 3.05 | 1
Feature 2 | 21 | 1 - Low | 1.0476 | 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
This sheet allows quick priortization to occur with qualitative value estimation and some form of duration estimate.
Step 1: List all of the possible options of features.
Step 2: Quickly do a relative forecast of these options. Typically this is ranking them from biggest to smallest, and then allocating some numerical duration value (points, sprints, days, etc) Doing planning poker on these is probably too much. Rolling a dice or other random number generator too little!
Step 3: Estimate the value for each item by drop-down (edit the list and value for each entry in the Setup tab in this spreadsheet)
The preferred order is listed. Start on the lowest number working up.

## WSJF Prioritization (moderate)
Feature or Story Information |  |  |  | Value Inputs |  | Calculations | Results
ID | Feature Name | Forecast Remaining Days | Pre-requisite Parent Id | Value | Value Unit | value / day | WSJF Preferred Order | Total COD per Day (inc. children) | WSJF Weight (inc. children) | Total COD per Day (no children) | WSJF Weight (no children)
1 | Feature 1 | 3 | 4 | 30000 | Month | 1000 | 4 | 1000 | 333.3333 | 1000 | 333.3333
2 | Feature 2 | 4 |  | 70000 | Month | 2333.3333 | 2 | 2333.3333 | 583.3333 | 2333.3333 | 583.3333
3 | Feature 3 | 6 | 4 | 90000 | Month | 3000 | 3 | 3000 | 500 | 3000 | 500
4 | Refactoring | 10 |  | 0 | Day | 0 | 1 | 4000 | 833.3333 | 0 | 0
5 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
6 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
7 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
8 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
9 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
10 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
11 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
12 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
13 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
14 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
15 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
16 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
17 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
18 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
19 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
20 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
21 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
22 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
23 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0
24 |  |  |  | 0 | Month | 0 |  | 0 | 0 | 0 | 0

## WSJF Prioritization (complex)
Feature or Story Information |  |  |  | Value and Cost Inputs | [7 empty] | Calculations |  |  |  | Results
ID | Feature Name | Forecast Remaining Days | Pre-requisite Parent Id | Revenue Added (RA) | RA Unit | Revenue Protected (RP) | RP Unit | Costs Saved (CS) | CS Unit | Costs Avoided (CA) | CA Unit | RA / day | RP / day | CS / day | CA / day | WSJF Preferred Order | Total COD per Day (inc. children) | WSJF Weight (inc. children) | Total COD per Day (no children) | WSJF Weight (no children)
1 | Feature 1 | 3 | 4 | 3 | Day | 0 | Month | 0 | Month | 0 | Month | 3 | 0 | 0 | 0 | 4 | 3 | 1 | 3 | 1
2 | Feature 2 | 4 | 4 | 7 | Day | 0 | Month | 0 | Month | 0 | Month | 7 | 0 | 0 | 0 | 2 | 7 | 1.75 | 7 | 1.75
3 | Feature 3 | 6 | 4 | 9 | Day | 0 | Month | 0 | Month | 0 | Month | 9 | 0 | 0 | 0 | 3 | 9 | 1.5 | 9 | 1.5
4 | Refactoring | 10 |  | 0 | Day | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 | 1 | 19 | 4.25 | 0 | 0
5 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
6 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
7 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
8 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
9 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
10 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
11 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
12 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
13 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
14 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
15 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
16 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
17 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
18 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
19 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
20 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
21 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
22 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
23 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
24 |  |  |  | 0 | Month | 0 | Month | 0 | Month | 0 | Month | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## Setup
Unit | Day Per Unit
Day | 1
Workday | 5
Week | 7
Month | 30
Year | 365
Priority Scale | Value
1 - Low | 1
2 - Medium | 2
3 - Medium/High | 3
4 - High | 4
5 - Critical | 5

## Example
Revenue By Month
| Duration | Revenue | Feature Prioritization | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Feature 1 | 3 | 3 | Biggest revenue first | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 9 | 16 | 16 | 16 | 19 | 103
Feature 2 | 4 | 7 | Shortest first |  |  |  | 3 | 3 | 3 | 3 | 10 | 10 | 10 | 10 | 10 | 10 | 19 | 91
Feature 3 | 6 | 9 | WSJF |  |  |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 16 | 16 | 16 | 19 | 109
To explain the concept of Weighted Shortest Job First, imagine three features (or projects) that have a defined duration and expected revenue.
Scheduling based on just the highest revenue first, or the lowest duration first gives a sub-optimal cashflow over the period to complete all projects.
WSJF offers a quick way to balance the revenue and duration aspects of scheduling to maximize cashflow.