## Readme
Want to learn how this works and how to use it? Read my "In-progress" book on Medium - Forecasting using Data
https://medium.com/forecasting-using-data
What is this: This spreadsheet helps identify the dependencies between teams for Experiments/epics/MVPs and to identify constraints and dependency hotspots.
Ideas, errors, requests? Email: troy.magennis@focusedobjective.com
Work licensed under a Creative Commons Attribution-NonCommercial-ShareAlike 4.0 International License.
Get more tools like this from: http://bit.ly/SimResources
About us: Focused Objective LLC offers tools, training and expert advice on metrics, risk and forecasting. We have more advanced tools to model Agile teams and projects that help analyze staffing options and risk, and a proven track record of positive results. We are always happy to discuss next steps and training opportunities should this tool prove useful. See our website: http://www.focusedobjective.com or email me at troy.magennis@focusedobjective.com.
About me….
I develop and teach how to use data in software development and operations teams for coaching or forecasting.
- Forecasting using Data workshop. Teach how to use these spreadsheets with practical hands-on examples based on your (and my) specific examples. Often run internally, sometimes publically.
- Data Driven Coaching workshop. Teach how to develop data driven approaches to improvement based on balancing multiple competing metrics. Often run internally, sometimes publically.
- Custom Dashboards or giving advice on your current dashboards. Take the next step in customizing our spreadsheets or deploying more advanced versions in Tableau or Power BI.
- Quantitative consulting or advice - give me a chance to answer something you need to know. I'll work with your teams in designing a prediction system or delivering a compelling visual demonstrting the issues.
Interested in chatting? Email me at troy.magennis@focusedobjective.com
Interested in stalking? Follow me on twitter @t_magennis
(best way to hear about new and improved spreadsheets like this)

## Experiments
Enter the experiments and when each team starts their work…
Enter experiment name |  | ALERTS | Who starts | When? | Then who gets it? | When? | Then who gets it? | When? | Then who gets it? | When? | Then who gets it? | When? | Then who gets it? | When? | Then who gets it? | When? | Date Delivered |  | IGNORE - CALCULATIONS - just leave these alone :)
|  | Calculated, don't touch |  | Date first team started |  | Date second team started |  | Date third team started |  | Date fourth team started |  | Date fifth team started |  | Date sixth team started |  | Date seventh team started
Experiment/MVP/Epic | Delivery Priority | Alert | First Team | Date Start 1 | Then Second Team | Date Start 2 | Then Third Team | Date Start 3 | Then Fourth Team | Date Start 4 | Then Fifth Team | Date Start 5 | Then Sixth Team | Date Start 6 | Then Seventh Team | Date Start 7 | Date Delivered | - | CT1 | CT2 | CT3 | CT4 | CT5 | CT6 | CT7 | TCT
A | High |  | Team 1 | 2019-01-01 | Team 2 | 2019-01-10 | Team 4 | 2019-01-15 | Team 6 | [7 empty] | 2019-02-01 |  | CT1: 9; CT2: 5; CT3: 17 | 31
B | Low |  | Team 2 | 2019-01-15 | Team 4 | 2019-01-25 | Team 1 | [11 empty] | CT1: 10
C | Critical | Priority, Not Started | Team 7 |  | Team 2
D | Low
E | High
F |  | No Priority Set
G | Critical |  | Team 2 | 2019-01-10 | Team 4 | 2019-01-13 | [10 empty] | 2019-01-17 |  | CT1: 3; CT2: 4 | 7
H | Urgent | Priority, No First Team
I | Low
J | Medium |  | Team 1 | 2019-02-01 | Team 2 |  | Team 4
K | Medium
L |  | No Priority Set
Enter the experiments/MVP or epics into this data table. Add new ones in the next blank row and the table should autosize. Split out what teams and what order those teams will be needed to deliver each piece of work. Enter the dates each of those teams start their work for each experiment, and eventually the date it was deivered. Edit the team names, up to 20 of them (i just limited this spreadsheet to 20, you are on your own if you hve more teams :) - nah, just email me)
Tips -
1. At first, just grab a sample of 10 prior features/epics or experiments and document their journey's. This will produce results in the charts o find likely constraints.
2. YOU DON'T NEED to have seven teams (in fact I recommend against it) just enter the ones you have.

## Forecasting
ALL CALCULATIONS, ADD AND EDIT DATA IN THE Experiments worksheet not here!!!
The name of the experiment, etc. | Priority | Current status | Who has it now |  |  |  | Trending abnormally? | Who gets it next | Expected…
| (useful filter, discuss criticals first?) | (useful filter to exclude delivered items) |  |  |  |  | (percent above average for this teams) | (the next team in the chain) | (current teams start + average expected days)
MVP/Epic/Experiment/Feature Name | Priority | status | current team | date started | expected days (avg) | days so far | days so far % of avg | next team | anticipated arrival date (avg)
A | High | Delivered
B | Low | In Progress | Team 4 | 2019-01-25 | 10.5 | 103.4846 | 985.6% | Team 1 | 2019-02-04 12:00
C | Critical | NOT Started
D | Low | NOT Started
E | High | NOT Started
F | 0 | NOT Started
G | Critical | Delivered
H | Urgent | NOT Started
I | Low | NOT Started
J | Medium | In Progress | Team 1 | 2019-02-01 | 9 | 96.4846 | 1072% | Team 2 | 2019-02-10
K | Medium | NOT Started
L | 0 | NOT Started
Formulas:
Expected… = IF(AND([date started]<>"",[expected days (avg)]<>""), [date started] + [expected days (avg)], "")

## Dependency Charts
Which dependencies are most common? (How often is there a dependency between teams)
From
|  | Team 1 | Team 2 | Team 3 | Team 4 | Team 5 | Team 6 | Team 7 | Team 8 | Team 9 | Team 10 | Team 11 | Team 12 | Team 13 | Team 14 | Team 15 | Team 16 | Team 17 | Team 18 | Team 19 | Team 20
To | Team 1 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 2 | 2 |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 3 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 4 | 0 | 4 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 6 | 0 | 0 | 0 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 7 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Team 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
| Team 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| Team 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Team 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Team 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
| Team 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Team 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
How long does it take for teams to complete their work? (cycle time between teams)
[5 empty] | Percentile (approx) |  |  | weight = # dependencies * cycle time avg |  |  |  |  | Intermediate Calculations
|  | Average cycle time |  |  | 85% |  |  | Constraint Weight | Constraint Rank |  |  |  | Avg1 | Avg2 | Avg3 | Avg4 | Avg5 | Avg6 | Avg7 |  | Pct1 | Pct2 | Pct3 | Pct4 | Pct5 | Pct6 | Pct7
| Team 1 | 9 |  |  | 9 |  |  | 9 | 3 |  |  |  | Intermediate Calculations Avg1: 9 |  | 9
| Team 2 | 5.75 |  |  | 8.3575 |  |  | 17.25 | 2 |  |  |  | Intermediate Calculations Avg1: 6.5; Intermediate Calculations Avg2: 5 |  | 8.95 | 5
Team 3
| Team 4 | 10.5 |  |  | 15.05 |  |  | 42 | 1 |  |  |  | Intermediate Calculations Avg2: 4; Intermediate Calculations Avg3: 17 |  |  | 4 | 17
Team 5
Team 6
Team 7
Team 8
Team 9
Team 10
Team 11
Team 12
Team 13
Team 14
Team 15
Team 16
Team 17
Team 18
Team 19
Team 20

## Team Setup
Team Name
Team 1
Team 2
Team 3
Team 4
Team 5
Team 6
Team 7
Team 8
Team 9
Team 10
Team 11
Team 12
Team 13
Team 14
Team 15
Team 16
Team 17
Team 18
Team 19
Team 20

## Setup
Priority Name | Alert
Critical | TRUE
Urgent | TRUE
High | FALSE
Medium | FALSE
Low | FALSE
Experiment WIP Limit |  | 3

## Week Calculations
Earliest date | 2019-01-01
Latest date | 2019-02-01
Week Starting (Sunday) | Week Ending (Saturday) | started this week | delivered this week | in-progress (last day of week) | limit
2018-12-30 | 2019-01-05 | 1 | 0 | 1 | 3
2019-01-06 | 2019-01-12 | 1 | 0 | 2 | 3
2019-01-13 | 2019-01-19 | 1 | 1 | 2 | 3
2019-01-20 | 2019-01-26 | 0 | 0 | 2 | 3
2019-01-27 | 2019-02-02 | 1 | 1 | 2 | 3
2019-02-03 | 2019-02-09 | 0 | 0 | 2 | 3
Formulas:
Week Starting (Sunday) = IF([Week Starting (Sunday), row above]<>"",IF([Week Starting (Sunday), row above]+7<DateMAx+7, [Week Starting (Sunday), row above]+7, ""),"")
Week Ending (Saturday) = IF([Week Starting (Sunday)]<>"",[Week Starting (Sunday)]+6,"")